{"text_format":"1","workbook":"xlsx","n_sheets":20,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":31,"n_cols":28,"rows_kept":31,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","26-Oct-2019",null,null,"Ship Name","DHT BAUHINIA"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,4399,"25/10/2019 2:55:41 PM","2019-05-07","Non Conformity","Owner / Marine / Tech. Suptd.","OM Insp. (Eg. SIRE, CDI etc.)","IS telephone system in pump room, donot have a direct connection to Nav Bridge","LSA / FFA","Communication","Industry Issue","5.17","Very High","","","Office to advice . Drawing and information sent for further action.(Office planned to installpassive antennas)","2019-07-31","DBAU195057","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,4400,"25/10/2019 3:11:11 PM","2019-05-15","Deficiency","Ship Staff","Ship Staff Insp.","Galley exhaust fan breaker-reset button defective.","Elect. Mach. & Equip.","General Appearance","Equipment Related","10.37","Medium","","","Requisition raised.","2019-11-01","DNAU190131","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,4401,"25/10/2019 3:13:47 PM","2019-05-27","Deficiency","Ship Staff","Ship Staff Insp.","Ballast pump #2 : Auto grease cup to replace.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Requisition raised.","2019-11-01","DBAU190138","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,4403,"25/10/2019 3:21:06 PM","2019-07-29","Deficiency","Ship Staff","Ship Staff Insp.","2 STBD WBT level not displayed.","Miscellaneous","Cargo / Ballast Systems","Equipment Related",8.1199999999999992,"Medium","Not Applicable","Not Applicable","Troubleshooting carried out, zero calibration done. Parameters will be adjusted for correcting the error.","2019-10-31",null,"In progress",null,"No","No","No","Internal"]
[null,null,null,null,4404,"25/10/2019 3:23:26 PM","2019-07-29","Deficiency","Ship Staff","Ship Staff Insp.","3STBD WBT level not displayed.","Miscellaneous","Cargo / Ballast Systems","Equipment Related",8.1199999999999992,"Medium","Not Applicable","Not Applicable","troubleshooting carried out, zero calibration done, Parameters will be adjusted for correcting the error.","2019-10-31",null,"In progress",null,"No","No","No","Internal"]
[null,null,null,null,4405,"25/10/2019 3:30:44 PM","2019-08-05","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Galley fridge cooling insufficient","Miscellaneous","MLC Related","Equipment Related","11.13","Low","","","Electronic control device ID-961 to be renewed. The module received on 31st july 2019 is a wrong supply. Landed in Singapore for replacement on 10th oct.2019","2019-10-31","","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,4406,"25/10/2019 3:37:10 PM","2019-08-09","Deficiency","Ship Staff","Ship Staff Insp.","Emergency generator room supply fan indication is not working.","Miscellaneous","Emgcy. Systems","Equipment Related","10.32","Very High","","","Starter control module is defective, requisition raised.","2019-11-30","DBAU190177","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,4407,"25/10/2019 3:39:44 PM","2019-10-10","Deficiency","Ship Staff","Ship Staff Insp.","Port windalss winch lever spool piece worn out.","Mooring Mach.","Mooring","Equipment Related","9.2","Very High","","","Requisition raised for new winch valve.","2019-11-30","DBAU190173","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,4408,"25/10/2019 3:41:49 PM","2019-10-17","Deficiency","Ship Staff","Ship Staff Insp.","LO purifier heater is leaking and the solenoid valve block is defective.","Purifier","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","requsition raised ","2019-11-30","DBAU190179","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,4409,"25/10/2019 3:51:13 PM","2019-09-11","Observation","Ship Staff","Ship Staff Insp.","M3 & M4 mooring winch operating lever valve leaking , brake cylinder valve block leaking.","Mooring Mach.","Mooring","Equipment Related","9.14","Medium","","","Vessel has raised the requsition of required spare parts. In the meantime , through some temporary repair ,M4 cylinder valve block leakage rectified.","2019-10-10","DBAU190205","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,4456,"25/10/2019 9:21:23 PM","2019-07-21","Deficiency","Ship Staff","Ship Staff Insp.","AC Compressor No. 2 condenser dryer cartridge was planned for replacement, but the valves are not holding.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Added to refman to be done in DD.","2019-10-20","","Deferred to D D",null,"Yes","No","No","Internal"]
[null,null,null,null,4457,"25/10/2019 9:24:10 PM","2019-08-28","Deficiency","Ship Staff","Ship Staff Insp.","Few of the ballast pumps local pressure gauges in pump room defective","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.8","Medium","","","Added in refman to be done at DD. Gauges ordered.","2019-12-30","DBAU190197","Deferred to D D",null,"Yes","No","No","Internal"]
[null,null,null,null,null,"29/10/2019 3:51:35 PM","2019-10-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Inadequate inventory management of operational critical spares in PAL.","Miscellaneous","ISM Related","Behaviour Based,Human Error",10.119999999999999,"Very High","Not Applicable","Not Applicable","Operational critical spares to identify, inventory to check and upfdate in PAL.","2019-11-15",null,"In progress",null,"No",null,null,"External"]
[null,null,null,null,null,"31/10/2019 1:10:49 PM","2019-10-30","Deficiency","Ship Staff","Ship Staff Insp.","Aft draft gauge indicator on cargo console in CCR is shwoing incorrect reading","Miscellaneous","Cargo / Ballast Systems","Equipment Related",11.1,"High","Not Applicable","Not Applicable","Blow off valvw will be checked and callibration will be done.","2019-11-30",null,"Not Started",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":119,"n_cols":28,"rows_kept":119,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","26-9-2019",null,null,"Ship Name","DHT BAUHINIA"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,4397,"25/10/2019 10:56:07 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Lub oil consumption for NO.2 high at 50 L/day.","Aux. Engine","Eng. / Strg. Comp.","Human Error","10.32","Very High","","","Indicated lub. oil leakage through cyclinder head guides or vents chocked or any external leakage to check and rectify.","2019-03-30","","Completed","2019-04-26","No","No","No","Internal"]
[null,null,null,null,4410,"24/10/2019 11:29:27 AM","2019-01-02","Deficiency","Ship Staff","Ship Staff Insp.","2S PV Valve leaks from pressure side.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.21","High","","","Replaced with overhauled spare.","2019-01-10","","Completed","2019-01-02","No","No","No","Internal"]
[null,null,null,null,4411,"25/10/2019 7:55:25 AM","2019-01-03","Deficiency","Ship Staff","Ship Staff Insp.","PV valve of SLOP P pressure and vacuum side leaks","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.21","High","","","Overhauled and replaced with spare.","2019-01-22","","Completed","2019-01-21","No","No","No","Internal"]
[null,null,null,null,4412,"25/10/2019 8:05:54 AM","2019-01-03","Deficiency","Ship Staff","Ship Staff Insp.","PV valve of 1C COT pressure and vacuum side leaks.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.21","High","","","To replace with overhauled spare.","2019-01-27","","Completed","2019-01-22","No","No","No","Internal"]
[null,null,null,null,4413,"25/10/2019 8:08:46 AM","2019-01-03","Deficiency","Ship Staff","Ship Staff Insp.","PV valve of 2C COT pressure and vacuum side leaks.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.21","High","","","To replace with overhauled spare.","2019-01-22","","Completed","2019-01-26","No","No","No","Internal"]
[null,null,null,null,4414,"25/10/2019 8:10:58 AM","2019-02-04","Deficiency","Ship Staff","Ship Staff Insp.","PV valve of 3C COT pressure and vacuum side laeks.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.21","High","","","To replace with overhauled spare.","2019-02-09","","Completed","2019-02-07","No","No","No","Internal"]
[null,null,null,null,4415,"25/10/2019 8:13:13 AM","2019-02-04","Deficiency","Ship Staff","Ship Staff Insp.","PV valve of 4C COT pressure and vacuum side leaks.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.21","High","","","To replace with overhauled spare.","2019-02-09","","Completed","2019-02-08","No","No","No","Internal"]
[null,null,null,null,4416,"25/10/2019 7:36:35 AM","2019-01-03","Deficiency","Ship Staff","Ship Staff Insp.","PV valves slop starboard pressure and vacuum side leaks","Cargo Mach.,Deck Pipe / Fittings,Inert Gas","Cargo / Ballast Systems","Equipment Related","8.21","High","","","Overhauled and replaced with spare one.","2019-01-22","","Completed","2019-01-14","No","No","No","Internal"]
[null,null,null,null,4417,"25/10/2019 8:21:35 AM","2019-02-04","Deficiency","Ship Staff","Ship Staff Insp.","PV valve of 5C pressure and vacuum side leaks.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.21","High","","","To replace with overhauled spare.","2019-02-10","","Completed","2019-02-08","No","No","No","Internal"]
[null,null,null,null,4418,"25/10/2019 8:33:18 AM","2019-02-17","Observation","Ship Staff","Ship Staff Insp.","1S Bunker tank heating coils 3 nos found leaking.","ER Pipes, valves & fittings","Structural Condn. / WT integrity ","Equipment Related","10.32","Very High","","","Added in REFMAN to be done at Dry dock.","2019-12-31","Refman no. BA/SDR/16","Completed","2019-02-23","Yes","No","No","Internal"]
[null,null,null,null,4419,"25/10/2019 8:38:24 AM","2019-02-14","Observation","Ship Staff","Ship Staff Insp.","EGB Manometer missing.","Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","New manometer fabricated and fitted, Work no. V-DBAU012212/19","2019-03-15","","Completed","2019-02-26","No","No","No","Internal"]
[null,null,null,null,4420,"25/10/2019 8:42:04 AM","2019-02-14","Observation","Ship Staff","Ship Staff Insp.","HFO purifier feed pump No.1 mechanical seal leaking.","Purifier","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Overhauled the pump and renewed the mechanical seal.","2019-03-10","JOB NO. DBAU012245/19","Completed","2019-02-20","No","No","No","Internal"]
[null,null,null,null,4421,"25/10/2019 9:06:06 AM","2019-02-17","Observation","Ship Staff","Ship Staff Insp.","Control air dryer water drain unit leaking.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.19","Very High","","","Overhauled and found working satisfactory.","2019-03-31","JOB NO. DBAU0122452/19","Completed","2019-02-22","No","No","No","Internal"]
[null,null,null,null,4422,"25/10/2019 9:08:43 AM","2019-02-17","Observation","Ship Staff","Ship Staff Insp.","Deck valve hydraulic box aft of port manifold found leaking.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","8.11","Medium","","","Leakage Rectified.","2019-04-30","JOB NO. DBAU012246/19","Completed","2019-03-01","No","No","No","Internal"]
[null,null,null,null,4423,"25/10/2019 9:12:24 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Observed steam continously venting - waste of steam/water.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Cleaned the atmospheric condenser tubes and found the steam venting to reduce.","2019-03-20","V-DBAU000514/17","Completed","2019-03-15","No","No","No","Internal"]
[null,null,null,null,4424,"25/10/2019 9:14:57 AM","2019-03-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hotwell observation tank glass looks dirty.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Opened the tank and cleaning carried out.","2019-05-15","V-DBAU001487/17","Completed","2019-03-14","No","No","No","Internal"]
[null,null,null,null,4425,"25/10/2019 9:18:43 AM","2019-02-27","Observation","Ship Staff","Ship Staff Insp.","10-6k steam relief valve found leaking mildly.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Opened the relief valve, lapped and boxed back, found no leaks.","2019-04-15","V-DBAU012091/19","Completed","2019-03-14","No","No","No","Internal"]
[null,null,null,null,4426,"25/10/2019 9:20:44 AM","2019-01-02","Deficiency","Ship Staff","Ship Staff Insp.","2S COT PV vlave leaks from pressure side.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.21","High","","","Replaced with overhauled spare.","2019-01-10","","Completed","2019-01-02","No","No","No","Internal"]
[null,null,null,null,4427,"25/10/2019 9:23:56 AM","2019-01-15","Deficiency","Ship Staff","Ship Staff Insp.","Port provision crane emergency stop valve frozen.","Deck Mach.","Structural Condn. / WT integrity ","Equipment Related","11.8","Low","","","Planned to lubricate and free up, if required to be removed and overhauled.","2019-01-22","","Completed","2019-01-17","No","No","No","Internal"]
[null,null,null,null,4428,"25/10/2019 9:28:11 AM","2019-01-15","Deficiency","Ship Staff","Ship Staff Insp.","Stbd Accommodation ladder angle indicator marker missing.","Deck Mach.","ISM Related","Human Error","5.47","Medium","","","Fabricate and re-fitted in place.","2019-01-22","","Completed","2019-01-22","No","No","No","Internal"]
[null,null,null,null,4429,"25/10/2019 9:31:51 AM","2019-01-15","Deficiency","Ship Staff","Ship Staff Insp.","Stbd Accommodation ladder 1 Nos. step found cracked.","Deck Mach.","Structural Condn. / WT integrity ","Equipment Related","5.47","Medium","","","Removed, refabricate and fitted back in place.","2019-01-22","","Completed","2019-01-22","No","No","No","Internal"]
[null,null,null,null,4430,"25/10/2019 9:35:19 AM","2019-01-02","Deficiency","Ship Staff","Ship Staff Insp.","Mooring winch No. 1, Aft drum(B), brake cylinder in poor condition.","Mooring Mach.","Mooring","Equipment Related","9.15","Medium","","","Power tooled and investigate, condition found satisfactory without leaks. Painted and re-fitted.","2019-01-22","","Completed","2019-01-07","No","No","No","Internal"]
[null,null,null,null,4431,"25/10/2019 10:03:17 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Package galley AC unit in AC compressor room, the suction filter seems chocked.","Miscellaneous","MLC Related","Human Error","11.13","Low","","","Cleaned the suction air filter satisfactorily.","2019-03-30","v-dbau012522/19","Completed","2019-03-18","No","No","No","Internal"]
[null,null,null,null,4432,"25/10/2019 10:07:06 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AC intake filter fine mesh missing.","Accommodation ","MLC Related","Human Error","11.13","Low","","","Fine mesh filter installed.","2019-03-30","V-DBAU012523/19","Completed","2019-03-18","No","No","No","Internal"]
[null,null,null,null,4433,"25/10/2019 10:10:40 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cable tray anchor bolts painted over.","Deck Pipe / Fittings","General Appearance","External Factors","11.1","High","","","Anchor bolts should be free and well greased - allowing free movements.","2019-03-25","","Completed","2019-03-24","No","No","No","Internal"]
[null,null,null,null,4434,"25/10/2019 10:12:49 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fwd liferafts stwing cradles rusted.","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.29","High","","","To de-rust and paint.","2019-03-30","","Completed","2019-03-24","No","No","No","Internal"]
[null,null,null,null,4435,"25/10/2019 10:15:52 AM","2019-02-14","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME Unit 7 punture valve slightly leaking.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","Tightened the punture valve to torque, presently no leaks and under observation.","2019-03-05","","Completed","2019-03-26","No","No","No","Internal"]
[null,null,null,null,4436,"25/10/2019 10:18:44 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No. 1 oil max filter found not in use, while engine was running.","Aux. Engine","Eng. / Strg. Comp.","Human Error","10.32","Very High","","","To ensure the centrifugal filter is always in use while running and while in idle.","2019-03-20","V-DBAU012618/19","Completed","2019-03-29","No","No","No","Internal"]
[null,null,null,null,4437,"25/10/2019 10:22:38 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No. 1 & 2 lub oil purifier was running, inlet set temperature at 85 deg C, and actual temperature was only 65 deg C.","Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Later understood temperature controller not working on auto - neither reported nor in DDRL, to check and revert status.","2019-03-30","V-DBAU012671/19","Completed","2019-03-29","No","No","No","Internal"]
[null,null,null,null,4438,"25/10/2019 10:25:03 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No.1 & 2 HFO Purifier was running, inlet set temp at 98 deg C and actual temp was only 83 deg C.","Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Later understood temp controller was not working on auto - neither reported nor in DDRL, to check and revert status.","2019-03-30","V-DBAU012669/19","Completed","2019-03-29","No","No","No","Internal"]
[null,null,null,null,4439,"25/10/2019 10:27:38 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Few units shall be due for decarb in another 3000 hrs.","Main Engine ","Eng. / Strg. Comp.","Knowledge Based","10.12","Very High","","","To raise RO and maintain sufficient spares for the units falling due +3 sets extra.","2019-04-15","DBAU190098","Completed","2019-04-02","No","No","No","Internal"]
[null,null,null,null,4440,"25/10/2019 10:29:35 AM","2019-02-13","Observation","Ship Staff","Ship Staff Insp.","ME fuel oil supplu pump No.1 mechanical seal leaking.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","To replace the mechanical seal.","2019-03-10","V-DBAU012685/19","Completed","2019-04-02","No","No","No","Internal"]
[null,null,null,null,4441,"25/10/2019 10:32:00 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both boiler gauge glass cocks remote valves not free.","Boiler","Eng. / Strg. Comp.","Human Error","10.32","Very High","","","Wires greased, leaking packing renewed. Need to ease up the cocks for free movement.","2019-03-30","V-DBAU012767/19, V-DBAU012768/19","Completed","2019-04-03","No","No","No","Internal"]
[null,null,null,null,4442,"25/10/2019 10:35:12 AM","2019-02-14","Observation","Ship Staff","Ship Staff Insp.","Aft winch system hydraulic tank level gauge blanked off with steel pipe.","Miscellaneous","Mooring","Human Error","10.25","Very High","","","Received spares, steel wires renewal in progress. Gauge glass will be renewed after mooring winch works are completed.","2019-03-15","V-DBAU012774/19","Completed","2019-04-05","No","No","No","Internal"]
[null,null,null,null,4443,"25/10/2019 10:37:50 AM","2019-02-23","Observation","Ship Staff","Ship Staff Insp.","Hinges of compactor room door found wasted and broken.","Deck Pipe / Fittings","General Appearance","Behaviour Based","11.8","Low","","","Door to be dismantled and taken to E/R workshop and repair by welding.","2019-03-30","","Completed","2019-04-09","No","No","No","Internal"]
[null,null,null,null,4444,"25/10/2019 10:40:44 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fwd light mast stays found fully rusted - devoid of grease.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Human Error","11.8","Low","","","To ensure they are well lubricated to avoid strand damages.","2019-03-25","","Completed","2019-04-06","No","No","No","Internal"]
[null,null,null,null,4445,"25/10/2019 10:42:45 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Stern light junction box base plate corroded.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","External Factors","11.8","Low","","","To renew the base plate.","2019-04-05","","Completed","2019-04-10","No","No","No","Internal"]
[null,null,null,null,4446,"25/10/2019 10:46:25 AM","2019-02-17","Observation","Ship Staff","Ship Staff Insp.","EGB mild leak observed near water inlet header.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Lagging removed and inspected. Cold work carried out for the corroded section. L-5cm, B-0.5cm.","2019-03-31","","Completed","2019-04-16","No","No","No","Internal"]
[null,null,null,null,4447,"25/10/2019 10:48:35 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Control air compressor external cooling fan kept for radiator.","Air Comp.","Eng. / Strg. Comp.","Human Error","10.32","Very High","","","Radiator cleaned and external fan removed from place.","2019-03-30","","Completed","2019-03-18","No","No","No","Internal"]
[null,null,null,null,4448,"25/10/2019 10:50:29 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Light glass fully dirty.","Deck Pipe / Fittings","General Appearance","Human Error","11.9","Low","","","To clean all stern light globes/glasses and fit back.","2019-03-30","V-DBAU012944/19","Completed","2019-04-11","No","No","No","Internal"]
[null,null,null,null,4449,"25/10/2019 10:52:58 AM","2019-02-13","Deficiency","Ship Staff","Ship Staff Insp.","Slop port steam return line corroded and holed.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.15","High","","","Repaired with the soft patch temporarily, planned to remove and repair by renewing the pipe in E/R Workshop.","2019-02-26","","Completed","2019-04-29","No","No","No","Internal"]
[null,null,null,null,4450,"25/10/2019 2:24:19 PM","2019-07-23","Deficiency","Ship Staff","Ship Staff Insp.","Wheel house telegraph printer-auto roll device defective.","Nav & comm. equip.","Navigation","Equipment Related","4.2","Medium","","","Deffective auto roll device changed.","2019-10-21","DBAU190169","Completed","2019-10-10","No","No","No","Internal"]
[null,null,null,null,4451,"25/10/2019 2:27:33 PM","2019-08-17","Deficiency","Ship Staff","Ship Staff Insp.","Emergency generator battery is malfunctioning.","LSA / FFA","Emgcy. Systems","Equipment Related","10.34","High","","","Batteries received and installed in place . Engine tried out, starting satisfactory.","2019-11-30","DBAU190174","Completed","2019-10-10","No","No","No","Internal"]
[null,null,null,null,4452,"25/10/2019 2:31:09 PM","2019-08-28","Deficiency","Ship Staff","Ship Staff Insp.","Ligthing diffusers defective in engine room","Elect. Mach. & Equip.","Eng. / Strg. Comp.","External Factors","10.15","Low","","","Engine room ligthing diffusers received on 10th oct.Deffective cracked diffuser in engine room changed with new spare.","2019-12-30","DBAU190190","Completed","2019-10-12","No","No","No","Internal"]
[null,null,null,null,4453,"25/10/2019 2:34:40 PM","2019-09-12","Deficiency","Ship Staff","Ship Staff Insp.","No.2 main fuel oil supply pump has slight leak from seal area .","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","pump overhauled with new seal.","2019-09-30","","Completed","2019-09-19","No","No","No","Internal"]
[null,null,null,null,4454,"25/10/2019 2:37:18 PM","2019-09-29","Deficiency","Ship Staff","Ship Staff Insp.","One of the section of atmospheric condenser S/W outlet pipline is observed to have a pin hole.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","External Factors","10.32","Very High","","","A new pipe fabricated and fitted in place .","2019-10-15","","Completed","2019-10-09","No","No","No","Internal"]
[null,null,null,null,4455,"25/10/2019 2:40:07 PM","2019-10-04","Deficiency","Ship Staff","Ship Staff Insp.","OWS bilge inlet pipe observed having a hole at the welded connection.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Behaviour Based,External Factors","6.14","High","","","In place hot work repair work carried out.","2019-10-06","","Completed","2019-10-05","No","No","No","Internal"]
[null,null,null,null,4458,"25/10/2019 3:53:54 PM","2019-09-12","Deficiency","Ship Staff","Ship Staff Insp.","25kg DCP portable extinguisher (helicopter)","LSA / FFA","LSA / FFA Appliances","Industry Issue","5.42","Medium","","","Repaired and painted. Requisition cancelled.","2019-10-15","DBAU190188","Completed","2019-10-18","No","No","No","Internal"]
[null,null,null,null,4459,"25/10/2019 3:26:11 PM","2019-10-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME L.O filter outlet valve flange leaking.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","Valve gasket renewed. ","2019-10-31","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,4460,"25/10/2019 3:33:17 PM","2019-08-05","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main engine No.7 unit lubricator leaking","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Lubricator top cover securing bolts tightened.","2019-10-31","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,4461,"25/10/2019 3:44:24 PM","2019-09-04","Deficiency","Ship Staff","Ship Staff Insp.","NO 3 foam monitor leaking , valve not holding.","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.38","High","","","Valve repaired and leakage rectified. Req. cancelled.","2019-10-15","DBAU190188","Completed","2019-10-17","No","No","No","Internal"]
[null,null,null,null,4462,"25/10/2019 3:47:20 PM","2019-09-08","Observation","Ship Staff","Ship Staff Insp.","After loading observed PV valve of SLOP S COT leaking from vaccum side.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.21","High","","","replaced by spare overhauled PV valve.","2019-09-30","","Completed","2019-10-16","No","No","No","Internal"]
[null,null,null,null,4463,"25/10/2019 2:48:03 PM","2019-08-28","Deficiency","Ship Staff","Ship Staff Insp.","Few of the ballast pump local pressure gauges defective.","Aux. Mach.","Structural Condn. / WT integrity ","Behaviour Based","8.5","Very High","","","Added to REFMAN to be done at drydock. ","2019-12-30","DBAU190197","Completed","2019-10-08","Yes","No","No","Internal"]
[null,null,null,null,4464,"25/10/2019 10:58:05 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mooring spring winches brake band stopper bolts clearance found less.","Deck Mach.","Mooring","External Factors","9.15","Medium","","","To adjust and to maintain around 5mm.","2019-03-25","","Completed","2019-04-30","No","No","No","Internal"]
[null,null,null,null,4465,"25/10/2019 11:01:50 AM","2019-02-17","Observation","Ship Staff","Ship Staff Insp.","Port hose handling crane found to give noise at 45 degrees.","Deck Mach.","Cargo / Ballast Systems","Equipment Related","8.5","Very High","","","Greasing carried out, found the noise to reduce.","2019-04-30","","Completed","2019-04-30","No","No","No","Internal"]
[null,null,null,null,4466,"25/10/2019 11:04:45 AM","2019-01-03","Observation","Ship Staff","Ship Staff Insp.","FGDS pumproom system calibration gas exhausted.","Accommodation ","Cargo / Ballast Systems","Human Error","8.46","Very High","","","RO raised and received. Bottle renewed.","2019-05-31","DBAU180221","Completed","2019-04-30","No","No","No","Internal"]
[null,null,null,null,4467,"25/10/2019 11:09:10 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","IGG operation not checked for long time.","Inert Gas","Cargo / Ballast Systems","Human Error","10.32","Very High","","","PI controller found not working satisfactory, same cheked and found few control air lines leaking, same rectified. ","2019-05-20","V-DBAU013309/19","Completed","2019-05-10","No","No","No","Internal"]
[null,null,null,null,4468,"25/10/2019 11:13:18 AM","2019-05-12","Deficiency","Ship Staff","Ship Staff Insp.","Stern tube Lub. oil flow meter defective.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","RO raised and recived, same fitted.","2019-05-12","V-DBAU013360/19","Completed","2019-05-12","No","No","No","Internal"]
[null,null,null,null,4469,"25/10/2019 11:15:18 AM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Provision crane - Boom rest pad/platform rusty.","Deck Mach.","Structural Condn. / WT integrity ","Equipment Related","11.8","Low","","","De-rusted and pinted.","2019-05-20","","Completed","2019-05-21","No","No","No","Internal"]
[null,null,null,null,4470,"25/10/2019 11:18:19 AM","2019-02-04","Deficiency","Ship Staff","Ship Staff Insp.","Mooring winch brake cylinder wasted and holed - M5,M6,M7 & M8.","Mooring Mach.","Mooring","Equipment Related","9.15","Medium","","","Repaired temporarily by welding doubler in E/R workshop. Spares received on 29th Apr 2019 nad replaced defective brake cylinders.","2019-05-20","DBAU190057","Completed","2019-05-21","No","No","No","Internal"]
[null,null,null,null,4471,"25/10/2019 11:20:23 AM","2019-01-06","Observation","Ship Staff","Ship Staff Insp.","Service air compressor air radiator leaking.","Air Comp.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Received new compressor on 26th Mar 2019 and installed, working satisfactory.","2019-05-20","","Completed","2019-05-21","No","No","No","Internal"]
[null,null,null,null,4472,"25/10/2019 11:24:05 AM","2019-05-21","Breakdown","Ship Staff","Ship Staff Insp.","No. 2 AC Compressor cyclinder head and pistons to inspect due to abnormal noise.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Play in port bank fwd piston gudgeon pin bush. All pistons, cylinder heads checked and spares replaced. Sump oil renewed, working satisfactory.","2019-05-21","V-DBAU013548/19","Completed","2019-05-21","No","No","No","Internal"]
[null,null,null,null,4473,"25/10/2019 11:26:33 AM","2019-05-24","Deficiency","Ship Staff","Ship Staff Insp.","Port provision crane found to make noise during luffing operation due to worn out flange bearing.","Deck Mach.","Structural Condn. / WT integrity ","Equipment Related","11.8","Low","","","Added in REFMAN.","2019-11-30","","Completed","2019-05-24","No","No","No","Internal"]
[null,null,null,null,4474,"25/10/2019 11:28:49 AM","2019-05-24","Observation","Ship Staff","Ship Staff Insp.","Atmospheric condenser sea water outlet line after the valve needs to be renewed with rubber coating.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Added in REFMAN.","2019-11-30","","Completed","2019-05-24","No","No","No","Internal"]
[null,null,null,null,4475,"25/10/2019 11:31:07 AM","2019-05-22","Deficiency","Ship Staff","Ship Staff Insp.","No.1 Aux Boiler FD fan air intake trunking crack to weld.","Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Cracked area gouged and welded. Boiler tried out and no leaks noted.","2019-05-24","","Completed","2019-05-24","No","No","No","Internal"]
[null,null,null,null,4476,"25/10/2019 11:33:20 AM","2019-05-26","Deficiency","Ship Staff","Ship Staff Insp.","Hose handling crane (port) : replace valve block No.104","Deck Mach.","Structural Condn. / WT integrity ","Equipment Related","8.5","Very High","","","Replaced valve block.","2019-05-30","DBAU195047","Completed","2019-05-28","No","No","No","Internal"]
[null,null,null,null,4477,"25/10/2019 11:35:17 AM","2019-05-10","Deficiency","Ship Staff","Ship Staff Insp.","No.2 COPT speed control governer switch in CCR to replace as defective.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","10.32","Very High","","","Replaced and tested.","2019-05-31","V-DBAU013589/19","Completed","2019-05-28","No","No","No","Internal"]
[null,null,null,null,4478,"25/10/2019 11:37:13 AM","2019-05-17","Deficiency","Ship Staff","Ship Staff Insp.","Fresh water generator ejector pump discharge valve to replcae as corroded.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.31","Very High","","","Spares recived on 25th May 2019. Valve replaced and put in service.","2019-05-30","V-DBAU13626/19","Completed","2019-05-30","No","No","No","Internal"]
[null,null,null,null,4479,"25/10/2019 12:17:45 PM","2019-05-08","Deficiency","Ship Staff","Ship Staff Insp.","Local fire fighting alarn control panel : push button defective","Critical Equip.","ISM Related","Equipment Related","5.39","Very High","","","RO received ON 25 MAY 2019. Office concurrence taken and push button replaced. Test carried out in Incinerator area. Working satisfactory. Hypermist system put back in auto mode.","2019-05-31","DBAU190080, V-DBAU013666/19","Completed","2019-05-30","No","No","No","Internal"]
[null,null,null,null,4480,"25/10/2019 12:20:30 PM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Incinerator exhaust blower vent controller defective.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Exhaust blower vent controller replaced, tried out. Sludge incineration tried out. Alarms and trips tested, working satisfactory.","2019-06-03","","Completed","2019-06-01","No","No","No","Internal"]
[null,null,null,null,4481,"25/10/2019 12:23:36 PM","2019-06-02","Deficiency","Ship Staff","Ship Staff Insp.","AE#3 : Air cooler to pressure test FW side as leaking","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Air cooler removed, chemically cleaned, pressure tested, tube plugged, boxed back and put in service. No leaks in system.","2019-06-10","","Completed","2019-06-04","No","No","No","Internal"]
[null,null,null,null,4482,"25/10/2019 12:50:26 PM","2019-06-07","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AE#1,2,3 : Alternator side to clean with air and chemical.","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Added to REFMAN.","2019-11-30","","Completed","2019-06-07","No","No","No","Internal"]
[null,null,null,null,4483,"25/10/2019 12:52:58 PM","2019-06-07","Deficiency","Ship Staff","Ship Staff Insp.","AE#1 : Mechanical overspeed mechnism to replace, dur to not operational while testing of alarms and trips(routine).","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Replaced with spare overspeed mechnism, tried out, working satisfactory.","2019-06-07","V-DBAU013804/19","Completed","2019-06-07","No","No","No","Internal"]
[null,null,null,null,4484,"25/10/2019 12:55:26 PM","2019-05-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Grey water line modification.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","External Factors","10.32","Very High","","","Consumable recived 25 MAY 2019, job completed, drawings, photos and permits added in PAL.","2019-06-15","V-DBAU013871/19","Completed","2019-06-10","No","No","No","Internal"]
[null,null,null,null,4485,"25/10/2019 12:58:04 PM","2019-05-11","Deficiency","Ship Staff","Suptd. Insp.","ME OMD : to replace PCB due to message in screen\"Replace EEPROM\"","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.21","Medium","","","PCB replaced and tested, working satisfactory.","2019-06-15","V-DBAU013903/19","Completed","2019-06-13","No","No","No","Internal"]
[null,null,null,null,4486,"25/10/2019 1:02:15 PM","2019-06-10","Deficiency","Ship Staff","Ship Staff Insp.","FW Generator : Evaporator bottom cover to remove as corroded in a section area, due to sea water seepage.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.31","Very High","","","Bottom and cover removed, found section area corroded (about 40 mm hole). Ingress of seawater dur to damage of rubber coating section area inserted, welded and fitted back. ","2019-06-15","V-DBAU013930/19","Completed","2019-06-14","No","No","No","Internal"]
[null,null,null,null,4487,"25/10/2019 12:26:21 PM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","U-Clamps on the IG line  - at china passage rusted and wasted.","Deck Pipe / Fittings","General Appearance","External Factors","11.4","Very High","","","U-Clamps replaced. De-rusting and painting of support angle bars carried out.","2019-06-15","","Completed","2019-06-06","No","No","No","Internal"]
[null,null,null,null,4488,"25/10/2019 1:06:39 PM","2019-03-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All hydraulic valve boxes hinges packing channels rusty.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","11.3","Medium","","","Channels de-rusted and painted.","2019-06-15","","Completed","2019-06-14","No","No","No","Internal"]
[null,null,null,null,4489,"25/10/2019 1:10:43 PM","2019-06-16","Deficiency","Ship Staff","Ship Staff Insp.","E/R Ventilation dampers actuators to replace as air sealing bushers/o-rings leaking. ","LSA / FFA","LSA / FFA Appliances","Equipment Related","10.32","Very High","","","Acutators received, same replaced and tested, working satisfactory.","2019-06-30","V-DBAU014044/19","Completed","2019-06-20","No","No","No","Internal"]
[null,null,null,null,4490,"25/10/2019 1:13:37 PM","2019-06-21","Deficiency","Ship Staff","Ship Staff Insp.","ME Fuel oil circulating pump No.1 to overhaul. Found spider coupling damaged and hard to turn during inspection.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pump overhauled, spider coupling and pump bearing replaced. Mechanical seal in good condition, tried out and working satisfactory.","2019-06-21","V-DBAU014042/19","Completed","2019-06-21","No","No","No","Internal"]
[null,null,null,null,4491,"25/10/2019 1:16:41 PM","2019-06-21","Deficiency","Ship Staff","Ship Staff Insp.","HFO auto backwash filter top cover : renew O-rings and seal as leaking.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Top cover overhauled and replaced O rings and seals. Put back in service.","2019-06-21","V-DBAU014043/19","Completed","2019-06-21","No","No","No","Internal"]
[null,null,null,null,4492,"25/10/2019 1:20:29 PM","2019-06-28","Deficiency","Ship Staff","Ship Staff Insp.","Incinerator : Combustion chamber thermocouple to replace as defective.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Same replaced, tried out. Found working satisfactory.","2019-06-28","V-DBAU014069/19, DBAU190150","Completed","2019-06-28","No","No","No","Internal"]
[null,null,null,null,4493,"25/10/2019 1:23:20 PM","2019-05-22","Observation","Ship Staff","Ship Staff Insp.","BHC indication plate of varios mooring winches heavily corroded.","Mooring Mach.","Mooring","Equipment Related","9.7","Medium","","","New plates for BHC fabricated and fixed back.","2019-07-15","","Completed","2019-06-19","No","No","No","Internal"]
[null,null,null,null,4494,"25/10/2019 1:25:53 PM","2019-06-22","Deficiency","Ship Staff","Ship Staff Insp.","E/R Sunken deck whether tight entrance door(port) hinge pin broken, same to be removed adn fabricated.","Miscellaneous","Eng. / Strg. Comp.","External Factors","11.6","Medium","","","Pin fabricated and fixed back.","2019-06-30","","Completed","2019-06-30","No","No","No","Internal"]
[null,null,null,null,4495,"25/10/2019 1:28:03 PM","2019-07-01","Deficiency","Ship Staff","Ship Staff Insp.","Bilge well Stbd : new gratings to fabicate as corroded.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","External Factors","10.29","Medium","","","Gratings fabricated and fixed back.","2019-07-15","V-DBAU002306/17","Completed","2019-07-10","No","No","No","Internal"]
[null,null,null,null,4496,"25/10/2019 1:30:00 PM","2019-06-27","Deficiency","Ship Staff","Ship Staff Insp.","Brake cylinder of mooring winch W1A corroded, wasted and holed.","Mooring Mach.","Mooring","Equipment Related","9.15","Medium","","","Brake cylinder renewed and BHC tested, found satisfactory.","2019-07-12","","Completed","2019-07-10","No","No","No","Internal"]
[null,null,null,null,4497,"25/10/2019 1:32:56 PM","2019-05-27","Breakdown","Ship Staff","Ship Staff Insp.","Control Air compresser : pin hole in the air cooler.","Air Comp.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Leak identified and arrested.","2019-07-15","V-DBAU013128/19","Completed","2019-07-02","No","No","No","Internal"]
[null,null,null,null,4498,"25/10/2019 1:35:24 PM","2019-07-15","Deficiency","Ship Staff","Ship Staff Insp.","HFO auto backwash filter : leak due to wear down of motor shaft support.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Motor support replaced found no leaks, working satisfactry.","2019-07-15","V-DBAU014592/19","Completed","2019-07-15","No","No","No","Internal"]
[null,null,null,null,4499,"25/10/2019 1:43:28 PM","2019-07-23","Deficiency","Ship Staff","Ship Staff Insp.","No.1 & No.2 bilge fire and GS Pump priming pump engaging cycliner not functioning properly.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","5.38","High","","","Priming unit engaging cylinder removed from place and overhauled.","2019-07-26","","Completed","2019-07-25","No","No","No","Internal"]
[null,null,null,null,4500,"25/10/2019 1:45:57 PM","2019-05-15","Deficiency","Ship Staff","Ship Staff Insp.","Hooter for E/R bottom platform not working.","Miscellaneous","Eng. / Strg. Comp.","External Factors","10.37","Medium","","","Hooter renewed with the spare.","2019-09-01","V-DBAU014924/19, DBAU190133","Completed","2019-08-05","No","No","No","Internal"]
[null,null,null,null,4501,"25/10/2019 1:48:11 PM","2019-06-19","Deficiency","Ship Staff","Ship Staff Insp.","E/R Workshop AC : Efficiency low due to under rated evaporator coil.","Aux. Mach.","MLC Related","Equipment Related","10.32","Very High","","","Workshop AC Evaporator renewed with new one.","2019-07-31","V-DBAU014988/19, DBAU190141","Completed","2019-08-08","No","No","No","Internal"]
[null,null,null,null,4502,"25/10/2019 1:52:14 PM","2019-06-23","Deficiency","Ship Staff","Ship Staff Insp.","Control air dryer : Control air low pressure. Problem traced to decsiccant, which need to replace every 2 years.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Decsiccant renewed with spare, control air dryer shuttle valve renewed.","2019-07-31","V-DBAU004454/17, DBAU190142","Completed","2019-08-03","No","No","No","Internal"]
[null,null,null,null,4503,"25/10/2019 1:59:21 PM","2019-08-03","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","air trunking fwd of IGG holed.","Miscellaneous","Eng. / Strg. Comp.","External Factors","10.32","Very High","","","trunking repaired by welding and insert.","2019-08-31","","Completed","2019-08-09","No","No","No","Internal"]
[null,null,null,null,4504,"25/10/2019 1:55:07 PM","2019-07-29","Deficiency","Ship Staff","Ship Staff Insp.","SAT-C Antenna on aft mast parted from base.","Nav & comm. equip.","Navigation","Equipment Related","11.8","Low","","","Permanent repair carried out.","2019-08-29","","Completed","2019-08-11","No","No","No","Internal"]
[null,null,null,null,4505,"25/10/2019 2:03:16 PM","2019-04-30","Deficiency","Ship Staff","Ship Staff Insp.","atmospheric condenser tubes chocked by 47%needs renewal.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","new atmospheric condenser installed in place and put in use.","2019-07-31","DBAU195066","Completed","2019-09-05","No","No","No","Internal"]
[null,null,null,null,4506,"25/10/2019 2:07:58 PM","2019-06-28","Deficiency","Ship Staff","Ship Staff Insp.","various ligthing diffusers needs to be replaceddeffective, wear and tear)","Elect. Mach. & Equip.","Eng. / Strg. Comp.","External Factors","10.15","Low","","","diffusers replaced with spare one.","2019-07-31","DBAU190149","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,4507,"25/10/2019 2:11:46 PM","2019-07-20","Deficiency","Ship Staff","Ship Staff Insp.","LT cooler #2(aft):SW valves not holding, planned to dismantle and clean the plates.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Renewed the valve not holding up.","2019-08-15","DBAU190160","Completed","2019-09-04","No","No","No","Internal"]
[null,null,null,null,4508,"25/10/2019 2:15:11 PM","2019-07-30","Deficiency","Ship Staff","Ship Staff Insp.","#2 LO purifier :auto operation function not working.","Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Heater used from no.1 system, the purifier working satisfactory.","2019-08-30","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,4509,"25/10/2019 2:18:26 PM","2019-08-05","Deficiency","Ship Staff","Ship Staff Insp.","Minor leakage from ME unit #7 Exhaust valve jacket water outlet pipe flange","Main Engine ","Eng. / Strg. Comp.","Behaviour Based,Equipment Related","10.29","Medium","","","Gasket renewed, leakage rectified.","2019-09-30","","Completed","2019-09-06","No","No","No","Internal"]
[null,null,null,null,4510,"25/10/2019 2:21:08 PM","2019-09-12","Deficiency","Ship Staff","Ship Staff Insp.","No.1 HFO purifier upper hood leaking same need to be replaced.","Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Upper hood replaced with new one, tried out found no leak.","2019-09-15","","Completed","2019-09-14","No","No","No","Internal"]
[null,null,null,null,null,"25/10/2019 2:43:29 PM","2019-07-29","Deficiency","Ship Staff","Ship Staff Insp.","Midship darft gauge port side shwoing incorrect reading.","Aux. Mach.","Structural Condn. / WT integrity ","Equipment Related",11.1,"High","Not Applicable","Not Applicable","Span and zero adjustemnt carried out. SAAB and indicator both are showing correct / APPROX. same reading. ","2019-10-31",null,"Completed","2019-10-28","No",null,null,"Internal"]
[null,null,null,null,null,"25/10/2019 3:17:55 PM","2019-07-29","Deficiency","Ship Staff","Ship Staff Insp.","Midship draft gauge stbd side showing incorrect reading.","Miscellaneous","Cargo / Ballast Systems","Equipment Related",11.1,"High","Not Applicable","Not Applicable","Span and zero adjustment carried out. SAAB and indicator both are showing correct / APPROX. same reading.","2019-10-31",null,"Completed","2019-10-28","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["LSA / FFA Appliances",8]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["MARPOL Related",9]
["ISM Related",7]
["ISPS Related",10]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Condn of Class / Memo",null,5]
["Critical Equipment",null,4]
["Deficiency",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":427,"n_cols":3,"rows_kept":427,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",8243]
["1.10","Low",8252]
["1.11","Low",8253]
["1.12","Low",8254]
["1.13","Low",8255]
["1.14","Low",8256]
["1.15","Low",8257]
["1.16","Low",8259]
["1.17","Low",8260]
["1.18","Low",8261]
["1.19","Low",8262]
["1.2","Low",8244]
["1.20","Low",8263]
["1.21","Low",8265]
["1.22","Low",8266]
["1.23","Low",8267]
["1.24","Low",8268]
["1.25","Low",8269]
["1.26","Low",8270]
["1.3","Low",8245]
["1.4","Low",8246]
["1.5","Low",8247]
["1.6","Low",8248]
["1.7","Low",8249]
["1.8","Low",8250]
["1.9","Low",8251]
["1.99","High",11258]
["10.1","Medium",8461]
["10.10","High",8470]
["10.11","Medium",8471]
["10.12","Very High",8472]
["10.13","Very High",8473]
["10.14","Medium",8474]
["10.15","Low",8475]
["10.16","Very High",8476]
["10.17","Very High",8477]
["10.18","High",8478]
["10.19","Very High",8479]
["10.2","Low",8462]
["10.20","High",8480]
["10.21","Medium",8481]
["10.22","Low",8482]
["10.23","Medium",8483]
["10.24","Low",8484]
["10.25","Very High",8485]
["10.26","High",8486]
["10.27","Medium",8487]
["10.28","Low",8488]
["10.29","Medium",8489]
["10.3","Medium",8463]
["10.30","High",8490]
["10.31","Very High",8491]
["10.32","Very High",8492]
["10.33","High",8493]
["10.34","High",8494]
["10.35","Very High",8495]
["10.36","Very High",8496]
["10.37","Medium",8497]
["10.38","Medium",8498]
["10.39","High",8499]
["10.4","High",8464]
["10.40","Medium",8500]
["10.41","Medium",8501]
["10.42","Medium",8502]
["10.43","Medium",8503]
["10.44","Medium",8504]
["10.45","Very High",8505]
["10.46","High",8506]
["10.47","Medium",8507]
["10.48","High",8508]
["10.49","Medium",8509]
["10.5","Low",8465]
["10.50","High",8510]
["10.51","Low",8511]
["10.52","Medium",8512]
["10.53","Medium",8513]
["10.54","High",8514]
["10.55","Low",8515]
["10.6","Very High",8466]
["10.7","Medium",8467]
["10.8","Medium",8468]
["10.9","Medium",8469]
["10.99","High",8516]
["11.1","High",8420]
["11.10","Medium",8429]
["11.11","Very High",8430]
["11.12","Low",8431]
["11.13","Low",8432]
["11.14","Medium",8433]
["11.15","Low",8434]
["11.16","Low",8435]
["11.17","Low",8436]
["11.2","Medium",8421]
["11.3","Medium",8422]
["11.4","Very High",8423]
["11.5","Medium",8424]
["11.6","Medium",8425]
["11.7","High",8426]
["11.8","Low",8427]
["11.9","Low",8428]
["11.99","High",8437]
["12.1","High",8438]
["12.10","High",8448]
["12.11","High",8449]
["12.12","High",8450]
["12.13","High",8451]
["12.14","High",8452]
["12.15","High",8453]
["12.16","High",8454]
["12.17","High",8455]
["12.18","High",8456]
["12.19","High",8457]
["12.2","High",8439]
["12.20","High",8458]
["12.21","High",8459]
["12.3","High",8441]
["12.4","High",8442]
["12.5","High",8443]
["12.6","High",8444]
["12.7","High",8445]
["12.8","High",8446]
["12.9","High",8447]
["12.99","High",8460]
["2.1","Very High",8296]
["2.1.9","Very High",11259]
["2.10","Medium",8304]
["2.11","Medium",8305]
["2.12","Low",8306]
["2.13","Low",8307]
["2.14","Low",8308]
["2.15","Low",8309]
["2.16","Medium",8310]
["2.2","Medium",8297]
["2.3","High",8295]
["2.4","Medium",8298]
["2.5","Medium",8299]
["2.6","Low",8300]
["2.7","High",8301]
["2.8","High",8302]
["2.9","Medium",8303]
["2.99","High",8311]
["3.1","High",8312]
["3.2","Very High",8313]
["3.3","High",8314]
["3.4","Low",8294]
["3.5","Medium",8315]
["3.6","High",8316]
["3.7","Very High",8317]
["3.8","Very High",8318]
["3.99","High",8319]
["4.1","High",8320]
["4.10","High",8329]
["4.11","Medium",8330]
["4.12","Very High",8331]
["4.13","Very High",8332]
["4.14","Very High",8333]
["4.15","Very High",8334]
["4.16","Very High",8335]
["4.17","Very High",8336]
["4.18","Very High",8337]
["4.19","Low",8338]
["4.2","Medium",8321]
["4.20","Very High",8339]
["4.21","High",8340]
["4.22","Low",8341]
["4.23","High",8342]
["4.24","High",8343]
["4.25","Low",8344]
["4.26","Low",8345]
["4.27","High",8346]
["4.3","Medium",8322]
["4.4","High",8323]
["4.5","Very High",8324]
["4.6","Medium",8325]
["4.7","High",8326]
["4.8","Medium",8327]
["4.9","Medium",8328]
["4.99","High",8347]
["5.1","Very High",8517]
["5.10","High",8526]
["5.11","Low",8527]
["5.12","Medium",8528]
["5.13","High",8529]
["5.14","Very High",8530]
["5.15","Medium",8531]
["5.16","Very High",8532]
["5.17","Very High",8533]
["5.18","High",8534]
["5.19","Medium",8535]
["5.2","Very High",8518]
["5.20","Medium",8536]
["5.21","Medium",8537]
["5.22","High",8539]
["5.23","Very High",8540]
["5.24","Very High",8541]
["5.25","Medium",8542]
["5.26","Medium",8543]
["5.27","Medium",8544]
["5.28","Very High",8545]
["5.29","High",8546]
["5.3","Low",8519]
["5.30","High",8547]
["5.31","High",8548]
["5.32","High",8549]
["5.33","High",8550]
["5.34","Low",8551]
["5.35","Medium",8552]
["5.36","Low",8553]
["5.37","Low",8554]
["5.38","High",8555]
["5.39","Very High",8556]
["5.4","High",8520]
["5.40","Very High",8557]
["5.41","Very High",8558]
["5.42","Medium",8559]
["5.43","High",8560]
["5.44","High",8561]
["5.45","Medium",8564]
["5.46","Medium",8565]
["5.47","Medium",8566]
["5.48","Medium",8567]
["5.5","Low",8521]
["5.6","Low",8522]
["5.7","Medium",8523]
["5.8","Medium",8524]
["5.9","Very High",8525]
["5.99","High",8568]
["6.1","Medium",8348]
["6.10","Low",8357]
["6.11","High",8358]
["6.12","Medium",8359]
["6.13","Low",8360]
["6.14","High",8361]
["6.15","High",8362]
["6.16","Very High",8363]
["6.17","Very High",8364]
["6.18","Medium",8365]
["6.19","Low",8366]
["6.2","High",8349]
["6.20","Medium",8367]
["6.21","High",8368]
["6.22","Medium",8369]
["6.3","Low",8350]
["6.4","High",8351]
["6.5","Medium",8352]
["6.6","Medium",8353]
["6.7","High",8354]
["6.8","High",8355]
["6.9","Low",8356]
["6.99","High",8370]
["7.1","High",8371]
["7.10","High",8380]
["7.11","High",8381]
["7.12","High",8382]
["7.13","Medium",8383]
["7.14","Medium",8384]
["7.15","High",8385]
["7.16","High",8386]
["7.17","High",8387]
["7.2","High",8372]
["7.3","Low",8373]
["7.4","Low",8374]
["7.5","Low",8375]
["7.6","Medium",8376]
["7.7","Low",8377]
["7.8","High",8378]
["7.9","High",8379]
["7.99","High",8388]
["8.1","Very High",8569]
["8.10","Very High",8578]
["8.100","Low",11227]
["8.101","Medium",11228]
["8.102","Low",11229]
["8.103","Low",11230]
["8.104","Low",11231]
["8.105","Medium",11232]
["8.106","Medium",11233]
["8.107","Low",11234]
["8.108","High",11235]
["8.109","Very High",11236]
["8.11","Medium",8579]
["8.110","High",11237]
["8.111","Medium",11238]
["8.112","High",11239]
["8.113","Medium",11240]
["8.114","Low",11241]
["8.115","High",11242]
["8.116","Medium",11243]
["8.117","Medium",11244]
["8.118","Medium",11245]
["8.119","High",11246]
["8.12","Medium",8580]
["8.120","High",11247]
["8.121","Medium",11248]
["8.122","High",11249]
["8.123","High",11250]
["8.124","Low",11251]
["8.125","High",11252]
["8.126","Medium",11253]
["8.127","Medium",11254]
["8.13","Medium",8581]
["8.14","Very High",8582]
["8.15","High",8583]
["8.16","Very High",8584]
["8.17","Low",8585]
["8.18","High",8586]
["8.19","High",8587]
["8.199","High",11255]
["8.2","Medium",8570]
["8.20","Medium",8588]
["8.21","High",8589]
["8.22","Very High",8590]
["8.23","Medium",8591]
["8.24","Medium",8592]
["8.25","Very High",8593]
["8.26","High",8594]
["8.27","Medium",8595]
["8.28","Medium",8596]
["8.29","High",8598]
["8.3","Very High",8571]
["8.30","High",8599]
["8.31","High",8600]
["8.32","Low",8601]
["8.33","Medium",8602]
["8.34","High",8603]
["8.35","Medium",8604]
["8.36","Medium",8605]
["8.37","High",8607]
["8.38","Medium",8608]
["8.39","Medium",8609]
["8.4","Medium",8572]
["8.40","High",8610]
["8.41","Medium",8611]
["8.42","Medium",8612]
["8.43","Very High",8613]
["8.44","High",8615]
["8.45","High",8616]
["8.46","Very High",8617]
["8.47","Very High",8618]
["8.48","Medium",8619]
["8.49","High",8620]
["8.5","Very High",8573]
["8.50","Medium",8621]
["8.51","Low",8622]
["8.52","Low",8623]
["8.53","Low",8624]
["8.54","High",8625]
["8.55","Low",11182]
["8.56","Medium",11183]
["8.57","Medium",11184]
["8.58","High",11185]
["8.59","High",11186]
["8.6","Medium",8574]
["8.60","High",11187]
["8.61","Medium",11188]
["8.62","Very High",11189]
["8.63","High",11190]
["8.64","Medium",11191]
["8.65","Low",11192]
["8.66","High",11193]
["8.67","High",11194]
["8.68","High",11195]
["8.69","Medium",11196]
["8.7","High",8575]
["8.70","Medium",11197]
["8.71","Very High",11198]
["8.72","Medium",11199]
["8.73","Medium",11200]
["8.74","High",11201]
["8.75","Medium",11202]
["8.76","Medium",11203]
["8.77","Medium",11204]
["8.78","Medium",11205]
["8.79","Medium",11206]
["8.8","Medium",8576]
["8.80","Medium",11207]
["8.81","Low",11208]
["8.82","Medium",11209]
["8.83","Low",11210]
["8.84","Low",11211]
["8.85","Medium",11212]
["8.86","Medium",11213]
["8.87","Medium",11214]
["8.88","Low",11215]
["8.89","High",11216]
["8.9","High",8577]
["8.90","High",11217]
["8.91","High",11218]
["8.92","Medium",11219]
["8.93","Low",11220]
["8.94","Low",11221]
["8.95","Medium",11222]
["8.96","Medium",11223]
["8.97","Low",11224]
["8.98","High",11225]
["8.99","Medium",11226]
["9.1","Low",8390]
["9.10","Medium",8399]
["9.11","Medium",8400]
["9.12","Medium",8401]
["9.13","Low",8402]
["9.14","Medium",8403]
["9.15","Medium",8404]
["9.16","High",8405]
["9.17","High",8406]
["9.18","Low",8407]
["9.19","Low",8408]
["9.2","Very High",8391]
["9.20","Medium",8409]
["9.21","Medium",8410]
["9.22","Low",8411]
["9.23","Low",8412]
["9.24","Medium",8413]
["9.25","Low",8414]
["9.26","Low",8415]
["9.27","Low",8416]
["9.28","Medium",8417]
["9.29","Low",8418]
["9.3","Very High",8392]
["9.4","High",8393]
["9.5","High",8394]
["9.6","Low",8395]
["9.7","Medium",8396]
["9.8","Medium",8397]
["9.9","Medium",8398]
["9.99","High",8419]

{"sheet":"Equipment_list","index":7,"n_rows":21,"n_cols":3,"rows_kept":21,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation ",null,12]
["Air Comp.",null,8]
["Aux. Engine",null,4]
["Aux. Mach.",null,7]
["Boiler",null,5]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck Mach.",null,18]
["Deck Pipe / Fittings",null,20]
["Documentation",null,21]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Main Engine ",null,3]
["Miscellaneous",null,22]
["Nav & comm. equip.",null,11]
["ER Pipes, valves & fittings",null,9]
["Purifier",null,6]
["Mooring Mach.",null,15]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":15,"n_cols":2,"rows_kept":15,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Others (Eg. Insurance etc.)",12]
["Flag State Insp.",5]
["Ship Staff Insp.",15]
["IT Audit",10]
["OM Insp. (Eg. SIRE, CDI etc.)",6]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["PSC Inspection",4]
["Suptd. Insp.",13]
["Terminal Insp.",11]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["Others (Eg. Insurance etc.)",null,9]
["FSC Inspector",null,5]
["Owner / Marine / Tech. Suptd.",null,3]
["PSC Insp.",null,6]
["Ship Staff",null,2]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["24","DHT BAUHINIA","24_1572074328523.xlsm"]