{"text_format":"1","workbook":"xlsx","n_sheets":20,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":29,"n_cols":28,"rows_kept":29,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","04-Dec-2019",null,null,"Ship Name","DHT FALCON (19-11-2019)"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,2622,"2019-10-12 06:08:20.000","2019-09-30","Observation","Ship Staff","Ship Staff Insp.","Mooring winch M5 leak from winch motor (inner motor)","Mooring Mach.","Mooring","Equipment Related","9.14","Medium","","","Renew the hydraulic motor","2019-11-30","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,2625,"2019-10-12 06:27:47.000","2019-08-30","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Paint faliure noted on many areas on deck","Miscellaneous","General Appearance","Equipment Related","11.4","Very High","","","De-rusting with hydroblaster, grit blaster is in progress on deck","2019-12-30","","In progress",null,"No","No","No","Internal","date revised"]
[null,null,null,null,2626,"2019-10-12 06:30:05.999","2019-08-30","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The Cargo and Marpol line has rust patches near midship area","Deck Pipe / Fittings","General Appearance","Equipment Related","11.4","Very High","","","De-rusting and painting is in progress","2019-12-30","","In progress",null,"No","No","No","Internal","revised completion date"]
[null,null,null,null,2627,"2019-10-12 06:33:49.999","2019-08-30","Observation","Ship Staff","Ship Staff Insp.","The anchor chain clearing rod is bent on both the gypsies","Mooring Mach.","Mooring","Equipment Related","9.2","Very High","","","DD Spec prepared in Refman","2021-07-31","","Deferred to D D",null,"No","No","No","Internal"]
[null,null,null,null,2631,"2019-10-22 04:06:56.999","2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Helipad area cosmetics to improve.","Deck Pipe / Fittings","General Appearance","Equipment Related","11.7","High","","","Helipad area to be derusted and painted.","2020-01-01","","Not Started",null,"No","No","No","Internal","update in weekly reports"]
[null,null,null,null,2634,"2019-10-22 04:16:10.000","2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Stbd Life boat platform gratings to renew.","Deck Pipe / Fittings","General Appearance","Equipment Related","11.7","High","","","Gratings to be renewed with new ones.","2020-01-01","","Not Started",null,"No","No","No","Internal","kindly complete on ASAP and close out"]
[null,null,null,null,2637,"2019-10-22 04:19:42.999","2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Gantry crane to paint.","Deck Mach.","General Appearance","Equipment Related","11.7","High","","","Planned for future.","2020-01-01","","Not Started",null,"No","No","No","Internal","close out ASAP , before arrival port in China"]
[null,null,null,null,2638,"2019-10-22 04:20:33.000","2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Ship side railings to clean and paint.","Deck Pipe / Fittings","General Appearance","Equipment Related","11.7","High","","","Railings will be cleaned, derusted and painted.","2020-01-01","","Not Started",null,"No","No","No","Internal","ok"]
[null,null,null,null,2662,"17/10/2019 6:53:43 AM","2019-11-15","Deficiency","Ship Staff","Ship Staff Insp.","No. 2 Hydrophore pump and DW pump to overhaul","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.1,"Medium","Not Applicable","Not Applicable","No. 2 Hydrophore pump and drinking water hydrophore pump to be overhauled with new spares, no spare shaft onboard, awaiting for spares.","2019-12-31",null,"Waiting spare",null,"No","No","No","Internal","raise RO for spares and complete the job on receipt of spares"]
[null,null,null,null,null,"2019-12-16T07:23:33","2019-11-23","Other","Ship Staff","Ship Staff Insp.","FWG DISTILLATE PUMP CASING RINGS WORN OUT, MOTOR BEARING HOUSING WORN OUT, PUMP MOTOR NOT GETTING ALIGNED.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.1,null,"Not Applicable","Not Applicable","TEMPORARY REPAIRS CARRIED OUT. PUMP OPERATING WITH LOW PERFORMANCE.","2019-12-31","DFAL190200","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-12-16T07:26:35","2019-10-28","Non Conformity","Ship Staff","Ship Staff Insp.","Pumproom EX-proof 9 glands (5 light fittings) inappropriate size. Unable to give explosing proof sealing.","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",8.48,"Medium","Not Applicable","Not Applicable","Awaiting spare","2020-01-20","DFAL190214","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-12-16T07:28:23","2019-08-09","Deficiency","Ship Staff","Ship Staff Insp.","SVDR REMOTE ALARM UNIT GIVING FAULTY ALARM. AS PER SERVICE TECHNICIAN ADVICE SAME NEEDS TO BE REPLACED WITH A NEW ONE.","Nav & comm. equip.","Navigation","Equipment Related",4.1100000000000003,"Medium","Not Applicable","Not Applicable","PO RAISED. AWAITING SPARE.","2019-12-25",null,"Waiting spare",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":170,"n_cols":28,"rows_kept":170,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","4-11-2019",null,null,"Ship Name","DHT FALCON (19-11-2019)"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,2630,"20/10/2019 5:40:25 PM","2019-10-16","Observation","Ship Staff","Ship Staff Insp.","Stbd side wing light nut and bolt missing","Deck Pipe / Fittings","General Appearance","Equipment Related","11.7","High","","","Spot derusting carried out. New Bolt & Nut Fixed.","2019-10-31","","Completed","2019-10-27","No","No","No","Internal"]
[null,null,null,null,2640,"2019-10-12 06:12:29.999","2019-08-30","Breakdown","Ship Staff","Ship Staff Insp.","lifeboat stbd side steering gear system gear worn out condition","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.28","Very High","","","Recieved required spares and ractified.","2019-10-15","DFAL190237","Completed","2019-10-10","No","No","No","Internal"]
[null,null,null,null,2641,"17/10/2019 5:26:28 AM","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","STBD. HH crane hyd cylinder eye pin end plate holding bolt broken","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.5","Very High","","","Extracted Broken bolt and fixed new bolt","2019-02-15","","Completed","2019-02-05","No","No","No","Internal"]
[null,null,null,null,2642,"17/10/2019 5:31:53 AM","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","ME starting air manifold, drain line exhaust gas leaking during engine running","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.1","Medium","","","Suspected unit 5 cyl starting air valve leaking. Starting air valve renewed and rectified leakage","2019-10-02","","Completed","2019-10-02","No","No","No","Internal"]
[null,null,null,null,2643,"17/10/2019 5:34:20 AM","2019-02-25","Observation","Ship Staff","Ship Staff Insp.","NO. 2 WBP leaking at spool piece between strainer & pump casing","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.12","Medium","","","Temporary repairs carried out & job added in docking list for permanent repairs.","2019-03-31","","Completed","2019-02-28","No","No","No","Internal"]
[null,null,null,null,2644,"17/10/2019 5:42:47 AM","2019-01-01","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Seepage in both lifeboats from remote wire opening","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.27","Medium","","","Silicone has been put in opening to avoid rain water ingress & checked for water integrity","2019-09-03","","Completed","2019-03-10","No","No","No","Internal"]
[null,null,null,null,2645,"17/10/2019 5:47:36 AM","2019-09-03","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","BA Compressor filling hose, leakage from sealing ring","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.43","High","","","Replaced with spare sealing ring & ordered new spares","2019-10-03","DFAL190108","Completed","2019-10-03","No","No","No","Internal"]
[null,null,null,null,2646,"17/10/2019 5:54:26 AM","2019-01-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hydroblaster to be overhauled on priority and put in use.","Miscellaneous","General Appearance","Equipment Related","11.7","High","","","Rupture disc replaced with the available spares & hydroblaster put in use.","2019-03-15","DFAL190072","Completed","2019-03-11","No","No","No","Internal"]
[null,null,null,null,2647,"17/10/2019 6:01:43 AM","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","Flash back arrestors and pr regulations for gas welding to renew (as per new vetting requirements, 5 yrly renewal)","Aux. Mach.","Eng. / Strg. Comp.","Industry Issue","10.12","Very High","","","Spares received, fitted at Oxygen & acetylene bottles","2019-03-31","","Completed","2019-03-12","No","No","No","Internal"]
[null,null,null,null,2648,"17/10/2019 6:07:48 AM","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","No. 1 FO purifier PCB defective in cold weather conditions , the PCB require warm heat, otherwise its function is satisfacory","Purifier","Eng. / Strg. Comp.","Equipment Related","10.12","Very High","","","New PCB recieved at Singapore and it is replaced, purifier now working satisfacory.","2019-03-16","DFAL180296","Completed","2019-03-14","No","No","No","Internal"]
[null,null,null,null,2649,"17/10/2019 6:11:15 AM","2019-02-02","Deficiency","Ship Staff","Ship Staff Insp.","Emcy DG LO contamination due to cooler flange material erosion and jacket water leak from body cover, holed at multiple places","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.12","Very High","","","Jacket water cover and lube oil cooler renewed. Engine tried out no more leakages observed.","2019-03-28","DFAL190055","Completed","2019-03-11","No","No","No","Internal"]
[null,null,null,null,2650,"17/10/2019 6:13:26 AM","2019-02-27","Deficiency","Ship Staff","Ship Staff Insp.","ME OMD giving fault alarms randomly","Main Engine ","","Equipment Related","10.21","Medium","","","Service engineer attended the job, checked the system and renewed the air pressure regulator","2019-10-03","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,2651,"17/10/2019 6:16:04 AM","2019-02-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Elevator tracks and internals dirty","Elect. Mach. & Equip.","General Appearance","Equipment Related,External Factors","11.7","High","","","Elevator tracks and internals cleaned","2019-03-14","","Completed","2019-03-14","No","No","No","Internal"]
[null,null,null,null,2652,"17/10/2019 6:18:14 AM","2019-02-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ECR door handle needs repair/ replacement","Miscellaneous","General Appearance","Equipment Related","11.7","High","","","ECR door handle repaired","2019-03-14","","Completed","2019-03-14","No","No","No","Internal"]
[null,null,null,null,2653,"17/10/2019 6:21:17 AM","2019-02-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Gangway motors P&S oil stains around","Deck Mach.","General Appearance","Equipment Related","11.7","High","","","Inspection of Filter & oiler unit carried out & rectified.","2019-03-15","","Completed","2019-03-15","No","No","No","Internal"]
[null,null,null,null,2654,"17/10/2019 6:24:44 AM","2019-02-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Accommodation random inspection- crew need to be reminded for better housekeeping","Accommodation ","General Appearance","Behaviour Based","11.7","High","","","Random inspection carried out & ship staff reminded on better housekeeping","2019-03-15","","Completed","2019-03-17","No","No","No","Internal"]
[null,null,null,null,2655,"17/10/2019 6:29:48 AM","2019-03-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Officers mess windows to clean and cooler space to be covered neatly with wood","Accommodation ","General Appearance","Behaviour Based","11.7","High","","","Windows cleaned & cooler space covered.","2019-03-23","","Completed","2019-03-20","No","No","No","Internal"]
[null,null,null,null,2656,"17/10/2019 6:34:37 AM","2019-07-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bridge window shades to repair","Accommodation ","General Appearance","Equipment Related","11.7","High","","","To overhaul the bridge window shades","2019-10-05","","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,2657,"17/10/2019 6:37:06 AM","2019-03-16","Observation","Ship Staff","Ship Staff Insp.","Oil leak observed from M4 mooring winc, found Regulator block leaking","Deck Mach.","Mooring","Equipment Related","9.2","Very High","","","Regulator block overhauled & O-ring renewed","2019-04-30","","Completed","2019-03-19","No","No","No","Internal"]
[null,null,null,null,2658,"17/10/2019 6:39:11 AM","2019-08-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","COW branch valve found very hard to open / shut","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","All COW machine valves lubricated & freed up","2019-08-04","","Completed","2019-08-20","No","No","No","Internal"]
[null,null,null,null,2659,"17/10/2019 6:43:07 AM","2019-08-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel casing cleaning and painting","Miscellaneous","General Appearance","External Factors","11.7","High","","","Funnel casing cleaned / Derusted as required and painted","2019-08-06","","Completed","2019-08-25","No","No","No","Internal"]
[null,null,null,null,2660,"17/10/2019 6:49:29 AM","2019-08-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","IG Branch valves found very hard to open / shut","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.3","Very High","","","Degreasing / lubrication of worm gear actuator carried out for manifold valves & valves freed up","2019-08-04","","Completed","2019-08-27","No","No","No","Internal"]
[null,null,null,null,2661,"17/10/2019 6:51:34 AM","2019-08-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Manifold valves P&S found very hard to open/ shut","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","Degreasing & lubrication of worm gear actuator carried out for manifold valves & valves freed up.","2019-08-04","","Completed","2019-08-31","No","No","No","Internal"]
[null,null,null,null,2663,"17/10/2019 6:55:56 AM","2019-03-22","Deficiency","Ship Staff","Ship Staff Insp.","Main engine Unit no. 3, 6 and 7 exhaust gas leakage from bellow","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.12","Very High","","","The leakage rectified by realigning the bellows","2019-03-31","","Completed","2019-03-28","No","No","No","Internal"]
[null,null,null,null,2664,"17/10/2019 6:58:07 AM","2019-03-22","Deficiency","Ship Staff","Ship Staff Insp.","Main engine unit No. 4 and 7 exhaust valve hydraulic line leakage","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.13","Very High","","","The leakage rectified by removing the O-rings","2019-03-31","","Completed","2019-03-23","No","No","No","Internal"]
[null,null,null,null,2665,"2019-10-17 07:18:04.999","2019-03-19","Deficiency","Ship Staff","Ship Staff Insp.","Main Engine unit No. 3 aft high  pressure pipe leakage from pump side.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The leakage rectified by overhauling the high pressure pipe","2019-03-31","","Completed","2019-04-26","No","No","No","Internal"]
[null,null,null,null,2666,"2019-10-17 07:20:25.000","2019-03-21","Deficiency","Ship Staff","Ship Staff Insp.","Spring air line have a pin hole to rectify","Mooring Mach.","","Equipment Related","9.5","High","","","The leakage rectified by renewing the section","2019-03-31","","Completed","2019-03-25","No","No","No","Internal"]
[null,null,null,null,2667,"2019-10-17 07:22:08.000","2019-01-03","Deficiency","Ship Staff","Ship Staff Insp.","Main engine control air pressure gauge to renew","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.21","Medium","","","The defective pressure gauge renewed","2019-03-31","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,2668,"18/10/2019 12:41:07 AM","2019-03-18","Deficiency","Ship Staff","Ship Staff Insp.","AE jacket cooler no. 1 sea water inlet section to renew as leakage is their from the flange","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The inlet section replaced with fabricated one.","2019-03-31","","Completed","2019-03-27","No","No","No","Internal"]
[null,null,null,null,2669,"18/10/2019 12:43:06 AM","2019-06-03","Deficiency","Ship Staff","Ship Staff Insp.","No. 2 steering gear servo pump, oil leakage observed from tell tale hole, seal to renew.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.39","High","","","Servo pump overhauled and the oil seal renewed","2019-08-04","","Completed","2019-08-07","No","No","No","Internal"]
[null,null,null,null,2670,"18/10/2019 12:44:33 AM","2019-02-03","Deficiency","Ship Staff","Ship Staff Insp.","IGS control air line filter leakage","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","8.22","Very High","","","IGS control air line filter renewed.","2019-03-31","","Completed","2019-03-13","No","No","No","Internal"]
[null,null,null,null,2671,"18/10/2019 12:46:10 AM","2019-03-14","Deficiency","Ship Staff","Ship Staff Insp.","ECR AC sea water inlet pipe section wasted and leaking","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The pipe section fabricated and fitted.","2019-03-31","","Completed","2019-03-26","No","No","No","Internal"]
[null,null,null,null,2672,"18/10/2019 12:48:13 AM","2019-03-03","Deficiency","Ship Staff","Ship Staff Insp.","Main engine jacket cooler sea water outlet section leakage from the flange","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.21","Medium","","","The leakage rectified by renewing the gasket.","2019-03-31","","Completed","2019-03-26","No","No","No","Internal"]
[null,null,null,null,2673,"18/10/2019 12:50:46 AM","2019-03-16","Deficiency","Ship Staff","Ship Staff Insp.","ME air cooler no. 2 sea water inlet section leakage","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The inlet section leakage rectified by replacing the section with fabricated spare. The sacrificial section also renewed and all the gaskets renewed.","2019-03-31","","Completed","2019-03-26","No","No","No","Internal"]
[null,null,null,null,2674,"18/10/2019 12:54:13 AM","2019-03-16","Deficiency","Ship Staff","Ship Staff Insp.","Main engine Air cooler No. 1 sea water inlet and outlet section leakage ","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The inlet section flange side welding totally wasted, the same build up by welding. The inlet side sacrificial section renewed. The outlet section replaceed with fabricated spare.","2019-03-31","","Completed","2019-03-26","No","No","No","Internal"]
[null,null,null,null,2675,"18/10/2019 12:56:04 AM","2019-03-19","Deficiency","Ship Staff","Ship Staff Insp.","Main engine HFO Autobackwash filter inlet and outlet valves not holding.","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The inlet and outlet valves renewed.","2019-03-31","","Completed","2019-03-24","No","No","No","Internal"]
[null,null,null,null,2676,"18/10/2019 12:58:19 AM","2019-03-20","Deficiency","Ship Staff","Ship Staff Insp.","Aux boiler no. 1 steam return valve from economiser leaking from bonnet.","Boiler","Eng. / Strg. Comp.","Equipment Related","10.9","Medium","","","The valve overhauled, gland packing and bonnet gasket renewed.","2019-03-31","","Completed","2019-03-25","No","No","No","Internal"]
[null,null,null,null,2677,"18/10/2019 1:00:02 AM","2019-03-20","Deficiency","Ship Staff","Ship Staff Insp.","ME lube oil cooler sea water inlet section leaking","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.7","Medium","","","The sea water inlet section found totally wasted at the flange, the same build up by welding. The inlet valve also renewed.","2019-03-31","","Completed","2019-03-30","No","No","No","Internal"]
[null,null,null,null,2678,"18/10/2019 1:02:17 AM","2019-03-03","Deficiency","Ship Staff","Ship Staff Insp.","IGS and ejector pump no. 1 seal leaking and the performance poor.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","8.22","Very High","","","The pump overhauled, mouth ring renewed. The performance is satisfactory now.","2019-03-31","","Completed","2019-03-17","No","No","No","Internal"]
[null,null,null,null,2679,"18/10/2019 1:03:48 AM","2019-03-03","Deficiency","Ship Staff","Ship Staff Insp.","Fresh water generator distillate pump making abnormal noise.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.1","Medium","","","The distillate pump overhauled, mouth ring renewed. The performance is satisfactory now.","2019-03-31","","Completed","2019-03-16","No","No","No","Internal"]
[null,null,null,null,2680,"18/10/2019 1:05:17 AM","2019-03-03","Deficiency","Ship Staff","Ship Staff Insp.","Hydraulic power pack No. 2 motor flexible coupling worn out.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","9.15","Medium","","","The spider coupling renewed.","2019-03-31","","Completed","2019-03-15","No","No","No","Internal"]
[null,null,null,null,2681,"18/10/2019 1:07:44 AM","2019-03-25","Deficiency","Ship Staff","Ship Staff Insp.","E/R blower flaps not colsing properly","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","All the flaps greasing carried out and at the sealing surface fire resistant packing placed. Now the doors are closing positively.","2019-03-31","","Completed","2019-03-30","No","No","No","Internal"]
[null,null,null,null,2682,"18/10/2019 1:09:28 AM","2019-03-25","Deficiency","Ship Staff","Ship Staff Insp.","E/R funnel hatch covers not sealing positively.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.11","Medium","","","The funnel hatch covers packings renewed and additional fire resistant packing fitted in such a way that the doors are closing positively now.","2019-03-31","","Completed","2019-03-30","No","No","No","Internal"]
[null,null,null,null,2683,"18/10/2019 1:38:59 AM","2019-03-20","Deficiency","Ship Staff","Ship Staff Insp.","Rudder carrier oil tank leakage.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.16","Very High","","","The gauge glass both side packing renewed and the supply line leakage rectified.","2019-03-31","","Completed","2019-03-29","No","No","No","Internal"]
[null,null,null,null,2684,"18/10/2019 1:40:34 AM","2019-03-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Wasted cable supports around accommodation to renew.","Elect. Mach. & Equip.","General Appearance","Equipment Related","11.7","High","","","Wasted cable supports around accommodation to renew at the earliest.","2019-03-31","","Completed","2019-03-22","No","No","No","Internal"]
[null,null,null,null,2685,"18/10/2019 1:42:24 AM","2019-04-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both cargo manifold tray gratings corroded.","Miscellaneous","General Appearance","Equipment Related","11.7","High","","","Derusting & painting to be carried out for manifold drip tray gratings","2019-04-30","","Completed","2019-04-23","No","No","No","Internal"]
[null,null,null,null,2686,"18/10/2019 1:44:37 AM","2019-03-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CCR & ECR and various common places need to be aesthetically maintained.","Accommodation ","General Appearance","Equipment Related","11.7","High","","","CCR & ECR to be aesthetically maintained.","2019-03-23","","Completed","2019-03-20","No","No","No","Internal"]
[null,null,null,null,2687,"18/10/2019 1:46:09 AM","2019-03-24","Deficiency","Ship Staff","Ship Staff Insp.","AE No. 3 LT water outlet valve bridge found broken","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The valve renewed.","2019-03-31","","Completed","2019-03-27","No","No","No","Internal"]
[null,null,null,null,2688,"18/10/2019 1:48:15 AM","2019-03-26","Deficiency","Ship Staff","Ship Staff Insp.","AC condenser sea water outlet pressure gauge, Ref condenser sea water outlet ressure gauge. Main engine unit no. 6 jacket cooluing water outlet temperature gauge, AE No. 3 Fuel oil inlet temperature gauge defective","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","All defective pressure and temperature gauges renewed.","2019-03-31","","Completed","2019-03-30","No","No","No","Internal"]
[null,null,null,null,2689,"18/10/2019 1:49:46 AM","2019-03-18","Deficiency","Ship Staff","Ship Staff Insp.","Light base around accomodation area wasted","Elect. Mach. & Equip.","General Appearance","Equipment Related","11.7","High","","","New base fabricated.","2019-04-30","","Completed","2019-04-05","No","No","No","Internal"]
[null,null,null,null,2690,"18/10/2019 1:52:32 AM","2019-03-29","Deficiency","Ship Staff","Ship Staff Insp.","ME fuel oil supply pump no. 1 considerable leakage is there from gland.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.8","Medium","","","ME supply pump no. 1 overhauled, bearing metal and gland packing renewed.","2019-04-15","","Completed","2019-04-01","No","No","No","Internal"]
[null,null,null,null,2691,"18/10/2019 2:07:11 AM","2019-03-29","Deficiency","Ship Staff","Ship Staff Insp.","ME fuel oil circulating pump no. 2 considerable leakage is there from gland.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.17","Very High","","","ME circulating pump no. 2 overhauled, bearing metal and gland packing renewed.","2019-04-15","","Completed","2019-04-01","No","No","No","Internal"]
[null,null,null,null,2692,"18/10/2019 2:21:57 AM","2019-01-04","Deficiency","Ship Staff","Ship Staff Insp.","EGE feed pump No. 2 not developing sufficient pressure.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The pump overhauled, all the mouth rings renewed. Now the pump performance is satisfactory.","2019-04-20","","Completed","2019-04-04","No","No","No","Internal"]
[null,null,null,null,2693,"18/10/2019 2:23:38 AM","2019-01-04","Deficiency","Ship Staff","Ship Staff Insp.","Aux boiler No. 2 water outlet valve to circulating pump leaking from gland packing","Boiler","Eng. / Strg. Comp.","Equipment Related","10.8","Medium","","","The boiler depressurised and gland packing renewed.","2019-04-15","","Completed","2019-04-03","No","No","No","Internal"]
[null,null,null,null,2694,"18/10/2019 2:25:50 AM","2019-03-04","Deficiency","Ship Staff","Ship Staff Insp.","ME HFO line overflow piston valve leaking","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.9","Medium","","","Overflow piston valve overhauled, all the O rings renewed.","2019-04-15","","Completed","2019-04-05","No","No","No","Internal"]
[null,null,null,null,2695,"18/10/2019 2:27:23 AM","2019-03-04","Deficiency","Ship Staff","Ship Staff Insp.","AE Emergencty air operated valve between diesel oil line and HFO line leaking from gasket","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The leakage rectified by renewing the gasket.","2019-04-15","","Completed","2019-04-05","No","No","No","Internal"]
[null,null,null,null,2696,"18/10/2019 2:29:37 AM","2019-04-03","Deficiency","Ship Staff","Ship Staff Insp.","ME HFO inlet to heater no. 1 valve gland packing renewed.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The valve gland packing renewed.","2019-04-15","","Completed","2019-05-04","No","No","No","Internal"]
[null,null,null,null,2697,"18/10/2019 2:32:03 AM","2019-04-04","Deficiency","Ship Staff","Ship Staff Insp.","Port Hose handling crane Hyd. metal pipes for boom/heave (up and down) ruptured and oil was leaking heavily.","Deck Mach.","Cargo / Ballast Systems","Equipment Related","8.5","Very High","","","5 piece of metal pipes replaced with new spares available onboard.","2019-04-30","","Completed","2019-04-18","No","No","No","Internal"]
[null,null,null,null,2698,"18/10/2019 2:34:24 AM","2019-04-17","Observation","Ship Staff","Ship Staff Insp.","Hydraulic return line for Port HHC found to be leaking","Deck Mach.","Cargo / Ballast Systems","Equipment Related","8.5","Very High","","","Section of leaking pipe dismantled, repaired & put back in place. Tried out the crane after installation. No leaks observed.","2019-04-30","","Completed","2019-04-18","No","No","No","Internal"]
[null,null,null,null,2699,"18/10/2019 2:36:04 AM","2019-04-17","Observation","Ship Staff","Ship Staff Insp.","Observed a twist  in Port & Stbd anchor cable","Mooring Mach.","Mooring","Equipment Related","8.5","Very High","","","Twist removed from P & S anchor cable","2019-04-30","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,2700,"18/10/2019 2:37:51 AM","2019-04-21","Observation","Ship Staff","Ship Staff Insp.","2 chairs hand rest found broken in Officer's Mess room","Accommodation ","General Appearance","Equipment Related","11.7","High","","","Hand rest repaired for both the chairs & chairs put in use.","2019-04-28","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,2701,"18/10/2019 2:40:05 AM","2019-04-19","Observation","Ship Staff","Ship Staff Insp.","Main steam inlet valve for heating coils on deck found leaking.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.15","High","","","Gasket to be removed.","2019-04-30","","Completed","2019-04-26","No","No","No","Internal"]
[null,null,null,null,2702,"18/10/2019 3:20:56 AM","2019-04-19","Observation","Ship Staff","Ship Staff Insp.","Mooring winch M4 interconnection line between two hydraulic motor found leaking.","Mooring Mach.","Mooring","Equipment Related","9.16","High","","","This line section removed from place and both side O-rings renewed.","2019-04-30","","Completed","2019-04-26","No","No","No","Internal"]
[null,null,null,null,2703,"18/10/2019 3:23:18 AM","2019-04-19","Observation","Ship Staff","Ship Staff Insp.","All three AE lube oil priming pump have some abnormal noise and vibration","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","All three motors overhauled, now working satisfactory.","2019-04-30","","Completed","2019-04-20","No","No","No","Internal"]
[null,null,null,null,2704,"18/10/2019 3:25:01 AM","2019-04-16","Observation","Ship Staff","Ship Staff Insp.","MSB room AC Sea water inlet section leaking","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The section fabricated and fitted","2019-04-30","","Completed","2019-04-16","No","No","No","Internal"]
[null,null,null,null,2705,"18/10/2019 3:27:10 AM","2019-04-16","Observation","Ship Staff","Ship Staff Insp.","Both EGB soot blower motor have some vibration and abnormal noise","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Both motors overhauled","2019-04-30","","Completed","2019-04-16","No","No","No","Internal"]
[null,null,null,null,2706,"18/10/2019 3:43:00 AM","2019-04-16","Observation","Ship Staff","Ship Staff Insp.","Drain Scupper section from lube oil cooler area to stbd. bilge well fully rusted","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Section fabricated and fitted","2019-04-30","","Completed","2019-04-17","No","No","No","Internal"]
[null,null,null,null,2707,"18/10/2019 3:47:06 AM","2019-04-17","Observation","Ship Staff","Ship Staff Insp.","Steam tracing line for HFO found leaking","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Leakage rectified","2019-04-17","","Completed","2019-04-30","No","No","No","Internal"]
[null,null,null,null,2708,"18/10/2019 8:14:16 AM","2019-04-17","Observation","Ship Staff","Ship Staff Insp.","HFO circulating pump no. 1 leaking from gland packing","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.8","Medium","","","Leakage rectified by renewing the packing","2019-04-30","","Completed","2019-04-20","No","No","No","Internal"]
[null,null,null,null,2709,"18/10/2019 8:15:57 AM","2019-04-20","Observation","Ship Staff","Ship Staff Insp.","All three AE pressure gauge panel not secured properly","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Pressure gauge panel secured firmly","2019-04-30","","Completed","2019-04-21","No","No","No","Internal"]
[null,null,null,null,2710,"18/10/2019 8:17:30 AM","2019-04-23","Observation","Ship Staff","Ship Staff Insp.","AE no. 2 sump oil low level alarm found inoperational.","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The sensor cleaned and sensor chamber cleared of sludge. The alarm is operating now.","2019-04-30","","Completed","2019-04-23","No","No","No","Internal"]
[null,null,null,null,2711,"18/10/2019 8:19:17 AM","2019-04-23","Observation","Ship Staff","Ship Staff Insp.","EGE feed pump no. 2 suction valve leakage from valve bonnet","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Leakage rectified by renewing the packing","2019-04-30","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,2712,"18/10/2019 8:20:52 AM","2019-04-19","Observation","Ship Staff","Ship Staff Insp.","AE diesel oil flushing pump leakage from pump cover","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The pump overhauled","2019-04-30","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,2713,"18/10/2019 8:22:56 AM","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","Service air compressor oil filter base frame ( aluminium casing) to renew","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Crack observed on the filter base threads, temporarily repaired and made new threads and used union of different size.","2019-05-15","DFAL190045","Completed","2019-04-23","No","No","No","Internal"]
[null,null,null,null,2714,"18/10/2019 8:24:30 AM","2019-04-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Gantry crane poor cosmetics. ","Deck Mach.","General Appearance","Equipment Related","11.7","High","","","Derusting & painting of the gantry crane track completed.","2019-04-30","","Completed","2019-04-30","No","No","No","Internal"]
[null,null,null,null,2715,"18/10/2019 8:25:56 AM","2019-04-18","Deficiency","Ship Staff","Ship Staff Insp.","Found 7 numbers of foam hydrants leaking","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.38","High","","","Leak rectified for all 7 foam hydrants.","2019-04-30","","Completed","2019-04-30","No","No","No","Internal"]
[null,null,null,null,2716,"18/10/2019 8:28:00 AM","2019-05-04","Deficiency","Ship Staff","Ship Staff Insp.","Cargo Tank 2P overfill alarm not reseting due to fault with PAXD-Module card","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.12","Medium","","","Module card renewed, working satisfacorily","2019-05-15","DFAL190121","Completed","2019-05-12","No","No","No","Internal"]
[null,null,null,null,2717,"18/10/2019 8:30:04 AM","2019-05-04","Deficiency","Ship Staff","Ship Staff Insp.","Slop P fault with overfill alarm due to fault with PAXD-Module card","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.12","Medium","","","Module card renewed, working satisfactorily","2019-05-15","","Completed","2019-05-12","No","No","No","Internal"]
[null,null,null,null,2718,"18/10/2019 8:37:47 AM","2019-02-05","Deficiency","Ship Staff","Ship Staff Insp.","Main air compressor no. 2 found leaking from Intercooler","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Intercooler gasket renewed, working satisfactory.","2019-05-15","","Completed","2019-05-02","No","No","No","Internal"]
[null,null,null,null,2719,"18/10/2019 8:39:05 AM","2019-04-05","Deficiency","Ship Staff","Ship Staff Insp.","Boiler fuel oil burning pump no. 2 found leaking from mechanical seal","Boiler","Eng. / Strg. Comp.","Equipment Related","10.9","Medium","","","Complete pump replaced with new one.","2019-05-15","","Completed","2019-05-06","No","No","No","Internal"]
[null,null,null,null,2720,"18/10/2019 8:40:23 AM","2019-04-05","Deficiency","Ship Staff","Ship Staff Insp.","2P bunker tank steam inlet valve found leaking ","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.8","Medium","","","Valve bonnet gasket renewed.","2019-05-15","","Completed","2019-05-06","No","No","No","Internal"]
[null,null,null,null,2721,"18/10/2019 8:41:42 AM","2019-05-05","Deficiency","Ship Staff","Ship Staff Insp.","COPT gland steam line found leaking as it developed cracks.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","8.8","Medium","","","The crack repaired by welding.","2019-05-15","","Completed","2019-05-06","No","No","No","Internal"]
[null,null,null,null,2722,"18/10/2019 8:44:17 AM","2019-08-05","Deficiency","PSC Insp.","PSC Inspection","Bridge both side doors were not sealing positively","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related","2.15","Low","Structural condition","","Both doors rail tracks adjusted now doors sealing positively.","2019-09-05","","Completed","2019-09-09","No","No","No","Internal"]
[null,null,null,null,2723,"18/10/2019 8:46:12 AM","2019-05-05","Deficiency","Ship Staff","Ship Staff Insp.","AE #1 fuel oil line pulse damper leaking","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","The pulse damper assembly removed from place, both side O-rings renewed and fitted back. Working satisfactorily","2019-05-15","","Completed","2019-05-11","No","No","No","Internal"]
[null,null,null,null,2724,"18/10/2019 8:47:46 AM","2019-05-05","Observation","Ship Staff","Ship Staff Insp.","ME shock absorber unit #6 found leaking","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Unit No. 6 shock absorber overhauled, sealing and wear rings renewed.","2019-05-15","","Completed","2019-05-14","No","No","No","Internal"]
[null,null,null,null,2725,"18/10/2019 8:50:00 AM","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","Rotating beacon light for cargo oil tank high level alarm defective","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.14","Very High","","","New rotating beacon light received, same fitted in place, working satisfactorily","2019-05-31","","Completed","2019-05-31","No","No","No","Internal"]
[null,null,null,null,2726,"18/10/2019 8:53:47 AM","2019-05-03","Observation","Ship Staff","Ship Staff Insp.","4P COT Temperature reading incorrect in Musasino tank radar system.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.12","Medium","","","New sensor recieved, temperature sensor element renewed. Now working satisfactorily.","2019-05-31","","Completed","2019-05-24","No","No","No","Internal"]
[null,null,null,null,2727,"19/10/2019 12:02:52 AM","2019-05-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Gantry crane cable drum winding mechanism to repair","Deck Mach.","General Appearance","Equipment Related","11.7","High","","","Cable drum winding mechanism overhauling carried out found working satisfactorily","2019-06-15","","Completed","2019-05-26","No","No","No","Internal"]
[null,null,null,null,2728,"19/10/2019 12:47:57 AM","2019-05-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Several lagging in engine room plan to renew during scrubber installation time","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Several lagging in engine room renewed.","2019-06-15","","Completed","2019-05-29","No","No","No","Internal"]
[null,null,null,null,2729,"19/10/2019 12:49:17 AM","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","No. 1 AC blower motor side pully to renew","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","damaged pully replaced with new one.","2019-06-15","","Completed","2019-06-15","No","No","No","Internal"]
[null,null,null,null,2730,"19/10/2019 12:51:23 AM","2019-05-02","Deficiency","Ship Staff","Ship Staff Insp.","AMS-field station - F, CPU module defective , due to this all DG alarms went offline and could not be monitored from AMS panel","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","New plc card received, same fitted in place. tried out, working satisfactorily.","2019-06-15","","Completed","2019-06-15","No","No","No","Internal"]
[null,null,null,null,2731,"19/10/2019 12:53:05 AM","2019-03-16","Observation","Ship Staff","Ship Staff Insp.","Oil leak observed from port windlass winch","Mooring Mach.","Mooring","Equipment Related","9.16","High","","","New hydraulic motor fitted in place. Tried out working satisfactorily.","2019-06-15","","Completed","2019-06-15","No","No","No","Internal"]
[null,null,null,null,2732,"19/10/2019 12:54:45 AM","2019-01-04","Deficiency","Ship Staff","Ship Staff Insp.","Waste oil incinerator display not clear","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","New display unit received, same fitted in place. Tried out, working satisfactory.","2019-06-15","","Completed","2019-06-14","No","No","No","Internal"]
[null,null,null,null,2733,"19/10/2019 12:56:06 AM","2019-05-13","Deficiency","Ship Staff","Ship Staff Insp.","ME cylinder head unit #1 exhaust gas outlet temerature gauge faulty ","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","New pyrometer received. Same fitted in place.","2019-06-15","","Completed","2019-06-15","No","No","No","Internal"]
[null,null,null,null,2734,"19/10/2019 12:58:37 AM","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","ME shaft earthing milli volt meter defective","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","New volt meter fitted in place working satisfactorily.","2019-06-30","","Completed","2019-06-30","No","No","No","Internal"]
[null,null,null,null,2735,"19/10/2019 1:00:02 AM","2019-02-15","Deficiency","Ship Staff","Ship Staff Insp.","Stbd. HH crane noise heard during lifting","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.5","Very High","","","Hyd. ram ( stbd.) lowering bearing renewed. working satisfactory.","2019-06-30","","Completed","2019-06-29","No","No","No","Internal"]
[null,null,null,null,2736,"19/10/2019 1:01:47 AM","2019-04-03","Observation","Ship Staff","Ship Staff Insp.","In Musasino tank radar system, Slop S COT, shows reading as 16% filled, where as the tank is empty.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.12","Medium","","","Job being attended by Musasino in DD, work in progress.","2019-04-07","","Completed","2019-07-04","No","No","No","Internal"]
[null,null,null,null,2737,"19/10/2019 1:03:27 AM","2019-07-04","Deficiency","Ship Staff","Ship Staff Insp.","Aux. boiler feed pump No. 1 bearing housing worn out.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.9","Medium","","","received spare bearing housing fitted on place. Pump tried out working satisfactorily.","2019-07-15","","Completed","2019-07-15","No","No","No","Internal"]
[null,null,null,null,2738,"19/10/2019 1:14:01 AM","2019-06-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Grating near break of accomodation to derust and paint.","Miscellaneous","General Appearance","Equipment Related","11.7","High","","","Renewed parts of grating and painted","2019-11-08","","Completed","2019-07-15","No","No","No","Internal"]
[null,null,null,null,2739,"19/10/2019 1:16:06 AM","2019-08-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","DO bunkering line to derust and paint.","Deck Pipe / Fittings","General Appearance","Equipment Related","11.7","High","","","Completed","2019-11-08","","Completed","2019-08-18","No","No","No","Internal"]
[null,null,null,null,2740,"19/10/2019 1:25:19 AM","2019-07-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Working platform next to Main IG V/v to be renewed","Deck Pipe / Fittings","General Appearance","Equipment Related","11.7","High","","","New platform fabricated and renewed","2019-11-08","","Completed","2019-07-28","No","No","No","Internal"]
[null,null,null,null,2741,"19/10/2019 1:26:26 AM","2019-08-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Derusting and Painting of Mooring winches","Mooring Mach.","General Appearance","Equipment Related","9.11","Medium","","","Completed","2019-11-08","","Completed","2019-08-22","No","No","No","Internal"]
[null,null,null,null,2742,"19/10/2019 1:27:56 AM","2019-07-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Paint locker to be arranged","Miscellaneous","General Appearance","Behaviour Based","11.7","High","","","Completed.","2019-11-08","","Completed","2019-07-21","No","No","No","Internal"]
[null,null,null,null,2743,"19/10/2019 1:29:18 AM","2019-08-14","Observation","Ship Staff","Ship Staff Insp.","Pump room davit lubricator broken","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.5","Very High","","","Renewed.","2019-08-22","","Completed","2019-08-14","No","No","No","Internal"]
[null,null,null,null,2744,"19/10/2019 1:31:00 AM","2019-07-06","Observation","Ship Staff","Ship Staff Insp.","Mooring winch hydraulic lines bar supports to be renewed at 5 locations","Deck Pipe / Fittings","General Appearance","Equipment Related","9.1","Low","","","New supports fabricated and renewed","2019-08-31","","Completed","2019-08-01","No","No","No","Internal"]
[null,null,null,null,2745,"19/10/2019 1:32:47 AM","2019-08-16","Observation","Ship Staff","Ship Staff Insp.","4S PV Valve pressure side leaking","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.19","High","","","Opened and lapping done , satisfactory now","2019-08-22","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,2746,"19/10/2019 1:34:09 AM","2019-08-16","Observation","Ship Staff","Ship Staff Insp.","1C PV Valve vaccum side leaking","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.19","High","","","Opened and lapping done , satisfactory now","2019-08-22","","Completed","2019-08-17","No","No","No","Internal"]
[null,null,null,null,2747,"19/10/2019 1:35:16 AM","2019-07-06","Observation","Ship Staff","Ship Staff Insp.","Mooring fairleads grooving to be filled up total 20 nos.","Miscellaneous","General Appearance","Equipment Related","11.7","High","","","Completed","2019-08-31","","Completed","2019-08-01","No","No","No","Internal"]
[null,null,null,null,2748,"19/10/2019 1:37:11 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Broken vent valve on Low sea chest to renew","Miscellaneous","Cargo / Ballast Systems","Equipment Related","8.2","Medium","","","Broken vent valve replaced with new valve.","2019-07-31","","Completed","2019-07-17","No","No","No","Internal"]
[null,null,null,null,2749,"19/10/2019 1:40:25 AM","2018-07-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME unit #1 exhaust valve top cover oil leakage from gasket to rectify.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.1","Medium","","","ME unit #1 exhaust valve top cover gasket replaced with new one. No further leaks.","2018-07-31","","Completed","2019-07-12","No","No","No","Internal"]
[null,null,null,null,2750,"19/10/2019 1:42:07 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME fuel line high pressure pipes to be protected with Anti splash tape","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.8","Medium","","","Anti splash tape fitted on high pressure pipe connections.","2019-07-31","","Completed","2019-07-30","No","No","No","Internal"]
[null,null,null,null,2751,"19/10/2019 1:43:47 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME fuel pump shaft bearing and linkage to be greased.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.8","Medium","","","Main engine all unit pump shaft and linkages lubricated. Regular lubrication is being done on weekly basis.","2019-07-31","","Completed","2019-07-30","No","No","No","Internal"]
[null,null,null,null,2752,"19/10/2019 1:44:57 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Control Air Leakage from VIT Actuator Control Unit to be rectified.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Lak rectified","2019-08-15","","Completed","2019-07-12","No","No","No","Internal"]
[null,null,null,null,2753,"19/10/2019 1:46:29 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Numerous lights inside Engine casing not working","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","fused lightings has been replaced with new one.","2019-07-31","","Completed","2019-08-21","No","No","No","Internal"]
[null,null,null,null,2754,"19/10/2019 1:47:51 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FO Supply Pump No.1 & 2 Suction Pressure Gauge to be renewed.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.8","Medium","","","pressure gauge renewed.","2019-07-31","","Completed","2019-08-02","No","No","No","Internal"]
[null,null,null,null,2755,"19/10/2019 1:49:07 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering Gear LO Storage Tank Minimum Level Marking as per SOLAS missing. ","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Minimum level has been marked with stencils.","2019-07-15","","Completed","2019-07-12","No","No","No","Internal"]
[null,null,null,null,2756,"19/10/2019 1:51:30 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","A/E Performance report indicates :-\n\nA/E 1 Unit #3 Fuel Injector to overhaul.\n\nA/E 2 Unit #4 Fuel Injector to overhaul. \n\nC/E to take corrective action\n\n","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","AE #1 unit 3 fuel injector removed and overhauled. AE #2 unit 4 fuel injector removed and overhauled.","2019-08-31","","Completed","2019-08-14","No","No","No","Internal"]
[null,null,null,null,2757,"19/10/2019 1:55:45 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME performance report indicates power imbalance between unit #3 and #7. C/E to take corrective action.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","completed. Performance marked.","2019-08-31","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,2758,"19/10/2019 1:57:09 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AHU room to be arranged.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","completed.","2019-07-31","","Completed","2019-07-30","No","No","No","Internal"]
[null,null,null,null,2759,"19/10/2019 1:58:39 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","numerous lagging missing/ damaged in E/R, same to be renewed","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","damaged lagging has been replaced with new lagging.","2019-08-15","","Completed","2019-08-06","No","No","No","Internal"]
[null,null,null,null,2760,"19/10/2019 2:19:42 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine/ electrical spares store room to be arranged","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Stores arranged.","2019-08-15","","Completed","2019-07-30","No","No","No","Internal"]
[null,null,null,null,2761,"19/10/2019 2:21:14 AM","2019-06-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Chemical Locker to be arranged","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Chemical locker arranged as per alkaline/acidic properties","2019-07-31","","Completed","2019-08-21","No","No","No","Internal"]
[null,null,null,null,2762,"19/10/2019 2:22:37 AM","2018-11-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Spares inventory to be updated in PAL","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.2","Low","","","Inventory checked and updated.","2019-07-31","","Completed","2019-08-21","No","No","No","Internal"]
[null,null,null,null,2763,"2019-10-19 02:27:15.000","2019-08-25","Observation","Ship Staff","Ship Staff Insp.","During discharging at Map ta Phut on 2nd  day of discharge Cargo system Bulkheadmaster v/v COV831 could not be opened when restarting the cargo discharge after a shore stoppage.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","operated manually activating the solenoid, solenoid coil on open side require renewal","2019-09-10","","Completed","2019-04-09","No","No","No","Internal"]
[null,null,null,null,2764,"2019-10-19 03:47:05.000","2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","starboard side gangway air leak ","Deck Mach.","General Appearance","Equipment Related","11.7","High","","","Air hose coupling tightned, no leak.","2019-10-23","","Completed","2019-10-19","No","No","No","Internal"]
[null,null,null,null,2765,"2019-10-20 03:15:34.000","2019-07-08","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CO2 room exhaust fan frame to be renewed","Deck Pipe / Fittings","General Appearance","Equipment Related","11.7","High","","","Frame renewed by fabrication","2019-08-11","","Completed","2019-06-09","No","No","No","Internal"]
[null,null,null,null,2766,"2019-10-20 03:19:17.000","2019-08-26","Deficiency","Ship Staff","Ship Staff Insp.","Dressor coupling on Cargo line No. 2 iwo 4C leaking","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.1","Very High","","","Renewed","2019-09-10","","Completed","2019-08-31","No","No","No","Internal"]
[null,null,null,null,2767,"2019-10-20 04:11:51.000","2019-08-26","Observation","Ship Staff","Ship Staff Insp.","COW line valve on 2C leaking","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.33","Medium","","","Repaired","2019-09-18","","Completed","2019-04-09","No","No","No","Internal"]
[null,null,null,null,2768,"20/10/2019 5:16:55 PM","2019-08-30","Deficiency","Ship Staff","Ship Staff Insp.","Flow in IG Deck seal filling line very low","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.27","Medium","","","Completed","2019-01-09","","Completed","2019-07-09","No","No","No","Internal"]
[null,null,null,null,2769,"20/10/2019 5:18:52 PM","2019-08-30","Deficiency","Ship Staff","Ship Staff Insp.","AUS discharge to Slp (S) line developed leak during de-rusting","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.8","Medium","","","2 sections of lines repaired and refitted","2019-01-09","","Completed","2019-06-09","No","No","No","Internal"]
[null,null,null,null,2770,"20/10/2019 5:20:30 PM","2019-08-29","Observation","Ship Staff","Ship Staff Insp.","Deck seal (semi dry type) kinetic pressure valve between U-seal and deck seal, flap broken","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.27","Medium","","","Flap repaired onboard and refitted","2019-01-09","","Completed","2019-08-31","No","No","No","Internal"]
[null,null,null,null,2771,"20/10/2019 5:21:40 PM","2019-08-25","Observation","Ship Staff","Ship Staff Insp.","Slight leak from valve actuator of COV 509","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","Top actuator seal renewed.","2019-09-20","","Completed","2019-09-29","No","No","No","Internal"]
[null,null,null,null,2772,"20/10/2019 5:23:12 PM","2019-08-30","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Many lifebuoy lines found in very poor condition.","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.31","High","","","Renewed lines of lifebuoys.","2019-10-30","","Completed","2019-09-27","No","No","No","Internal"]
[null,null,null,null,2773,"20/10/2019 5:25:14 PM","2019-08-22","Observation","Ship Staff","Ship Staff Insp.","Valve indicator for COV 834 & COV 914 flickers when operated intermittent","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","COV 934indicator limits were adjusted and working satisfactory. COV 914 position indicator unit renewed.","2019-09-20","","Completed","2019-01-10","No","No","No","Internal"]
[null,null,null,null,2774,"20/10/2019 5:27:03 PM","2019-08-22","Observation","Ship Staff","Ship Staff Insp.","One hydraulic box hinge got broken","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.1","Very High","","","Completed.","2019-05-10","","Completed","2019-04-10","No","No","No","Internal"]
[null,null,null,null,2775,"20/10/2019 5:29:38 PM","2019-09-10","Observation","Ship Staff","Ship Staff Insp.","Crude oilwashing line dressor coupling fwd of midship leaking","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.33","Medium","","","Renewed seal rings of dressor coupling","2019-09-10","","Completed","2019-09-10","No","No","No","Internal"]
[null,null,null,null,2776,"20/10/2019 5:31:51 PM","2019-10-13","Observation","Ship Staff","Ship Staff Insp.","IG dressor coupling leaking","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.22","Very High","","","Dressor coupling tightened and checked, no leak observed.","2019-10-13","","Completed","2019-10-13","No","No","No","Internal"]
[null,null,null,null,2777,"20/10/2019 5:34:10 PM","2019-10-16","Observation","Ship Staff","Ship Staff Insp.","Stbd. side MOB marker support angle broken","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.31","High","","","Same fabricated and now in state of readiness.","2019-10-20","","Completed","2019-10-20","No","No","No","Internal"]
[null,null,null,null,2778,"21/10/2019 5:48:58 PM","2019-10-15","Breakdown","Owner / Marine / Tech. Suptd.","Suptd. Insp.","stay wires for vsat antenna to renew","Nav & comm. equip.","Communication","External Factors","4.6","Medium","","","Renewed with new wire ropes","2020-01-15","","Completed","2019-10-31","No","No","No","Internal"]
[null,null,null,null,2779,"21/10/2019 5:53:52 PM","2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","two accomodation door closers on stbd side to renew","Accommodation ","General Appearance","Equipment Related","11.1","High","","","Old damaged Door closers renewed with new ones","2019-12-16","","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,2780,"21/10/2019 6:00:54 PM","2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","stbd gangway securing wires to renew","Deck Mach.","Structural Condn. / WT integrity ","Equipment Related","","","","","New wire rope splicing carried out & refitted","2020-01-01","","Completed","2019-10-28","No","No","No","Internal"]
[null,null,null,null,2781,"2019-10-22 04:22:30.000","2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo line #2 dresser coupling on top of #4 COT seal rings to renew.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.8","Medium","","","All three Cargo line dresser coupling seal rings on top of #4 COT renewed.","2019-10-23","","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,6081,"43760.1834143519","2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","COW valve for 2centre not holding well, to overhaul or renew.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.34","High","","","Renewed with new Valve recieved at singapore.","2019-11-15","","Completed","2019-10-26","No","No","No","Internal"]
[null,null,null,null,null,43750.263391203705,"2019-08-30","Breakdown","Ship Staff","Ship Staff Insp.","VECS System pressure reading in CCR not accurate.","Inert Gas","Cargo / Ballast Systems","Equipment Related",8.25,"Very High","Not Applicable","Not Applicable","V to I convertor has been replaced, Calibration has been done by simulator. now Guage is in CCR showing the correct pressure. ","2019-12-30","DFAL190244","Completed","2019-10-28","No",null,null,"Internal"]
[null,null,null,null,null,43750.266192129631,"2019-08-17","Breakdown","Ship Staff","Ship Staff Insp.","Port side Hose handling crane limit switch leaking.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.5,"Very High","Not Applicable","Not Applicable","Opened and cleaned the limit switch and o-Ring renewed, refitted and crane tried out no leak, Load test done after repair, Recieved a new Limit switch. fitted & tested","2019-10-30","DFAL190264","Completed","2019-10-31","No",null,null,"Internal"]
[null,null,null,null,null,43750.276747685188,"2019-09-10","Deficiency","Ship Staff","Ship Staff Insp.","2P, 4P & 4S cargo tank hi-hi level alarm resistance tape faulty","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.24,"Medium","Not Applicable","Not Applicable","2P, 4P & 4S resistance tape( sensor) has been renewed, High level alarms tried out, working satisfactorily.","2019-12-31","DFAL190264","Completed","2019-10-16","No",null,null,"Internal"]
[null,null,null,null,null,"20/10/2019 5:37:49 PM","2019-10-16","Observation","Ship Staff","Ship Staff Insp.","Cable for BNWAS reset unit on Stbd. side bridge wing not secured to Bulwark","Deck Pipe / Fittings","General Appearance","Equipment Related",11.7,"High","Not Applicable","Not Applicable","Effective Securing carried","2019-10-30",null,"Completed","2019-12-16","No",null,null,"Internal"]
[null,null,null,null,null,43760.172662037039,"2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bunker line near accommodation break to be painted","Deck Pipe / Fittings","General Appearance","Equipment Related",11.7,"High","Not Applicable","Not Applicable","Bunker line stenciling done by engine room staff in midship, port & starboard side.","2020-01-01",null,"Completed","2019-10-31","No",null,null,"Internal"]
[null,null,null,null,null,43760.174560185187,"2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Two fire hose boxes on main deck to replace with fabricated boxes in ER.","LSA / FFA","LSA / FFA Appliances","Equipment Related",5.38,"High","Not Applicable","Not Applicable","Fabrication of new Fire Hose boxes carried out. New Brackets welded after taking Concurrance from office","2020-10-01",null,"Completed","2019-10-29","No",null,null,"Internal"]
[null,null,null,null,null,43760.178726851853,"2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Scupper drain forward of acetylene room to repair.","Deck Pipe / Fittings","General Appearance","Equipment Related",11.7,"High","Not Applicable","Not Applicable","Hot work carried out. Fabricated insert fitted","2020-01-01",null,"Completed","2019-10-29","No",null,null,"Internal"]
[null,null,null,null,null,43760.179768506947,"2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","M5 mooring winch minor oil weep from flange to rectify.","Mooring Mach.","Mooring","Equipment Related",9.16,"High","Not Applicable","Not Applicable","Control unit bolts re-tightened with allen key bolts","2019-12-15",null,"Completed","2019-11-15","No",null,null,"Internal"]
[null,null,null,null,null,43760.18341435185,"2019-10-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","COW valve for 2centre not holding well, to overhaul or renew.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.34,"High","Not Applicable","Not Applicable","Repaired. Renewed with a new one","2019-11-12",null,"Completed","2019-02-11","No",null,null,"Internal"]
[null,null,null,null,null,"16/12/2019 7:18:39 AM","2019-11-11","Other","Ship Staff","Ship Staff Insp.","IG scrubber pump disch. Elbow holed & gasket leaking.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Pump  isolated, elbow taken out for repair & , built up work carried out, gasker renewed and fitted in place. Pump tried out and found no leakages.","2019-12-05",null,"Completed","2019-11-12","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["LSA / FFA Appliances",8]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["MARPOL Related",9]
["ISM Related",7]
["ISPS Related",10]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Condn of Class / Memo",null,5]
["Critical Equipment",null,4]
["Deficiency",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":427,"n_cols":3,"rows_kept":427,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",8243]
["1.10","Low",8252]
["1.11","Low",8253]
["1.12","Low",8254]
["1.13","Low",8255]
["1.14","Low",8256]
["1.15","Low",8257]
["1.16","Low",8259]
["1.17","Low",8260]
["1.18","Low",8261]
["1.19","Low",8262]
["1.2","Low",8244]
["1.20","Low",8263]
["1.21","Low",8265]
["1.22","Low",8266]
["1.23","Low",8267]
["1.24","Low",8268]
["1.25","Low",8269]
["1.26","Low",8270]
["1.3","Low",8245]
["1.4","Low",8246]
["1.5","Low",8247]
["1.6","Low",8248]
["1.7","Low",8249]
["1.8","Low",8250]
["1.9","Low",8251]
["1.99","High",11258]
["10.1","Medium",8461]
["10.10","High",8470]
["10.11","Medium",8471]
["10.12","Very High",8472]
["10.13","Very High",8473]
["10.14","Medium",8474]
["10.15","Low",8475]
["10.16","Very High",8476]
["10.17","Very High",8477]
["10.18","High",8478]
["10.19","Very High",8479]
["10.2","Low",8462]
["10.20","High",8480]
["10.21","Medium",8481]
["10.22","Low",8482]
["10.23","Medium",8483]
["10.24","Low",8484]
["10.25","Very High",8485]
["10.26","High",8486]
["10.27","Medium",8487]
["10.28","Low",8488]
["10.29","Medium",8489]
["10.3","Medium",8463]
["10.30","High",8490]
["10.31","Very High",8491]
["10.32","Very High",8492]
["10.33","High",8493]
["10.34","High",8494]
["10.35","Very High",8495]
["10.36","Very High",8496]
["10.37","Medium",8497]
["10.38","Medium",8498]
["10.39","High",8499]
["10.4","High",8464]
["10.40","Medium",8500]
["10.41","Medium",8501]
["10.42","Medium",8502]
["10.43","Medium",8503]
["10.44","Medium",8504]
["10.45","Very High",8505]
["10.46","High",8506]
["10.47","Medium",8507]
["10.48","High",8508]
["10.49","Medium",8509]
["10.5","Low",8465]
["10.50","High",8510]
["10.51","Low",8511]
["10.52","Medium",8512]
["10.53","Medium",8513]
["10.54","High",8514]
["10.55","Low",8515]
["10.6","Very High",8466]
["10.7","Medium",8467]
["10.8","Medium",8468]
["10.9","Medium",8469]
["10.99","High",8516]
["11.1","High",8420]
["11.10","Medium",8429]
["11.11","Very High",8430]
["11.12","Low",8431]
["11.13","Low",8432]
["11.14","Medium",8433]
["11.15","Low",8434]
["11.16","Low",8435]
["11.17","Low",8436]
["11.2","Medium",8421]
["11.3","Medium",8422]
["11.4","Very High",8423]
["11.5","Medium",8424]
["11.6","Medium",8425]
["11.7","High",8426]
["11.8","Low",8427]
["11.9","Low",8428]
["11.99","High",8437]
["12.1","High",8438]
["12.10","High",8448]
["12.11","High",8449]
["12.12","High",8450]
["12.13","High",8451]
["12.14","High",8452]
["12.15","High",8453]
["12.16","High",8454]
["12.17","High",8455]
["12.18","High",8456]
["12.19","High",8457]
["12.2","High",8439]
["12.20","High",8458]
["12.21","High",8459]
["12.3","High",8441]
["12.4","High",8442]
["12.5","High",8443]
["12.6","High",8444]
["12.7","High",8445]
["12.8","High",8446]
["12.9","High",8447]
["12.99","High",8460]
["2.1","Very High",8296]
["2.1.9","Very High",11259]
["2.10","Medium",8304]
["2.11","Medium",8305]
["2.12","Low",8306]
["2.13","Low",8307]
["2.14","Low",8308]
["2.15","Low",8309]
["2.16","Medium",8310]
["2.2","Medium",8297]
["2.3","High",8295]
["2.4","Medium",8298]
["2.5","Medium",8299]
["2.6","Low",8300]
["2.7","High",8301]
["2.8","High",8302]
["2.9","Medium",8303]
["2.99","High",8311]
["3.1","High",8312]
["3.2","Very High",8313]
["3.3","High",8314]
["3.4","Low",8294]
["3.5","Medium",8315]
["3.6","High",8316]
["3.7","Very High",8317]
["3.8","Very High",8318]
["3.99","High",8319]
["4.1","High",8320]
["4.10","High",8329]
["4.11","Medium",8330]
["4.12","Very High",8331]
["4.13","Very High",8332]
["4.14","Very High",8333]
["4.15","Very High",8334]
["4.16","Very High",8335]
["4.17","Very High",8336]
["4.18","Very High",8337]
["4.19","Low",8338]
["4.2","Medium",8321]
["4.20","Very High",8339]
["4.21","High",8340]
["4.22","Low",8341]
["4.23","High",8342]
["4.24","High",8343]
["4.25","Low",8344]
["4.26","Low",8345]
["4.27","High",8346]
["4.3","Medium",8322]
["4.4","High",8323]
["4.5","Very High",8324]
["4.6","Medium",8325]
["4.7","High",8326]
["4.8","Medium",8327]
["4.9","Medium",8328]
["4.99","High",8347]
["5.1","Very High",8517]
["5.10","High",8526]
["5.11","Low",8527]
["5.12","Medium",8528]
["5.13","High",8529]
["5.14","Very High",8530]
["5.15","Medium",8531]
["5.16","Very High",8532]
["5.17","Very High",8533]
["5.18","High",8534]
["5.19","Medium",8535]
["5.2","Very High",8518]
["5.20","Medium",8536]
["5.21","Medium",8537]
["5.22","High",8539]
["5.23","Very High",8540]
["5.24","Very High",8541]
["5.25","Medium",8542]
["5.26","Medium",8543]
["5.27","Medium",8544]
["5.28","Very High",8545]
["5.29","High",8546]
["5.3","Low",8519]
["5.30","High",8547]
["5.31","High",8548]
["5.32","High",8549]
["5.33","High",8550]
["5.34","Low",8551]
["5.35","Medium",8552]
["5.36","Low",8553]
["5.37","Low",8554]
["5.38","High",8555]
["5.39","Very High",8556]
["5.4","High",8520]
["5.40","Very High",8557]
["5.41","Very High",8558]
["5.42","Medium",8559]
["5.43","High",8560]
["5.44","High",8561]
["5.45","Medium",8564]
["5.46","Medium",8565]
["5.47","Medium",8566]
["5.48","Medium",8567]
["5.5","Low",8521]
["5.6","Low",8522]
["5.7","Medium",8523]
["5.8","Medium",8524]
["5.9","Very High",8525]
["5.99","High",8568]
["6.1","Medium",8348]
["6.10","Low",8357]
["6.11","High",8358]
["6.12","Medium",8359]
["6.13","Low",8360]
["6.14","High",8361]
["6.15","High",8362]
["6.16","Very High",8363]
["6.17","Very High",8364]
["6.18","Medium",8365]
["6.19","Low",8366]
["6.2","High",8349]
["6.20","Medium",8367]
["6.21","High",8368]
["6.22","Medium",8369]
["6.3","Low",8350]
["6.4","High",8351]
["6.5","Medium",8352]
["6.6","Medium",8353]
["6.7","High",8354]
["6.8","High",8355]
["6.9","Low",8356]
["6.99","High",8370]
["7.1","High",8371]
["7.10","High",8380]
["7.11","High",8381]
["7.12","High",8382]
["7.13","Medium",8383]
["7.14","Medium",8384]
["7.15","High",8385]
["7.16","High",8386]
["7.17","High",8387]
["7.2","High",8372]
["7.3","Low",8373]
["7.4","Low",8374]
["7.5","Low",8375]
["7.6","Medium",8376]
["7.7","Low",8377]
["7.8","High",8378]
["7.9","High",8379]
["7.99","High",8388]
["8.1","Very High",8569]
["8.10","Very High",8578]
["8.100","Low",11227]
["8.101","Medium",11228]
["8.102","Low",11229]
["8.103","Low",11230]
["8.104","Low",11231]
["8.105","Medium",11232]
["8.106","Medium",11233]
["8.107","Low",11234]
["8.108","High",11235]
["8.109","Very High",11236]
["8.11","Medium",8579]
["8.110","High",11237]
["8.111","Medium",11238]
["8.112","High",11239]
["8.113","Medium",11240]
["8.114","Low",11241]
["8.115","High",11242]
["8.116","Medium",11243]
["8.117","Medium",11244]
["8.118","Medium",11245]
["8.119","High",11246]
["8.12","Medium",8580]
["8.120","High",11247]
["8.121","Medium",11248]
["8.122","High",11249]
["8.123","High",11250]
["8.124","Low",11251]
["8.125","High",11252]
["8.126","Medium",11253]
["8.127","Medium",11254]
["8.13","Medium",8581]
["8.14","Very High",8582]
["8.15","High",8583]
["8.16","Very High",8584]
["8.17","Low",8585]
["8.18","High",8586]
["8.19","High",8587]
["8.199","High",11255]
["8.2","Medium",8570]
["8.20","Medium",8588]
["8.21","High",8589]
["8.22","Very High",8590]
["8.23","Medium",8591]
["8.24","Medium",8592]
["8.25","Very High",8593]
["8.26","High",8594]
["8.27","Medium",8595]
["8.28","Medium",8596]
["8.29","High",8598]
["8.3","Very High",8571]
["8.30","High",8599]
["8.31","High",8600]
["8.32","Low",8601]
["8.33","Medium",8602]
["8.34","High",8603]
["8.35","Medium",8604]
["8.36","Medium",8605]
["8.37","High",8607]
["8.38","Medium",8608]
["8.39","Medium",8609]
["8.4","Medium",8572]
["8.40","High",8610]
["8.41","Medium",8611]
["8.42","Medium",8612]
["8.43","Very High",8613]
["8.44","High",8615]
["8.45","High",8616]
["8.46","Very High",8617]
["8.47","Very High",8618]
["8.48","Medium",8619]
["8.49","High",8620]
["8.5","Very High",8573]
["8.50","Medium",8621]
["8.51","Low",8622]
["8.52","Low",8623]
["8.53","Low",8624]
["8.54","High",8625]
["8.55","Low",11182]
["8.56","Medium",11183]
["8.57","Medium",11184]
["8.58","High",11185]
["8.59","High",11186]
["8.6","Medium",8574]
["8.60","High",11187]
["8.61","Medium",11188]
["8.62","Very High",11189]
["8.63","High",11190]
["8.64","Medium",11191]
["8.65","Low",11192]
["8.66","High",11193]
["8.67","High",11194]
["8.68","High",11195]
["8.69","Medium",11196]
["8.7","High",8575]
["8.70","Medium",11197]
["8.71","Very High",11198]
["8.72","Medium",11199]
["8.73","Medium",11200]
["8.74","High",11201]
["8.75","Medium",11202]
["8.76","Medium",11203]
["8.77","Medium",11204]
["8.78","Medium",11205]
["8.79","Medium",11206]
["8.8","Medium",8576]
["8.80","Medium",11207]
["8.81","Low",11208]
["8.82","Medium",11209]
["8.83","Low",11210]
["8.84","Low",11211]
["8.85","Medium",11212]
["8.86","Medium",11213]
["8.87","Medium",11214]
["8.88","Low",11215]
["8.89","High",11216]
["8.9","High",8577]
["8.90","High",11217]
["8.91","High",11218]
["8.92","Medium",11219]
["8.93","Low",11220]
["8.94","Low",11221]
["8.95","Medium",11222]
["8.96","Medium",11223]
["8.97","Low",11224]
["8.98","High",11225]
["8.99","Medium",11226]
["9.1","Low",8390]
["9.10","Medium",8399]
["9.11","Medium",8400]
["9.12","Medium",8401]
["9.13","Low",8402]
["9.14","Medium",8403]
["9.15","Medium",8404]
["9.16","High",8405]
["9.17","High",8406]
["9.18","Low",8407]
["9.19","Low",8408]
["9.2","Very High",8391]
["9.20","Medium",8409]
["9.21","Medium",8410]
["9.22","Low",8411]
["9.23","Low",8412]
["9.24","Medium",8413]
["9.25","Low",8414]
["9.26","Low",8415]
["9.27","Low",8416]
["9.28","Medium",8417]
["9.29","Low",8418]
["9.3","Very High",8392]
["9.4","High",8393]
["9.5","High",8394]
["9.6","Low",8395]
["9.7","Medium",8396]
["9.8","Medium",8397]
["9.9","Medium",8398]
["9.99","High",8419]

{"sheet":"Equipment_list","index":7,"n_rows":21,"n_cols":3,"rows_kept":21,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation ",null,12]
["Air Comp.",null,8]
["Aux. Engine",null,4]
["Aux. Mach.",null,7]
["Boiler",null,5]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck Mach.",null,18]
["Deck Pipe / Fittings",null,20]
["Documentation",null,21]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Main Engine ",null,3]
["Miscellaneous",null,22]
["Nav & comm. equip.",null,11]
["ER Pipes, valves & fittings",null,9]
["Purifier",null,6]
["Mooring Mach.",null,15]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":16,"n_cols":2,"rows_kept":16,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Others (Eg. Insurance etc.)",12]
["Engineering Audit",16]
["Flag State Insp.",5]
["Ship Staff Insp.",15]
["IT Audit",10]
["OM Insp. (Eg. SIRE, CDI etc.)",6]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["PSC Inspection",4]
["Suptd. Insp.",13]
["Terminal Insp.",11]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["Others (Eg. Insurance etc.)",null,9]
["FSC Inspector",null,5]
["Owner / Marine / Tech. Suptd.",null,3]
["PSC Insp.",null,6]
["Ship Staff",null,2]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["22","DHT FALCON (19-11-2019)","22_1575455983509.xlsm"]