{"text_format":"1","workbook":"xlsx","n_sheets":20,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":29,"n_cols":28,"rows_kept":29,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","27-Nov-2019",null,null,"Ship Name","CHATTANOOGA (26-11-2019)"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,6846,"15/11/2019 6:17:57 PM","2019-06-09","Deficiency","Ship Staff","Ship Staff Insp.","UV lamp controller for UV sterilizer","Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Rcvd spare UV controller under req. CHAT190178 Note : UV controller can use for spare, and need UV starter to replace the defective parts/ re-order.CHAT190224","2019-12-30","CHAT190224","Waiting spare",null,"No","No","No","Internal","Based on VFF, order should be ready on 13th December 2019.\nThus, target date should be amended to be in par with delivery date."]
[null,null,null,null,6847,"15/11/2019 6:25:36 PM","2019-11-09","Deficiency","Ship Staff","Ship Staff Insp.","NO.1 D.W.B. TANK","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","RAISED UNDER CHAT190185-pls.Give us date of supply to have realistic Target date","2019-12-30","CHAT190185","Waiting spare",null,"No","No","No","Internal","Based on VFF, order is awaiting readiness."]
[null,null,null,null,6848,"15/11/2019 6:29:03 PM","2019-11-09","Deficiency","Ship Staff","Ship Staff Insp.","NO.4B D.W.B. TK (P)","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","RAISED UNDER 190185-Pls Give us Supply date to plan realistic target date","2019-12-30","CHAT190185","Waiting spare",null,"No","No","No","Internal","Based on VFF, order is awaiting readiness advice."]
[null,null,null,null,6850,"15/11/2019 6:36:08 PM","2019-11-09","Deficiency","Ship Staff","Ship Staff Insp.","MDO & MGO TK (P)","Hull & Tanks","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","RAISED UNDER CHAT190185-Pls. give us supply date to plan realistic target date","2019-12-30","CHAT190185","Waiting spare",null,"No","No","No","Internal","Based on VFF, order is awaiting readiness advice."]
[null,null,null,null,6853,"15/11/2019 6:51:39 PM","2019-10-29","Critical Equipment","Ship Staff","Ship Staff Insp.","Windlass Anchor chain's roller found  frozen","Deck Mach.,Mooring Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Roller are alrerady moving slightly but not yet fully free. ","2019-12-30",null,"In progress",null,"No","No","No","Internal","Pls revert with update on your progress to free-up the roller."]
[null,null,null,null,6856,"15/11/2019 7:07:13 PM","2019-10-29","Observation","Ship Staff","Ship Staff Insp.","Motor Fan Cargo hold No.4 not working /low insulation","Cargo Mach.,Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Checked and found 4 motors in cargo hold fans need shore repair..request for landing In progress","2019-12-30",null,"In progress",null,"No","No","No","Internal","Pls revert with Electrician's findings on posible cause of low insulation & fan failure to operate, since the target date is already overdue."]
[null,null,null,null,6858,"15/11/2019 7:27:26 PM","2019-11-09","Deficiency","Ship Staff","Ship Staff Insp.","TOP 5 11.1 - MAIN AIR COMP NO.1 RUBBER BONDED METAL SUPPORT WASTED AND NEED TO BE REPLACE","Air Comp.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","TO BE REPLACE RUBBER BONDED METAL SUPPORT BASE OF MAIN AIR COMP. NO.1","2019-12-30","CHAT190214","Waiting spare",null,"No","No","No","Internal","Based on VFF, RO# is still in processing stage."]
[null,null,null,null,null,"30/11/2019 2:28:06 PM","2019-11-23","Observation","Ship Staff","Ship Staff Insp.","TOP 5 11.4 - AuX boiler burner oil pump heating element   defective.","Boiler","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","To be renewed spare heating element .","2019-12-30","RO CHAT190233","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,null,"2019-11-29","Observation","Ship Staff","Ship Staff Insp.","Top 5 11.10 - Bay 22 cargo hold motor junction box found broken.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace broken junction box","2019-12-30",null,"Not Started",null,"No",null,null,"External"]
[null,null,null,null,null,null,"2019-11-29","Observation","Ship Staff","Ship Staff Insp.","TOP 5 11.11 - Bay 19 aft cross deck center found reefer socket box not working","Deck Mach.","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","To check the reefer socket box and repairthe required parts.","2019-12-30",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,null,"2019-11-29","Observation","Ship Staff","Ship Staff Insp.","TOP 5 11.12 - Bridge wings (P/S)n nav. equipt control box found worn -out.","Nav & comm. equip.","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace worn-out part In progress 40 %","2020-01-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,null,"2019-11-29","Observation","Ship Staff","Ship Staff Insp.","TOP 5 11.13 - Aft rope store overhead insulation lagging observed some miising around the access ladder","Accommodation ","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","To add inlation lagging at aft rope store.","2019-12-30",null,"Not Started",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":179,"n_cols":28,"rows_kept":179,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","27-10-2019",null,null,"Ship Name","CHATTANOOGA (26-11-2019)"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,5952,"2019-09-11 20:22:00.000","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","UV STERILIZER QUARTZ TUBE LEAKING","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACED WITH NEW UV LAMP WIRE HARNESS QUARTZ JACKET O RING","2019-02-28","CHAT190037","Completed","2019-02-22","No","No","No","Internal"]
[null,null,null,null,5953,"2019-09-11 19:39:44.999","2019-01-01","Observation","Ship Staff","Ship Staff Insp.","ICU LEAKAGE UNIT NO.1","Main Engine ","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACE NEW SPARE","2019-02-28","CHAT195004","Completed","2019-01-08","No","No","No","Internal"]
[null,null,null,null,5954,"2019-09-11 19:46:14.999","2019-01-14","Deficiency","Ship Staff","Ship Staff Insp.","LEAKING MECHANICAL SEAL OF BILGE,FIREPUMP & GEN.SERVICE PUMP NO.2","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACE WITH NEW MECHANICAL SEAL SPARE","2019-01-16","","Completed","2019-01-15","No","No","No","Internal"]
[null,null,null,null,5955,"2019-09-11 19:52:31.000","2019-01-03","Deficiency","Ship Staff","Ship Staff Insp.","WO INCENERATOR TEMPERATURE SENSOR","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACE WITH NEW SPARE TEMP.SENSOR","2019-01-30","CHAT190007","Completed","2019-01-31","No","No","No","Internal"]
[null,null,null,null,5956,"2019-09-11 19:58:17.000","2019-01-09","Deficiency","Ship Staff","Ship Staff Insp.","LAUNDRY MACHINE DEFECTIVE","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACE WITH NEW SUPPLIED WACHING MACHINE","2019-01-20","CHAT190017","Completed","2019-01-31","No","No","No","Internal"]
[null,null,null,null,5957,"2019-09-11 20:07:28.000","2019-01-12","Deficiency","Ship Staff","Ship Staff Insp.","BROKEN DRIVE BELT OF GALLEY AIRCONDITION UNIT","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","RENEWED 2 PCS DRIVE BELT","2019-01-20","CHAT190020","Completed","2019-02-08","No","No","No","Internal"]
[null,null,null,null,5958,"2019-09-11 20:16:14.999","2019-01-12","Deficiency","Ship Staff","Ship Staff Insp.","CORRODED LIMIT SWITCHES OF MIDSHIP ACCOMODATION LADDER PORTSIDE","Elect. Mach. & Equip.","ISM Related","Equipment Related","","","","","RENEWED LIMIT SWITCHES WITH SUPPLIED SPARE","2019-01-20","CHAT190019","Completed","2019-02-09","No","No","No","Internal"]
[null,null,null,null,5959,"2019-09-11 20:26:03.000","2019-01-16","Deficiency","Ship Staff","Ship Staff Insp.","ME OIL MIST EEPROM NEED TO REPLCED","Main Engine ","Eng. / Strg. Comp.","Equipment Related","","","","","REPLCED WITH NEW EEPROM","2019-02-28","CHAT195006","Completed","2019-02-23","No","No","No","Internal"]
[null,null,null,null,5960,"2019-09-11 20:38:24.000","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","ICU LEAKAGE ,UNIT NO.4","Main Engine ","Eng. / Strg. Comp.","Equipment Related","","","","","REPLCED WITH NEW SUPPLIED SPARE","2019-02-28","CHAT195004","Completed","2019-02-26","No","No","No","Internal"]
[null,null,null,null,5961,"2019-09-11 20:43:31.000","2019-01-16","Deficiency","Ship Staff","Ship Staff Insp.","BROKEN LEVEL SWITCH OF AUX.NO.3 LUBOIL SUMP","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED  FLOAT SWITCH","2019-02-28","CHAT190021","Completed","2019-02-27","No","No","No","Internal"]
[null,null,null,null,5962,"2019-09-11 20:52:34.000","2019-01-22","Deficiency","Ship Staff","Ship Staff Insp.","WASHOUT AND MISSING FORWARD ANCHOR LIGHT","Nav & comm. equip.","Navigation","Equipment Related","","","","","INSTALLD NEW SUPPLIED FORWARD ANCHOR LIGHT","2019-03-02","CHAT190033","Completed","2019-03-02","No","No","No","Internal"]
[null,null,null,null,5963,"2019-09-11 20:57:32.000","2019-01-25","Deficiency","Ship Staff","Ship Staff Insp.","BROKEN AND DEFECTIVE TEMP SWITCH OF HT FW COOLING A.E. NO.2","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","RENEWED WITH NEW SUPPLIED SPARE PART","2019-03-30","CHAT190034","Completed","2019-03-04","No","No","No","Internal"]
[null,null,null,null,5964,"2019-09-11 21:04:08.000","2019-03-04","Critical Equipment","Ship Staff","Ship Staff Insp.","RESCUE BOAT UNABLE TO SWING 115 DEG. FROM STOWED POSITION","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","CHECKED AND FOUND NOT ENOUGH PRESSURE . PUMP PRESSURE TO 190 MB. AND DEF.RECTIFIED","2019-03-30","","Completed","2019-03-04","No","No","No","Internal"]
[null,null,null,null,5965,"2019-09-11 21:09:28.000","2019-01-25","Deficiency","Ship Staff","Ship Staff Insp.","BROKEN AND DEFECTIVE TEMP SWITCH OF A.E. NO.1 HT FW COOLING.","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","RENEWED WITH SUPPLIED NEW SPARE","2019-03-30","CHAT190034","Completed","2019-03-07","No","No","No","Internal"]
[null,null,null,null,5966,"2019-10-11 00:59:30.000","2019-01-19","Deficiency","Ship Staff","Ship Staff Insp.","BROKEN AND DEFECTIVE TEMP. SWITCH OF A.E.NO.2 HT COOLING","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","RENEWED WITH SUPPLIED NEW SPARE","2019-03-30","CHAT190034","Completed","2019-03-11","No","No","No","Internal"]
[null,null,null,null,5967,"2019-10-11 01:03:34.000","2019-03-13","Critical Equipment","Ship Staff","Ship Staff Insp.","GENERAL FAULT IN LOOP 10 MAIN DECK","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","REPLACED DEFECTIVE MCP IN CO2 ROOM","2019-03-13","","Completed","2019-03-13","No","No","No","Internal"]
[null,null,null,null,5968,"2019-10-11 01:06:54.000","2019-03-13","Deficiency","Ship Staff","Ship Staff Insp.","ABNORMAL NOISE IN CIRCULATING PUMP NO.2","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACE NEW BEARINGS IN CURCULATING PUMP MOTOR","2019-03-13","","Completed","2019-03-13","No","No","No","Internal"]
[null,null,null,null,5969,"2019-10-11 01:11:15.000","2019-03-13","Deficiency","Ship Staff","Ship Staff Insp.","DAMAGE LIGHTING FIXTURE IN THE POOP DECK","Accommodation ","ISM Related","Equipment Related","","","","","REPLACED WITH NEW SPARE","2019-03-30","","Completed","2019-03-15","No","No","No","Internal"]
[null,null,null,null,5970,"2019-10-11 01:15:37.000","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","M.E. FUEL PUMP NO.1 LEAKAGE","Main Engine ","Eng. / Strg. Comp.","Equipment Related","","","","","GRIND HIGH PRESSURE PIPE","2019-03-30","CHAT190011","Completed","2019-03-16","No","No","No","Internal"]
[null,null,null,null,5971,"2019-10-11 01:19:45.000","2019-03-25","Deficiency","Ship Staff","Ship Staff Insp.","FIRE ALARM GENRAL AND POWER SUPPLY FAULT","Accommodation ","Emgcy. Systems","Equipment Related","","","","","CHANGE 9V BATTERY AND RESET THE WHOLE SYSTEM","2019-03-25","","Completed","2019-03-25","No","No","No","Internal"]
[null,null,null,null,5972,"2019-10-11 01:23:01.000","2019-03-25","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE TELEPHONE HANDSET OF INMARSAT ON BRIDGE","Accommodation ","Communication","Equipment Related","","","","","RENEWED WITH SPARE","2019-03-25","","Completed","2019-03-25","No","No","No","Internal"]
[null,null,null,null,5973,"2019-10-11 01:27:41.000","2019-02-04","Deficiency","Ship Staff","Ship Staff Insp.","AUTO SERVO OIL BACKWASH FILTER LEAKING ON SHAFT.BACK FLUSHING AND PIVOTIC SOLENOID VALVE DEFECTIVE","Main Engine ","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACED O-RING AND SOLENOID VALVE","2019-05-30","CHAT190041","Completed","2019-03-25","No","No","No","Internal"]
[null,null,null,null,5974,"2019-10-11 01:32:03.000","2019-03-20","Deficiency","Ship Staff","Ship Staff Insp.","UNSYNC OF INMARSAT C NO.2","Nav & comm. equip.","Communication","Equipment Related","","","","","REPAIRED BY SHORE TECHNICIAN","2019-03-30","CHAT195011","Completed","2019-03-26","No","No","No","Internal"]
[null,null,null,null,5975,"2019-10-11 01:35:23.000","2019-03-26","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE HANDSET OF VHF IN THE BRIDGE","Nav & comm. equip.","Communication","Equipment Related","","","","","RENEWED WITH NEW SUPPLIED SPARE","2019-04-30","CHATCHAT190057","Completed","2019-04-02","No","No","No","Internal"]
[null,null,null,null,5976,"2019-10-11 01:39:20.000","2019-03-19","Deficiency","Ship Staff","Ship Staff Insp.","RESCUEBOAT HOISTING UP AND DOWN DELAY WHEN STOPPING","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","RENEWED BREAK LINING","2019-04-30","","Completed","2019-04-22","No","No","No","Internal"]
[null,null,null,null,5977,"2019-10-11 01:44:41.000","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","MAIN VALVE AIR BOTTLE OUTLET PASSING","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","THOROUGH CHECKED BOTH MAIN VALVE NO PASSING THE LEAKAGE IS RECTIFIED","2019-04-30","","Completed","2019-04-30","No","No","No","Internal"]
[null,null,null,null,5978,"2019-10-11 01:47:58.000","2019-04-03","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE BATTERY OF ALDIS LAMP","Nav & comm. equip.","Navigation","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED BATTERY","2019-05-30","CHAT190064","Completed","2019-05-01","No","No","No","Internal"]
[null,null,null,null,5979,"2019-10-11 01:58:18.000","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","PROV.REF.PLANT CONDENSER NO.2 SUSPECTED LEAKING","Accommodation ","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED SPARE","2019-05-30","CHAT190036","Completed","2019-05-02","No","No","No","Internal"]
[null,null,null,null,5980,"2019-10-11 02:01:21.999","2019-04-05","Deficiency","Ship Staff","Ship Staff Insp.","BATTERY FAULT ON LOCAL WATER MIST SYATEM","Critical Equip.","Emgcy. Systems","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED BATTERY","2019-05-30","CHAT190070","Completed","2019-05-02","No","No","No","Internal"]
[null,null,null,null,5981,"2019-10-11 02:04:34.999","2019-04-22","Deficiency","Ship Staff","Ship Staff Insp.","INACCURATE READING OF ANEMOMETER","Nav & comm. equip.","Navigation","Equipment Related","","","","","INSTALLED NEW SUPPLIED ANENOMETER","2019-05-30","CHAT195013","Completed","2019-05-09","No","No","No","Internal"]
[null,null,null,null,5982,"2019-10-11 02:08:08.999","2019-04-05","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE REFRIGERATOR IN THE HOSPITAL","Elect. Mach. & Equip.","ISM Related","Equipment Related","","","","","INSTALLED NEW SUPPLIED REF.","2019-05-30","CHAT190069","Completed","2019-05-22","No","No","No","Internal"]
[null,null,null,null,5983,"2019-10-11 02:12:11.000","2019-04-14","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE FO PURIFIER NO.1,BURNT BEARINGS,BROKEN NECK BEARING COVER AND LUBRICATION OIL ORIFICE","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACE WITH NEW SUPPLIED SPARE","2019-05-30","CHAT190081","Completed","2019-05-22","No","No","No","Internal"]
[null,null,null,null,5984,"2019-10-11 02:15:06.999","2019-04-08","Deficiency","Ship Staff","Ship Staff Insp.","WECS POWER SUPPLY FAIL","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACED POWER SUPPLY WITH SUPPLIED SPARE","2019-05-30","CHAT190075","Completed","2019-05-24","No","No","No","Internal"]
[null,null,null,null,5985,"2019-10-11 02:19:24.999","2019-04-01","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE 24V SEALED LAMP ON FORWARD STBD EMBARKATION LADDER","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED SEALED LAMP","2019-05-30","CHAT190052","Completed","2019-05-24","No","No","No","Internal"]
[null,null,null,null,5986,"2019-10-11 02:22:25.000","2019-04-30","Deficiency","Ship Staff","Ship Staff Insp.","FILLING VALVE OF MAIN AIR BOTTLE PASSING","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","GRINDED","2019-05-30","","Completed","2019-05-30","No","No","No","Internal"]
[null,null,null,null,5987,"2019-10-11 02:25:49.000","2019-06-03","Deficiency","Ship Staff","Ship Staff Insp.","ABNORMAL NOISE ON DC FAN BLOWER OF MARINE RADAR PROCESSOR UNIT","Nav & comm. equip.","Navigation","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED DC FAN BLOWER","2019-06-30","CHAT190101","Completed","2019-06-10","No","No","No","Internal"]
[null,null,null,null,5988,"2019-10-11 02:28:55.000","2019-03-19","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE SALINITY SENSOR","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED SALINITY SENSOR","2019-06-30","CHAT190056","Completed","2019-06-12","No","No","No","Internal"]
[null,null,null,null,5989,"2019-10-11 02:34:17.000","2019-03-29","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE 220VAC SOCKETS ON MAIN DECK","Elect. Mach. & Equip.","ISM Related","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED SOCKETS,FUSES AND LAMP INDICATORS","2019-06-30","CHAT190059","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,5990,"2019-10-11 02:38:00.000","2019-05-30","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE IN LCD DISPLAY OF ACP IN BRIDGE","Nav & comm. equip.","Navigation","Equipment Related","","","","","RENEWED WITH NEW SUPPLIED LSCD DISPLAY","2019-06-30","CHAT195025","Completed","2019-06-23","No","No","No","Internal"]
[null,null,null,null,5991,"2019-10-11 02:41:00.000","2019-06-27","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE BRDIGE WINDOW WIPER","Nav & comm. equip.","Navigation","Equipment Related","","","","","RECTIFIED","2019-07-31","","Completed","2019-06-28","No","No","No","Internal"]
[null,null,null,null,5992,"2019-10-11 02:43:41.000","2019-06-30","Deficiency","Ship Staff","Ship Staff Insp.","LOW INSULATION OF AHU MOTOR","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","RE-INSULATE AHU MOTOIR","2019-06-30","","Completed","2019-06-30","No","No","No","Internal"]
[null,null,null,null,5993,"2019-10-11 02:47:49.999","2019-05-10","Deficiency","Ship Staff","Ship Staff Insp.","PMS ALARM IN AMS HAS INVALID DATA.ALL PMS ALARMS ARE NOT OPERATIONAL","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","KONSBERG SERVICE ASSISTANCE","2019-06-30","CHAT190117","Completed","2019-07-08","No","No","No","Internal"]
[null,null,null,null,5994,"2019-10-11 02:51:10.000","2019-06-29","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE CONTACTOR AND OVERLOAD RELAY OF AHU FAN","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED CONTACTOR AND OVERLOAD RELAY","2019-07-31","CHAT190122","Completed","2019-07-15","No","No","No","Internal"]
[null,null,null,null,5995,"2019-10-11 02:54:37.999","2019-06-24","Deficiency","Ship Staff","Ship Staff Insp.","DAMAGE LIMIT SWITCH OF PROVISION CRANE","Deck Mach.","ISM Related","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED SPARE","2019-07-31","CHAT190114","Completed","2019-07-15","No","No","No","Internal"]
[null,null,null,null,5996,"2019-10-11 02:58:10.000","2019-07-10","Deficiency","Ship Staff","Ship Staff Insp.","PROVISION CHAMBER-ICE ACCUMULATION IN THE MEAT ROOM FLOORING","Miscellaneous","ISM Related","Equipment Related","","","","","INSTALLED VALVE IN THE DRAIN PIPE","2019-07-31","","Completed","2019-07-31","No","No","No","Internal"]
[null,null,null,null,5997,"2019-10-11 03:01:16.000","2019-06-27","Breakdown","Ship Staff","Ship Staff Insp.","DEFCTIVE WASHING MACHINE","Elect. Mach. & Equip.","ISM Related","Equipment Related","","","","","RENEWED WITH NEW SUPPLIED WASHING MACHINE","2019-07-31","CHAT190118","Completed","2019-07-31","No","No","No","Internal"]
[null,null,null,null,5998,"2019-10-11 03:04:36.999","2019-06-24","Deficiency","Ship Staff","Ship Staff Insp.","DAMAGE LIMIT SWITCH OF RESCUEBOAT","Elect. Mach. & Equip.","LSA / FFA Appliances","Equipment Related","","","","","REPLACE WITH NEW SUPPLIED LIMIT SWICTH","2019-07-31","CHAT190114","Completed","2019-08-08","No","No","No","Internal"]
[null,null,null,null,5999,"2019-10-11 03:07:25.000","2019-08-08","Breakdown","Ship Staff","Ship Staff Insp.","PROVISION COMPRESSOR NO.1 BREAKDOWN","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","OVERHAULED","2019-08-08","","Completed","2019-08-09","No","No","No","Internal"]
[null,null,null,null,6000,"2019-10-11 03:12:37.000","2019-06-27","Deficiency","Ship Staff","Ship Staff Insp.","DEFECTIVE SWITCH OF BOILER BURNER OPERATION.BURNER MOTOR PURGING NOT WORKING","Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACE WITH NEW SWITCH OF CONTROL PANEL.TEMPORARY BRIDGE BURNER MOTOR","2019-08-31","CHAT190119","Completed","2019-08-04","No","No","No","Internal"]
[null,null,null,null,6001,"2019-10-11 04:15:46.000","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","2p cARGO TANK HIGH LEVEL ALARM STUCK IN ALARM POSITION SAME TO BE REMOVED AND FREED","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","REMOVED ,CLEANED,REINSTALLED AND TESTED IN WORKING CONDITION","2019-08-18","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,6002,"2019-10-11 04:18:46.000","2019-08-15","Deficiency","Ship Staff","Ship Staff Insp.","ANENOMETER NOT SHOWING RELATIVE SPEED","Nav & comm. equip.","Navigation","Equipment Related","","","","","ETO FOUND LOOSE CONNECTION","2019-08-20","","Completed","2019-08-17","No","No","No","Internal"]
[null,null,null,null,6003,"2019-10-11 04:22:25.000","2019-08-16","Deficiency","Ship Staff","Ship Staff Insp.","BRIDGE WINDOW WIPER FRON RIGHT SIDE NOT WORKING","Nav & comm. equip.","Navigation","Equipment Related","","","","","RENEWED WITH NEW SPARE","2019-08-20","","Completed","2019-08-17","No","No","No","Internal"]
[null,null,null,null,6004,"2019-10-11 04:26:30.000","2019-08-17","Deficiency","Ship Staff","Ship Staff Insp.","rUDDER INDICATOR AT WING P/S AND WING CONSOLE P/S ARE NOT SYNCHRONISED WITH MAIN CONSOLE RUDDER INDICATOR","Nav & comm. equip.","Navigation","Equipment Related","","","","","ETO CHECKED AND ADJUSTED","2019-08-20","","Completed","2019-08-18","No","No","No","Internal"]
[null,null,null,null,6005,"2019-10-11 04:31:32.000","2019-08-13","Deficiency","Ship Staff","Ship Staff Insp.","ONE PANEL OF BRIDGE WINDOW WIPER STBD FRONT NOT WORKING","Nav & comm. equip.","Navigation","Equipment Related","","","","","ETO REPAIRED","2019-08-31","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,6006,"2019-10-11 04:35:19.000","2019-08-13","Deficiency","Ship Staff","Ship Staff Insp.","SOME EMERG.LIGHT IN PASSAGE WAY AND RESCUE BOAT ARE NOT WORKING","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","","","","","ETO CHANGE BUSTED BULB AND RECTIFIED ","2019-08-17","","Completed","2019-08-17","No","No","No","Internal"]
[null,null,null,null,6007,"2019-10-11 04:38:12.000","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","M.E. ICU LEAKAGE IN UNIT NO.2","Main Engine ","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED SPARE","2019-07-31","CHAT195004","Completed","2019-08-09","No","No","No","Internal"]
[null,null,null,null,6008,"2019-10-11 04:42:49.000","2019-01-10","Deficiency","Ship Staff","Ship Staff Insp.","NO.4B(P) DWBT TK SENSOR FAULTY","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED SPARE","2019-07-31","CHAT190040","Completed","2019-08-24","No","No","No","Internal"]
[null,null,null,null,6009,"2019-10-11 04:45:21.000","2019-01-10","Deficiency","Ship Staff","Ship Staff Insp.","NO.4A(P) SWBT SENSOR FAULTY","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","REPLCED WITH NEW SUPPLIED SPARE","2019-07-31","CHAT1900040","Completed","2019-08-24","No","No","No","Internal"]
[null,null,null,null,6010,"2019-10-11 04:47:54.000","2019-01-10","Deficiency","Ship Staff","Ship Staff Insp.","NO.4B(P) SWBT SENSOR FAULTY","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED SPARE","2019-07-31","CHAT190040","Completed","2019-08-24","No","No","No","Internal"]
[null,null,null,null,6011,"2019-10-11 04:52:00.000","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","HFO NO.1 OVERFLOW TK FAULTY LEVEL SENSOR","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","REPLACED WITH NEW SUPPLIED SPARE","2019-07-31","CHAT190040","Completed","2019-08-24","No","No","No","Internal"]
[null,null,null,null,6012,"2019-10-11 04:57:06.999","2019-03-28","Deficiency","Ship Staff","Ship Staff Insp.","LOW INSULATIONON NO.1 REEFER POWER SOCKETS IN IRP7 AND IRP8","Elect. Mach. & Equip.","ISM Related","Equipment Related","","","","","RENEWED DEFECTIVE SOCKETS,CIRCUIT BREAKER, AND TERMINAL BLOCKS SOCKETS","2019-07-31","CHAT190065","Completed","2019-08-22","No","No","No","Internal"]
[null,null,null,null,6013,"2019-10-11 05:00:46.000","2019-03-28","Deficiency","Ship Staff","Ship Staff Insp.","LOW INSULATION ON NO.3 REEFER POWER SOCKETS","Elect. Mach. & Equip.","ISM Related","Equipment Related","","","","","RENEWED DEFECTIVE SOCKETS,CIRCUIT BREAKER AND TERMINAL BLOCKS SOCKET","2019-07-31","CHAT190065","Completed","2019-08-22","No","No","No","Internal"]
[null,null,null,null,6014,"2019-10-11 05:05:25.999","2019-08-16","Breakdown","Ship Staff","Ship Staff Insp.","ELECTROTYPHONE MOTOR BREAKDOWN","Nav & comm. equip.","Navigation","Equipment Related","","","","","RENEWED WITH SUPPLIED MOTOR","2019-08-31","CHAT190144","Completed","2019-08-28","No","No","No","Internal"]
[null,null,null,null,6015,"2019-10-11 05:08:39.000","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NO.2 FEED WATER PUMP DISCHARGE PRESSURE GUAGE FAULTY","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","DECLOGGED AND CLEANED","2019-08-23","","Completed","2019-08-14","No","No","No","Internal"]
[null,null,null,null,6016,"2019-10-11 05:13:26.999","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME SUMP TK & DRAIN TK SOUNDING PIPE OPENING LEVER STUCK .SAME TO FREED","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","REPAIRED OPENING LEVER","2019-08-23","","Completed","2019-08-14","No","No","No","Internal"]
[null,null,null,null,6017,"2019-10-11 05:16:34.000","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME VISCOTHERM HAS AN ERROR,SENSOR TO BE TAKEN OUT AND CLEANED","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","CHECKED AND CLEANED","2019-08-16","","Completed","2019-08-15","No","No","No","Internal"]
[null,null,null,null,6018,"2019-10-11 05:29:04.999","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","BUNKER CHECKLIST 12.04.744.01 WAS NOT FILLED FOR LAST BUNKER OPERATION","Miscellaneous","Cert. & Docu.","Behaviour Based","","","","","FILLED UP","2019-08-14","","Completed","2019-08-14","No","No","No","Internal"]
[null,null,null,null,6019,"2019-10-11 05:33:07.000","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ENGINE CONTROL BOOK NOT FILLED ALL EVENTS AS PER REQUIREMENTS IN THE INITIAL PAGE.","Documentation","Cert. & Docu.","Behaviour Based","","","","","FILLED UP","2019-08-15","","Completed","2019-08-15","No","No","No","Internal"]
[null,null,null,null,6020,"2019-10-11 05:39:41.999","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LOGBOOK WAS FILLED ONLY ONCE AND MANY PARAMETERS WERE LEFT BLANK","Documentation","Cert. & Docu.","Human Error","","","","","FILLED UP","2019-08-15","","Completed","2019-08-15","No","No","No","Internal"]
[null,null,null,null,6021,"2019-10-11 05:44:28.999","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ORB ENTRIES ON TANDOM CHECKED FOR INCENERATOR TANK NOT MATCHING AS EVAPORATION WAS NOT SHOWN.ALSO ONLY C/E WAS SIGNING ALL ENTRIES,DUTY ENGINEER WAS SIGNING ANY ENTRIES","Documentation","Cert. & Docu.","Human Error","","","","","ORB CORRECTED AND DUTY ENGINEER SIGNED","2019-08-15","","Completed","2019-08-15","No","No","No","Internal"]
[null,null,null,null,6840,"16/11/2019 2:00:39 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel top flatform has one of the exh. pipe welding support crack,In total all flatform 6 in no.rubber has hardened & crckd,8 in no.nuts have become loose,1 in no. stud crckd","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To Be repaired","2019-08-25","","Completed","2019-08-19","No","No","No","Internal"]
[null,null,null,null,6860,"15/11/2019 12:24:00 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sulphur Record book all the tanks of Mgo were not mention during the change over","Documentation","Cert. & Docu.","Human Error","","","","","To Be filled Up,All tank been recorded","2019-08-16","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,6861,"15/11/2019 7:23:16 PM","2019-10-29","Deficiency","Ship Staff","Ship Staff Insp.","FWD HORN FOUND TEMPORARILY SECURED WITH ROPE","LSA / FFA","General Appearance","Equipment Related","","","","","TO BE RECTIFIED WITH SECURED BYV STEEL BRACKET PERMANENTLY ","2019-11-30","","Completed","2019-11-14","No","No","No","Internal"]
[null,null,null,null,6862,"Sat Nov 16 2019 09:51:42 GMT+0000 (Coordinated Universal Time)","2019-08-13","Observation","Owner / Marine / Tech. Suptd.,SIRE / CDI Insp.","Suptd. Insp.","Some emergency light in passage way & rescue boat are not working faults need to be found & rectified. Also passage way lights which are from emergency source to be marked green ","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","","","","","To rectified  and make a marked.","2019-08-15","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,6863,"Sat Nov 16 2019 09:58:46 GMT+0000 (Coordinated Universal Time)","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Galley heat sensor cover is damaged cover to be replaced with new one.","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","Renewed the cover  ","2019-08-16","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,6864,"Sat Nov 16 2019 10:05:18 GMT+0000 (Coordinated Universal Time)","2019-08-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","2P cargo tank high levelalrm stuck in alarm position same to be removed and freed","Deck Pipe / Fittings","General Appearance","Equipment Related","","","","","To be rectified ","2019-08-18","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,6865,"Sat Nov 16 2019 10:10:46 GMT+0000 (Coordinated Universal Time)","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Anemometer on bridge not showing reading ,to be check","Nav & comm. equip.","Navigation","Equipment Related","","","","","To be check ","2019-08-16","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,6866,"Sat Nov 16 2019 10:16:12 GMT+0000 (Coordinated Universal Time)","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","A lot of old bunker sample lying in steering gear room store room apart from last one year samples all other samples disposed off.","Miscellaneous","General Appearance","Equipment Related","","","","","Old sample to be disposed","2019-08-23","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,6867,"Sat Nov 16 2019 10:36:12 GMT+0000 (Coordinated Universal Time)","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","HFO trasfer pump seal leaking on glass , no greasing done ,Carry out greasing & check if leak stops else change the seal.","Aux. Mach.","General Appearance","Equipment Related","","","","","Checked and rectified leak greasing needed","2019-08-23","","Completed","2019-08-16","No","No","No","Internal"]
[null,null,null,null,6868,"16/11/2019 1:41:57 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aft Bilge well to be empty and clean thoroughly","Hull & Tanks","MARPOL Related","Equipment Related","","","","","to clean up","2019-08-23","","Completed","2019-08-17","No","No","No","Internal"]
[null,null,null,null,6869,"16/11/2019 1:47:57 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","After receiving chemicals newport FOT same to be dosed in 2SFOT,Then internal Transfer of fuel to be carried out from other bunker tank,emptied bunker tank then paln to clean","Miscellaneous","MARPOL Related","Equipment Related","","","","","FOT to be dose & other FO tank to conduct inspection.","2019-08-23","","Completed","2019-08-17","No","No","No","Internal"]
[null,null,null,null,6870,"16/11/2019 2:04:10 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No 1 Ballast  pp suc.pipe has soft patch,Permanent repair to be carried out.","ER Pipes, valves & fittings","Cargo / Ballast Systems","Equipment Related","","","","","To be repaired","2019-09-13","","Completed","2019-08-22","No","No","No","Internal"]
[null,null,null,null,6871,"16/11/2019 2:08:03 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CSWPP & HT PP stdy p/ps are not coming to stnadby due to elect. fault","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","To be rectified","2019-08-28","","Completed","2019-08-25","No","No","No","Internal"]
[null,null,null,null,6872,"16/11/2019 2:10:56 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ER many of the bottoms plates are not secured/screw missing,to order for screw and secure","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Put up missing screw","2019-08-28","","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,6873,"16/11/2019 2:15:08 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Elect.store room is not stored in properly,including critical spares,To be arrange properly and inventory to be taken.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related,Inappropriate Procedure","","","","","To be arrange and spare inventory.","2019-08-28","","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,6874,"16/11/2019 2:18:26 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo hold passage bulb port and stbd which are from emergency source to be identified and mark by red.","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","","","","","Make kark to be identified","2019-08-21","","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,6875,"16/11/2019 2:22:26 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","HFO transfer pump auto cut in and cut off not working due to possiblly sticking float to be rectified","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To be rectified","2019-09-13","","Completed","2019-08-27","No","No","No","Internal"]
[null,null,null,null,6876,"16/11/2019 2:26:15 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Water sensor not showing correct reading for sensor water content","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To be checked and rectified","2019-09-13","","Completed","2019-08-13","No","No","No","Internal"]
[null,null,null,null,6877,"16/11/2019 2:30:09 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No.2 boiler F>O> p/p seal leaking to be rectified & No.1 pp discharge pressure gauge opaque needs to be change.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Change oil seal,rectified laek.","2019-08-23","","Completed","2019-08-22","No","No","No","Internal"]
[null,null,null,null,6878,"16/11/2019 2:33:15 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Many of the sounding pipe relief valve missing,same to be fabricated and connected","ER Pipes, valves & fittings","Emgcy. Systems","Equipment Related","","","","","Complete valve nuts and connected","2019-09-03","","Completed","2019-08-17","No","No","No","Internal"]
[null,null,null,null,6879,"16/11/2019 2:37:12 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Duck keel tunnel has water accumated aft due to steam leak,leak to be arrested and water to clear as iti is forming rust spots,Present derust spots in duct.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","to be rectified","2019-08-28","","Completed","2019-08-24","No","No","No","Internal"]
[null,null,null,null,6880,"Sun Nov 17 2019 07:31:08 GMT+0000 (Coordinated Universal Time)","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Door Closure to be fitted on A-60 door as per fire plan.","Accommodation ","General Appearance","Equipment Related","","","","","To be installed after we recieved the equipement ","2019-08-28","CHAT190142","Completed","2019-08-30","No","No","No","Internal"]
[null,null,null,null,6881,"Sun Nov 17 2019 07:52:51 GMT+0000 (Coordinated Universal Time)","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Self Closing door device on A class door as per fire plan are missing from many places, same to fitted after suppling the door closure ","Accommodation ","General Appearance","Equipment Related","","","","","To install after we recieve the equipement ","2019-08-20","CHAT190142","Completed","2019-08-30","No","No","No","Internal"]
[null,null,null,null,6882,"Sun Nov 17 2019 07:58:28 GMT+0000 (Coordinated Universal Time)","2019-01-31","Deficiency","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","ICU Leakage unit no.3 ","Main Engine ","Eng. / Strg. Comp.","Equipment Related","","","","","To replace with new spare","2019-07-31","CHAT195004","Completed","2019-09-07","No","No","No","Internal"]
[null,null,null,null,6883,"Sun Nov 17 2019 08:03:00 GMT+0000 (Coordinated Universal Time)","2019-10-06","Deficiency","Ship Staff","Ship Staff Insp.","Forward Manual Davit ","Miscellaneous","General Appearance","Equipment Related","","","","","To Overhaul","2019-07-31","","Completed","2019-09-15","No","No","No","Internal"]
[null,null,null,null,6884,"Sun Nov 17 2019 08:09:07 GMT+0000 (Coordinated Universal Time)","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Manual davit winch of Bosun store aft cover broken ,same needs to be repaired. fasbricated","Deck Mach.","General Appearance","Equipment Related","","","","","Already removedderusted and painted with primer and bring to E/R workshop","2019-08-23","","Completed","2019-09-15","No","No","No","Internal"]
[null,null,null,null,6885,"17/11/2019 10:14:44 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","One of the cargo hold vent thightening nuts broken to be repaired.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","To removed and bring to E/R workshop for repair.","2019-09-28","","Completed","2019-08-20","No","No","No","Internal"]
[null,null,null,null,6886,"17/11/2019 10:18:40 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Manila Passage,many places local rust spots originating port and stbd to be derusted and painted.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Spot derust and painted to port stbd side manila passage completed","2019-09-28","","Completed","2019-09-05","No","No","No","Internal"]
[null,null,null,null,6887,"17/11/2019 10:22:04 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Rescueboat davit accumulator pressure gauge opaque need to be replaced with new.","Deck Pipe / Fittings","LSA / FFA Appliances","Equipment Related","","","","","ordered and new spare arrive","2019-09-29","","Completed","2019-08-27","No","No","No","Internal"]
[null,null,null,null,6888,"17/11/2019 10:25:52 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Spare Piston on higher side to be renewed with new spare piston crown when rcvd.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","","","","","spare requested and rcvd,renewed piston crown","2019-10-13","","Completed","2019-09-07","No","No","No","Internal"]
[null,null,null,null,6889,"17/11/2019 10:29:14 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AHU no.2 compressor suction and discharge pressure gauge faulty.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","to be replaced with new spare","2019-08-28","","Completed","2019-08-27","No","No","No","Internal"]
[null,null,null,null,6890,"17/11/2019 10:32:00 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Seawage air blower pressure gauge broken to be replaced with new","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Renewed pressure gauage","2019-08-28","","Completed","2019-08-27","No","No","No","Internal"]
[null,null,null,null,6891,"17/11/2019 10:36:51 AM","2019-01-13","Deficiency","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","No.4A(P) DDWBT tk sensor faulty","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Awaiting spare. spare supplied and renewed","2019-07-31","","Completed","2019-09-13","No","No","No","Internal"]
[null,null,null,null,6892,"17/11/2019 10:43:16 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both E/R vent.flaps are slightly opened when closed position due to rust formation on the channel.to be deruted,portside 1 limit switch is broken,stbdside air cylinder studs broken,repair kit for air cylinder to be requested and replaced.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","Derusted and painted,limit switch repqired,air cylinder supplied and renewed","2019-09-28","","Completed","2019-09-15","No","No","No","Internal"]
[null,null,null,null,6893,"17/11/2019 10:46:37 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both E/R ventillation fan flaps doors lip seal is getting rusted to be derusted and painted","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","Derusted and painted bot port and stbd.","2019-09-28","","Completed","2019-09-15","No","No","No","Internal"]
[null,null,null,null,6894,"17/11/2019 10:50:06 AM","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","No.4A(S) SWBT tk sensor Faulty","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Awaiting spare requested. Spare supplied and rectified","2019-07-31","CHAT190040","Completed","2019-09-13","No","No","No","Internal"]
[null,null,null,null,6895,"17/11/2019 10:52:43 AM","2019-01-31","Deficiency","Ship Staff","Ship Staff Insp.","NO.4B(S) SWBT tk faulty","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Awaiting spare..Spare supplied and rectified","2019-07-31","CAH190040","Completed","2019-09-13","No","No","No","Internal"]
[null,null,null,null,6896,"17/11/2019 10:56:53 AM","2019-04-10","Deficiency","Ship Staff","Ship Staff Insp.","Defective UV lamp and Solenoid valve of UVK sterilizer","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","awaiting for spare,Spare supplied ,But found out the UV starter is also at fault..Clsed this item and defect for UV starter created","2019-07-31","CHAT190088","Completed","2019-09-15","No","No","No","Internal"]
[null,null,null,null,6897,"18/11/2019 4:39:02 AM","2019-06-19","Deficiency","Ship Staff","Ship Staff Insp.","Damaged Lighting Fixtures 5 pcs, bridge, 2 pcs D-Deck ,1 pc. C-Deck .2 Pcs B-deck and 4 pcs A-deck.","Accommodation ","General Appearance","Equipment Related","","","","","To Replace damaged lighting fixtures.","2019-08-31","CHAT190102","Completed","2019-09-15","No","No","No","Internal"]
[null,null,null,null,6898,"18/11/2019 4:43:43 AM","2019-08-21","Deficiency","Ship Staff","Ship Staff Insp.","Air Dryer Compressor Motor Burnt Out ","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Compressor motor has been order and awaiting to supply ","2019-08-21","CHAT192156","Completed","2019-09-15","No","No","No","Internal"]
[null,null,null,null,6899,"18/11/2019 4:47:24 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Air dryer fan compressor not working only fan.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Checke / Repair","2019-08-23","","Completed","2019-09-15","No","No","No","Internal"]
[null,null,null,null,6900,"18/11/2019 4:51:37 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AHU before filter section bottom plates wasted, to be repaired with cement & board.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","We are now in working for new plate to kept the duct fixed.","2019-09-13","","Completed","2019-09-18","No","No","No","Internal"]
[null,null,null,null,6901,"18/11/2019 4:57:10 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aircon Galley the outer cover is temporary damaged ,same to be covered /repaired with galvanize","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Soon to carried out after AHU after the AHU before filter duct completed.","2019-09-30","","Completed","2019-09-22","No","No","No","Internal"]
[null,null,null,null,6902,"18/11/2019 5:04:09 AM","2019-08-13","Non Conformity,Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AHU air duct cover temporary repairs to be carried out by putting addiional support and support plate","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Soon to carried out after AHU before filter duct completed.","2019-09-30","","Completed","2019-09-22","No","No","No","Internal"]
[null,null,null,null,6903,"18/11/2019 5:09:34 AM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port side windlass lining worn around 50 % same to be palnned at next anchorage.","Deck Mach.","Mooring","Equipment Related","","","","","New brake lining lining is available on board ,will wait for the  exact time when to change at anchorage.","2019-09-30","","Completed","2019-09-28","No","No","No","Internal"]
[null,null,null,null,6904,"18/11/2019 5:15:11 AM","2019-09-26","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","\tIsolation valve pressure gauge bracket found broken ","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","To replace the pressure gauge brake by fabricatiing new bracket.","2019-10-07","","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,6905,"18/11/2019 5:23:48 AM","2019-06-25","Deficiency","Ship Staff","Ship Staff Insp.","Renew all electrical components of PS midship ACCOM ladder.","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Not yet started as need to do first some others most urgent jobs to rectified first to avoid deoperdized of normal operation.Plan to begin this week and target date will be this week dated 19 Sept. 2019 ","2019-09-30","CHAT190115","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,6906,"18/11/2019 5:32:14 AM","2019-08-08","Breakdown","Ship Staff","Ship Staff Insp.","MID pilot ladder Portside control to be renew.","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Not yet started as need to do first some others most urgent jobs to rectified first to avoid deopardized of normal operation .Plan to begin this week end and target dated 19 Sept. 2019 ","2019-09-30","","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,6907,"18/11/2019 5:40:50 AM","2019-09-26","Deficiency","Ship Staff","Ship Staff Insp.","Lashing turn buckle pin was detached","Miscellaneous","General Appearance","Equipment Related","","","","","Lashing Materials turn buckle was brought to ER workshop and weld detatched pin.","2019-10-07","","Completed","2019-10-05","No","No","No","Internal"]
[null,null,null,null,6908,"18/11/2019 5:49:15 AM","2019-06-10","Deficiency","Ship Staff","Ship Staff Insp.","Dented 2 pcs of container socket at BAY 17 ROW 03 ","Miscellaneous","General Appearance","Equipment Related","","","","","Almost full cargo loading season .We will take chances everytime and include in cargo planning if we can vacate the slot BAY 17 row 03 and clear the sorroundings with DG cargo.","2019-10-30","","Completed","2019-10-06","No","No","No","Internal"]
[null,null,null,null,6909,"18/11/2019 5:54:07 AM","2019-08-16","Deficiency","Ship Staff","Ship Staff Insp.","MAin Sea water cooling pump spare","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Awaiting to supply soonest as this is very important.","2019-09-30","CHAT190145","Completed","2019-10-05","No","No","No","Internal"]
[null,null,null,null,6910,"18/11/2019 5:57:38 AM","2019-09-26","Deficiency","Ship Staff","Ship Staff Insp.","Sea water pump mechanical seal damaged","ER Pipes, valves & fittings","General Appearance","Equipment Related","","","","","Raised under RO CHAT190145","2019-09-30","CHAT190145","Completed","2019-10-05","No","No","No","Internal"]
[null,null,null,null,6911,"18/11/2019 6:01:27 AM","2019-10-01","Deficiency","Ship Staff","Ship Staff Insp.","Rectifier Power Supply FOR AMS ","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Awaiting to supply soonest as this very important.","2019-10-20","CHAT190196","Completed","2019-10-05","No","No","No","Internal"]
[null,null,null,null,6912,"18/11/2019 6:06:09 AM","2019-09-26","Deficiency","Ship Staff","Ship Staff Insp.","Pilot ladder (S) subject for replacement due to old condition ","Deck Mach.","General Appearance","Equipment Related","","","","","RCVD 2 pcs at SHnghai 14.10.2019/Port/Stbd, pilot ladder renewed 15.10.2019.","2019-10-15","CHAT190183","Completed","2019-10-15","No","No","No","Internal"]
[null,null,null,null,6913,"18/11/2019 6:10:09 AM","2019-08-13","Observation","Ship Staff","Suptd. Insp.","Doubler found on the FWD central cooler inlet pipe ,new pipe to be ordered fabricate ?connected.","ER Pipes, valves & fittings","General Appearance","Equipment Related","","","","","Completed replaced new FWD central coller inlet pipe.","2019-10-15","","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,6914,"18/11/2019 6:13:53 AM","2019-09-11","Deficiency","Ship Staff","Ship Staff Insp.","Fuel oil Conditioning unit","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Replaced new rcvd spare upgraded EVT 30 sensor.","2019-10-30","CHAT190183","Completed","2019-10-29","No","No","No","Internal"]
[null,null,null,null,6915,"18/11/2019 6:16:59 AM","2019-09-26","Deficiency","Ship Staff","Ship Staff Insp.","Boiler pump FO no.2 pump mechanical seal damage.","Boiler","General Appearance","Equipment Related","","","","","Renewed new rcvd spare mechanical seal ","2019-10-30","CHAT190155","Completed","2019-10-30","No","No","No","Internal"]
[null,null,null,null,6916,"Mon Nov 18 2019 09:43:13 GMT+0000 (Coordinated Universal Time)","2019-09-26","Deficiency","Ship Staff","Ship Staff Insp.","fwd MAST LADDER guard rail found rusty and broken weld ","Deck Pipe / Fittings","General Appearance","Equipment Related","","","","","Materials are supplied on board under CHAT190215 .Parts are already fabricated .Waiting for good oppurtunity timing to install the guard rail.","2019-11-30","CHAT 190215 ","Completed","2019-11-07","No","No","No","Internal"]
[null,null,null,null,6917,"Mon Nov 18 2019 09:48:04 GMT+0000 (Coordinated Universal Time)","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Additional lightings to be installed on passage way between the cargo hold on amin deck as per flag requirement RFQ for Required materials to be raised accordingly.","Elect. Mach. & Equip.,Miscellaneous","General Appearance","Equipment Related","","","","","Job done has been cancelled from the office by supt. Aneet Singh.","2019-10-30","","Completed","2019-10-30","No","No","No","Internal"]
[null,null,null,null,6918,"Mon Nov 18 2019 09:53:18 GMT+0000 (Coordinated Universal Time)","2019-09-26","Deficiency","Ship Staff","Ship Staff Insp.","Engine Room ventilation fan (S) screen found worn out.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Received materials and renewed ventilation screen.","2019-03-11","","Completed","2019-11-09","No","No","No","Internal"]
[null,null,null,null,6919,"Mon Nov 18 2019 09:57:44 GMT+0000 (Coordinated Universal Time)","2019-10-29","Observation","Ship Staff","Ship Staff Insp.","3/OFF cabin toilet faucet leaking ","Accommodation ","General Appearance","Equipment Related","","","","","Overhauled faucet and fit back and rectified water leakage.","2019-11-15","","Completed","2019-11-15","No","No","No","Internal"]
[null,null,null,null,6920,"Mon Nov 18 2019 10:01:23 GMT+0000 (Coordinated Universal Time)","2019-10-29","Observation","Ship Staff","Ship Staff Insp.","Emergency gen. ventilation flaps and control wheel frozen.","Deck Mach.","General Appearance","Equipment Related","","","","","Derusted ,paint and greased ventilation flaps and control wheel.","2019-11-15","","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,6921,"Mon Nov 18 2019 10:05:49 GMT+0000 (Coordinated Universal Time)","2019-10-29","Observation","Ship Staff","Ship Staff Insp.","Aircon room ventilation flaps and control wheel frozen.","Deck Mach.","General Appearance","Equipment Related","","","","","Derusted ,paint and greased ventilation flaps and control wheel.","2019-11-15","","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,6922,"Mon Nov 18 2019 10:09:48 GMT+0000 (Coordinated Universal Time)","2019-10-29","Observation","Ship Staff","Ship Staff Insp.","Bunker sample btls to be transferred to paint room.","Miscellaneous","MARPOL Related","Equipment Related","","","","","Bunker sample transferred inside paint room.","2019-11-15","","Completed","2019-11-07","No","No","No","Internal"]
[null,null,null,null,6923,"Mon Nov 18 2019 10:13:47 GMT+0000 (Coordinated Universal Time)","2019-10-29","Observation","Ship Staff","Ship Staff Insp.","Flaps screen of Bow Thruster found not fitted.","Deck Mach.","General Appearance","Equipment Related","","","","","Derusted paint and instlled flaps.","2019-05-11","","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,6924,"Mon Nov 18 2019 10:18:11 GMT+0000 (Coordinated Universal Time)","2019-10-29","Deficiency","Ship Staff","Ship Staff Insp.","FWD horn found temporarily secured with rope.","LSA / FFA","General Appearance","Equipment Related","","","","","To be secured with steel bracket permanently ","2019-11-30","","Completed","2019-11-14","No","No","No","Internal"]
[null,null,null,null,6925,"Mon Nov 18 2019 10:23:01 GMT+0000 (Coordinated Universal Time)","2019-10-29","Deficiency","Ship Staff","Ship Staff Insp.","Brridge indicator side tunnel watertight door found alarm during inspection.","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Electrician to checked the limit switch condition .Rectified adjusted limit switch no alarm.","2019-11-15","","Completed","2019-11-04","No","No","No","Internal"]
[null,null,null,null,6926,"Mon Nov 18 2019 10:27:44 GMT+0000 (Coordinated Universal Time)","2019-08-11","Deficiency","Ship Staff","Ship Staff Insp.","To caary out replace wasted V-belt of AHU /Defective electrical wire power supply ","Air Comp.,Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To rectified replaced new spare V-belt /wire of AHU moto power supply.","2019-08-11","","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,6927,"Mon Nov 18 2019 10:35:10 GMT+0000 (Coordinated Universal Time)","2019-11-16","Deficiency","Ship Staff","Ship Staff Insp.","Rescue boat Davit Winch brake lining slowly release ,noticed during operation.","Deck Mach.","General Appearance","Equipment Related","","","","","Rectified ajusted brake lining and tested found no more slowly release and  brake was working properly.","2019-11-16","","Completed","2019-11-16","No","No","No","Internal"]
[null,null,null,null,null,"Mon Nov 18 2019 10:41:43 GMT+0000 (Coordinated Universal Time)","2019-11-18","Deficiency","Ship Staff","Ship Staff Insp.","AHU blower fan air duct support and casing wasted support some angle bar support deterioted.vibration made  and detached bolts.","Aux. Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","To be renewed wasted part  of  accom.AHU air duct fan angle bar support and fixed with bolts.Done repaired and back to service ","2019-11-20",null,"Completed","2019-11-19","No",null,null,"Internal"]
[null,null,null,null,null,"15/11/2019 7:15:21 PM","2019-11-13","Deficiency","Ship Staff","Ship Staff Insp.","During testing Temp. DG no.1 C.F.W. High temp. cut out switch defective.","Aux. Engine","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","To be renew with new  spare C.F.W. high temp. switch. Recieved spare At Shnghai and fixed and tested and observed  working in good order","2019-11-13","CHAT190230","Completed","2019-11-22","No",null,null,"Internal"]
[null,null,null,null,null,"15/11/2019 5:22:39 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck  derusting to carry out on rust spots","Deck Pipe / Fittings","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Main Deck passage way (P&S) cosmetics completed .Main deck de-rusted, applied 3 coats of primer and top coat paint.","2019-11-30",null,"Completed","2019-11-20","No",null,null,"Internal"]
[null,null,null,null,null,"15/11/2019 6:58:51 PM","2019-10-29","Other","Ship Staff","Ship Staff Insp.","Bridge Chart Drawing not operating properly","Miscellaneous","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","repaired damaged part by inserting bracket inside the drawer and installing ramp for the drawer.","2019-11-15",null,"Completed","2019-11-14","No",null,null,"Internal"]
[null,null,null,null,null,"15/11/2019 7:03:01 PM","2019-10-29","Observation","Ship Staff","Ship Staff Insp.","3/Off cabin outlet Faucit leaking","Miscellaneous","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Overhauled faucet, fit bacK and checked. No more leaking observed","2019-11-15",null,"Completed","2019-11-14","No",null,null,"Internal"]
[null,null,null,null,null,"2019-11-28T12:26:44","2019-11-18","Non Conformity","PSC Insp.","PSC Inspection","Fire damper for purifier room exhaust ventillation duct fail to be closed.","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Fire safety","Asia and the Pacific","Free-up frozen fire damper ","2019-11-18",null,"Completed","2019-11-18","No",null,null,"External"]
[null,null,null,null,null,"2019-11-28T12:40:40","2019-11-18","Non Conformity","PSC Insp.","PSC Inspection","Main engine fuel leakage out of order","Main Engine ","Eng. / Strg. Comp.","Equipment Related",null,null,"Alarms","Asia and the Pacific","Electrician trouble shoot out of order","2019-11-18",null,"Completed","2019-11-18","No",null,null,"External"]
[null,null,null,null,null,"2019-11-28T12:45:36","2019-11-18","Non Conformity","PSC Insp.","PSC Inspection","Three Aux. Engine fuel inlet valves located near the engines which not consistent with ships drawing.","Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Emergency Systems","Asia and the Pacific","DNV GL -surveyor to proved that the AE fuel inlet valves are as per drawing and PSC had wrongly identified.","2019-11-18",null,"Completed","2019-11-18","No",null,null,"External"]
[null,null,null,null,null,"2019-11-28T13:26:19","2019-11-18","Non Conformity","PSC Insp.","PSC Inspection","End of handle axe for fire mans oufit not full insulation.","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Fire safety","Asia and the Pacific","AXE renewed -supplied by agent Ningbo.","2019-11-18",null,"Completed","2019-11-18","No",null,null,"External"]
[null,null,null,null,null,"2019-11-28T13:29:44","2019-11-18","Non Conformity","PSC Insp.","PSC Inspection","Free fall lifeboat windows glass unclear ","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Life saving appliances","Asia and the Pacific","Washout and cleaned windows","2019-11-18",null,"Completed","2019-11-20","No",null,null,"External"]
[null,null,null,null,null,"2019-11-28T13:34:24","2019-11-18","Non Conformity","PSC Insp.","PSC Inspection","Desiccator for 15 ppm oil meter worn out","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Alarms","Asia and the Pacific","Requested spare to office","2019-11-22",null,"Completed","2019-11-22","No",null,null,"External"]
[null,null,null,null,null,"2019-11-28T13:39:45","2019-11-18","Non Conformity","PSC Insp.","PSC Inspection","Small vent cock on sounding pipe of many oil tanks in E/R missing.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Pollution Prevention","Asia and the Pacific","Tech. dept. to supply needed spare.","2019-11-22",null,"Completed","2019-11-22","No",null,null,"External"]
[null,null,null,null,null,"2019-11-28T10:43:37","2019-11-28","Observation","Ship Staff","Ship Staff Insp.","During   round check routine inspection at sea passage observed main engine air cooler gasket is leaking( Air Side).","Main Engine ","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Prepare high temp. gasket main engine air cooler upon  alongside arrival port  Incheon korea priority to replaced w/ new gasket.","2019-11-29",null,"Completed","2019-11-28","No",null,null,"Internal"]
[null,null,null,null,null,"30/11/2019 2:23:25 PM","2019-11-18","Critical Equipment","Ship Staff","Ship Staff Insp.","During testing Pressure regulator broken of air bottle engine room ventilation fire damper.","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Renewed new supplier presure regulator valve.","2019-11-25","RO CHAT190232","Completed","2019-11-25","No",null,null,"Internal"]
[null,null,null,null,null,43749.553391203699,"2019-04-01","Deficiency","Ship Staff","Ship Staff Insp.","defective/corroded stanchion post","Miscellaneous","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Maintenance job in replacing defective / corroded stanchion post completed 100%","2019-12-15","chat190063","Completed","2019-11-30","No",null,null,"Internal"]
[null,null,null,null,null,"15/11/2019 6:03:36 PM","2019-08-18","Deficiency","Ship Staff","Ship Staff Insp.","Rudder indicator stbd. wing broken","Nav & comm. equip.","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","Awaiting spare to be ready on 26 november but not rcvd..pls expedite Pilots always asking for this and you know pilots are connected to PSC. Done rectified received new spares and fixed the unit and working back to normal.","2019-12-15","CHAT190151","Completed","2019-12-12","No",null,null,"Internal"]
[null,null,null,null,null,"28/11/2019 10:36:35 AM","2019-11-28","Observation","Ship Staff","Ship Staff Insp.","TOP 5 11.3 - Engine room toilet bathroom 6 pcs tiles  on flooring are removed.","Miscellaneous","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Re-fitted tiles on flooring putting with white cement. Done rectified 04 December 2019.","2019-12-30",null,"Completed","2019-12-04","No",null,null,"Internal"]
[null,null,null,null,null,"15/11/2019 6:40:10 PM","2019-03-16","Deficiency","Ship Staff","Ship Staff Insp.","NO.1 HFO TK (S) SENSOR FAULTY","Hull & Tanks","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","RAISED UNDER CHAT190185-Pls. give us supply date to plan realistic target date.Note : rcvd spare at icnheon 11 decemeber 2019. Fixed it and confrimed working good oorder date completed 12-december 2019.","2019-12-15","CHAT190185","Completed","2019-12-12","No",null,null,"Internal"]
[null,null,null,null,null,"15/11/2019 6:45:11 PM","2019-09-26","Deficiency","Ship Staff","Ship Staff Insp.","Gasoline for Rescue boat engine","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Not Applicable","Not Applicable","RAISED UNDER CHAT190211-Pls. give us supply date to plan realistic target date.supplied rcvd at incheon 03 december 2019.","2019-12-15","CHAT190211","Completed","2019-12-03","No",null,null,"Internal"]
[null,null,null,null,null,"28/11/2019 10:32:13 AM","2019-11-28","Observation","Ship Staff","Ship Staff Insp.","TOP 5 11.2 - Watertight Door frozen at the middle port side tunnel going to fuel storage tank valve  heating.","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","Need to excercise and recondtion to be smooth opening/ closing -done rectified.Cleared frozen opening/ closing smoohtly exercise and corfirmed no more frozen valve handle. 05 December 2019","2019-12-15",null,"Completed","2019-05-12","No",null,null,"Internal"]
[null,null,null,null,null,"15/11/2019 12:18:52 PM","2019-10-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Gratings to be change for damage and badly rusted one with new spare...In Progress","Deck Pipe / Fittings","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","De-rustiing and painting  of cross bay angular frame and completed. Painting 3 coats of primer and 1 top coat paint. Replaced worn -out gratings 100 % Dated completed 10 December 2019.","2019-12-31",null,"Completed","2019-12-10","No",null,null,"Internal"]
[null,null,null,null,null,"15/11/2019 6:32:14 PM","2019-11-09","Deficiency","Ship Staff","Ship Staff Insp.","NO.2 HFO TK. (P)","Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Replaced new tank snesor supplied.13 December 2019.","2019-12-15","CHAT190185","Completed","2019-12-13","No",null,null,"Internal"]
[null,null,null,null,null,"15/11/2019 6:11:20 PM","2019-08-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Water sensor not showing correct reading for sensor water content","Miscellaneous","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Renewed New spare supplied Water Sensor 14 december 2019.","2019-12-15","CHAT190172","Completed","2019-12-14","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["LSA / FFA Appliances",8]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["MARPOL Related",9]
["ISM Related",7]
["ISPS Related",10]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Condn of Class / Memo",null,5]
["Critical Equipment",null,4]
["Deficiency",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":21,"n_cols":3,"rows_kept":21,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation ",null,12]
["Air Comp.",null,8]
["Aux. Engine",null,4]
["Aux. Mach.",null,7]
["Boiler",null,5]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck Mach.",null,18]
["Deck Pipe / Fittings",null,20]
["Documentation",null,21]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Main Engine ",null,3]
["Miscellaneous",null,22]
["Nav & comm. equip.",null,11]
["ER Pipes, valves & fittings",null,9]
["Purifier",null,6]
["Mooring Mach.",null,15]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":16,"n_cols":2,"rows_kept":16,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Others (Eg. Insurance etc.)",12]
["Engineering Audit",16]
["Flag State Insp.",5]
["Ship Staff Insp.",15]
["IT Audit",10]
["OM Insp. (Eg. SIRE, CDI etc.)",6]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["PSC Inspection",4]
["Suptd. Insp.",13]
["Terminal Insp.",11]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["Others (Eg. Insurance etc.)",null,9]
["FSC Inspector",null,5]
["Owner / Marine / Tech. Suptd.",null,3]
["PSC Insp.",null,6]
["Ship Staff",null,2]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["95","CHATTANOOGA (26-11-2019)","95_1574817619191.xlsm"]