{"text_format":"1","workbook":"xlsx","n_sheets":20,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":41,"n_cols":28,"rows_kept":41,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","07-Dec-2019",null,null,"Ship Name","DHT EUROPE (07-12-2019)"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,2263,"17/10/2019 1:43:27 PM","2019-08-24","Observation","Ship Staff","Ship Staff Insp.","Port side forward Vapor return line manifold valve worm gear damaged / worn out completely. ","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.25","Very High","","","Renew worm gear / valve","2019-12-25","","Deferred to D D",null,"Yes","No","No","Internal"]
[null,null,null,null,2264,"17/10/2019 2:05:12 PM","2019-08-24","Observation","Ship Staff","Ship Staff Insp.","ME rpm indicator at local manouvering platform not working.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","RO to be raised for new RPM indicator","2019-12-20","DEUR190044","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,2269,"17/10/2019 4:02:10 PM","2019-09-07","Deficiency","Ship Staff","Ship Staff Insp.","Light fittings in E/rm cracked same need to be replaced","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","11.1","High","","","WS","2019-12-20","DEUR190037","Waiting spare",null,"No","No","No","Internal","This RO is already supplied ??"]
[null,null,null,null,2270,"17/10/2019 4:06:19 PM","2019-09-03","Deficiency","Ship Staff","Ship Staff Insp.","ME Bearing wear monitoring system display not operational","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.21","Medium","","","WS","2019-12-30","DEUR190054","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,2271,"17/10/2019 4:24:01 PM","2019-09-03","Deficiency","Ship Staff","Ship Staff Insp.","Steering gear #1 and #3 valve block leak from safety valve base","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Leak to be arrested at next available oportunity","2019-12-30","","Not Started",null,"No","No","No","Internal","Job to be completed at the earliest opportunity or anchorage. Target date revised."]
[null,null,null,null,2272,"17/10/2019 4:30:36 PM","2019-09-03","Deficiency","Ship Staff","Ship Staff Insp.","Steering gear oil leak from ram #2","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Seal to be renewed in DD","2019-12-30","","Not Started",null,"Yes","No","No","Internal"]
[null,null,null,null,2273,"17/10/2019 4:32:21 PM","2019-09-03","Deficiency","Ship Staff","Ship Staff Insp.","Sewage holding tank level gauge missing","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","WS","2019-12-31","DEUR190041","Waiting spare",null,"No","No","No","Internal","Still quote for spare is awaited. Target date revised."]
[null,null,null,null,2274,"17/10/2019 4:38:05 PM","2019-09-03","Deficiency","Ship Staff","Ship Staff Insp.","Echo Sounder Repeater Screen on Bridge Front Panel Not Visible ","Nav & comm. equip.","Navigation","Equipment Related","4.7","High","","","WS","2019-12-30","DEUR190053","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,2278,"17/10/2019 5:10:56 PM","2019-09-18","Deficiency","Ship Staff","Ship Staff Insp.","STBD low sea chest rubber lining torn at few places ","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Rubber lining to be renewed in DD. At present area cleaned and coated with epoxy.","2020-01-15","","Not Started",null,"Yes","No","No","Internal"]
[null,null,null,null,2279,"18/10/2019 1:27:38 AM","2019-09-19","Deficiency","Ship Staff","Ship Staff Insp.","220 V Insulation low same to be improved","Elect. Mach. & Equip.","Communication","Equipment Related","10.38","Medium","","","Fault finding in progress","2019-12-30","","In progress",null,"No","No","No","Internal","When it is expected to be completed. IT has been so long since the defect is existing."]
[null,null,null,null,5621,"25/10/2019 6:37:26 AM","2019-09-02","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME TOP BRACING SUPPORT PLATE CRACKED","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Support plate to be welded / renewed in DD","2020-01-10","","Deferred to D D",null,"Yes","No","No","Internal"]
[null,null,null,null,5625,"26/10/2019 9:10:45 AM","2019-10-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Spares inventory to be updated in PAL with Loacation","Documentation","Cert. & Docu.","Human Error","","","","","Spares inventory to be updated in PAL with location","2020-01-31","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,6263,"19-11-2019 23:00:37","2019-11-17","Observation","Ship Staff","Ship Staff Insp.","Telephone exchange alarm popping up on the panel.","Accommodation ","Communication","Equipment Related","10.28","Low","","","I/O card need replacement","2019-12-15","DEUR190078","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,6265,"20/11/2019 2:19:15 PM","2019-11-18","Observation","Ship Staff","Ship Staff Insp.","Washing Machine in ship Laundry to be repaired","Elect. Mach. & Equip.","MLC Related","Equipment Related","11.14","Medium","","","Vessel need Door and spares for same.RO DEUR190014 Raised","2019-12-30","DEUR190014","Waiting spare",null,"No","No","No","Internal","Will be supplied in Singapore."]
[null,null,null,null,null,"14/12/2019 10:16:01 AM","2019-12-05","Observation","Ship Staff","Ship Staff Insp.","Cargo and ballast valves noticed to have discrepancy in the indicators. The indicators noticed to sluggish and erratic in some cases ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,"Low","Not Applicable","Not Applicable","Vessel carrying out checks on the cargo and ballast valves to populate a list and to tackle them accordingly.","2019-12-28",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"15/12/2019 7:37:47 AM","2019-12-10","Observation","Ship Staff","Ship Staff Insp.","Soot tank not emptying when ejector is used. Instead level increases suspect overboard valves not opening.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.31,"Very High","Not Applicable","Not Applicable","Overboard valves to be renewed","2020-03-10",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"18/12/2019 2:54:18 PM","2019-12-11","Observation","Ship Staff","Ship Staff Insp.","ME unit #5 fuel pump inlet valve having small leak","Main Engine ","Eng. / Strg. Comp.","Equipment Related",10.31,"Very High","Not Applicable","Not Applicable","Valve gasket to be renewed","2020-01-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"22/12/2019 10:40:47 AM","2019-12-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency generator room fixed CO2 fixed installation system release handle door wasted","Deck Pipe / Fittings","LSA / FFA Appliances","Equipment Related",null,null,"Not Applicable","Not Applicable","The cabinet for CO2 release for emg gen. completely wasted. The job would require hot work for cropping and renewal.","2020-04-01",null,"Deferred to D D",null,"No",null,null,"Internal"]
[null,null,null,null,null,"22/12/2019 10:43:22 AM","2019-12-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck workshop entrance step cracked ","Accommodation ","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","The entrance platform for other stores are also in the same condition. The renewals would require cropping and renwal of the step. To be carried out in Dry Dock.","2020-04-01",null,"Deferred to D D",null,"No",null,null,"Internal"]
[null,null,null,null,null,"22/12/2019 10:49:01 AM","2019-12-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main deck walkway chequered plate securing bolts missing.Main deck walkway chequered plate slippery due to thick coat of paint. These plates to be chip & apply thin coat of paint. In case chequered dots are wasted, plate to renew.\r\n","Deck Pipe / Fittings","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","The walkways on deck have wasted areas which ahve been covered with putty and hence the thick coat of paint. The plates to be renewed in dry dock.","2020-04-01",null,"Deferred to D D",null,"No",null,null,"Internal"]
[null,null,null,null,null,"22/12/2019 10:52:34 AM","2019-12-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo tank 5s, COW machine no. 3 reported not working","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","During handing over it was told that the COW machine is not working. To be tried out during next discharge/COW operations and repairs to be carried out if found not working.","2020-01-25",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"22/12/2019 10:55:45 AM","2019-12-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck locker (S) housekeeping to improve further.","Miscellaneous","General Appearance","Human Error",null,null,"Not Applicable","Not Applicable","Vessel has carried out arranging and cleaning of stores locker inside the accommodation and garbage locker. SOPEP locker to be cleaned and painted. Items in the locker to be properly arranged.","2020-01-08",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"22/12/2019 11:00:33 AM","2019-12-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bosun store davit reported frozen.","Deck Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","The davit movable parts seem to have not been greased for a very long time leading to the freezing of the movement. Vessel staff will try to move the davit and carry out greasing.","2020-01-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"22/12/2019 11:04:14 AM","2019-12-16","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Windlass (S) claw coupling engaging lever fulcrum pin detached","Deck Mach.","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable","The detached fulcrum pin is to be welded back at location. Vessel staff would try to repair the same, if not it has to be done in Dry Dock","2020-04-01",null,"Not Started",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":72,"n_cols":28,"rows_kept":72,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","7-11-2019",null,null,"Ship Name","DHT EUROPE (07-12-2019)"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,2262,"17/10/2019 10:40:45 AM","2019-08-24","Observation","Ship Staff","Ship Staff Insp.","Hydroblaster inoperational due to lack of spares","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Overhauling carried out, Working satisfactory.","2019-11-20","DEUR195022","Completed","2019-11-11","No","No","No","Internal"]
[null,null,null,null,2265,"17/10/2019 3:19:56 PM","2019-08-28","Observation","Ship Staff","Ship Staff Insp.","PORT LT Cooler, Sea water outlet distance piece/corrosion flange having a minor leak.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","Sacrificial flange  renewed","2019-12-30","","Completed","2019-11-07","No","No","No","Internal"]
[null,null,null,null,2266,"17/10/2019 3:25:09 PM","2019-09-02","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bridge telegraph printer not working properly","Nav & comm. equip.","Navigation","Equipment Related","4.7","High","","","On board Repairs caried out.presently working satisfactory","2019-10-20","","Completed","2019-10-18","No","No","No","Internal"]
[null,null,null,null,2267,"17/10/2019 3:43:37 PM","2019-09-05","Deficiency","Ship Staff","Ship Staff Insp.","Pumproom phone communication not audible on Bridge/CCR","Nav & comm. equip.","Communication","Equipment Related","5.17","Very High","","","Repairs carried out, working satisfactory.","2019-10-20","","Completed","2019-10-12","No","No","No","Internal"]
[null,null,null,null,2268,"17/10/2019 3:45:56 PM","2019-09-05","Deficiency","Ship Staff","Ship Staff Insp.","Foam Hose box Stb side near Manifold poor condition","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.38","High","","","New foam hose box received, same renewed.","2019-10-10","","Completed","2019-10-26","No","No","No","Internal"]
[null,null,null,null,2275,"17/10/2019 4:49:58 PM","2019-09-18","Deficiency","Ship Staff","Ship Staff Insp.","Atmospheric condensor SW outlet pipe holed","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Leak rectified, For permanent repairs vessel needs anchorage","2019-11-30","","Completed","2019-12-03","No","No","No","Internal"]
[null,null,null,null,2276,"17/10/2019 4:53:59 PM","2019-09-15","Deficiency","Ship Staff","Ship Staff Insp.","Bridge Aircon not effective ","Aux. Mach.","General Appearance","Equipment Related","","","","","Leak arrested","2019-10-30","","Completed","2019-10-27","No","No","No","Internal"]
[null,null,null,null,2277,"17/10/2019 5:08:01 PM","2019-09-15","Deficiency","Ship Staff","Ship Staff Insp.","Steering motor #2 hydraulic lock alarm activating, without effecting the performance ","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Linear synchro needs to be adjusted","2019-10-30","","Completed","2019-10-29","No","No","No","Internal"]
[null,null,null,null,2280,"18/10/2019 1:46:11 AM","2019-09-30","Deficiency","Ship Staff","Ship Staff Insp.","Main SW pump pressure transmitter erratic output ","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Transmitter to be checked and calibrated","2019-10-05","","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,2281,"20/10/2019 5:39:16 AM","2019-10-02","Deficiency","Ship Staff","Ship Staff Insp.","Navtex JRC printer / Printing faded / unreadable","Nav & comm. equip.","Navigation","Equipment Related","4.7","High","","","New printer received and same renewed.","2019-12-30","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,2282,"20/10/2019 5:42:14 AM","2019-10-11","Deficiency","Ship Staff","Ship Staff Insp.","VRCS return hydraulic line pin hole leak on deck","Deck Pipe / Fittings","General Appearance","Equipment Related","","","","","Pipe removed welding carried out and boxed back.","2019-11-30","","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,2283,"20/10/2019 5:45:16 AM","2019-10-14","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE, CDI etc.)","Critical spare part list min requirred showing nil in Pal","Documentation","Cert. & Docu.","Inappropriate Procedure","10.13","Very High","","","Min required spares to be updated in PAL from office","2019-10-14","","Completed","2019-10-18","No","No","No","External"]
[null,null,null,null,2284,"20/10/2019 5:50:47 AM","2019-10-13","Deficiency","Ship Staff","Ship Staff Insp.","Aux boiler # 2 Feed water level controller erratic","Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Service engineer attended in Fujiarah. System performance shall be tested during discharging operation.","2019-11-10","DEUR195042","Completed","2019-11-02","No","No","No","Internal"]
[null,null,null,null,2285,"17/10/2019 1:32:04 PM","2019-08-24","Observation","Ship Staff","Ship Staff Insp.","Hydraulic oil leak on the mooring winch M5 - A small diameter pipe on the return line of mooring winch motor sheared off ","Deck Mach.,Deck Pipe / Fittings","Mooring","Equipment Related","9.14","Medium","","","Pipe repaired and Pressure test","2019-09-02","","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,2286,"18/10/2019 1:56:57 AM","2019-08-24","Observation","Ship Staff","Ship Staff Insp.","Slight hydraulic oil leak from the control lever of M3 mooring winch, vessel staff changed O rings but leak is persistent. Further investigation required. ","Deck Pipe / Fittings","Mooring","Equipment Related","9.14","Medium","","","O ring renewed and spol piecce cleaned.Leak rectified.","2019-09-20","","Completed","2019-10-07","No","No","No","Internal"]
[null,null,null,null,2287,"18/10/2019 2:22:13 AM","2019-08-24","Observation","Ship Staff","Ship Staff Insp.","BMT Hull stress monitor is not working. As per ship staff the CPU of the unit which is kept on bridge got damaged. ","Deck Mach.","Cargo / Ballast Systems","Equipment Related","","","","","As discussed with Office same job deffered to DD","2019-09-05","","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,2288,"18/10/2019 2:25:24 AM","2019-08-24","Observation","Ship Staff","Ship Staff Insp.","CCTV cameras are inoperational ","Miscellaneous","Communication","Equipment Related","","","","","RO raised by office, CCTVs shall be supplied in Singapore, ship staff to install upon receiving the same","2019-09-05","","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,2289,"18/10/2019 2:31:43 AM","2019-08-23","Observation","Ship Staff","Ship Staff Insp.","ME lub oil auto back wash filter Hydraulic motor indicator broken ","Main Engine ","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","New hydraulic motor to be replaced","2019-12-15","","Completed","2019-09-18","No","No","No","Internal"]
[null,null,null,null,2290,"18/10/2019 2:37:13 AM","2019-09-06","Observation","Ship Staff","Ship Staff Insp.","All DGs LO running hours exceed 2000 hrs  ","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","All DGs sump oil renewed","2019-09-15","","Completed","2019-09-12","No","No","No","Internal"]
[null,null,null,null,2291,"18/10/2019 2:55:07 AM","2019-09-06","Deficiency","Ship Staff","Ship Staff Insp.","Both FWGs production very low   ","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Need to check and rectify","2019-09-20","","Completed","2019-09-11","No","No","No","Internal"]
[null,null,null,null,2292,"18/10/2019 2:58:18 AM","2019-09-11","Deficiency","Ship Staff","Ship Staff Insp.","DG LO purifier temp not coming up     ","Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Heater cleaned and control valve overhauled, temp:95","2019-09-20","","Completed","2019-09-14","No","No","No","Internal"]
[null,null,null,null,2293,"18/10/2019 3:02:52 AM","2019-09-06","Deficiency","Ship Staff","Ship Staff Insp.","Port life boat engine sound abnormal in AHD direction         ","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.29","High","","","Drive shaft lubricated, noise now normal","2019-09-20","","Completed","2019-09-13","No","No","No","Internal"]
[null,null,null,null,2294,"18/10/2019 3:06:21 AM","2019-08-24","Observation","Ship Staff","Ship Staff Insp.","2 Foam monitors found leaking","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.35","Medium","","","Foam monitor valves repaired","2019-09-10","","Completed","2019-09-10","No","No","No","Internal"]
[null,null,null,null,2295,"18/10/2019 3:21:54 AM","2019-08-24","Observation","Ship Staff","Ship Staff Insp.","4 Fire hydrant valves found leaking    ","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.35","Medium","","","Fire hydrants removed, lapping carried out and fitted back","2019-09-10","","Completed","2019-09-10","No","No","No","Internal"]
[null,null,null,null,2296,"18/10/2019 3:30:28 AM","2019-09-03","Deficiency","Ship Staff","Ship Staff Insp.","Paint store sprinkler system valve not holding","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.35","Medium","","","Renew / replace valve","2019-09-13","","Completed","2019-09-12","No","No","No","Internal"]
[null,null,null,null,2297,"18/10/2019 3:32:51 AM","2019-08-24","Observation","Ship Staff","Ship Staff Insp.","Slight oil leak observed from STBD windlass hydaulic line flange near deck penetration. ","Deck Mach.","Mooring","Equipment Related","9.2","Very High","","","Renew / Replace O ring","2019-09-20","","Completed","2019-09-11","No","No","No","Internal"]
[null,null,null,null,2298,"18/10/2019 3:38:42 AM","2019-09-03","Observation","Ship Staff","Ship Staff Insp.","ME FO auto filter leaking from spindle top","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Seal rings to be renewed","2019-09-30","","Completed","2019-09-15","No","No","No","Internal"]
[null,null,null,null,2299,"18/10/2019 3:53:36 AM","2019-09-06","Deficiency","Ship Staff","Ship Staff Insp.","Elevator telephone handset communication not audible","Nav & comm. equip.","Communication","Equipment Related","","","","","To be repaired","2019-09-30","","Completed","2019-09-24","No","No","No","Internal"]
[null,null,null,null,2300,"18/10/2019 3:58:32 AM","2019-09-10","Deficiency","Ship Staff","Ship Staff Insp.","Crew laundry drier not operational","Miscellaneous","General Appearance","Equipment Related","","","","","Drier made operation","2019-09-30","","Completed","2019-09-25","No","No","No","Internal"]
[null,null,null,null,2301,"18/10/2019 4:12:42 AM","2019-09-10","Observation","Ship Staff","Ship Staff Insp.","Both LT collers performance bad, may be chocked","Elect. Mach. & Equip.,ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","LT coolers strainer cleaned and chemical circulation carried out","2019-09-20","","Completed","2019-09-19","No","No","No","Internal"]
[null,null,null,null,2302,"18/10/2019 4:14:48 AM","2019-09-07","Deficiency","Ship Staff","Ship Staff Insp.","E/r Blower No 2 flap stuck an dnot closing","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.18","High","","","Actuator overhauled flap function normal","2019-09-15","","Completed","2019-09-10","No","No","No","Internal"]
[null,null,null,null,2303,"18/10/2019 4:19:12 AM","2019-09-30","Observation","Ship Staff","Ship Staff Insp.","Leaking Air line near manifold area","Deck Pipe / Fittings","General Appearance","Equipment Related","","","","","Repairs to be carried out","2019-09-30","","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,2304,"18/10/2019 1:48:29 AM","2019-09-30","Observation","Ship Staff","Ship Staff Insp.","Various pressure gauges in E/rm damaged ","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Damaged gauges to be replaced with new ","2019-10-12","","Completed","2019-10-12","No","No","No","Internal"]
[null,null,null,null,2305,"17/10/2019 4:12:09 PM","2019-09-03","Observation","Ship Staff","Ship Staff Insp.","Cooling water expansion tank level gauge leaking while checking level","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Leak to be arrested","2019-10-15","","Completed","2019-10-12","No","No","No","Internal"]
[null,null,null,null,2306,"20/10/2019 5:18:18 AM","2019-10-14","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE, CDI etc.)","Stbd accommodation ladder shifting wire slightly deformed / loose strends","Deck Mach.","General Appearance","Equipment Related","5.47","Medium","","","Wire renewed with new spare wire onboard","2019-11-20","","Completed","2019-10-18","No","No","No","External"]
[null,null,null,null,2307,"20/10/2019 5:22:43 AM","2019-10-18","Deficiency","Ship Staff","Ship Staff Insp.","Mian Air compr # 1 I stage pressure erratic","Air Comp.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","1st stage suction plate found broken same renewed with new spare","2019-10-20","","Completed","2019-10-18","No","No","No","Internal"]
[null,null,null,null,2308,"20/10/2019 5:37:00 AM","2019-10-19","Deficiency","Ship Staff","Ship Staff Insp.","FWG # 1 vacuum low","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Ejector pump strainer found chocked same cleaned","2019-10-20","","Completed","2019-10-19","No","No","No","Internal"]
[null,null,null,null,5617,"26/10/2019 9:07:38 AM","2019-10-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FW TANK S VENT HEAD DEFLECTOR PLATE IS CORRODED","Deck Pipe / Fittings","General Appearance","Equipment Related","","","","","Plate renewed","2019-11-05","","Completed","2019-10-30","No","No","No","Internal"]
[null,null,null,null,5618,"25/10/2019 6:46:23 AM","2019-10-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Suction and Discharge press gauge of stern tube LO pump no. 2 is not working. To be replaced","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Gauges to be replaced","2019-10-28","","Completed","2019-10-28","No","No","No","Internal"]
[null,null,null,null,5619,"25/10/2019 7:14:42 AM","2019-10-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","There is an auto bilge water separator installed for incinerator drain, which is not in use any more. Same to be entered in LOTO record book","Documentation","Eng. / Strg. Comp.","Equipment Related","","","","","Entry in LOTO record book","2019-10-28","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,5620,"26/10/2019 8:59:14 AM","2019-10-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Spare DG T/C cartridge is store but not covered. The cartridge may get damaged","Miscellaneous","Eng. / Strg. Comp.","Inappropriate Procedure","","","","","To be covered and secured","2019-10-31","","Completed","2019-10-26","No","No","No","Internal"]
[null,null,null,null,5622,"25/10/2019 6:42:51 AM","2019-09-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Water cooler outside ECR, compressor not working","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","New water fountain installed","2019-11-30","DEUR190045","Completed","2019-11-07","No","No","No","Internal"]
[null,null,null,null,5623,"25/10/2019 7:02:56 AM","2019-10-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main steam stop valve to COPT near LT coolers, Leaking form the gland. Gland to be tightened or renewed","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Gland to be nipped up / packing to renewed","2019-11-21","","Completed","2019-11-28","No","No","No","Internal"]
[null,null,null,null,5624,"25/10/2019 7:16:53 AM","2019-10-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Water Cooler on upper deck not operational","Accommodation ","MLC Related","Equipment Related","","","","","To  be replace, RO raised","2019-11-21","DEUR190045","Completed","2019-11-28","No","No","No","Internal"]
[null,null,null,null,5626,"25/10/2019 6:54:17 AM","2019-10-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Various save all of bunker tanks capacity plate too rusted to view. Capacity tag plate to cleaned and if required to be stencillled","Miscellaneous","General Appearance","Equipment Related","","","","","Save alls to be de rusted and stencilling to be carried out","2019-10-28","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,6259,"19-11-2019 18:46:12","2019-10-14","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Water fountain in upper deck not working","Accommodation ","MLC Related","Equipment Related","10.16","Very High","","","Water fountain shall be replaced with new spare","2019-11-15","","Completed","2019-11-28","No","No","No","Internal"]
[null,null,null,null,6260,"19-11-2019 18:48:17","2019-11-11","Deficiency","Ship Staff","Ship Staff Insp.","ME FO heater #1 steam leak from end cover","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.31","Very High","","","Heater end cover gasket to be renewed","2019-12-02","","Completed","2019-12-06","No","No","No","Internal"]
[null,null,null,null,6266,"13/11/2019 3:58:37 PM","2019-11-10","Breakdown","Ship Staff","Ship Staff Insp.","FWG#1 Ejector overboard line holed.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.33","High","","","Pipe section removed and new fabricated section fitted","2019-11-15","","Completed","2019-11-11","No","No","No","External"]
[null,null,null,null,6267,"13/11/2019 4:00:56 PM","2019-11-13","Breakdown","Ship Staff","Ship Staff Insp.","ME LO purifier vibration sensor erratic","Purifier","Eng. / Strg. Comp.","Equipment Related","10.35","Very High","","","Sensor renewed with new spare.","2019-11-15","","Completed","2019-11-13","No","No","No","External"]
[null,null,null,null,6268,"20-11-2019 14:06:31","2019-11-12","Observation","Ship Staff","Ship Staff Insp.","Sanitary exhaust blower belts loose.","Accommodation ","Eng. / Strg. Comp.","Equipment Related","10.15","Low","","","Belts renewed and pulley aligned","2019-11-30","","Completed","2019-11-20","No","No","No","Internal"]
[null,null,null,null,null,"20-11-2019 14:03:58","2019-11-11","Observation","Ship Staff","Ship Staff Insp.","Jobs to be triggered in PAL","Documentation","ISM Related","Industry Issue",10.29,"Medium","Not Applicable","Not Applicable","Jobs triggered in PAL","2019-12-31",null,"Completed","2019-12-13","No",null,null,"Internal"]
[null,null,null,null,null,"19-11-2019 21:45:41","2019-11-07","Observation","Ship Staff","Ship Staff Insp.","Economiser soot blower steam leak from gland","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.29,"Medium","Not Applicable","Not Applicable","Leak rectified from gland","2019-12-17",null,"Completed","2019-12-09","No",null,null,"Internal"]
[null,null,null,null,null,"14/12/2019 10:22:02 AM","2019-12-06","Observation","Ship Staff","Ship Staff Insp.","Hyraulic oil leakgae noticed from actuator of mastriser valve.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Actuator isolated presently,valve is operational but oil drips from actuator.Leak be rectified by opening the actuator.","2019-12-20",null,"Completed","2019-12-18","No",null,null,"Internal"]
[null,null,null,null,null,"14/12/2019 10:24:40 AM","2019-12-12","Observation","Ship Staff","Ship Staff Insp.","Hydraulic oil leakage noticed from controller for mooring winch M1. ","Mooring Mach.","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable","Controller dismantled. O rings and lip seals renewed and winch tried out. FOund working without any leak.","2019-12-20",null,"Completed","2019-12-18","No",null,null,"Internal"]
[null,null,null,null,null,"19-11-2019 18:51:46","2019-11-09","Deficiency","Ship Staff","Ship Staff Insp.","DG FO auto filter leaking from top cover","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.27,"Medium","Not Applicable","Not Applicable","filter top cover O-ring to renewed","2019-12-15","DEUR190008","Completed","2019-12-22","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["LSA / FFA Appliances",8]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["MARPOL Related",9]
["ISM Related",7]
["ISPS Related",10]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Condn of Class / Memo",null,5]
["Critical Equipment",null,4]
["Deficiency",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":427,"n_cols":3,"rows_kept":427,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",8243]
["1.10","Low",8252]
["1.11","Low",8253]
["1.12","Low",8254]
["1.13","Low",8255]
["1.14","Low",8256]
["1.15","Low",8257]
["1.16","Low",8259]
["1.17","Low",8260]
["1.18","Low",8261]
["1.19","Low",8262]
["1.2","Low",8244]
["1.20","Low",8263]
["1.21","Low",8265]
["1.22","Low",8266]
["1.23","Low",8267]
["1.24","Low",8268]
["1.25","Low",8269]
["1.26","Low",8270]
["1.3","Low",8245]
["1.4","Low",8246]
["1.5","Low",8247]
["1.6","Low",8248]
["1.7","Low",8249]
["1.8","Low",8250]
["1.9","Low",8251]
["1.99","High",11258]
["10.1","Medium",8461]
["10.10","High",8470]
["10.11","Medium",8471]
["10.12","Very High",8472]
["10.13","Very High",8473]
["10.14","Medium",8474]
["10.15","Low",8475]
["10.16","Very High",8476]
["10.17","Very High",8477]
["10.18","High",8478]
["10.19","Very High",8479]
["10.2","Low",8462]
["10.20","High",8480]
["10.21","Medium",8481]
["10.22","Low",8482]
["10.23","Medium",8483]
["10.24","Low",8484]
["10.25","Very High",8485]
["10.26","High",8486]
["10.27","Medium",8487]
["10.28","Low",8488]
["10.29","Medium",8489]
["10.3","Medium",8463]
["10.30","High",8490]
["10.31","Very High",8491]
["10.32","Very High",8492]
["10.33","High",8493]
["10.34","High",8494]
["10.35","Very High",8495]
["10.36","Very High",8496]
["10.37","Medium",8497]
["10.38","Medium",8498]
["10.39","High",8499]
["10.4","High",8464]
["10.40","Medium",8500]
["10.41","Medium",8501]
["10.42","Medium",8502]
["10.43","Medium",8503]
["10.44","Medium",8504]
["10.45","Very High",8505]
["10.46","High",8506]
["10.47","Medium",8507]
["10.48","High",8508]
["10.49","Medium",8509]
["10.5","Low",8465]
["10.50","High",8510]
["10.51","Low",8511]
["10.52","Medium",8512]
["10.53","Medium",8513]
["10.54","High",8514]
["10.55","Low",8515]
["10.6","Very High",8466]
["10.7","Medium",8467]
["10.8","Medium",8468]
["10.9","Medium",8469]
["10.99","High",8516]
["11.1","High",8420]
["11.10","Medium",8429]
["11.11","Very High",8430]
["11.12","Low",8431]
["11.13","Low",8432]
["11.14","Medium",8433]
["11.15","Low",8434]
["11.16","Low",8435]
["11.17","Low",8436]
["11.2","Medium",8421]
["11.3","Medium",8422]
["11.4","Very High",8423]
["11.5","Medium",8424]
["11.6","Medium",8425]
["11.7","High",8426]
["11.8","Low",8427]
["11.9","Low",8428]
["11.99","High",8437]
["12.1","High",8438]
["12.10","High",8448]
["12.11","High",8449]
["12.12","High",8450]
["12.13","High",8451]
["12.14","High",8452]
["12.15","High",8453]
["12.16","High",8454]
["12.17","High",8455]
["12.18","High",8456]
["12.19","High",8457]
["12.2","High",8439]
["12.20","High",8458]
["12.21","High",8459]
["12.3","High",8441]
["12.4","High",8442]
["12.5","High",8443]
["12.6","High",8444]
["12.7","High",8445]
["12.8","High",8446]
["12.9","High",8447]
["12.99","High",8460]
["2.1","Very High",8296]
["2.1.9","Very High",11259]
["2.10","Medium",8304]
["2.11","Medium",8305]
["2.12","Low",8306]
["2.13","Low",8307]
["2.14","Low",8308]
["2.15","Low",8309]
["2.16","Medium",8310]
["2.2","Medium",8297]
["2.3","High",8295]
["2.4","Medium",8298]
["2.5","Medium",8299]
["2.6","Low",8300]
["2.7","High",8301]
["2.8","High",8302]
["2.9","Medium",8303]
["2.99","High",8311]
["3.1","High",8312]
["3.2","Very High",8313]
["3.3","High",8314]
["3.4","Low",8294]
["3.5","Medium",8315]
["3.6","High",8316]
["3.7","Very High",8317]
["3.8","Very High",8318]
["3.99","High",8319]
["4.1","High",8320]
["4.10","High",8329]
["4.11","Medium",8330]
["4.12","Very High",8331]
["4.13","Very High",8332]
["4.14","Very High",8333]
["4.15","Very High",8334]
["4.16","Very High",8335]
["4.17","Very High",8336]
["4.18","Very High",8337]
["4.19","Low",8338]
["4.2","Medium",8321]
["4.20","Very High",8339]
["4.21","High",8340]
["4.22","Low",8341]
["4.23","High",8342]
["4.24","High",8343]
["4.25","Low",8344]
["4.26","Low",8345]
["4.27","High",8346]
["4.3","Medium",8322]
["4.4","High",8323]
["4.5","Very High",8324]
["4.6","Medium",8325]
["4.7","High",8326]
["4.8","Medium",8327]
["4.9","Medium",8328]
["4.99","High",8347]
["5.1","Very High",8517]
["5.10","High",8526]
["5.11","Low",8527]
["5.12","Medium",8528]
["5.13","High",8529]
["5.14","Very High",8530]
["5.15","Medium",8531]
["5.16","Very High",8532]
["5.17","Very High",8533]
["5.18","High",8534]
["5.19","Medium",8535]
["5.2","Very High",8518]
["5.20","Medium",8536]
["5.21","Medium",8537]
["5.22","High",8539]
["5.23","Very High",8540]
["5.24","Very High",8541]
["5.25","Medium",8542]
["5.26","Medium",8543]
["5.27","Medium",8544]
["5.28","Very High",8545]
["5.29","High",8546]
["5.3","Low",8519]
["5.30","High",8547]
["5.31","High",8548]
["5.32","High",8549]
["5.33","High",8550]
["5.34","Low",8551]
["5.35","Medium",8552]
["5.36","Low",8553]
["5.37","Low",8554]
["5.38","High",8555]
["5.39","Very High",8556]
["5.4","High",8520]
["5.40","Very High",8557]
["5.41","Very High",8558]
["5.42","Medium",8559]
["5.43","High",8560]
["5.44","High",8561]
["5.45","Medium",8564]
["5.46","Medium",8565]
["5.47","Medium",8566]
["5.48","Medium",8567]
["5.5","Low",8521]
["5.6","Low",8522]
["5.7","Medium",8523]
["5.8","Medium",8524]
["5.9","Very High",8525]
["5.99","High",8568]
["6.1","Medium",8348]
["6.10","Low",8357]
["6.11","High",8358]
["6.12","Medium",8359]
["6.13","Low",8360]
["6.14","High",8361]
["6.15","High",8362]
["6.16","Very High",8363]
["6.17","Very High",8364]
["6.18","Medium",8365]
["6.19","Low",8366]
["6.2","High",8349]
["6.20","Medium",8367]
["6.21","High",8368]
["6.22","Medium",8369]
["6.3","Low",8350]
["6.4","High",8351]
["6.5","Medium",8352]
["6.6","Medium",8353]
["6.7","High",8354]
["6.8","High",8355]
["6.9","Low",8356]
["6.99","High",8370]
["7.1","High",8371]
["7.10","High",8380]
["7.11","High",8381]
["7.12","High",8382]
["7.13","Medium",8383]
["7.14","Medium",8384]
["7.15","High",8385]
["7.16","High",8386]
["7.17","High",8387]
["7.2","High",8372]
["7.3","Low",8373]
["7.4","Low",8374]
["7.5","Low",8375]
["7.6","Medium",8376]
["7.7","Low",8377]
["7.8","High",8378]
["7.9","High",8379]
["7.99","High",8388]
["8.1","Very High",8569]
["8.10","Very High",8578]
["8.100","Low",11227]
["8.101","Medium",11228]
["8.102","Low",11229]
["8.103","Low",11230]
["8.104","Low",11231]
["8.105","Medium",11232]
["8.106","Medium",11233]
["8.107","Low",11234]
["8.108","High",11235]
["8.109","Very High",11236]
["8.11","Medium",8579]
["8.110","High",11237]
["8.111","Medium",11238]
["8.112","High",11239]
["8.113","Medium",11240]
["8.114","Low",11241]
["8.115","High",11242]
["8.116","Medium",11243]
["8.117","Medium",11244]
["8.118","Medium",11245]
["8.119","High",11246]
["8.12","Medium",8580]
["8.120","High",11247]
["8.121","Medium",11248]
["8.122","High",11249]
["8.123","High",11250]
["8.124","Low",11251]
["8.125","High",11252]
["8.126","Medium",11253]
["8.127","Medium",11254]
["8.13","Medium",8581]
["8.14","Very High",8582]
["8.15","High",8583]
["8.16","Very High",8584]
["8.17","Low",8585]
["8.18","High",8586]
["8.19","High",8587]
["8.199","High",11255]
["8.2","Medium",8570]
["8.20","Medium",8588]
["8.21","High",8589]
["8.22","Very High",8590]
["8.23","Medium",8591]
["8.24","Medium",8592]
["8.25","Very High",8593]
["8.26","High",8594]
["8.27","Medium",8595]
["8.28","Medium",8596]
["8.29","High",8598]
["8.3","Very High",8571]
["8.30","High",8599]
["8.31","High",8600]
["8.32","Low",8601]
["8.33","Medium",8602]
["8.34","High",8603]
["8.35","Medium",8604]
["8.36","Medium",8605]
["8.37","High",8607]
["8.38","Medium",8608]
["8.39","Medium",8609]
["8.4","Medium",8572]
["8.40","High",8610]
["8.41","Medium",8611]
["8.42","Medium",8612]
["8.43","Very High",8613]
["8.44","High",8615]
["8.45","High",8616]
["8.46","Very High",8617]
["8.47","Very High",8618]
["8.48","Medium",8619]
["8.49","High",8620]
["8.5","Very High",8573]
["8.50","Medium",8621]
["8.51","Low",8622]
["8.52","Low",8623]
["8.53","Low",8624]
["8.54","High",8625]
["8.55","Low",11182]
["8.56","Medium",11183]
["8.57","Medium",11184]
["8.58","High",11185]
["8.59","High",11186]
["8.6","Medium",8574]
["8.60","High",11187]
["8.61","Medium",11188]
["8.62","Very High",11189]
["8.63","High",11190]
["8.64","Medium",11191]
["8.65","Low",11192]
["8.66","High",11193]
["8.67","High",11194]
["8.68","High",11195]
["8.69","Medium",11196]
["8.7","High",8575]
["8.70","Medium",11197]
["8.71","Very High",11198]
["8.72","Medium",11199]
["8.73","Medium",11200]
["8.74","High",11201]
["8.75","Medium",11202]
["8.76","Medium",11203]
["8.77","Medium",11204]
["8.78","Medium",11205]
["8.79","Medium",11206]
["8.8","Medium",8576]
["8.80","Medium",11207]
["8.81","Low",11208]
["8.82","Medium",11209]
["8.83","Low",11210]
["8.84","Low",11211]
["8.85","Medium",11212]
["8.86","Medium",11213]
["8.87","Medium",11214]
["8.88","Low",11215]
["8.89","High",11216]
["8.9","High",8577]
["8.90","High",11217]
["8.91","High",11218]
["8.92","Medium",11219]
["8.93","Low",11220]
["8.94","Low",11221]
["8.95","Medium",11222]
["8.96","Medium",11223]
["8.97","Low",11224]
["8.98","High",11225]
["8.99","Medium",11226]
["9.1","Low",8390]
["9.10","Medium",8399]
["9.11","Medium",8400]
["9.12","Medium",8401]
["9.13","Low",8402]
["9.14","Medium",8403]
["9.15","Medium",8404]
["9.16","High",8405]
["9.17","High",8406]
["9.18","Low",8407]
["9.19","Low",8408]
["9.2","Very High",8391]
["9.20","Medium",8409]
["9.21","Medium",8410]
["9.22","Low",8411]
["9.23","Low",8412]
["9.24","Medium",8413]
["9.25","Low",8414]
["9.26","Low",8415]
["9.27","Low",8416]
["9.28","Medium",8417]
["9.29","Low",8418]
["9.3","Very High",8392]
["9.4","High",8393]
["9.5","High",8394]
["9.6","Low",8395]
["9.7","Medium",8396]
["9.8","Medium",8397]
["9.9","Medium",8398]
["9.99","High",8419]

{"sheet":"Equipment_list","index":7,"n_rows":21,"n_cols":3,"rows_kept":21,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation ",null,12]
["Air Comp.",null,8]
["Aux. Engine",null,4]
["Aux. Mach.",null,7]
["Boiler",null,5]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck Mach.",null,18]
["Deck Pipe / Fittings",null,20]
["Documentation",null,21]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Main Engine ",null,3]
["Miscellaneous",null,22]
["Nav & comm. equip.",null,11]
["ER Pipes, valves & fittings",null,9]
["Purifier",null,6]
["Mooring Mach.",null,15]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":16,"n_cols":2,"rows_kept":16,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Others (Eg. Insurance etc.)",12]
["Engineering Audit",16]
["Flag State Insp.",5]
["Ship Staff Insp.",15]
["IT Audit",10]
["OM Insp. (Eg. SIRE, CDI etc.)",6]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["PSC Inspection",4]
["Suptd. Insp.",13]
["Terminal Insp.",11]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["Others (Eg. Insurance etc.)",null,9]
["FSC Inspector",null,5]
["Owner / Marine / Tech. Suptd.",null,3]
["PSC Insp.",null,6]
["Ship Staff",null,2]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["88","DHT EUROPE (07-12-2019)","88_1575707055070.xlsm"]