{"text_format":"1","workbook":"xlsx","n_sheets":20,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":99,"n_cols":28,"rows_kept":99,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","03-Dec-2019",null,null,"Ship Name","PROMOTER"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,null,"2019-06-12T15:13:15","2019-12-04","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Various protection plates/covers for pipes on main deck wasted.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","New plates/covers to be fabricated and fitted","2020-03-03",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-06-12T15:18:12","2019-12-04","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Various angle bar supports on main deck wasted.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","New angle bars to be fabricated and fitted","2020-03-03",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-06-12T15:25:30","2019-12-04","Deficiency","Ship Staff","Ship Staff Insp.","Port and stbd side lifeboat rowing port cover securing hinge broken","LSA / FFA","LSA / FFA Appliances","Equipment Related,External Factors,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Fabricate new cover for port side lifeboat and repair stbd side lifeboat cover","2019-12-08",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-06-12T15:38:58","2019-12-04","Deficiency","Ship Staff","Ship Staff Insp.","Port side gangway lower platform stauchion base pipe broken","Deck Mach.","Structural Condn. / WT integrity ","Behaviour Based,Equipment Related,External Factors",null,null,"Not Applicable","Not Applicable","New stauchion pipe to be fabricated.","2019-12-07",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-12-06T17:03:50","2019-12-04","Deficiency","Ship Staff","Ship Staff Insp.","One no. UTI found with tape detached/broken from sensor and one no. UTI tape kinked at various locations.","Cargo Mach.,Critical Equip.","Cargo / Ballast Systems","Equipment Related,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Serivicing and calibration of UTI's to be carried out.","2019-12-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-06-12T17:37:43","2019-12-04","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Broken round bar at end of port pilot embarkation platform near ship side.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Platform to be dismantled and repaired","2020-02-03",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-06-12T17:53:55","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both port & stbd side lifeboat canopy light foundation rusted.","LSA / FFA","LSA / FFA Appliances","Equipment Related,External Factors",null,null,"Not Applicable","Not Applicable","To fabricate new light foundation","2020-02-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-06-12T17:58:13","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","SIP markings missing on all accommodation vents.","Miscellaneous","Cargo / Ballast Systems","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Markings to be carried out.","2020-01-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-06-12T18:03:25","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","IMO posters and symbols on deck faded in various locations","LSA / FFA","LSA / FFA Appliances","Inappropriate Procedure,Knowledge Based",null,null,"Not Applicable","Not Applicable","New IMO symbols to be ordered.","2020-01-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-07-12T11:17:30","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port & Stbd sides liferaft maintenance davits frozen.","LSA / FFA,Miscellaneous","LSA / FFA Appliances","Equipment Related,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Davit ti be freed up","2020-01-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-07-12T11:26:18","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Propeller warning boards in poop deck in faded condition","Miscellaneous","General Appearance","Behaviour Based,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","New markings to be made.","2020-02-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-07-12T11:34:21","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Toilet tiles in majority of cabins found broken.","Accommodation ","MLC Related","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Toilet tiles to be renewed.","2020-02-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-07-12T11:36:50","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Shower curtains missing inside few cabin toilets.","Accommodation ","MLC Related","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","New shower curtains to be installed.","2020-01-04",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-07-12T11:43:39","2019-12-06","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Section of tank gauging pipeline support found wasted near 3 across area and line in contact with deck.","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Pipeline temporary clamping arrangement to be made with adjacent support brackets","2019-12-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-07-12T14:54:03","2019-12-04","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fwd ETA in poor condition","Documentation","Cargo / Ballast Systems","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","ETA to be dersuted and painted.","2020-02-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 02:13:40","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Midship stores, engine stores, deck & galley stores poorly arranged.","Miscellaneous","General Appearance","Behaviour Based,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","All stores to be arranged and inventories to be taken","2020-01-04",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 02:26:47","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Wasted forward section of MOT ladder","Miscellaneous","General Appearance","Inappropriate Procedure",5.47,"Medium","Not Applicable","Not Applicable","Wasted section to be renewed","2020-01-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 02:42:38","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Water weeping marks observed on both anchor chain washing lines in forecastle store.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","Section of pipeline to be renewed","2020-01-20",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 02:50:06","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Toilet bowl on CCR deck broken & blocked","Accommodation ","MLC Related","External Factors",null,null,"Not Applicable","Not Applicable","Toilet bowl to pe replaced","2020-01-30",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 03:03:44","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Missing curtains/bed lights in crew cabins.","Accommodation ","MLC Related","External Factors,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Curtains and lights to be procured and replaced ","2020-01-30",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 03:24:33","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Broken tiles, missing mirror cabinets & dirty bulkheads/floors for crew toilets.","Accommodation ","MLC Related","External Factors,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Broken tiles, mirrors to be replaced ","2020-03-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 03:29:10","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Broken floor tiles in Galley.","Accommodation ","MLC Related","External Factors",null,null,"Not Applicable","Not Applicable","Broken floor tiles in Galley to be replaced","2020-03-03",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 03:34:58","2019-12-05","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Missing entertain system in Crew smoke room, Chief Engineer cabins. Officer smoke room entertainment system in poor condition.","Accommodation ","MLC Related","External Factors",null,null,"Not Applicable","Not Applicable","RO to be raised for  entertainment systems","2020-02-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 03:39:23","2019-12-05","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Crew & officer smoke rooms sofas in poor condition","Accommodation ","MLC Related","External Factors",null,null,"Not Applicable","Not Applicable","RO to be raised for refurbishment","2020-02-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 03:43:59","2019-12-05","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bridge very hot & need to be equipped with 2 tons split air condition to avoid damage to electronic components","Accommodation ","MLC Related","External Factors",null,null,"Not Applicable","Not Applicable","RO to be raised new air con","2020-02-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 03:50:55","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both life boats lookout glasses dirty/not clear.","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Not Applicable","Not Applicable","Glasses to be cleaned","2019-12-20",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 04:01:14","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Galley exhaust mushrooms on bridge deck wasted on edges/junction box area.","Miscellaneous","Structural Condn. / WT integrity ","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Vent head to be dismantled and repairs works to be carried ouy","2020-01-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 04:10:04","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","General service & GMDSS batteries expired & with poor performance","Critical Equip.,Nav & comm. equip.","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","New batteries to procured","2019-12-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:04:00","2019-12-02","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No instrument provided for recording ME and aux engine performance","Aux. Engine,Main Engine ","Eng. / Strg. Comp.","Behaviour Based,Equipment Related,External Factors",null,null,"Not Applicable","Not Applicable","Vessel Awaiting spare for Performance measuring Instrument","2020-01-31",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:12:45","2019-12-02","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","As per the running hours provided by previous Management # 6 unit decarb will be due in 1200 hours and # 7 unit decarb will be due in 2700 hours. Also Exhaust valve for # 7 unit will due for overhaul.","Main Engine ","Eng. / Strg. Comp.","External Factors",null,null,"Not Applicable","Not Applicable","Consult with technical department, upon sighting the performance and condition ans spares, and plan the job as required","2020-03-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:15:41","2019-12-02","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both Camshaft Making Abnormal noise while engine standstill.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Check spares and overhaul at next convienent opporunity","2020-01-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:18:55","2019-12-02","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main engine and Aux engine fuel oil supply and booster pump making abnormal sound, need to overhaul all 4 pumps\t","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","check spares and raise requistion and overhaul the pumps","2020-03-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:22:05","2019-12-02","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fresh Water Generator china make producing reported 10 tons per day against the capacity of 30 tons per day","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Fresh water generator condenser and evaporator to clean manaually and check the perforamnce of FWG at various loads.","2020-01-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:28:14","2019-12-02","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering Gear System having Leaks from all four rams","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","To check the cause, tightened all the four rams bolts and check","2019-12-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:31:59","2019-12-02","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering gear motor starboard side making abnormal Noise.\t","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","To find root cause and overhaul motor as required at convienet opporunity","2020-04-30",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:36:12","2019-12-02","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Area Above FD fan poorly lighted and poorly maintained\t","Miscellaneous","Eng. / Strg. Comp.","External Factors,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Cleaning in progress. Vessel awaiting cleaning chemicals and paints, Also all the light fittings tubelights and bulbs changed.","2020-01-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:39:58","2019-12-02","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine room bulkhead with dirt depoists","Miscellaneous","Eng. / Strg. Comp.","External Factors",null,null,"Not Applicable","Not Applicable","Cleaning already in progress. Vessel awaiting paints and cleaning chemicals","2020-01-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:42:19","2019-12-03","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Area behind Cascade tank dirty","Miscellaneous","Eng. / Strg. Comp.","External Factors",null,null,"Not Applicable","Not Applicable","Cleaning in progress, Vessel awaiting paints.","2020-01-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:50:05","2019-12-03","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Area below hyrdophore and OWS dirty","Miscellaneous","Eng. / Strg. Comp.","External Factors",null,null,"Not Applicable","Not Applicable","Cleaning in progress.Vessel awaiting Paints and Cleaning chemicals.","2020-01-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:58:18","2019-12-03","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","# 1 LO purifier slight leak from top of hood","Purifier","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","To change the o-ring.","2019-12-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 13:03:06","2019-12-03","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Starboard hydraulic valve block panel having leak from 102 and 103 valve blocks","Deck Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Check spares and renew at next opporunity","2020-01-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 13:06:31","2019-12-03","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deak seal pumps outlet pipe having leaks from pipe and flanges.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","to renew flange gasket and bolts after discharging operation.","2019-12-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 13:13:50","2019-12-04","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ows inlet and outlet pipes lagging dirty","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Lagging to renew/ and carry out painiting.","2020-01-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 13:24:02","2019-12-04","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency fire pump and steering gear drain valave located at aft bottom part near forward stearn tube seal tank, frozen /rusted.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","External Factors",null,null,"Not Applicable","Not Applicable","valve cleaned. de rusting required and painting required. Vessel awaiting paints.","2020-01-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 13:26:24","2019-12-04","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aft stbd winch having slight leakage from flange","Mooring Mach.","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable","To check for spares and renew O-rings/ gasket at next possible opportunity","2020-01-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 13:29:14","2019-12-04","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Dirty lagging of pipes in lobby, vegetable room and linen store","Accommodation ","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","To change lagging and paint as required. Awaiting stores and paints","2020-01-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"17-12-2019 06:43:16","2019-12-04","Deficiency","Ship Staff","Ship Staff Insp.","Aux engine Fuel oil inlet and Outlet flowmeters not working.","Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","To order new flowmeters","2020-03-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"17-12-2019 06:50:02","2019-12-04","Observation","Ship Staff","Ship Staff Insp.","Vacuum condenser cooling sea water pump suction filter body in holed.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Tempapory repairs carried out. The filter casing is wasted in many parts inisde. Need to fabricate filter ccasing from shore.","2020-03-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"17-12-2019 06:52:34","2019-12-05","Observation","Ship Staff","Ship Staff Insp.","IG scrubber cooling sea water Pump Suction Filter having soft patches all over the filter casing","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","To change the filter casing by fabrication ne suction filter","2020-03-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"17-12-2019 07:24:42","2019-12-05","Deficiency","Ship Staff","Ship Staff Insp.","Both Lifeboat Batteries both the batteries expired\t","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace with new batteires","2020-01-31","PROM190005","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"17-12-2019 07:34:00","2019-12-05","Deficiency","Ship Staff","Ship Staff Insp.","GMDSS Asnd Ship general service Batteries Expired","Critical Equip.","Emgcy. Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","To renew batteries after receiving spare","2019-12-31","PROM190002","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"17-12-2019 07:36:40","2019-12-05","Observation","Ship Staff","Ship Staff Insp.","Fire Alarm Panel Batteries Expired","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Not Applicable","Not Applicable","RO raised . To renew new spare","2019-12-31","PROM190003","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"17-12-2019 07:39:46","2019-12-07","Other","Ship Staff","Ship Staff Insp.","Service Air/Compressor Out of Use as vessel doesnt have necessary grade of oil.","Air Comp.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Currently Air supplied through MAC, RO raised for OIL.","2019-12-31",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 16:13:34","2019-12-08","Observation","Ship Staff","Ship Staff Insp.","Hydraulic leak noticed from No.1 Cargo Pump Discharge  Valve 305 inside pumproom.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Leak to be rectified","2020-02-08",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 16:25:49","2019-12-08","Deficiency,Observation","Ship Staff","Ship Staff Insp.","Many in use mooring ropes condition found bad.","Miscellaneous,Mooring Mach.","Mooring","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","New mooring ropes to be ordered and deteriorated ones to be discarded","2020-01-07",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 18:15:49","2019-12-04","Observation","Ship Staff","Ship Staff Insp.","Stbd lifeboat winch brake shoe pads worn out.","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Not Applicable","Not Applicable","Brake shoe pads to be replaced","2020-12-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 18:22:10","2019-12-05","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All mooring winch brake bands are rusted and not os stainless steel material.","Mooring Mach.","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable","Bands to be derusted temporarily and same to be renewed with SS bands","2020-05-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 20:38:09","2019-12-05","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Stbd side ship name board light fixture support corroded.","Miscellaneous","General Appearance","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","To renew the corroded section.","2020-03-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 21:00:19","2019-12-05","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Monorail platform wasted and holed at various locations","Deck Mach.","General Appearance","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Platform to be renewed","2020-03-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 21:35:20","2019-12-05","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Monorail cable guide rollers frozen","Deck Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Rollers to be freed up","2020-03-05",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 21:40:41","2019-12-05","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both port & stbd sidelight top plate corroded","Miscellaneous","Navigation","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Sidelight top plate to be cropped & renewed","2020-08-05",null,"Deferred to D D",null,"No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 21:44:56","2019-12-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency generator filling pipe and vent heavily rusted.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","To derust and paint.","2020-03-06",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 23:43:03","2019-12-07","Observation","Ship Staff","Ship Staff Insp.","Basin taps inside Galley and Crew Pantry missing / not working","Accommodation ","MLC Related","Equipment Related",null,null,"Not Applicable","Not Applicable","New taps to be placed","2020-03-06",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 00:02:08","2019-12-07","Observation","Owner / Marine / Tech. Suptd.,Ship Staff","Suptd. Insp.","Suez canal light cable penetration pipe wasted","Deck Pipe / Fittings","General Appearance","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Pipe to be crop & renew","2020-10-06",null,"Deferred to D D",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 00:09:52","2019-12-07","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Forward embarkation ladder observed to be in poor condition","LSA / FFA","LSA / FFA Appliances","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Ladder to be replaced","2020-02-06",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 00:20:22","2019-12-09","Deficiency","Ship Staff","Ship Staff Insp.","Some of the mooring tails in use are more then 18 months in service and overall condition found deteriorated.","Miscellaneous","Mooring","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","New rope tails to be ordered","2020-02-08",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 00:28:47","2019-12-10","Observation","Ship Staff","Ship Staff Insp.","No.2 stdb and No.5 port WBT level gauges reading erratic.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Level gauge pipelines to be inspected and troubleshooting to be carried out.","2020-08-12",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 00:37:13","2019-12-10","Observation","Ship Staff","Ship Staff Insp.","Onboard walkie talkies and battery condition is poor","Nav & comm. equip.","Communication","Equipment Related,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","New walkie talkie and batteries to be ordered","2020-02-09",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 00:45:12","2019-12-18","Observation","Ship Staff","Ship Staff Insp.","Both AUS vacuum pumps constantly tripping during operation","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","troubleshooting to be carried out.","2020-02-17",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 00:49:56","2019-12-18","Deficiency","Ship Staff","Ship Staff Insp.","Hydraulic oil loss from VRCS observed during discharging operations.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Investigation to be carried out to find the source of leak.","2020-02-17",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 00:52:28","2019-12-18","Deficiency","Ship Staff","Ship Staff Insp.","Slop Stbd valve not holding","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Valve seat ring to be renewed","2020-02-17",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 00:56:54","2019-12-18","Observation","Ship Staff","Ship Staff Insp.","No.1 drop valve observed to be leaking","Deck Pipe / Fittings","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Valve seat ring to be renewed","2020-02-17",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 01:03:21","2019-12-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Channel of most of the valve hydraulic boxes on deck are corroded.","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","Box channels to be renewed","2020-03-11",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 01:06:26","2019-12-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deep grooving observed on most of the closed chokes","Deck Pipe / Fittings","Mooring","Equipment Related,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Grooving to be build up","2020-08-11",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 01:14:05","2019-12-12","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Rust weepings observed from anchor wash pipe","Deck Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Pipe to dismantled and inspected.","2020-03-11",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 01:20:22","2019-12-12","Observation","Ship Staff","Ship Staff Insp.","Loadicator printer inoperational","Miscellaneous","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Trouble shooting to be carried out and new printer to be procured","2020-01-11",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 01:24:01","2019-12-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Liferafts emergency light box foundation wasted","Deck Pipe / Fittings","General Appearance","Equipment Related,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Light foundation to be renewed","2020-04-06",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 01:27:38","2019-12-07","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Boss connecting links in poor condition were fitted to few of the wires, while majority of the links are mandal shackles","Miscellaneous","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable","Mandal shackles to be procured to replace the boss shackle","2020-03-06",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"24/12/2019 8:54:40 PM","2019-12-11","Breakdown","Ship Staff","Ship Staff Insp.","HFO Purifier # 2 While trying out found in seized condition.\t","Purifier","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Purifier spares to check and overhaul.","2019-12-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"25/12/2019 3:13:10 AM","2019-12-16","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE, CDI etc.)","Latest Company Pilot card ( Company Form 12.01.11.051.01) dated 15 December 2019 did not include minimum steering speed as suggested by BPG 5 Edition annex 3 section A2 Pilot Card.","Miscellaneous,Nav & comm. equip.","Navigation","Inappropriate Procedure",4.3,"Medium","Not Applicable","Not Applicable","Pilot Card to be revised.","2020-01-15",null,"Not Started",null,"No",null,null,"External"]
[null,null,null,null,null,"25/12/2019 3:46:57 AM","2019-12-16","Deficiency","SIRE / CDI Insp.","OM Insp. (Eg. SIRE, CDI etc.)","The vessel was not provided with software ( program) for engine and boiler water as required by Company procedures. Request for the supply was sighted in the onboard record","Boiler,Main Engine ","Eng. / Strg. Comp.","Equipment Related,External Factors",10.32,"Very High","Not Applicable","Not Applicable","Software to be installed","2020-01-15",null,"In progress",null,"No",null,null,"External"]
[null,null,null,null,null,"25/12/2019 3:49:30 AM","2019-12-16","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE, CDI etc.)","SOPEP/VOC/STS Manuals were submitted to Class for Approval. Vessel was waiting\r\nClass approval.","Documentation","Cert. & Docu.","External Factors,Inappropriate Procedure",2.1,"Very High","Not Applicable","Not Applicable","Approval to be sought from Class","2020-01-16",null,"In progress",null,"No",null,null,"External"]

{"sheet":"Completed","index":1,"n_rows":28,"n_cols":28,"rows_kept":28,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","3-11-2019",null,null,"Ship Name","PROMOTER"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,null,"2019-06-12T17:44:28","2019-12-04","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Loose earth cable for wilden pumps on deck.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Earthing cable fitted properly in place and clamping area paint removed.","2019-12-07",null,"Completed","2019-12-06","No",null,null,"Internal"]
[null,null,null,null,null,"13/12/2019 02:00:13","2019-12-05","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Missing handle of hydraulic isolation valve of mooring which forward of deck seal.","Deck Pipe / Fittings,Mooring Mach.","Mooring","Equipment Related,Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Valve handle / wheel replaced","2019-12-15",null,"Completed","2019-12-06","No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:00:07","2019-12-02","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Low pressure trip for ME LO and Canshaft LO Bypassed by previous crew , investigation to inprogress and pinpoint cause for defect. engine room to be kept manned\t","Main Engine ","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","ME alarms and trips inhibited from ECR by inhibit push button. After removing Inhibit and trying out the alarms found alarms and trips for M|E saftey system working satisfactorily.","2019-12-10",null,"Completed","2019-12-08","No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:24:51","2019-12-02","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Incinerator Flame Failure not operational","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Changed relay and found flame faliure working satisfactorliy","2019-12-10",null,"Completed","2019-12-06","No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:46:02","2019-12-03","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME area above scavenge mainfold on aft starboard side oil/dirt","Main Engine ","Eng. / Strg. Comp.","External Factors",null,null,"Not Applicable","Not Applicable","Area cleaned.","2019-12-31",null,"Completed","2019-12-12","No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 12:54:00","2019-12-03","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both LO Purifier oil inlet temperature maintained at 85 deg cent against 90 ~ 95 deg cent","Purifier","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Heater setting increased now maintaining 90 deg cent.","2019-12-10",null,"Completed","2019-12-08","No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 13:10:01","2019-12-04","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Vacuum condensor pump having leak marks at shaft area","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Gland tightened and old leak marks removed. found no leaks from shaft area.","2019-12-31",null,"Completed","2019-12-13","No",null,null,"Internal"]
[null,null,null,null,null,"14-12-2019 13:20:45","2019-12-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Oxygen/ acetylene cylinders stored on wood","Miscellaneous","Eng. / Strg. Comp.","External Factors,Human Error",null,null,"Not Applicable","Not Applicable","Wood removed and new metal stand fabricated and bottles placed on stand.","2019-12-10",null,"Completed","2019-12-05","No",null,null,"Internal"]
[null,null,null,null,null,"19/12/2019 13:40:57","2019-12-07","Deficiency","Ship Staff","Ship Staff Insp.","One no. SCBA face mask neck straps found broken.","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Not Applicable","Not Applicable","Strap replaced with spare onboard","2019-12-08",null,"Completed","2019-12-07","No",null,null,"Internal"]
[null,null,null,null,null,"17-12-2019 07:09:05","2019-12-05","Deficiency","Ship Staff","Ship Staff Insp.","Pump Room Bilge Alarm indication not showing in CCR","Miscellaneous","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Indication light renewed","2019-12-10",null,"Completed","2019-12-05","No",null,null,"Internal"]
[null,null,null,null,null,"20/12/2019 00:15:47","2019-12-07","Observation","Ship Staff","Ship Staff Insp.","Starboard side anchor not hawsed in completely","Miscellaneous","Mooring","Inappropriate Procedure",null,null,"Not Applicable","Not Applicable","Kink removed from the anchor chain","2020-01-06",null,"Completed","2019-12-08","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["LSA / FFA Appliances",8]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["MARPOL Related",9]
["ISM Related",7]
["ISPS Related",10]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Condn of Class / Memo",null,5]
["Critical Equipment",null,4]
["Deficiency",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":427,"n_cols":3,"rows_kept":427,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",8243]
["1.10","Low",8252]
["1.11","Low",8253]
["1.12","Low",8254]
["1.13","Low",8255]
["1.14","Low",8256]
["1.15","Low",8257]
["1.16","Low",8259]
["1.17","Low",8260]
["1.18","Low",8261]
["1.19","Low",8262]
["1.2","Low",8244]
["1.20","Low",8263]
["1.21","Low",8265]
["1.22","Low",8266]
["1.23","Low",8267]
["1.24","Low",8268]
["1.25","Low",8269]
["1.26","Low",8270]
["1.3","Low",8245]
["1.4","Low",8246]
["1.5","Low",8247]
["1.6","Low",8248]
["1.7","Low",8249]
["1.8","Low",8250]
["1.9","Low",8251]
["1.99","High",11258]
["10.1","Medium",8461]
["10.10","High",8470]
["10.11","Medium",8471]
["10.12","Very High",8472]
["10.13","Very High",8473]
["10.14","Medium",8474]
["10.15","Low",8475]
["10.16","Very High",8476]
["10.17","Very High",8477]
["10.18","High",8478]
["10.19","Very High",8479]
["10.2","Low",8462]
["10.20","High",8480]
["10.21","Medium",8481]
["10.22","Low",8482]
["10.23","Medium",8483]
["10.24","Low",8484]
["10.25","Very High",8485]
["10.26","High",8486]
["10.27","Medium",8487]
["10.28","Low",8488]
["10.29","Medium",8489]
["10.3","Medium",8463]
["10.30","High",8490]
["10.31","Very High",8491]
["10.32","Very High",8492]
["10.33","High",8493]
["10.34","High",8494]
["10.35","Very High",8495]
["10.36","Very High",8496]
["10.37","Medium",8497]
["10.38","Medium",8498]
["10.39","High",8499]
["10.4","High",8464]
["10.40","Medium",8500]
["10.41","Medium",8501]
["10.42","Medium",8502]
["10.43","Medium",8503]
["10.44","Medium",8504]
["10.45","Very High",8505]
["10.46","High",8506]
["10.47","Medium",8507]
["10.48","High",8508]
["10.49","Medium",8509]
["10.5","Low",8465]
["10.50","High",8510]
["10.51","Low",8511]
["10.52","Medium",8512]
["10.53","Medium",8513]
["10.54","High",8514]
["10.55","Low",8515]
["10.6","Very High",8466]
["10.7","Medium",8467]
["10.8","Medium",8468]
["10.9","Medium",8469]
["10.99","High",8516]
["11.1","High",8420]
["11.10","Medium",8429]
["11.11","Very High",8430]
["11.12","Low",8431]
["11.13","Low",8432]
["11.14","Medium",8433]
["11.15","Low",8434]
["11.16","Low",8435]
["11.17","Low",8436]
["11.2","Medium",8421]
["11.3","Medium",8422]
["11.4","Very High",8423]
["11.5","Medium",8424]
["11.6","Medium",8425]
["11.7","High",8426]
["11.8","Low",8427]
["11.9","Low",8428]
["11.99","High",8437]
["12.1","High",8438]
["12.10","High",8448]
["12.11","High",8449]
["12.12","High",8450]
["12.13","High",8451]
["12.14","High",8452]
["12.15","High",8453]
["12.16","High",8454]
["12.17","High",8455]
["12.18","High",8456]
["12.19","High",8457]
["12.2","High",8439]
["12.20","High",8458]
["12.21","High",8459]
["12.3","High",8441]
["12.4","High",8442]
["12.5","High",8443]
["12.6","High",8444]
["12.7","High",8445]
["12.8","High",8446]
["12.9","High",8447]
["12.99","High",8460]
["2.1","Very High",8296]
["2.1.9","Very High",11259]
["2.10","Medium",8304]
["2.11","Medium",8305]
["2.12","Low",8306]
["2.13","Low",8307]
["2.14","Low",8308]
["2.15","Low",8309]
["2.16","Medium",8310]
["2.2","Medium",8297]
["2.3","High",8295]
["2.4","Medium",8298]
["2.5","Medium",8299]
["2.6","Low",8300]
["2.7","High",8301]
["2.8","High",8302]
["2.9","Medium",8303]
["2.99","High",8311]
["3.1","High",8312]
["3.2","Very High",8313]
["3.3","High",8314]
["3.4","Low",8294]
["3.5","Medium",8315]
["3.6","High",8316]
["3.7","Very High",8317]
["3.8","Very High",8318]
["3.99","High",8319]
["4.1","High",8320]
["4.10","High",8329]
["4.11","Medium",8330]
["4.12","Very High",8331]
["4.13","Very High",8332]
["4.14","Very High",8333]
["4.15","Very High",8334]
["4.16","Very High",8335]
["4.17","Very High",8336]
["4.18","Very High",8337]
["4.19","Low",8338]
["4.2","Medium",8321]
["4.20","Very High",8339]
["4.21","High",8340]
["4.22","Low",8341]
["4.23","High",8342]
["4.24","High",8343]
["4.25","Low",8344]
["4.26","Low",8345]
["4.27","High",8346]
["4.3","Medium",8322]
["4.4","High",8323]
["4.5","Very High",8324]
["4.6","Medium",8325]
["4.7","High",8326]
["4.8","Medium",8327]
["4.9","Medium",8328]
["4.99","High",8347]
["5.1","Very High",8517]
["5.10","High",8526]
["5.11","Low",8527]
["5.12","Medium",8528]
["5.13","High",8529]
["5.14","Very High",8530]
["5.15","Medium",8531]
["5.16","Very High",8532]
["5.17","Very High",8533]
["5.18","High",8534]
["5.19","Medium",8535]
["5.2","Very High",8518]
["5.20","Medium",8536]
["5.21","Medium",8537]
["5.22","High",8539]
["5.23","Very High",8540]
["5.24","Very High",8541]
["5.25","Medium",8542]
["5.26","Medium",8543]
["5.27","Medium",8544]
["5.28","Very High",8545]
["5.29","High",8546]
["5.3","Low",8519]
["5.30","High",8547]
["5.31","High",8548]
["5.32","High",8549]
["5.33","High",8550]
["5.34","Low",8551]
["5.35","Medium",8552]
["5.36","Low",8553]
["5.37","Low",8554]
["5.38","High",8555]
["5.39","Very High",8556]
["5.4","High",8520]
["5.40","Very High",8557]
["5.41","Very High",8558]
["5.42","Medium",8559]
["5.43","High",8560]
["5.44","High",8561]
["5.45","Medium",8564]
["5.46","Medium",8565]
["5.47","Medium",8566]
["5.48","Medium",8567]
["5.5","Low",8521]
["5.6","Low",8522]
["5.7","Medium",8523]
["5.8","Medium",8524]
["5.9","Very High",8525]
["5.99","High",8568]
["6.1","Medium",8348]
["6.10","Low",8357]
["6.11","High",8358]
["6.12","Medium",8359]
["6.13","Low",8360]
["6.14","High",8361]
["6.15","High",8362]
["6.16","Very High",8363]
["6.17","Very High",8364]
["6.18","Medium",8365]
["6.19","Low",8366]
["6.2","High",8349]
["6.20","Medium",8367]
["6.21","High",8368]
["6.22","Medium",8369]
["6.3","Low",8350]
["6.4","High",8351]
["6.5","Medium",8352]
["6.6","Medium",8353]
["6.7","High",8354]
["6.8","High",8355]
["6.9","Low",8356]
["6.99","High",8370]
["7.1","High",8371]
["7.10","High",8380]
["7.11","High",8381]
["7.12","High",8382]
["7.13","Medium",8383]
["7.14","Medium",8384]
["7.15","High",8385]
["7.16","High",8386]
["7.17","High",8387]
["7.2","High",8372]
["7.3","Low",8373]
["7.4","Low",8374]
["7.5","Low",8375]
["7.6","Medium",8376]
["7.7","Low",8377]
["7.8","High",8378]
["7.9","High",8379]
["7.99","High",8388]
["8.1","Very High",8569]
["8.10","Very High",8578]
["8.100","Low",11227]
["8.101","Medium",11228]
["8.102","Low",11229]
["8.103","Low",11230]
["8.104","Low",11231]
["8.105","Medium",11232]
["8.106","Medium",11233]
["8.107","Low",11234]
["8.108","High",11235]
["8.109","Very High",11236]
["8.11","Medium",8579]
["8.110","High",11237]
["8.111","Medium",11238]
["8.112","High",11239]
["8.113","Medium",11240]
["8.114","Low",11241]
["8.115","High",11242]
["8.116","Medium",11243]
["8.117","Medium",11244]
["8.118","Medium",11245]
["8.119","High",11246]
["8.12","Medium",8580]
["8.120","High",11247]
["8.121","Medium",11248]
["8.122","High",11249]
["8.123","High",11250]
["8.124","Low",11251]
["8.125","High",11252]
["8.126","Medium",11253]
["8.127","Medium",11254]
["8.13","Medium",8581]
["8.14","Very High",8582]
["8.15","High",8583]
["8.16","Very High",8584]
["8.17","Low",8585]
["8.18","High",8586]
["8.19","High",8587]
["8.199","High",11255]
["8.2","Medium",8570]
["8.20","Medium",8588]
["8.21","High",8589]
["8.22","Very High",8590]
["8.23","Medium",8591]
["8.24","Medium",8592]
["8.25","Very High",8593]
["8.26","High",8594]
["8.27","Medium",8595]
["8.28","Medium",8596]
["8.29","High",8598]
["8.3","Very High",8571]
["8.30","High",8599]
["8.31","High",8600]
["8.32","Low",8601]
["8.33","Medium",8602]
["8.34","High",8603]
["8.35","Medium",8604]
["8.36","Medium",8605]
["8.37","High",8607]
["8.38","Medium",8608]
["8.39","Medium",8609]
["8.4","Medium",8572]
["8.40","High",8610]
["8.41","Medium",8611]
["8.42","Medium",8612]
["8.43","Very High",8613]
["8.44","High",8615]
["8.45","High",8616]
["8.46","Very High",8617]
["8.47","Very High",8618]
["8.48","Medium",8619]
["8.49","High",8620]
["8.5","Very High",8573]
["8.50","Medium",8621]
["8.51","Low",8622]
["8.52","Low",8623]
["8.53","Low",8624]
["8.54","High",8625]
["8.55","Low",11182]
["8.56","Medium",11183]
["8.57","Medium",11184]
["8.58","High",11185]
["8.59","High",11186]
["8.6","Medium",8574]
["8.60","High",11187]
["8.61","Medium",11188]
["8.62","Very High",11189]
["8.63","High",11190]
["8.64","Medium",11191]
["8.65","Low",11192]
["8.66","High",11193]
["8.67","High",11194]
["8.68","High",11195]
["8.69","Medium",11196]
["8.7","High",8575]
["8.70","Medium",11197]
["8.71","Very High",11198]
["8.72","Medium",11199]
["8.73","Medium",11200]
["8.74","High",11201]
["8.75","Medium",11202]
["8.76","Medium",11203]
["8.77","Medium",11204]
["8.78","Medium",11205]
["8.79","Medium",11206]
["8.8","Medium",8576]
["8.80","Medium",11207]
["8.81","Low",11208]
["8.82","Medium",11209]
["8.83","Low",11210]
["8.84","Low",11211]
["8.85","Medium",11212]
["8.86","Medium",11213]
["8.87","Medium",11214]
["8.88","Low",11215]
["8.89","High",11216]
["8.9","High",8577]
["8.90","High",11217]
["8.91","High",11218]
["8.92","Medium",11219]
["8.93","Low",11220]
["8.94","Low",11221]
["8.95","Medium",11222]
["8.96","Medium",11223]
["8.97","Low",11224]
["8.98","High",11225]
["8.99","Medium",11226]
["9.1","Low",8390]
["9.10","Medium",8399]
["9.11","Medium",8400]
["9.12","Medium",8401]
["9.13","Low",8402]
["9.14","Medium",8403]
["9.15","Medium",8404]
["9.16","High",8405]
["9.17","High",8406]
["9.18","Low",8407]
["9.19","Low",8408]
["9.2","Very High",8391]
["9.20","Medium",8409]
["9.21","Medium",8410]
["9.22","Low",8411]
["9.23","Low",8412]
["9.24","Medium",8413]
["9.25","Low",8414]
["9.26","Low",8415]
["9.27","Low",8416]
["9.28","Medium",8417]
["9.29","Low",8418]
["9.3","Very High",8392]
["9.4","High",8393]
["9.5","High",8394]
["9.6","Low",8395]
["9.7","Medium",8396]
["9.8","Medium",8397]
["9.9","Medium",8398]
["9.99","High",8419]

{"sheet":"Equipment_list","index":7,"n_rows":21,"n_cols":3,"rows_kept":21,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation ",null,12]
["Air Comp.",null,8]
["Aux. Engine",null,4]
["Aux. Mach.",null,7]
["Boiler",null,5]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck Mach.",null,18]
["Deck Pipe / Fittings",null,20]
["Documentation",null,21]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Main Engine ",null,3]
["Miscellaneous",null,22]
["Nav & comm. equip.",null,11]
["ER Pipes, valves & fittings",null,9]
["Purifier",null,6]
["Mooring Mach.",null,15]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":16,"n_cols":2,"rows_kept":16,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Others (Eg. Insurance etc.)",12]
["Engineering Audit",16]
["Flag State Insp.",5]
["Ship Staff Insp.",15]
["IT Audit",10]
["OM Insp. (Eg. SIRE, CDI etc.)",6]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["PSC Inspection",4]
["Suptd. Insp.",13]
["Terminal Insp.",11]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["Others (Eg. Insurance etc.)",null,9]
["FSC Inspector",null,5]
["Owner / Marine / Tech. Suptd.",null,3]
["PSC Insp.",null,6]
["Ship Staff",null,2]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["100","PROMOTER","100_1575341220416.xlsm"]