{"text_format":"1","workbook":"xlsx","n_sheets":20,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":29,"n_cols":28,"rows_kept":29,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","26-Nov-2019",null,null,"Ship Name","KALAMAZOO (26-11-2019)"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,6742,"Wed Dec 11 2019 12:24:05 GMT+0000 (Coordinated Universal Time)","2019-09-30","Deficiency","Ship Staff","Ship Staff Insp.","Bunkering davit port and stbd hard to turn","Deck Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","we will renew the bearing once the weather condition clear/bearing have been received","2019-12-31","KALA190193","In progress",null,"No","No","No","Internal","What is the possible cause for both davits hard to turn? Presume you have investigated same & requested for the required spare parts.  Based on VFF, the RO is currently in the processing stage. Target date is already indicating job as overdue, thus you will need to amend same to a later date."]
[null,null,null,null,6743,"Wed Dec 11 2019 12:26:57 GMT+0000 (Coordinated Universal Time)","2019-09-16","Deficiency","Ship Staff","Ship Staff Insp.","7pcs Ballast tank Sensors to be renewed.","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","RO raised KALA190182","2019-12-31","KALA190182","In progress",null,"No","No","No","Internal","Based on VFF, the order is currently awaiting readiness."]
[null,null,null,null,6751,"Wed Dec 11 2019 12:44:07 GMT+0000 (Coordinated Universal Time)","2019-10-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port side blower vent flap closure limit switch to replace with new.","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","RO raised/ under RO KALA190201 kindly approve in yourside","2019-12-31","KALA190201","Waiting spare",null,"No","No","No","Internal","Based on VFF, this RO was not received in this office. Pls check & verifiy if RO was indeed approved & submitted via PAL system."]
[null,null,null,null,6754,"Wed Dec 11 2019 12:50:52 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Wiper time out alarm in ballast no.1 system to be cleaned & rectified","Deck Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Open up the BWT system found that there is no magnet and wiper missing. Need to ask maker of spare parts list no spare parts list onboard in order to request RO. Informed office.","2019-12-31","KALA190059","In progress",null,"No","No","No","Internal","Based on VFF, this order was supplied on board at Pusan on 14/11/2019. Pls proceed with repairs soonest since the job is already overdue. If repairs not feasible, suggest you amend the target date."]
[null,null,null,null,6755,"Wed Dec 11 2019 12:52:43 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aphoulstry of many cabin not in good condition ,material to order & rectify, damaged shower mixer to order ,also missing toilet flush button to order & replace","Accommodation ","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","IN PROGRESS","2019-12-15","KALA190223","In progress",null,"No","No","No","Internal","Based on VFF, Order was supplied to vessel on 14/11/2019 @ Pusan. Pls update current status for said job. If require, pls amend target date as same is already overdue."]
[null,null,null,null,6756,"Wed Dec 11 2019 12:54:49 GMT+0000 (Coordinated Universal Time)","2019-11-02","Deficiency","Ship Staff","Ship Staff Insp.","Galley oven not working due to burnt electric parts","Elect. Mach. & Equip.","MLC Related","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace damage components","2019-12-31","KALA190227","Waiting spare",null,"No","No","No","Internal","Based on VFF, the RO is still in processing status."]
[null,null,null,null,6757,"Wed Dec 11 2019 12:56:45 GMT+0000 (Coordinated Universal Time)","2019-11-02","Deficiency","Ship Staff","Ship Staff Insp.","Corroded lighting fixtures around accommodation area","Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace damage lighting fixtures. The diffuser is in progress already. Changed yellowish diffuser.","2019-12-31","KALA190213,KALA190214,  KALA190209","In progress",null,"No","No","No","Internal","Based on VFF, KALA190213 have been supplied to vessel on 14/11/2019 @ Pusan, KALA190214 - in processing status, KALA190209 - supplier awaiting delivery instructions.\n\nWhen do you plan to commence the job since the electrical tools & lighting fixtures / materials have been supplied on board voa PO#KALA190213"]
[null,null,null,null,6758,"Wed Dec 11 2019 12:58:40 GMT+0000 (Coordinated Universal Time)","2019-11-01","Deficiency","Ship Staff","Ship Staff Insp.","Defective PD controller","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","To replaced defective PD controller/ RO raise KALA190197 kindly approve at your side","2019-12-31","KALA190197","Waiting spare",null,"No","No","No","Internal","Based on VFF, RO#KALA190197 not received in PAL by this office. Pls check & confirm that same was indeed approved & submitted to office via PAL system."]
[null,null,null,null,null,"2019-12-01T05:06:17","2019-11-13","Breakdown","Ship Staff","Ship Staff Insp.","Defective water boiler in galley equipment\t","Accommodation ","Crew Management","Equipment Related",null,null,"Not Applicable","Not Applicable","request to renew with boiler catle ","2019-12-31","KALA190231","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"2019-12-12T12:34:07","2019-12-05","Deficiency","Ship Staff","Ship Staff Insp.","Defective crewmess exhaust fan.","Accommodation ,Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Inform office and raise RO","2019-12-31","KALA190254","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"17/12/2019 3:36:40 PM","2019-12-16","Deficiency","Ship Staff","Ship Staff Insp.","Defective metos toaster.","Accommodation ","Crew Management","Equipment Related",null,null,"Not Applicable","Not Applicable","To replaced heating elements of toaster. To raise RO next year","2020-01-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"23/12/2019 1:09:14 PM","2019-12-23","Breakdown,Deficiency","Ship Staff","Ship Staff Insp.","Sludge pump not working.","Aux. Mach.","MARPOL Related","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace rotor and stator","2020-01-15","KALA190258","Waiting spare",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":122,"n_cols":28,"rows_kept":122,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","26-10-2019",null,null,"Ship Name","KALAMAZOO (26-11-2019)"]
[]
[]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,6747,"Wed Dec 11 2019 10:47:58 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Wilden pp kept in port side duct keel to be flushed & clean & keep in steering flat ","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Wilden pump flushed & clean & keep in steering flat. ","2019-10-24","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,6748,"Wed Dec 11 2019 10:50:56 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Crane/davit hook missing for life raft davit, all small davits, same to fabricate","Deck Pipe / Fittings","General Appearance","Equipment Related","","","","","Fabricated missing latch forhooks at crane davit, life raft davit, all small davits.","2019-10-28","","Completed","2019-10-28","No","No","No","Internal"]
[null,null,null,null,6749,"Wed Dec 11 2019 10:53:44 GMT+0000 (Coordinated Universal Time)","2019-10-22","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency bulb fitting near L/B deck locking bolt stud, broken to be rectified.","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","Fabricated  locking bolt stud for Emergency bulb ","2019-10-25","","Completed","2019-10-25","No","No","No","Internal"]
[null,null,null,null,6750,"Tue Nov 12 2019 10:56:53 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bunker tank  high level alarm panel portside buzzer fused & STBD side all light glowing ,to rectify prior USCG inspection","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Checked electrical connections","2019-10-28","","Completed","2019-10-28","No","No","No","Internal"]
[null,null,null,null,6759,"Wed Dec 11 2019 04:52:07 GMT+0000 (Coordinated Universal Time)","2019-01-04","Deficiency","Ship Staff","Ship Staff Insp.","Leaking mechanical seal of MSW pump no.1 ","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Rectified leaking / replaced new spare mechanical seal of Main Sea water p/p no.1 ","2019-01-05","","Completed","2019-01-05","No","No","No","Internal"]
[null,null,null,null,6760,"Mon Nov 11 2019 16:09:46 GMT+0000 (Coordinated Universal Time)","2019-01-04","Deficiency","Ship Staff","Ship Staff Insp.","Rectify Balalst Water treatment pump no.1 wiping \"timeout alarm\" ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","To rectified alarmed of BWT no.1 found position switch defective -restored magnet to detect the system,Replaced 4 pcs UV lamp/ 2 pcs quarts jacket.","2019-01-15","","Completed","2019-01-05","No","No","No","Internal"]
[null,null,null,null,6761,"Mon Nov 11 2019 16:15:19 GMT+0000 (Coordinated Universal Time)","2019-01-04","Deficiency","Ship Staff","Ship Staff Insp.","Defective flame detector at incinerator area ","Elect. Mach. & Equip.","LSA / FFA Appliances","Equipment Related","","","","","To replace with new spare  flame detector ","2019-01-15","KALA190005","Completed","2019-01-20","No","No","No","Internal"]
[null,null,null,null,6762,"Mon Nov 11 2019 16:18:48 GMT+0000 (Coordinated Universal Time)","2019-01-21","Deficiency","Ship Staff","Ship Staff Insp.","Rcvd newBallast sensor from supplier to install to 3B SWB tk. port side defective sensor reading.","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","To renewed new rcvd ballast sensor 3B SWB port side and back to normal reading.","2019-01-21","","Completed","2019-01-21","No","No","No","Internal"]
[null,null,null,null,6763,"Mon Nov 11 2019 16:23:21 GMT+0000 (Coordinated Universal Time)","2019-01-26","Deficiency","Ship Staff","Ship Staff Insp.","Aux. Boiler burner oil pump broken driving shaft gear.and no pressure build up due to broken gear","Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Rectified and repaired take the old pump driving shaft and gear  fixed it and testing pressure come-up and back to normal and testted firing and working satisfactory.","2019-01-26","","Completed","2019-01-26","No","No","No","Internal"]
[null,null,null,null,6764,"Mon Nov 11 2019 16:28:48 GMT+0000 (Coordinated Universal Time)","2019-02-03","Deficiency","Ship Staff","Ship Staff Insp.","Heat Defector on paint store defector fault appearing on panel during testing ","Elect. Mach. & Equip.","LSA / FFA Appliances","Equipment Related","","","","","Rectified changed new spare heat detector / back to normal working.","2019-02-03","","Completed","2019-02-03","No","No","No","Internal"]
[null,null,null,null,6765,"Mon Nov 11 2019 16:30:55 GMT+0000 (Coordinated Universal Time)","2019-02-04","Deficiency","Ship Staff","Ship Staff Insp.","Leaking Gasket of Main steam valve of aux. boiler","Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Rectified laeaking changed new fabricated gasket and observed after no more leaking exist.","2019-02-04","","Completed","2019-02-04","No","No","No","Internal"]
[null,null,null,null,6766,"Mon Nov 11 2019 17:12:28 GMT+0000 (Coordinated Universal Time)","2019-01-22","Deficiency","Ship Staff","Ship Staff Insp.","Galley oven burned -out transformer ","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","To be replace new transformer ","2019-01-31","KALA190035","Completed","2019-02-20","No","No","No","Internal"]
[null,null,null,null,6767,"Mon Nov 11 2019 17:17:29 GMT+0000 (Coordinated Universal Time)","2018-07-26","Deficiency","Ship Staff","Ship Staff Insp.","No UV lamp therefore the UVK sterilizer unoperational ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","To replace UV lamp ( Rcvd spares KALA180140)Need more spare re-order ( UV Lamp)","2018-08-30","KALA185102-KALA180174","Completed","2019-02-27","No","No","No","Internal"]
[null,null,null,null,6768,"Mon Nov 11 2019 17:20:41 GMT+0000 (Coordinated Universal Time)","2019-02-26","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emg gen fuel storage tank doesn't have marking on gauge glass of min fuel required to RUN for 18hours of operation as required by SOLAS regulations","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","To stencil FO tank level of 18hrs continous running","2019-03-01","","Completed","2019-03-06","No","No","No","Internal"]
[null,null,null,null,6769,"Mon Nov 11 2019 17:33:02 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","WS grinding m/c making noise, motor to o'haul","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To overhaul/changed bearing","2019-03-14","KALA190035","Completed","2019-03-06","No","No","No","Internal"]
[null,null,null,null,6770,"Mon Nov 11 2019 17:36:26 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ER logbook reading were written only once a day, to be written twice a day.","Documentation","Cert. & Docu.","Equipment Related","","","","","To comply as required","2019-02-28","","Completed","2019-02-28","No","No","No","Internal"]
[null,null,null,null,6771,"Mon Nov 11 2019 17:41:19 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pneumatic air regulators for BWTS control 3 way vv to be drained everyday, same to be stencilled","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To drain everyday and stencilled \"Drain Everyday\"","2019-03-01","","Completed","2019-03-01","No","No","No","Internal"]
[null,null,null,null,6772,"Mon Nov 11 2019 17:44:43 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Near OWS ovbd v/v notice to put \"NOT TO BE OPERATED WITHOUT PERMISSION OF MASTER & CHIEF ENGINEER\"","Documentation","Cert. & Docu.","Equipment Related","","","","","To post poster near OWS valve","2019-03-14","","Completed","2019-03-07","No","No","No","Internal"]
[null,null,null,null,6773,"Mon Nov 11 2019 17:47:22 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No. 2 steering gear space heater bulb fused to renew","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","ETO to check","2019-03-04","","Completed","2019-03-07","No","No","No","Internal"]
[null,null,null,null,6774,"Mon Nov 11 2019 17:49:44 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sewage plant 2 in no. transparent hose to be replaced with new as part of 3 monthly routines.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To replace with new transparent hose","2019-03-14","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6775,"Mon Nov 11 2019 17:51:57 GMT+0000 (Coordinated Universal Time)","2019-02-28","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sewage plant air blower spares for motor & pump to order, urgently order for pressure gauge of required range & thread for air blower line","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To raise RO","2019-03-14","Kala190062","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6776,"Mon Nov 11 2019 17:54:30 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No. 2 Lube oil purifier top cover seal leaking, to replace with new","Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","To check/Renewed o-ring","2019-03-09","","Completed","2019-03-08","No","No","No","Internal"]
[null,null,null,null,6777,"Mon Nov 11 2019 17:56:36 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo hold space smoke detector both motor to overhaul","Elect. Mach. & Equip.","LSA / FFA Appliances","Equipment Related","","","","","To check for spare ball bearing ","2019-03-30","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6778,"Mon Nov 11 2019 17:58:35 GMT+0000 (Coordinated Universal Time)","2019-03-06","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MSDS for paints & chemicals are old edition to renew with new edition","Documentation","Cert. & Docu.","Equipment Related","","","","","MSDS Renewed with new edition","2019-03-06","","Completed","2019-03-06","No","No","No","Internal"]
[null,null,null,null,6779,"Mon Nov 11 2019 18:00:28 GMT+0000 (Coordinated Universal Time)","2019-03-06","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering room entrance door  rubber seal gasket damaged, to renew","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Rubber seal gasket renewed","2019-03-09","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6780,"Mon Nov 11 2019 18:02:53 GMT+0000 (Coordinated Universal Time)","2019-03-06","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Missing IMO symbols for fire hoses, embarkation level, embarkation etc. to be renew with new as required, raise RO if required.","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","IMO symbols renewed ","2019-03-06","","Completed","2019-03-06","No","No","No","Internal"]
[null,null,null,null,6781,"Mon Nov 11 2019 18:05:50 GMT+0000 (Coordinated Universal Time)","2019-03-06","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","On board Complaint box/suggestion box to be fabricated in Crew smoke room as part of MLC survey.","Miscellaneous","MLC Related","Equipment Related","","","","","Fabricate On Board Complaint/Suggestion box in crew smoke room  as part of MLC","2019-03-09","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6782,"Mon Nov 11 2019 18:08:25 GMT+0000 (Coordinated Universal Time)","2019-03-06","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All the deck machineries where greasing is required including LB davits etc., need to be marked with yellow paint for easy identification.","Deck Pipe / Fittings","General Appearance","Equipment Related","","","","","All the deck machineries where greasing is required including LB davits etc, Marked with yellow paint for easy identification.","2019-03-07","","Completed","2019-03-06","No","No","No","Internal"]
[null,null,null,null,6783,"Mon Nov 11 2019 18:10:45 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Boiler chloride level is 130 which is on higher side, blow down to be carried out & cooling water nitrate level is too low, to add chemicals. Also testing chemicals have expired, need to order new.","Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Vessel to raise RO for testing reagent","2019-03-04","","Completed","2019-03-08","No","No","No","Internal"]
[null,null,null,null,6784,"Mon Nov 11 2019 18:12:44 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Lagging to fitted on main engine fuel pp no.2 HP pipe outlet. All temp piping to be covered with insulation lagging including ME and Dg T/Cs as it is fire hazard.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To put insulation lagging","2019-03-06","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6785,"Mon Nov 11 2019 18:14:41 GMT+0000 (Coordinated Universal Time)","2019-02-28","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME fuel pp leak off tank gives alarm when engine running on higher speed. Source of leakage to be identified after opening the tank in port, investigation report report to be forwarded to supt.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","","","","","Engine staff to check and rectify","2019-03-30","","Completed","2019-03-10","No","No","No","Internal"]
[null,null,null,null,6786,"Mon Nov 11 2019 18:16:32 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Air compressor Lube oil low pressure trip set at very low pressure, to check from manual the cut off pressure & adjust accordingly.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To be check and confirm","2019-03-14","","Completed","2019-03-10","No","No","No","Internal"]
[null,null,null,null,6787,"Mon Nov 11 2019 18:18:24 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Vessel fuel oil C/O approved procedures to ECA/SECA to be posted in ECR","Documentation","Cert. & Docu.","Equipment Related","","","","","To be posted at ECR","2019-04-14","","Completed","2019-03-10","No","No","No","Internal"]
[null,null,null,null,6788,"Mon Nov 11 2019 18:20:41 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME backwas servo filter differential press coming frequently & both auto backwash & bypass are kept in use, plan backwash filter to clean at every port stay. Check for proper operation of backwash cycle confirming both solenoid are activated. Also check if the frequency of backwash can be reduced","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Cleaned every arrival port the Auto and manual filter","2019-03-06","","Completed","2019-03-12","No","No","No","Internal"]
[null,null,null,null,6789,"Mon Nov 11 2019 18:23:16 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Luminance to increase in purifier room, plan to install additional LED ligh","Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","ETO to install additional lighting","2019-03-30","","Completed","2019-03-12","No","No","No","Internal"]
[null,null,null,null,6790,"Mon Nov 11 2019 18:25:07 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sewage plant metering pp not dosing the chemical to recheck the correct operation from manual.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To check the operating instruction of the Metering pump","2019-03-02","","Completed","2019-03-14","No","No","No","Internal"]
[null,null,null,null,6791,"Mon Nov 11 2019 18:27:15 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aux boiler burner hing door limit switch in operational, to replace with new.","Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","ETO to check","2019-03-14","","Completed","2019-03-14","No","No","No","Internal"]
[null,null,null,null,6792,"Mon Nov 11 2019 18:31:37 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All the ER ovbd v/v has no stencilling for identification, same to be stencilled","Documentation","Cert. & Docu.","Equipment Related","","","","","Engine staff to stencile","2019-03-30","","Completed","2019-03-12","No","No","No","Internal"]
[null,null,null,null,6793,"Mon Nov 11 2019 18:33:45 GMT+0000 (Coordinated Universal Time)","2019-03-06","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both pilot ladders were supplied in yard & not in accordance with IMO resolution A.1024. To order new ladder  ","Deck Mach.","General Appearance","Equipment Related","","","","","New pilot ladders supplied in accordance with IMO 1045 A(27)","2019-03-16","","Completed","2019-03-16","No","No","No","Internal"]
[null,null,null,null,6794,"Mon Nov 11 2019 18:35:39 GMT+0000 (Coordinated Universal Time)","2019-03-06","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Duct keel bottom platform has rust spots ,same to power tooled & painted","Deck Pipe / Fittings","General Appearance","Equipment Related","","","","","Duct keel bottom platform has rust spots, De rusting, power tooled & painted.","2019-03-31","","Completed","2019-03-20","No","No","No","Internal"]
[null,null,null,null,6795,"Mon Nov 11 2019 18:37:39 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","On funnel 1 DG welding support bracket broken, same to be rewelded. Attach photo","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To weld by engine fitter","2019-04-30","","Completed","2019-03-21","No","No","No","Internal"]
[null,null,null,null,6796,"Mon Nov 11 2019 18:39:30 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Many rubber supports for tensioning bolts of exhaust pipe have got hardened & bronken. To order the rubber supports, 4 in no. tensioning rods are broken, same to be rewelded","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To Raise RO/Renewed tensioning bolts and rubber supports","2019-03-30","","Completed","2019-03-27","No","No","No","Internal"]
[null,null,null,null,6797,"Mon Nov 11 2019 18:41:58 GMT+0000 (Coordinated Universal Time)","2019-02-28","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bilge tank has heavy traces of fuel oil on top, oil to be skimmed & absorbent pad to be laid on top of the tank. Most importantly the source of the oil traces needs to be traced & rectified. Investigation report to be forwarded to supt.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To open up and remove traces of oil","2019-03-31","","Completed","2019-04-07","No","No","No","Internal"]
[null,null,null,null,6798,"Mon Nov 11 2019 18:44:01 GMT+0000 (Coordinated Universal Time)","2019-01-21","Deficiency","Ship Staff","Ship Staff Insp.","HFO Purifier feed pump no.1 & 2 Leaking oil seal ","Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","To renew oil seal leaking of HFO feed pump no.1 & 2","2019-01-31","","Completed","2019-04-07","No","No","No","Internal"]
[null,null,null,null,6799,"Mon Nov 11 2019 18:46:13 GMT+0000 (Coordinated Universal Time)","2019-02-28","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME lube oil servo auto backwash filter is used in conjunction with bypass filter as candle filters get chocked when only on auto backwash filter. Auto backwash filter operation, its solenoid v/vs to be check for its correct operation. Investigation report to be forwarded to supt & spares to be ordered as required","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To be checked for proper operation","2019-03-15","","Completed","2019-04-12","No","No","No","Internal"]
[null,null,null,null,6800,"Mon Nov 11 2019 18:48:06 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel platform boiler/EGE outlet bellow leaking, also some DG bellows leaking, same to be opened during port stay & check for leakages, order the bellows accordingly","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To check and if found leaking to raise RO of same. Retightened loose bolts and nuts.","2019-03-27","","Completed","2019-04-18","No","No","No","Internal"]
[null,null,null,null,6801,"Wed Dec 11 2019 07:55:26 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Ship Staff","Ship Staff Insp.","No.3 DG CW high temp sensor wire broken, new temp switch to order & replace","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","To order new temp switch, rectify broken wire","2019-03-14","Kala190074","Completed","2019-04-18","No","No","No","Internal"]
[null,null,null,null,6802,"Wed Dec 11 2019 07:59:59 GMT+0000 (Coordinated Universal Time)","2019-04-24","Deficiency","Ship Staff","Ship Staff Insp.","Defective float switch for bilge alarms","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Replaced Float level switch","2019-04-24","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,6803,"Wed Dec 11 2019 08:02:37 GMT+0000 (Coordinated Universal Time)","2019-01-14","Deficiency","Ship Staff","Ship Staff Insp.","Cargo hold fan No:08 -3GS5  -port side burned -out motor wiring ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","To be replace new motor assembly both casargo hold supply fan 3GS5","2019-04-30","","Completed","2019-05-08","No","No","No","Internal"]
[null,null,null,null,6804,"Wed Dec 11 2019 08:04:45 GMT+0000 (Coordinated Universal Time)","2019-04-28","Deficiency","Ship Staff","Ship Staff Insp.","Defective engine room blower  gauze wire screen.","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To replace with new wire screen.","2019-05-31","KALA190105","Completed","2019-05-31","No","No","No","Internal"]
[null,null,null,null,6805,"Wed Dec 11 2019 08:13:16 GMT+0000 (Coordinated Universal Time)","2019-02-26","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emg fire p/p priming pump clutch lining was not touching the pump lining during stop condition, same to be adjusted","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","To check the clutch of priming unit","2019-05-31","KALA190088","Completed","2019-06-03","No","No","No","Internal"]
[null,null,null,null,6806,"Wed Dec 11 2019 08:21:39 GMT+0000 (Coordinated Universal Time)","2019-04-06","Deficiency","Ship Staff","Ship Staff Insp.","Defective Galvanic Isolator of Cargo Hold Smoke Detector","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Office Informed and RO Raised","2019-06-30","KALA190086","Completed","2019-06-21","No","No","No","Internal"]
[null,null,null,null,6807,"Wed Dec 11 2019 08:25:36 GMT+0000 (Coordinated Universal Time)","2019-07-30","Deficiency","PSC Insp.","PSC Inspection","Ceiling light in Battery room- not turned on","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","Other",2,"Replaced immediately with new spare","2019-07-30","","Completed","2019-07-30","No","No","No","External"]
[null,null,null,null,6808,"Wed Dec 11 2019 08:27:50 GMT+0000 (Coordinated Universal Time)","2019-07-30","Deficiency","PSC Insp.","PSC Inspection","Emergency  light near life raft ,PS SS - Not turned on","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","","","Emergency Systems",2,"Replaced immediately with new spare","2019-07-30","","Completed","2019-07-30","No","No","No","External"]
[null,null,null,null,6809,"Tue Nov 12 2019 08:30:12 GMT+0000 (Coordinated Universal Time)","2019-05-31","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp."," No.1 DG CW high temp sensor wire broken, new temp switch to order & replace","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Checked broken wire and same problem persist. Report sent and awaiting instruction from maker regarding the defect/alarm.","2019-07-31","KALA190124","Completed","2019-07-28","No","No","No","Internal"]
[null,null,null,null,6810,"Wed Dec 11 2019 08:32:54 GMT+0000 (Coordinated Universal Time)","2019-07-15","Deficiency","Ship Staff","Ship Staff Insp.","Defective Valve Block","Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","RO Raised","2019-08-15","KALA190073","Completed","2019-08-05","No","No","No","Internal"]
[null,null,null,null,6811,"Wed Dec 11 2019 08:35:48 GMT+0000 (Coordinated Universal Time)","2019-07-15","Deficiency","Ship Staff","Ship Staff Insp.","Defective Bonded Stator of Incinerator Dosing Pump","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","RO Raised","2019-08-15","Kala190137","Completed","2019-08-02","No","No","No","Internal"]
[null,null,null,null,6812,"Wed Dec 11 2019 08:37:36 GMT+0000 (Coordinated Universal Time)","2019-07-25","Deficiency","Ship Staff","Ship Staff Insp.","Defective Impeller of Incinerator Circulating Pump","Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","RO raised for Impeller and O-rings","2019-08-15","KALA190139","Completed","2019-08-05","No","No","No","Internal"]
[null,null,null,null,6813,"Wed Dec 11 2019 08:39:26 GMT+0000 (Coordinated Universal Time)","2019-01-14","Deficiency","Ship Staff","Ship Staff Insp.","Cargo hold fan NO.11 3GS4 port side burned -out motor wiring ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","To replace new motor assembly hold supply fan no. 11 3GS4.","2019-09-30","KALA190121","Completed","2019-08-21","No","No","No","Internal"]
[null,null,null,null,6814,"Wed Dec 11 2019 08:41:53 GMT+0000 (Coordinated Universal Time)","2018-09-24","Deficiency","Ship Staff","Ship Staff Insp.","Defective No. 1& 2  HFO service tank sensor","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Cleaned sensor and retighten the wirings. To be order next year due to tight budget.","2019-09-30","Kala190066","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,6815,"Wed Dec 11 2019 08:43:56 GMT+0000 (Coordinated Universal Time)","2019-02-23","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Rescue Boat Davit Accumulator press gauge to order & check for hose coupling for charging nitrogen","LSA / FFA","MLC Related","Equipment Related","","","","","To raise RO for Charging Hose of Accumulator","2019-09-30","KALA190089","Completed","2019-09-03","No","No","No","Internal"]
[null,null,null,null,6816,"Wed Dec 11 2019 08:49:23 GMT+0000 (Coordinated Universal Time)","2018-02-04","Deficiency","Ship Staff","Ship Staff Insp.","Ballast sensors 23 pcs to renew","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Received  8 pcs ballast sensors  and 8 pcs.  already installed.","2019-09-30","Kala 190066","Completed","2019-09-27","No","No","No","Internal"]
[null,null,null,null,6817,"Wed Dec 11 2019 08:51:31 GMT+0000 (Coordinated Universal Time)","2019-07-15","Deficiency","Ship Staff","Ship Staff Insp.","Sluggish movement of LT Actuator Control Valve","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","RO raised for o-ring and seals, spares received","2019-10-15","KALA190136","Completed","2019-10-10","No","No","No","Internal"]
[null,null,null,null,6818,"Wed Dec 11 2019 10:13:58 GMT+0000 (Coordinated Universal Time)","2019-08-29","Deficiency","Ship Staff","Ship Staff Insp.","Defective control transformer for accom. Ladder port side","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","RO raised","2019-10-15","KALA 190154","Completed","2019-10-06","No","No","No","Internal"]
[null,null,null,null,6819,"Wed Dec 11 2019 09:59:22 GMT+0000 (Coordinated Universal Time)","2019-09-13","Deficiency","Ship Staff","Ship Staff Insp."," Rescue boat davit defective shut-off valve.","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","RO raised","2019-10-15","KALA 190171","Completed","2019-10-14","No","No","No","Internal"]
[null,null,null,null,6820,"Wed Dec 11 2019 10:01:39 GMT+0000 (Coordinated Universal Time)","2019-08-18","Deficiency","Ship Staff","Ship Staff Insp.","Defective safety interlock switch/ Door lock for incinerator","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Ro raised ","2019-10-30","KALA 190146","Completed","2019-10-17","No","No","No","Internal"]
[null,null,null,null,6821,"Wed Dec 11 2019 10:04:22 GMT+0000 (Coordinated Universal Time)","2019-10-10","Deficiency","Ship Staff","Ship Staff Insp.","Gyro failure alarm","Elect. Mach. & Equip.","Navigation","Equipment Related","","","","","Service technician will attend","2019-11-15","KALA195037","Completed","2019-10-17","No","No","No","Internal"]
[null,null,null,null,6822,"Wed Dec 11 2019 10:06:29 GMT+0000 (Coordinated Universal Time)","2019-09-07","Deficiency","Ship Staff","Ship Staff Insp.","Defective life boat battery charger","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","Replaced new battery charger","2019-10-30","KALA 190165","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,6823,"Wed Dec 11 2019 10:09:05 GMT+0000 (Coordinated Universal Time)","2019-10-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Replaced damage lighting fixture at A-deck","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Replaced lighting fixture","2019-11-15","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,6824,"Wed Dec 11 2019 10:11:34 GMT+0000 (Coordinated Universal Time)","2019-10-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","To repair PS crane limit switch not working","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Limit switch operational. Problem in the electrical connection.","2019-11-15","KALA190201","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,6825,"Wed Dec 11 2019 10:13:48 GMT+0000 (Coordinated Universal Time)","2019-10-14","Deficiency","Ship Staff","Ship Staff Insp.","Replaced damage lighting fixture at ships name","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Replaced lighting fixture","2019-11-15","","Completed","2019-10-25","No","No","No","Internal"]
[null,null,null,null,6826,"Wed Dec 11 2019 10:15:49 GMT+0000 (Coordinated Universal Time)","2019-10-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Remove/hide LAN and sockets in A-deck","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Removed cables","2019-11-15","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,6827,"Wed Dec 11 2019 10:17:55 GMT+0000 (Coordinated Universal Time)","2019-10-10","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Repair bao of hoisting in PS crane","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Renewed limit switch and overhaul bao","2019-11-15","","Completed","2019-10-25","No","No","No","Internal"]
[null,null,null,null,6828,"Wed Dec 11 2019 10:20:07 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NOX file records for ALL DG & ME to be updated.","Documentation","Cert. & Docu.","Equipment Related","","","","","NOX files updated","2019-10-24","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,6829,"Wed Dec 11 2019 10:22:30 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel flap mainly STBD side has slight gap, Not 100% close, to make it free to close fully","Aux. Mach.","Structural Condn. / WT integrity ","Equipment Related","","","","","Fixed and adjusted funnel flap","2019-10-25","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,6830,"Wed Dec 11 2019 10:25:29 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Marpol sample for last 1 year to be kept in chronological order.","Miscellaneous","MARPOL Related","Equipment Related","","","","","Marpol sample last 1 year separetely keep","2019-10-24","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,6831,"Wed Dec 11 2019 10:27:47 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bridge PC to activate for navtracker & update the ENPs on it as well","Nav & comm. equip.","Navigation","Equipment Related","","","","","install and activate navtracker at Bridge PC","2019-11-21","","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,6832,"Wed Dec 11 2019 10:30:21 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","New washing machine to be fitted in laundry","Accommodation ","MLC Related","Equipment Related","","","","","Washing machine installed at Laundry room","2019-10-26","","Completed","2019-10-26","No","No","No","Internal"]
[null,null,null,null,6833,"Wed Dec 11 2019 10:32:58 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LT cooler auto electrical operating unit to fit back & check the system.","ER Pipes, valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Fitted back & checked LT cooler auto electrical operating unit","2019-10-26","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,6834,"Wed Dec 11 2019 10:35:27 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","One of the drain in galley is chocked ,same to be cleared ","Accommodation ","General Appearance","Equipment Related","","","","","Unblocked and decloged galley drain","2019-10-28","","Completed","2019-10-28","No","No","No","Internal"]
[null,null,null,null,6835,"Wed Dec 11 2019 10:37:56 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Suez cabin to be cleared of garbage & galley materials, toilet is in shabby condition, to be arranged & light changed.","Accommodation ","General Appearance","Equipment Related","","","","","Organize and cleaned Suez cabin, transfer some stores to cabin locker","2019-10-26","","Completed","2019-10-26","No","No","No","Internal"]
[null,null,null,null,6836,"Wed Dec 11 2019 10:40:20 GMT+0000 (Coordinated Universal Time)","2019-10-22","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port side Vent head rusted & damaged, need to Refabricate.","Deck Pipe / Fittings","General Appearance","Equipment Related","","","","","Renew port side vent box","2019-10-26","","Completed","2019-10-25","No","No","No","Internal"]
[null,null,null,null,6837,"Wed Dec 11 2019 10:43:09 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","EAL grease to be applied on the rudder carrier ,Lifeboat davit wire, Life raft wires & aft gangway wires","Miscellaneous","General Appearance","Equipment Related","","","","","Applied EAL grease on rudder carrier, lifeboat, rescue boat/liferaft, gangway wirtes.","2019-10-26","","Completed","2019-10-26","No","No","No","Internal"]
[null,null,null,null,6838,"Wed Dec 11 2019 10:45:29 GMT+0000 (Coordinated Universal Time)","2019-10-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","BDN for 3 years i.e. till Nov16 carried out ,should be available ","Documentation","Cert. & Docu.","Equipment Related","","","","","BDN for the last 3 years till Nov'16 filed.","2019-10-24","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,6839,"Wed Dec 11 2019 08:46:48 GMT+0000 (Coordinated Universal Time)","2019-02-27","Deficiency","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME viscotherm unit pressure gauge faulty, to replace. Again check all the gauges & thermometer & replace as required.","Main Engine ","Eng. / Strg. Comp.","Equipment Related","","","","","Spares received and to be installed","2019-09-30","Office RO","Completed","2019-09-23","No","No","No","Internal"]
[null,null,null,null,null,"Mon Nov 11 2019 18:50:56 GMT+0000 (Coordinated Universal Time)","2019-01-01","Deficiency","Ship Staff","Ship Staff Insp.","Main SW pump no. 1 leaking mechanical seal","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","renew mechanical seal with new spare received","2019-11-30","KALA190009","Completed","2019-11-23","No",null,null,"Internal"]
[null,null,null,null,null,"Wed Dec 11 2019 12:16:14 GMT+0000 (Coordinated Universal Time)","2019-09-13","Deficiency","Ship Staff","Ship Staff Insp.","Defective  engine room  crane limit switch","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","renew with new spare tested found working satisfactory","2019-10-30","KALA 190174","Completed","2019-11-17","No",null,null,"Internal"]
[null,null,null,null,null,"Wed Dec 11 2019 12:18:49 GMT+0000 (Coordinated Universal Time)","2019-09-11","Deficiency","Ship Staff","Ship Staff Insp.","Hfo purifier no.1 defective water valve block.","Purifier","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","renewed with new spare recieved ","2019-11-15","KALA 190160","Completed","2019-11-21","No",null,null,"Internal"]
[null,null,null,null,null,"Wed Dec 11 2019 12:33:36 GMT+0000 (Coordinated Universal Time)","2019-10-14","Deficiency","Ship Staff","Ship Staff Insp.","Defective solenoid valve","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Not Applicable","Not Applicable","renewed with new spare","2019-11-15","KALA190204","Completed","2019-11-19","No",null,null,"Internal"]
[null,null,null,null,null,"Wed Dec 11 2019 12:48:53 GMT+0000 (Coordinated Universal Time)","2019-10-30","Deficiency","Ship Staff","Ship Staff Insp.","BWTS NO. 1 COOLING SOLENOID VALVE NOT FUNCTIONING WELL","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Not closing nor opening then cleaned solenoid valve. After cleaning, it takes time to close the valve causing it to fail first. To replace solenoid valve./renew with new spare ","2019-11-30","KALA190218","Completed","2019-11-18","No",null,null,"Internal"]
[null,null,null,null,null,"Tue Nov 12 2019 10:17:24 GMT+0000 (Coordinated Universal Time)","2019-08-15","Deficiency","Ship Staff","Ship Staff Insp.","Defective bridge wing thruster controller/ starboard SIDE","Nav & comm. equip.","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","renewed with new spare","2019-11-15","KALA190143","Completed","2019-11-18","No",null,null,"Internal"]
[null,null,null,null,null,"2019-12-06T11:08:49","2019-07-30","Deficiency","PSC Insp.","PSC Inspection","Ceiling Light in Battery - not turned on","Miscellaneous","General Appearance","Equipment Related",null,null,"Other","Asia and the Pacific","Rectified light before departure","2019-07-30",null,"Completed","2019-07-30","No",null,null,"External"]
[null,null,null,null,null,"2019-12-06T11:12:49","2019-07-30","Deficiency","PSC Insp.","PSC Inspection","Emergency light near liferaft (both sides) - not turned on","Miscellaneous","Emgcy. Systems","Equipment Related",null,null,"Emergency Systems","Asia and the Pacific","Rectified both emergency lights before departure","2019-07-30",null,"Completed","2019-07-30","No",null,null,"External"]
[null,null,null,null,null,"2019-06-12T11:18:00","2019-09-09","Deficiency","PSC Insp.","PSC Inspection","Fireman's outfit in bosun store - Firemans cloth was missing ( crew forgot bring back after last fire fighting drill)","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Fire safety","Asia and the Pacific","Return back firemans cloth at fwd bosun store before departure.","2019-09-09",null,"Completed","2019-09-09","No",null,null,"External"]
[null,null,null,null,null,"2019-06-12T11:21:29","2019-09-09","Deficiency","PSC Insp.","PSC Inspection","Copy of DMLC part I & II - Not posted at conspicuous place\t","Documentation","Cert. & Docu.","Equipment Related",null,null,"Certificates & Documentation","Asia and the Pacific","Posted DMLC part I & II at messroom alleyway before departure","2019-09-09",null,"Completed","2019-09-09","No",null,null,"External"]
[null,null,null,null,null,"2019-06-12T11:25:00","2019-09-09","Deficiency","PSC Insp.","PSC Inspection","Accumulator launching appliance for R/B and L/R - not ready to use due to no pressure","LSA / FFA","LSA / FFA Appliances","Equipment Related",null,null,"Life saving appliances","Asia and the Pacific","Pressure was increase and rectified before departure.","2019-09-09",null,"Completed","2019-09-09","No",null,null,"External"]
[null,null,null,null,null,"2019-12-06T11:32:53","2019-10-28","Deficiency","PSC Insp.","PSC Inspection","Auxiliary machinery spaces which do not contain machinery having a pressure lubrication system and where storage of combustibles is prohibited, such as; steering gear room. Found bunker fuel samples in the emergency steering space. Samples were moved to forward paint locker.","Miscellaneous","MARPOL Related","Equipment Related",null,null,"Dangerous Goods","USCG","All bunker samples were move to fwd paint locker before departure.","2019-10-28",null,"Completed","2019-10-28","No",null,null,"External"]
[null,null,null,null,null,"2019-06-12T11:41:54","2019-10-28","Deficiency","PSC Insp.","PSC Inspection","Ventilation ducts shall be of stell or equivalent material. Found a section in the emergency steering space that is corroded through on the ventilation ducts","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related",null,null,"Structural condition","USCG","The corroded section of ventilation duct was repaired by fitting/welding with 2mm sheet metal and rectified before departure.","2019-11-28",null,"Completed","2019-10-30","No",null,null,"External"]
[null,null,null,null,null,"Wed Dec 11 2019 12:46:42 GMT+0000 (Coordinated Universal Time)","2019-10-10","Deficiency","Ship Staff","Ship Staff Insp.","BALLAST COMPUTER AT SHIP'S OFFICE MALFUNCTION/NO POWER","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Replaced defective berg computer on cargo office","2019-12-31","OFFICE PO","Completed","2019-12-18","No",null,null,"Internal"]
[null,null,null,null,null,"Wed Dec 11 2019 12:38:47 GMT+0000 (Coordinated Universal Time)","2019-10-06","Deficiency","Ship Staff","Ship Staff Insp.","Defective FCM front module","Main Engine ","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Replaced defective FCM front module of AELO purifier","2019-12-31","KALA190194","Completed","2019-12-19","No",null,null,"Internal"]
[null,null,null,null,null,"2019-12-12T12:36:21","2019-12-08","Critical Equipment,Deficiency","Ship Staff","Ship Staff Insp.","Damage throttle cable astern and ahead of rescue boat","Critical Equip.","Emgcy. Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Raise RO","2019-12-31","KALA190255","Completed","2019-12-21","No",null,null,"Internal"]
[null,null,null,null,null,"23/12/2019 12:23:22 PM","2019-09-14","Deficiency","Ship Staff","Ship Staff Insp.","Clock not synchronize on Bridge engine movement order","Nav & comm. equip.","Communication","Equipment Related",null,null,"Not Applicable","Not Applicable","Immediately synchronized clock at bridge engine movement to local time and utc.","2019-09-14",null,"Completed","2019-09-14","No",null,null,"Internal"]
[null,null,null,null,null,"Wed Dec 11 2019 12:13:44 GMT+0000 (Coordinated Universal Time)","2019-09-13","Deficiency","Ship Staff","Ship Staff Insp.","Wasted  anode of low and high sea chest","Hull & Tanks","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","RO raised","2019-12-31","KALA 190175","Completed","2019-12-17","No",null,null,"Internal"]
[null,null,null,null,null,"Wed Dec 11 2019 12:31:08 GMT+0000 (Coordinated Universal Time)","2019-10-09","Deficiency","Ship Staff","Ship Staff Insp.","Defective pressure gauge","Miscellaneous","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","renewed with new spare","2019-12-31","KALA190198","Completed","2019-12-18","No",null,null,"Internal"]
[null,null,null,null,null,"Wed Dec 11 2019 12:36:30 GMT+0000 (Coordinated Universal Time)","2019-10-03","Deficiency","Ship Staff","Ship Staff Insp.","Non working davit(bunker davit Port & stbd)","Deck Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","same item previous report  raw 18","2019-12-31","KALA190193","Completed","2019-12-25","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["LSA / FFA Appliances",8]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["MARPOL Related",9]
["ISM Related",7]
["ISPS Related",10]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Condn of Class / Memo",null,5]
["Critical Equipment",null,4]
["Deficiency",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":21,"n_cols":3,"rows_kept":21,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation ",null,12]
["Air Comp.",null,8]
["Aux. Engine",null,4]
["Aux. Mach.",null,7]
["Boiler",null,5]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck Mach.",null,18]
["Deck Pipe / Fittings",null,20]
["Documentation",null,21]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Main Engine ",null,3]
["Miscellaneous",null,22]
["Nav & comm. equip.",null,11]
["ER Pipes, valves & fittings",null,9]
["Purifier",null,6]
["Mooring Mach.",null,15]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":16,"n_cols":2,"rows_kept":16,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Others (Eg. Insurance etc.)",12]
["Engineering Audit",16]
["Flag State Insp.",5]
["Ship Staff Insp.",15]
["IT Audit",10]
["OM Insp. (Eg. SIRE, CDI etc.)",6]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["PSC Inspection",4]
["Suptd. Insp.",13]
["Terminal Insp.",11]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":9,"n_cols":3,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["Others (Eg. Insurance etc.)",null,9]
["FSC Inspector",null,5]
["Owner / Marine / Tech. Suptd.",null,3]
["PSC Insp.",null,6]
["Ship Staff",null,2]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["94","KALAMAZOO (26-11-2019)","94_1574745544777.xlsm"]