{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":25,"n_cols":28,"rows_kept":25,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","31-Dec-2019",null,null,"Ship Name","ARTEMIS (27-12-2019)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,7135,"40_Wed Dec 11 2019 02:58:19 GMT+0000","2019-08-20","Breakdown","Ship Staff","Ship Staff Insp.","AE 1 Centrifugal Filter Body damaged","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Wrong spare part received under previous PO#MZHU190208.\nEquipment isolated until spares are received.\n\nVessel comment: Aux engine fitted with additional oil max centrifugal filter which is in continuous operation and regularly being cleaned. Sump Oil condition regularly being monitored on weekly basis for TBN, viscosity and water content.","2020-02-29","MZHU190372","Waiting spare",null,"No","No","No","Internal","Based on supplier readiness advice, ordered part is expected to be ready in 75 days from date of order confirmation. (tentatively end Feb 2020).  Since the equipment is isolated, you should closely monitor the condition of the lub oil and carry out purification using the LO purifier, when the AE is shut down."]
[null,null,null,null,7989,"40_Wed Dec 18 2019 07:10:36 GMT+0000","2019-12-01","Breakdown","Ship Staff","Ship Staff Insp.","Aux Engine No. 1 Exhaust gas inlet to TC temperature sensor for remote indication  malfunction.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Monitoring TC inlet Temperature  by local temperature gauge  and requistion has been raised for spare part as vessel is out of stock for temperature sensor.","2020-01-30","MZHU 190380","Waiting spare",null,"No","No","No","External","Order ready at Japan. Will arrange supply to vessel at convenient port."]
[null,null,null,null,8074,"40_Wed Dec 18 2019 10:20:32 GMT+0000","2019-12-02","","Ship Staff","Ship Staff Insp.","SHIP\"S PERSONNEL ELEVATOR OVER TRAVEL SWITCH  DAMAGE","Accommodation","ISM Related","Equipment Related","","","","","BROKERN SWITCH  REPAIRED BY USING LOCKTITE  AND REQUISITION HAS BEEN RAISED FOR NEW SWITCH.","2020-02-25","MZHU 190378","Waiting spare",null,"No","No","No","External","Based on VFF, this RO is in processing stage."]
[null,null,null,null,8076,"40_Wed Dec 18 2019 10:31:14 GMT+0000","2019-12-09","Defect","Ship Staff","Ship Staff Insp.","2 PORT CARGO TANK LEVEL GAUGE MALFUNCTIONING / ERROR, SHOWING INCORRECT READING.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","INFORMED MUSSASINO (MAKER), AWAITING REPLY","2020-02-09","","Not Started",null,"No","No","No","External","Pls keep this office updated once you receive response from maker."]
[null,null,null,null,8077,"40_Wed Dec 18 2019 10:34:55 GMT+0000","2019-12-10","Defect","Ship Staff","Ship Staff Insp.","CARGO /BALLAST VALVE REMOTE HYDRAULIC SYSTEM ACCUMULATOR NITROGEN CHARGING ADAPTOR PIN DAMAGE.","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","RO RAISED FOR NEW ADAPTOR","2020-02-10","MZHU 190391","Waiting spare",null,"No","No","No","External","Based on VFF this RO# is still in processing stage."]
[null,null,null,null,9323,"40_19/12/2019 5:49:08 PM","2019-12-17","Defect","Ship Staff","Ship Staff Insp.","SG #2 MOTOR CONTROL  AMP PCB  FOUND FAULTY","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","PCB LANDED FOR REPAIR AT FUJAIRAH, RO RAISED FOR SPARE PCB ","2020-01-25","","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,null,"40_01/01/2020 12:01:47 AM","2019-12-31","Defect","Ship Staff","Ship Staff Insp."," Engine control  room alarm printer out of order.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Requisition will be raised  in PAL for year 2020","2020-01-20",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"40_01/01/2020 12:14:19 AM","2019-12-31","Defect","Ship Staff","Ship Staff Insp.","Cargo manifold valve and filing valve remote indication malfunction due to faulty potentiometer and micro switch.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Valve position being monitored locally and RO has been raised for spare parts.. ","2020-01-31","MZHU190387","Waiting spare",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":26,"n_cols":28,"rows_kept":26,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","31-11-2019",null,null,"Ship Name","ARTEMIS (27-12-2019)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,5557,"40_25/10/2019 12:42:11 PM","2019-08-20","Defect","Ship Staff","Ship Staff Insp.","fire and GS pump mechanical seal leak and submerged bearing  damage","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","pump repaired with used spares and new requistion has been  for spare parts.","2019-11-10","MZHU 190250","Completed","2019-11-25","No","No","No","Internal","Order was supplied on board during vessel docking at Keppel Shipyard (SG) on 15112019. Presume the supplied parts are being stored on board as spares.  What is the current operational status of the pump after repaired with used parts?  If all is well, you should consider closing this defect."]
[null,null,null,null,5558,"40_25/10/2019 12:51:04 PM","2019-08-20","Breakdown","Ship Staff","Ship Staff Insp.","AE 1 L.O. centifugal fiter body cracked.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","equipment isolated and requisition has been raised for the same.","2020-03-15","MZHU190208","Completed","2019-11-25","No","No","No","Internal","Item 2  - supplied on board on 05112019 @ Singapore.\nItem 1 - expected readiness on 05th March 2020"]
[null,null,null,null,5559,"40_25/10/2019 12:56:31 PM","2019-09-09","Breakdown","Ship Staff","Ship Staff Insp.","Aux boiler feed water pump #1 impeller, mechanical seal damaged.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","repaired impellers and Mechanical seal converted to gland packing , pump tested and kept on stby.Requistion has been raised for the spare parts. mech seal received at singapore on 15/09/2019","2019-11-10","MZHU190267","Completed","2019-11-10","No","No","No","Internal","Based on VFF, order was supplied on board at Dry-dock on 08112019 but status code still showing \"Waiting Spare\".  Have the pump been operated or still kept on stby?"]
[null,null,null,null,5560,"40_25/10/2019 1:01:57 PM","2019-10-04","Breakdown","Ship Staff","Ship Staff Insp.","LPG  Ref C.S.W. Pump impeller, mech seal, line bearing and mouth rings damged","E/R - Aux. Mach.","Cargo / Ballast Systems","Equipment Related","","","","","mech seal replaced with new spare mech seal.fabricated line bearing, mouth rings buildup and machined.Pump assembled and put into service. Requisition for complete  new pump has been created.","2019-11-10","MZHU 190302","Completed","2019-12-18","No","No","No","Internal","Based on VFF, requisition is pending approval.  How is the performance of the re-built pump? If all is well, you can close-out this defect for now.\n18122019 - T.Supt agreed that this defect can be closed-out for now since the pump is running fine. New pump will be supplied in 2020 once budget is approved."]
[null,null,null,null,5561,"40_25/10/2019 1:11:33 PM","2019-10-21","Breakdown","Ship Staff","Ship Staff Insp.","AC/DC converter for AE 2 control system damaged","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Requisition has been raised for the same","2019-11-10","MZHU190334","Completed","2019-11-10","No","No","No","Internal","Order was supplied on board dry-docking @ Keppel SG on 05112019. Presume AC/DC converter for AE2 has been replaced.\nIf not, pls advice reason for delay in replacing same."]
[null,null,null,null,5562,"40_26/10/2019 7:12:18 PM","2019-10-26","Breakdown","Ship Staff","Ship Staff Insp.","Fan damaged of Meat room evaporator.","Elect. Mach. & Equip.","MLC Related","Equipment Related","","","","","All meat shifted to  fish room urgent requisition has been raised for new fan set.","2019-11-05","MZHU 190335","Completed","2019-11-09","No","No","No","Internal","Order was supplied on board on 08112019 @ Singapore during D/D. Why does the status code still indicate \"waiting spare\". We presume the faulty fan should have been replaced. If not, when do you plan to do so?"]
[null,null,null,null,5563,"40_30/10/2019 2:52:57 PM","2019-10-29","Non Conformity","Ship Staff","Ship Staff Insp.","Stbd life boad davit pneumatic master valve faulty.","LSA / FFA","LSA / FFA Appliances","Equipment Related","","","","","Dismantled and found mechanism missing. Urgent requisition has been raised for new Master valve..","2019-12-15","MZHU 190337","Completed","2019-11-22","Yes","No","No","Internal","Based on VFF, this requisition was Cancelled by Tech. Supt. on 06122019. Pls advice current status of the pneumatic master valve and operational status of the davit."]
[null,null,null,null,5564,"40_25/10/2019 1:06:27 PM","2019-10-13","Breakdown","Ship Staff","Ship Staff Insp.","IGG C.S.W. Pump  Electrical motor damaged","Inert Gas","Cargo / Ballast Systems","Equipment Related","","","",""," requistion has been raised for new EL motor and damaged motor landed for rewinding.","2019-10-22","MZHU190331","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,8075,"40_Wed Dec 18 2019 10:25:32 GMT+0000","2019-12-01","Breakdown","Ship Staff","Ship Staff Insp.","EL MOTOR DAMAGE FOR CALORIFIER  HOT WATER CIRCULATION PUMP","E/R - Aux. Mach.","MLC Related","Equipment Related","","","","","STANDBY PUMP IN OPERATION AND REQUISITION HAS BEEN RAISED FOR NEW EL MOTOR.","2020-01-28","MZHU 190379","Completed","2019-12-24","No","No","No","External","Order is being arranged at Fujairah on 21/12/2019"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["LSA / FFA Appliances",8]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":379,"n_cols":3,"rows_kept":379,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",10160]
["1.10","Low",10169]
["1.11","Low",10170]
["1.12","Low",10171]
["1.13","Low",10172]
["1.14","Low",10173]
["1.15","Low",10174]
["1.16","Low",10176]
["1.17","Low",10177]
["1.18","Low",10178]
["1.19","Low",10179]
["1.2","Low",10161]
["1.20","Low",10180]
["1.21","",10181]
["1.22","Low",10183]
["1.23","Low",10184]
["1.24","Low",10185]
["1.25","Low",10186]
["1.26","Low",10187]
["1.3","Low",10162]
["1.4","Low",10163]
["1.5","Low",10164]
["1.6","Low",10165]
["1.7","Low",10166]
["1.8","Low",10167]
["1.9","Low",10168]
["1.99","High",16296]
["10.1","Medium",10354]
["10.10","High",10363]
["10.11","Medium",10364]
["10.12","Very High",10365]
["10.13","Very High",10366]
["10.14","Medium",10367]
["10.15","Low",10368]
["10.16","Very High",10369]
["10.17","Very High",10370]
["10.18","High",10371]
["10.19","Very High",10372]
["10.2","Low",10355]
["10.20","High",10373]
["10.21","Medium",10374]
["10.22","Low",10375]
["10.23","Medium",10376]
["10.24","Low",10377]
["10.25","Very High",10378]
["10.26","High",10379]
["10.27","Medium",10380]
["10.28","Low",10381]
["10.29","Medium",10382]
["10.3","Medium",10356]
["10.30","High",10383]
["10.31","Very High",10384]
["10.32","Very High",10385]
["10.33","High",10386]
["10.34","High",10387]
["10.35","Very High",10388]
["10.36","Very High",10389]
["10.37","Medium",10390]
["10.38","Medium",10391]
["10.39","High",10392]
["10.4","High",10357]
["10.40","Medium",10393]
["10.41","Medium",10394]
["10.42","Medium",10395]
["10.43","Medium",10396]
["10.44","Medium",10397]
["10.45","Very High",10398]
["10.46","High",10399]
["10.47","Medium",10400]
["10.48","High",10401]
["10.49","Medium",10402]
["10.5","Low",10358]
["10.50","High",10403]
["10.51","Low",10404]
["10.52","Medium",10405]
["10.53","Medium",10406]
["10.54","High",10407]
["10.55","Low",10408]
["10.6","Very High",10359]
["10.7","Medium",10360]
["10.8","Medium",10361]
["10.9","Medium",10362]
["10.99","High",10409]
["11.1","High",10313]
["11.10","Medium",10322]
["11.11","Very High",10323]
["11.12","Low",10324]
["11.13","Low",10325]
["11.14","Medium",10326]
["11.15","Low",10327]
["11.16","Low",10328]
["11.17","Low",10329]
["11.2","Medium",10314]
["11.3","Medium",10315]
["11.4","Very High",10316]
["11.5","Medium",10317]
["11.6","Medium",10318]
["11.7","High",10319]
["11.8","Low",10320]
["11.9","Low",10321]
["11.99","High",10330]
["12.1","High",10331]
["12.10","High",10341]
["12.11","High",10342]
["12.12","High",10343]
["12.13","High",10344]
["12.14","High",10345]
["12.15","High",10346]
["12.16","High",10347]
["12.17","High",10348]
["12.18","High",10349]
["12.19","High",10350]
["12.2","High",10332]
["12.20","High",10351]
["12.21","High",10352]
["12.3","High",10334]
["12.4","High",10335]
["12.5","High",10336]
["12.6","High",10337]
["12.7","High",10338]
["12.8","High",10339]
["12.9","High",10340]
["12.99","High",10353]
["2.1","Very High",10190]
["2.1.9","Very High",16297]
["2.10","Medium",10198]
["2.11","Medium",10199]
["2.12","Low",10200]
["2.13","Low",10201]
["2.14","Low",10202]
["2.15","Low",10203]
["2.16","Medium",10204]
["2.2","Medium",10191]
["2.3","High",10189]
["2.4","Medium",10192]
["2.5","Medium",10193]
["2.6","Low",10194]
["2.7","High",10195]
["2.8","High",10196]
["2.9","Medium",10197]
["2.99","High",10205]
["3.1","High",10206]
["3.2","Very High",10207]
["3.3","High",10208]
["3.4","Low",10188]
["3.5","Medium",10209]
["3.6","High",10210]
["3.7","Very High",10211]
["3.8","Very High",10212]
["3.99","High",10213]
["4.1","High",10214]
["4.10","High",10223]
["4.11","Medium",10224]
["4.12","Very High",10225]
["4.13","Very High",10226]
["4.14","Very High",10227]
["4.15","Very High",10228]
["4.16","Very High",10229]
["4.17","Very High",10230]
["4.18","Very High",10231]
["4.19","Low",10232]
["4.2","Medium",10215]
["4.20","Very High",10233]
["4.21","High",10234]
["4.22","Low",10235]
["4.23","High",10236]
["4.24","High",10237]
["4.25","Low",10238]
["4.26","Low",10239]
["4.27","High",10240]
["4.3","Medium",10216]
["4.4","High",10217]
["4.5","Very High",10218]
["4.6","Medium",10219]
["4.7","High",10220]
["4.8","Medium",10221]
["4.9","Medium",10222]
["4.99","High",10241]
["5.1","Very High",10410]
["5.10","High",10419]
["5.11","Low",10420]
["5.12","Medium",10421]
["5.13","High",10422]
["5.14","Very High",10423]
["5.15","Medium",10424]
["5.16","Medium",10425]
["5.17","Very High",10426]
["5.18","High",10427]
["5.19","Medium",10428]
["5.2","Very High",10411]
["5.20","Medium",10429]
["5.21","Medium",10430]
["5.22","High",10432]
["5.23","Very High",10433]
["5.24","Very High",10434]
["5.25","Medium",10435]
["5.26","Medium",10436]
["5.27","Medium",10437]
["5.28","Very High",10438]
["5.29","High",10439]
["5.3","Low",10412]
["5.30","High",10440]
["5.31","High",10441]
["5.32","High",10442]
["5.33","High",10443]
["5.34","Low",10444]
["5.35","Medium",10445]
["5.36","Low",10446]
["5.37","Low",10447]
["5.38","High",10448]
["5.39","Very High",10449]
["5.4","High",10413]
["5.40","Very High",10450]
["5.41","Very High",10451]
["5.42","Medium",10452]
["5.43","High",10453]
["5.44","High",10454]
["5.45","Medium",10457]
["5.46","Medium",10458]
["5.47","Low",10459]
["5.48","Medium",10460]
["5.5","Low",10414]
["5.6","Low",10415]
["5.7","Medium",10416]
["5.8","Medium",10417]
["5.9","Very High",10418]
["5.99","High",10461]
["6.1","Medium",10242]
["6.10","Low",10251]
["6.11","High",10252]
["6.12","Medium",10253]
["6.13","Low",10254]
["6.14","High",10255]
["6.15","High",10256]
["6.16","Very High",10257]
["6.17","Very High",10258]
["6.18","Medium",10259]
["6.19","Low",10260]
["6.2","High",10243]
["6.20","Medium",10261]
["6.21","High",10262]
["6.22","Medium",10263]
["6.3","Low",10244]
["6.4","High",10245]
["6.5","Low",10246]
["6.6","Medium",10247]
["6.7","High",10248]
["6.8","High",10249]
["6.9","Low",10250]
["6.99","High",10264]
["7.1","High",10265]
["7.10","High",10274]
["7.11","High",10275]
["7.12","High",10276]
["7.13","Medium",10277]
["7.14","Medium",10278]
["7.15","High",10279]
["7.16","High",10280]
["7.17","High",10281]
["7.2","High",10266]
["7.3","Low",10267]
["7.4","Low",10268]
["7.5","Low",10269]
["7.6","Medium",10270]
["7.7","Low",10271]
["7.8","High",10272]
["7.9","High",10273]
["7.99","High",10282]
["8.1","Very High",10462]
["8.10","Very High",10471]
["8.11","Very High",10472]
["8.12","Medium",10473]
["8.13","High",10474]
["8.14","Very High",10475]
["8.15","Medium",10476]
["8.16","Medium",10477]
["8.17","Very High",10478]
["8.18","High",10479]
["8.19","Very High",10480]
["8.2","Medium",10463]
["8.20","Very High",10481]
["8.21","Very High",10482]
["8.22","High",10483]
["8.23","Medium",10484]
["8.24","High",10485]
["8.25","High",10486]
["8.26","Medium",10487]
["8.27","Medium",10488]
["8.28","High",10489]
["8.29","Medium",10491]
["8.3","Medium",10464]
["8.30","Very High",10492]
["8.31","Very High",10493]
["8.32","High",10494]
["8.33","High",10495]
["8.34","Very High",10496]
["8.35","Very High",10497]
["8.36","Very High",10498]
["8.37","Very High",10500]
["8.38","Very High",10501]
["8.39","Very High",10502]
["8.4","Medium",10465]
["8.40","Very High",10503]
["8.41","Very High",10504]
["8.42","Very High",10505]
["8.43","Very High",10506]
["8.44","Medium",10508]
["8.45","High",10509]
["8.46","High",10510]
["8.47","Medium",10511]
["8.48","Very High",10512]
["8.49","Medium",10513]
["8.5","Medium",10466]
["8.50","High",10514]
["8.51","Very High",10515]
["8.52","Very High",10516]
["8.53","Very High",10517]
["8.54","High",10518]
["8.55","High",16222]
["8.56","Very High",16223]
["8.57","Very High",16224]
["8.58","Very High",16225]
["8.59","Medium",16226]
["8.6","Very High",10467]
["8.60","Medium",16227]
["8.61","Medium",16228]
["8.62","Very High",16229]
["8.63","Very High",16230]
["8.64","High",16231]
["8.65","Very High",16232]
["8.66","Medium",16233]
["8.67","Medium",16234]
["8.68","Medium",16235]
["8.69","Very High",16236]
["8.7","High",10468]
["8.70","Very High",16237]
["8.71","Medium",16238]
["8.72","Very High",16239]
["8.73","Medium",16240]
["8.74","High",16241]
["8.75","High",16242]
["8.76","Medium",16243]
["8.77","Medium",16244]
["8.78","Medium",16245]
["8.79","Very High",16246]
["8.8","High",10469]
["8.9","Very High",10470]
["8.99","High",16266]
["9.1","Low",10283]
["9.10","Medium",10292]
["9.11","Medium",10293]
["9.12","Medium",10294]
["9.13","Low",10295]
["9.14","Medium",10296]
["9.15","Medium",10297]
["9.16","High",10298]
["9.17","High",10299]
["9.18","Low",10300]
["9.19","Low",10301]
["9.2","Very High",10284]
["9.20","Medium",10302]
["9.21","Medium",10303]
["9.22","Low",10304]
["9.23","Low",10305]
["9.24","Medium",10306]
["9.25","Low",10307]
["9.26","Low",10308]
["9.27","Low",10309]
["9.28","Medium",10310]
["9.29","Low",10311]
["9.3","Very High",10285]
["9.4","High",10286]
["9.5","High",10287]
["9.6","Low",10288]
["9.7","Medium",10289]
["9.8","Medium",10290]
["9.9","Medium",10291]
["9.99","High",10312]

{"sheet":"Equipment_list","index":7,"n_rows":27,"n_cols":3,"rows_kept":27,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation ",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["40","ARTEMIS (27-12-2019)","40_1577775811468.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":10,"n_cols":2,"rows_kept":10,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]