{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":22,"n_cols":28,"rows_kept":22,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","31-Dec-2019",null,null,"Ship Name","RIDGEBURY ALINA L (19-12-2019)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,4084,"35_22/10/2019 1:10:23 AM","2018-08-15","Defect","Ship Staff","Ship Staff Insp.","BOTH BOILER MODULATION IN CASCADE MODE","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related",10.35,"Very High","Not Applicable","Not Applicable","Recommendation from technician already tried still full automatic operation is not working. Further investigation required. 14/09/2019: changes done on Port boiler, air damper following increase in fuel pressure.  Stbd boiler in Cascade mode air damper hunting. 31/10/2019: Will check performance in MGO, No. 1 Boiler (stbd) air damper hunting in cascade mode after doing same adjustment as Port Boiler. 12/11/2019: Discharge at Thessalonki done in LSMGO, controls done in manual as smoke emission when change in load. 30/11/2019: Port boiler working fine in FO but Stbd boiler hunting. In LSMGO, both boilers were controlled manually as smoke emission during change of load. Both boiler working on auto on 6K mode but not modulating properly on 16 K mode","2020-01-31",null,"In progress",null,"No","No","No","Internal","Tech. Supt pls advice your plans to resolve this issue."]
[null,null,null,null,4171,"35_2019-08-01 01:10:23.000","2019-06-27","Defect","Ship Staff","Ship Staff Insp.","ACCOM LADDER NO 1 HOIST WINCH NOT WORKING PROPERLY AND MAKING THE LADDER VIBRATE WHILE LOWERING OR HEAVING UP CONDITION.            ","Miscellaneous","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","RO raised for new accom. Ladder #1 hoist winch gear box. RO No: RALI190238","2020-01-31","RALI190238","In progress",null,"No","No","No","Internal","Based on VFF, estimated readiness is 05/11/2019. Have requested Mr. Sikandar to check with supplier and revert with readiness advice."]
[null,null,null,null,4175,"35_2019-08-05 01:10:23.000","2019-07-10","Defect","Ship Staff","Ship Staff Insp.","No.2 Port bunker, high high level alarm float not fitted.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","To fit float. 20/08/2019 : No floats on board, no holes/penetration done in DD (Possible in 2016, tank may be having oil). Only wires laid out and jointed to avoid alarm. Float not on board. Will require hotwork. 15/10/2019: Awaiting requistion","2020-03-31","RALI190297","Deferred to D D",null,"No","No","No","Internal","Est. readiness of order is 05/12/2019. Technical Supt pls advice if job is  concurred for DD. If so, same should be closed out from this list and moved to dry-dock list, c/w specification / details."]
[null,null,null,null,4178,"35_2019-08-08 01:10:23.000","2019-08-23","Defect","Ship Staff","Ship Staff Insp.","Stbd boiler, Circulating pump outlet valve leaking.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","New valve recd in Fujairah: will change. As will require to depressurize aux.boiler, job would be carried out at next anchorage.","2020-01-31","RALI190266","Not Started",null,"No","No","No","Internal","Despite spares been supplied on board at Khorfakkan on 24092019, your status code still indicates \"Waiting Spares\". Pls revert with updated status on progress for valve renewal. Target date is also way overdue."]
[null,null,null,null,4180,"35_2019-08-10 01:10:23.000","2019-08-31","Defect","Ship Staff","Ship Staff Insp.","Aux.engine FO Inlet valves leaking.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","To renew all fuel valves of the aux.engs. Spares received.  Will require to black out. Planned for next confirmed anchorage","2020-01-31","RALI190266","Not Started",null,"No","No","No","Internal","Basis spares supplied on board at Khorfakkan on 24092019, pls advice when you plan to carry out the job, as the status code indicates \"Not started\". Any reason for the delay in carrying out same."]

{"sheet":"Completed","index":1,"n_rows":206,"n_cols":28,"rows_kept":206,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","31-11-2019",null,null,"Ship Name","RIDGEBURY ALINA L (19-12-2019)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,4085,"35_24/10/2019 9:27:12 AM","2018-11-13","Defect","Ship Staff","Ship Staff Insp.","Hyraulic oil leaking at Hauling winch motor on Stbd Hose handling Crane.          ","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","Hoisting Winch motor valve block renewed and crane operation tried out. ","2019-01-08","RALI180190","Completed","2019-01-07","No","No","No","Internal"]
[null,null,null,null,4170,"35_2019-03-03 09:27:11.995","2019-02-13","Defect","Ship Staff","Ship Staff Insp.","Port side provision crane ramp seal leaking.  ","Deck - Machinery","General Appearance","Equipment Related","8.5","Very High","","","DD Spec raised for the job.","2019-05-30","","Completed","2019-04-26","Yes","No","No","Internal"]
[null,null,null,null,4182,"35_2019-02-01 09:27:12.000","2019-01-08","Defect","Ship Staff","Ship Staff Insp.","No 2 HFO purifier Bowl found leaking, some noise observed during operation ","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Bowl cleaning carried out and vertical shaft bearings renewed","2019-01-12","","Completed","2019-01-10","No","No","No","Internal"]
[null,null,null,null,4183,"35_2019-02-02 09:27:11.995","2018-12-18","Defect","Ship Staff","Ship Staff Insp.","Fire line at manifold area found badly corroded needs to be replaced with new pipe line.","LSA / FFA","LSA / FFA Appliances","Equipment Related","11.4","Very High","","","Fire line renewed with new pipe line","2019-01-31","","Completed","2019-01-10","No","No","No","Internal"]
[null,null,null,null,4184,"35_2019-02-03 09:27:11.995","2018-12-18","Defect","Ship Staff","Ship Staff Insp.","Stbd Hose handling crane block - One sheave found frozen and not moving needs to be repaired.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","8.63","High","","","Frozen sheave made free. ","2019-01-31","","Completed","2019-01-10","No","No","No","Internal"]
[null,null,null,null,4185,"35_2019-02-04 09:27:11.995","2019-01-17","Defect","Ship Staff","Ship Staff Insp.","FWG SW outlet line after ejector got holed ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pipe to be removed and repaired by welding","2019-01-20","","Completed","2019-01-18","No","No","No","Internal"]
[null,null,null,null,4186,"35_2019-02-05 09:27:11.995","2018-12-18","Defect","Ship Staff","Ship Staff Insp.","Stbd side Gangway motor found not working, needs to be overhauled.","Deck - Machinery","General Appearance","Equipment Related","5.47","Medium","","","Gangway motor overhauled","2019-01-31","","Completed","2019-01-24","No","No","No","Internal"]
[null,null,null,null,4187,"35_2019-02-06 09:27:11.995","2018-12-18","Defect","Ship Staff","Ship Staff Insp.","Stbd side gangway found difficult to haul in, on investigation found fwd roller to the inward side found not rotating.","Deck - Machinery","General Appearance","Equipment Related","5.47","Medium","","","Stbd gangway sheaves made free.","2019-01-31","","Completed","2019-01-31","No","No","No","Internal"]
[null,null,null,null,4188,"35_2019-02-07 09:27:11.995","2019-01-29","Defect","Ship Staff","Ship Staff Insp.","AE#2 centrifugal oil-max filter support stand on crankcase door cracked","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Aux engine taken out of service, isolated and crankcase door crack rectified with weld repair.","2019-02-28","","Completed","2019-01-30","No","No","No","Internal"]
[null,null,null,null,4189,"35_2019-02-08 09:27:11.995","2019-01-07","Defect","Ship Staff","Ship Staff Insp.","HFO purifier no 2 observed to have abnormal noise while in operation","E/R - Boiler,E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","HFO no 2 purifier overhauled, shaft assembly inspected, bearings renewed upon establishing problem caused by worn out bearing.","2019-02-06","","Completed","2019-01-08","No","No","No","Internal"]
[null,null,null,null,4190,"35_2019-02-09 09:27:11.995","2019-01-29","Defect","Ship Staff","Ship Staff Insp.","COPT no 3 and water ballast pump turbine casing drain valve found leaking from flange ends.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.19","High","","","Both COPT no 3 and steam WBPT casing drain valves were renewed with gaskets. Valve renewed for COPT no 3 drain line.","2019-02-08","","Completed","2019-01-30","No","No","No","Internal"]
[null,null,null,null,4191,"35_2019-02-10 09:27:11.995","2019-01-30","Defect","Ship Staff","Ship Staff Insp.","OWS sight glass near 3-way valve found loosened out of place ","Critical Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Same sight glass was cleaned, thread cleaned, lubricated and fastened to the assembly with new gasket. ","2019-02-28","","Completed","2019-01-31","No","No","No","Internal"]
[null,null,null,null,4192,"35_2019-02-11 09:27:11.995","2019-02-07","Defect","Ship Staff","Ship Staff Insp.","Incinerator DO inlet copper pipe connection to the pressure switch found partially leaking.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Copper pipe connection renewed and leak rectified.","2019-02-28","","Completed","2019-02-08","No","No","No","Internal"]
[null,null,null,null,4193,"35_2019-02-12 09:27:11.995","2019-02-06","Defect","Ship Staff","Ship Staff Insp.","Aux-boiler no 1, starboard side gauge glass leaking.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Gauge glass renewed with a pressure tested one, leak rectified.","2019-03-05","","Completed","2019-02-07","No","No","No","Internal"]
[null,null,null,null,4194,"35_2019-02-13 09:27:11.995","2018-12-18","Defect","Ship Staff","Ship Staff Insp.","Fire line is having an insert near no 4 foam monitor, same to be renewed with new pipeline.","LSA / FFA","LSA / FFA Appliances","Equipment Related","11.4","Very High","","","Fire line section renewed with new pipeline.","2019-01-31","","Completed","2019-02-14","No","No","No","Internal"]
[null,null,null,null,4195,"35_2019-02-14 09:27:11.995","2019-02-04","Defect","Ship Staff","Ship Staff Insp.","Port side LT fresh water cooler sea water inlet reducer connection leaking.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related,External Factors","10.32","Very High","","","New reducer installed in place and LT cooler in use","2019-04-03","","Completed","2019-02-11","No","No","No","Internal"]
[null,null,null,null,4196,"35_2019-02-15 09:27:11.995","2019-02-05","Defect","Ship Staff","Ship Staff Insp.","LT fresh water cooler (port side) sea water inlet pressure gauge faulty","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","LT cooler (port side) isolated and pressure gauge renewed.","2019-04-04","","Completed","2019-02-09","No","No","No","Internal"]
[null,null,null,null,4197,"35_2019-02-16 09:27:11.995","2019-02-06","Defect","Ship Staff","Ship Staff Insp.","Aux-engines (1, 2 & 3) exhaust gas drain pipes water seal pot pipes wasted / partly broken.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","For all 3 aux-engines, old drain pipes taken out and fabricated new pipes, installed in place (3 locations)","2019-02-14","","Completed","2019-02-14","No","No","No","Internal"]
[null,null,null,null,4198,"35_2019-02-17 09:27:11.995","2019-02-19","Defect","Ship Staff","Ship Staff Insp.","Port LT cooler SW outlet pressure gauge faulty.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Port LT fresh water cooler isolated and SW outlet faulty pressure gauge installed with new one.","2019-04-18","","Completed","2019-02-23","No","No","No","Internal"]
[null,null,null,null,4199,"35_2019-02-18 09:27:11.995","2019-02-08","Defect","Ship Staff","Ship Staff Insp.","Section of Gratings at the entrance of Port side Hose handling crane platform found wasted.","Miscellaneous","General Appearance","Equipment Related","8.63","High","","","Wasted Grating section to be repired.","2019-03-09","","Completed","2019-02-25","No","No","No","Internal"]
[null,null,null,null,4200,"35_2019-02-19 09:27:11.995","2019-03-13","Defect","Ship Staff","Ship Staff Insp.","FWG ejector sea water inlet pressure gauge faulty.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pressure gauge renewed ","2019-05-12","","Completed","2019-03-14","No","No","No","Internal"]
[null,null,null,null,4201,"35_2019-02-20 09:27:11.995","2019-03-08","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Exhaust pipings on funnel smoke stack pipes for No.3 AE, ME exhaust gas leaking due to wastage. Flame screens found damaged.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Shall raise item fo DD","2019-04-30","","Completed","2019-04-27","No","No","No","Internal"]
[null,null,null,null,4202,"35_2019-02-21 09:27:11.995","2019-03-03","Defect","Ship Staff","Ship Staff Insp.","Flashback arrestor faulty (partially leaking) for the oxygen bottle connection at the poop deck designated bottle space. Need renewal.","Miscellaneous","LSA / FFA Appliances","Equipment Related,Inappropriate Procedure","5.26","Medium","","","Flash back arrestor to be renewed upon receiving the spare onboard. (Requisition No: RALI190115)","2019-06-02","RALI190115","Completed","2019-04-02","No","No","No","Internal"]
[null,null,null,null,4203,"35_2019-02-22 09:27:11.995","2019-03-20","Defect","Ship Staff","Ship Staff Insp.","Elevator Car door defective. Unit out of operation temporarily  ","Accommodation","General Appearance","Equipment Related","10.32","Very High","","","Troubleshooting was carried-out. Some of the components  in the car door controller PCB were found burned. ","2019-04-05","RALI190116","Completed","2019-04-04","No","No","No","Internal"]
[null,null,null,null,4204,"35_2019-02-23 09:27:11.995","2019-02-27","Defect","Ship Staff","Ship Staff Insp.","COPT steam (common line) warming up not holding.  ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","Warming up valve need overhaul / renewal.","2019-05-26","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,4205,"35_2019-02-24 09:27:11.995","2018-10-27","Defect","Ship Staff","Ship Staff Insp.","DG FO AUTO FILTER NOT HOLDING ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Change-over valve overhauled fitted with new seals","2019-03-26","RALI180226","Completed","2019-04-23","No","No","No","Internal"]
[null,null,null,null,4206,"35_2019-02-25 09:27:11.995","2019-02-04","Defect","Ship Staff","Ship Staff Insp.","Port side LT fresh water cooler sea water inlet reducer connection leaking.  ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Renewal of the sea water reducer connection","2019-04-03","","Completed","2019-04-26","No","No","No","Internal"]
[null,null,null,null,4207,"35_2019-02-26 09:27:11.995","2019-02-25","Defect","Ship Staff","Ship Staff Insp.","Atmospheric condenser sea water inlet and outlet pipes (above boiler feed water tank) have holed section at the pipe length and on the elbow section.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","New sections fitted","2019-05-19","","Completed","2019-04-25","No","No","No","Internal"]
[null,null,null,null,4208,"35_2019-02-27 09:27:11.995","2019-02-27","Defect","Ship Staff","Ship Staff Insp.","COPT steam (common line) warming up not holding. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","Valve renewed.","2019-05-26","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,4209,"35_2019-02-28 09:27:11.995","2019-02-27","Defect","Ship Staff","Ship Staff Insp.","Exhasut gas economiser outlet temperature local thermometer broken","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","",".  Renewed with Spares and no leaks any more","2019-05-26","","Completed","2019-04-25","No","No","No","Internal"]
[null,null,null,null,4210,"35_2019-03-01 09:27:11.995","2018-02-20","Defect","Ship Staff","Ship Staff Insp.","Doppler main display unit not operational since 20-FEB-2018","Navigation - Echo Sounder / Speed Log","Navigation","Equipment Related","4.7","High","","","DD Spec raised for the job","2019-04-30","RALI180029","Completed","2019-04-26","Yes","No","No","Internal"]
[null,null,null,null,4211,"35_2019-03-02 09:27:11.995","2019-02-12","Defect","Ship Staff","Ship Staff Insp.","Port side Hose handling crane Jib pin Assembly bearing found broken","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.5","Very High","",""," DD Spec raised for the job.","2019-05-30","","Completed","2019-04-26","Yes","No","No","Internal"]
[null,null,null,null,4212,"35_2019-04-29 09:27:11.995","2019-05-11","Defect","Ship Staff","Ship Staff Insp.","Port side lifeboat steering unit not operational.  ","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.28","Very High","","","new spare full steering mechanism fitted","2019-06-30","RALI190170","Completed","2019-06-25","No","No","No","Internal"]
[null,null,null,null,4213,"35_2019-04-30 09:27:11.995","2019-05-22","Defect","Ship Staff","Ship Staff Insp.","Hydraulic valve OT 108 in Cargo system showing 20% open even when it the valve is fully close. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Valve position indicator defective. RO raised.","2019-06-30","RALI190215","Completed","2019-06-25","No","No","No","Internal"]
[null,null,null,null,4214,"35_2019-05-01 09:27:11.995","2019-05-22","Critical Equipment","Ship Staff","Ship Staff Insp.","No.4 port cargo tank main valve found unoperational.  ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.21","High","","","RO raised ","2019-06-30","RALI190201","Completed","2019-06-25","No","No","No","Internal"]
[null,null,null,null,4215,"35_2019-05-02 09:27:11.995","2019-06-22","Defect","Ship Staff","Ship Staff Insp.","Port side bitter end pin found jam. ","Deck - Mooring Machinery","Mooring","Equipment Related","9.22","Low","","","Pin made free.","2019-06-29","","Completed","2019-06-28","No","No","No","Internal"]
[null,null,null,null,4216,"35_2019-05-03 09:27:11.995","2019-06-22","Defect","Ship Staff","Ship Staff Insp.","Oil found leaking from forward hydraullic valve connections going to bosun store  ","Deck - Machinery","Mooring","Equipment Related","5.35","Medium","","","One of the O ring was found damaged, replaced with new one.","2019-06-29","","Completed","2019-06-28","No","No","No","Internal"]
[null,null,null,null,4217,"35_2019-05-04 09:27:11.995","2019-06-12","Defect","Ship Staff","Ship Staff Insp.","Anchor lashing for one of the anchor found parted away ","Miscellaneous","Mooring","Equipment Related","5.11","Low","","","Old lashing replaced by new one.","2019-06-12","","Completed","2019-06-12","No","No","No","Internal"]
[null,null,null,null,4218,"35_2019-05-05 09:27:11.995","2019-06-13","Defect","Ship Staff","Ship Staff Insp.","Fire damper in provision store unable to kept in open condition ","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.14","Very High","","","Overhauled and rectified.","2019-06-15","","Completed","2019-06-15","No","No","No","Internal"]
[null,null,null,null,4219,"35_2019-05-06 09:27:11.995","2019-07-12","Defect","Ship Staff","Ship Staff Insp.","Port boiler feed line water leak  ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Section between inlet valve and control valve was found having crack, Crack repaired and pressure tested.","2019-07-23","","Completed","2019-07-23","No","No","No","Internal"]
[null,null,null,null,4220,"35_2019-05-07 09:27:11.995","2019-07-11","Defect","Ship Staff","Ship Staff Insp.","Port boiler uptake valve pneumatic block found leaking  ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Uptake valve removed, pneumatic block changed, o-rings changed, checked its operation by air, found satisfactory.","2019-07-23","","Completed","2019-07-14","No","No","No","Internal"]
[null,null,null,null,4221,"35_2019-05-08 09:27:11.995","2019-07-12","Defect","Ship Staff","Ship Staff Insp.","Aux feed line water leak ","Elect. Mach. & Equip.,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Suction pipe for no.2 Aux feed pump was found having crack, same section changed with newly fabricated pipeline.","2019-07-23","","Completed","2019-07-16","No","No","No","Internal"]
[null,null,null,null,4222,"35_2019-05-09 09:27:11.995","2019-07-15","Defect","Ship Staff","Ship Staff Insp.","Ballast eductor valve seat ring found damaged ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.8","Medium","","","New seat ring installed.","2019-07-18","","Completed","2019-07-18","No","No","No","Internal"]
[null,null,null,null,4223,"35_2019-05-10 09:27:11.995","2019-07-13","Defect","Ship Staff","Ship Staff Insp.","Emergency stop for COP line found having holes and air leaking. ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.56","Medium","","","LINE REPAIRED AND FITTED BACK","2019-07-20","","Completed","2019-07-18","No","No","No","Internal"]
[null,null,null,null,4224,"35_2019-05-11 09:27:11.995","2019-07-10","Breakdown","Ship Staff","Ship Staff Insp.","No.3 COPT governor defective unable to control speed ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Received new complete governor in suez, changed with the new ones.","2019-07-30","RALI190220/ RALI19022","Completed","2019-07-21","No","No","No","Internal"]
[null,null,null,null,4225,"35_2019-05-12 09:27:11.995","2019-07-10","Defect","Ship Staff","Ship Staff Insp.","Port boiler Exhaust gas leak","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","",""," Port  Main exhaust pipe a part of its section was found wasted between water collector and IG uptake branch pipe, dubbler fabricated for the same section and fitted in place, insulations were renewed.","2019-07-23","","Completed","2019-07-21","No","No","No","Internal"]
[null,null,null,null,4226,"35_2019-05-13 09:27:11.995","2019-04-28","Defect","Ship Staff","Ship Staff Insp.","Port HHC runner drum limiters not working ","Deck - Machinery","General Appearance","Equipment Related","8.26","High","","","Received spares in suez, changed the limit switch with  new ones.","2019-07-16","RALI190202","Completed","2019-07-30","No","No","No","Internal"]
[null,null,null,null,4227,"35_2019-05-14 09:27:11.995","2019-07-29","Defect","Ship Staff","Ship Staff Insp.","Goose neck abaft NRV on the IG to NO.3 cargo line found oil droplets spraying from it. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Valve overhauled and cleaned and spraying rectified","2019-08-05","","Completed","2019-07-30","No","No","No","Internal"]
[null,null,null,null,4228,"35_2019-05-15 09:27:11.995","2019-07-28","Defect","Ship Staff","Ship Staff Insp.","NO.1 AUS motor found leaking from the mechanical seal during discharging at Italy. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","New mechanical seal installed and the damaged one replaced.","2019-08-10","","Completed","2019-08-06","No","No","No","Internal"]
[null,null,null,null,4229,"35_2019-05-16 09:27:11.995","2019-08-07","Defect","Ship Staff","Ship Staff Insp.","Fire line found leaking from dresser coupling area ","Deck - Pipe / Fittings","LSA / FFA Appliances","Equipment Related","5.35","Medium","","","New packing installed to sustain the leak. ","2019-08-07","","Completed","2019-08-07","No","No","No","Internal"]
[null,null,null,null,4230,"35_2019-05-17 09:27:11.995","2019-08-07","Defect","Ship Staff","Ship Staff Insp.","Fire line found badly corroded on opening of dresser ","Deck - Pipe / Fittings","LSA / FFA Appliances","Equipment Related","5.35","Medium","","","coupling  Part of the line corroded badly was cut and a new piece was welded in line and tried out and found free of any leaks","2019-08-07","","Completed","2019-08-07","No","No","No","Internal"]
[null,null,null,null,4231,"35_2019-05-18 09:27:11.995","2019-04-28","Defect","Ship Staff","Ship Staff Insp.","ACB # 1 &2 Over current trip unit  faulty.  ","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","11.1","High","","","Shall renew when vsl anchored safely ","2019-08-31","RALI190165","Completed","2019-08-05","No","No","No","Internal"]
[null,null,null,null,4232,"35_2019-05-19 09:27:11.995","2019-08-02","Defect","Ship Staff","Ship Staff Insp.","AUS pump seal leaking. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Seal renewed with spare","2019-08-31","","Completed","2019-08-05","No","No","No","Internal"]
[null,null,null,null,4233,"35_2019-05-20 09:27:11.995","2019-08-02","Defect","Ship Staff","Ship Staff Insp.","FWG ejector pump leaking ","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pump overhauled","2019-08-31","","Completed","2019-08-07","No","No","No","Internal"]
[null,null,null,null,4234,"35_2019-05-21 09:27:11.995","2019-08-02","Defect","Ship Staff","Ship Staff Insp.","Main Feed Pump No.2 seal leaking ","E/R - Boiler","General Appearance","Equipment Related","10.32","Very High","","","To overhaul pump","2019-08-31","","Completed","2019-08-09","No","No","No","Internal"]
[null,null,null,null,4235,"35_2019-05-22 09:27:11.995","2019-08-08","Defect","Ship Staff","Ship Staff Insp.","Purifier feed water line leaking. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To repair/renew pipe","2019-08-30","","Completed","2019-08-08","No","No","No","Internal"]
[null,null,null,null,4236,"35_2019-05-23 09:27:11.995","2019-08-03","Defect","Ship Staff","Ship Staff Insp.","LT cooler No.2 dirty ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Cleaned cooler","2019-08-30","","Completed","2019-08-04","No","No","No","Internal"]
[null,null,null,null,4237,"35_2019-05-24 09:27:11.995","2019-08-10","Defect","Ship Staff","Ship Staff Insp.","Aux.blower No.2 starting in Auto.  ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Changed timers in the Aux.Blower panel","2019-08-31","","Completed","2019-08-12","No","No","No","Internal"]
[null,null,null,null,4239,"35_2019-05-26 09:27:11.995","2019-08-20","Defect","Ship Staff","Ship Staff Insp.","MAC No.3 LP piston found broken. ","E/R - Air Comp.,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To renew piston","2019-08-31","","Completed","2019-08-21","No","No","No","Internal"]
[null,null,null,null,4240,"35_2019-05-27 09:27:11.995","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Fwd breast winch gauge glass found leaking. ","Deck - Machinery","Mooring","Equipment Related","9.14","Medium","","","Old gauge glass removed and new gauge glass installed. Tested found no leaks","2019-08-21","","Completed","2019-08-21","No","No","No","Internal"]
[null,null,null,null,4241,"35_2019-05-28 09:27:11.995","2019-08-25","Defect","Ship Staff","Ship Staff Insp.","Hydraullic line for cargo tank valve found leaking from previous repair area","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.21","High","","","Small section of line cut and renewed with new pipe and a new connector.","2019-08-25","","Completed","2019-08-25","No","No","No","Internal"]
[null,null,null,null,4242,"35_2019-05-29 09:27:11.995","2019-08-28","Defect","Ship Staff","Ship Staff Insp.","One foam monitor valve found leaking","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.35","Medium","","","Valve overhauled, seat cleaned and boxed back,tested no leaks found. ","2019-08-28","","Completed","2019-08-28","No","No","No","Internal"]
[null,null,null,null,4243,"35_2019-05-30 09:27:11.995","2019-08-23","Defect","Ship Staff","Ship Staff Insp.","Stbd boiler blow down valve not working ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To renew valve, same being ordered to be delivered at Fujairah","2019-09-30","","Completed","2019-08-31","No","No","No","Internal"]
[null,null,null,null,4244,"35_2019-05-31 09:27:11.995","2019-06-02","Defect","Ship Staff","Ship Staff Insp.","AFT HPP observed not loading/unloading on different modes","Deck - Mooring Machinery","General Appearance","Equipment Related","9.14","Medium","","","Relay for high pressure mode defective, Spares received work in progress. 04/08/2019 Spares renewed with rec'd, tested satisfactory. Will observe and complete during  loading port","2019-08-16","","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,4245,"35_2019-06-01 09:27:11.995","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","Drain line on top of COPT platform has holes in many places. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","6.6","Medium","","","To repair/renew pipe, pipe cleared","2019-08-30","","Completed","2019-08-18","No","No","No","Internal"]
[null,null,null,null,4246,"35_2019-06-02 09:27:11.995","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","ER toilet, FW line leaking. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To repair/renew pipe","2019-08-31","","Completed","2019-08-22","No","No","No","Internal"]
[null,null,null,null,4247,"35_2019-06-03 09:27:11.995","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","Many of the ER drain/scuppers lines are holed. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To clear scupper, work started but would take time","2019-08-31","","Completed","2019-08-17","No","No","No","Internal"]
[null,null,null,null,4249,"35_2019-06-05 09:27:11.995","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","MAC NO.2 LP valve stud turning. ","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Rethreaded the casing and stud made to fit, M16 on the casing and M12 for head.","2019-08-31","","Completed","2019-08-30","No","No","No","Internal"]
[null,null,null,null,4250,"35_2019-06-06 09:27:11.995","2019-08-24","Defect","Ship Staff","Ship Staff Insp.","Crew toilet not working, line choked. ","Accommodation","General Appearance","Equipment Related","","","","","26/08/2013, Blocked line connection removed, blockage couldn't be accessed. Pipe removed by cutting and same filtted with clamps. Will require few fittings and clamps for future usage","2019-08-30","","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,4251,"35_2019-06-07 09:27:11.995","2019-08-25","Defect","Ship Staff","Ship Staff Insp.","Vaccum toilet vaccumarator Pump seal leaking","Accommodation","General Appearance","Equipment Related","","","","","Repaired","2019-08-30","","Completed","2019-08-25","No","No","No","Internal"]
[null,null,null,null,4252,"35_2019-06-08 09:27:11.995","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","Crew clean clothes laundary defective. ","Accommodation","MLC Related","Equipment Related","","","","","To rectify fault and if required order new machine","2019-08-31","","Completed","2019-08-29","No","No","No","Internal"]
[null,null,null,null,4253,"35_2019-06-09 09:27:11.995","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","Drain line on top of COPT platform has holes in many places. ","Cargo Mach.,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","6.6","Medium","","","To repair/renew pipe, pipe cleared","2019-08-31","","Completed","2019-08-28","No","No","No","Internal"]
[null,null,null,null,4254,"35_2019-06-10 09:27:11.995","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","ER toilet, FW line leaking ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To repair/renew pipe, pipe cleared","2019-08-31","","Completed","2019-08-22","No","No","No","Internal"]
[null,null,null,null,4255,"35_2019-06-11 09:27:11.995","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","Many of the ER drain/scuppers lines are holed.  ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To clear scupper, work started but would take time","2019-08-31","","Completed","2019-08-17","No","No","No","Internal"]
[null,null,null,null,4256,"35_2019-03-04 09:27:11.995","2019-02-22","Defect","Ship Staff","Ship Staff Insp.","1P COT fwd programmable COW machine found not working.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.34","High","",""," NEED TO OVERHAUL.","2019-03-30","","Completed","2019-04-06","No","No","No","Internal"]
[null,null,null,null,4257,"35_2019-03-05 09:27:11.995","2019-02-26","Defect","Ship Staff","Ship Staff Insp.","Oxygen/ Vapour pressure monitoring and alarm system not showing correct readings.  ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.31","High","","","O2 sensor and  All tubing inside the cabinet for O2 sensor needs replacement. RO raised.","2019-04-30","RALI190103, RALI 190104","Completed","2019-04-25","No","No","No","Internal"]
[null,null,null,null,4258,"35_2019-03-06 09:27:11.995","2019-02-26","Defect","Ship Staff","Ship Staff Insp.","Valve indication in CCR control panel for AUS No 1 & 2 found Very sluggish with respect to actual movement of valve in Pump room.  ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Needs to rectify control air leak in the system.","2019-04-30","","Completed","2019-04-25","Yes","No","No","Internal"]
[null,null,null,null,4259,"35_2019-03-07 09:27:11.995","2019-02-26","Defect","Ship Staff","Ship Staff Insp.","AUS Discharge control Valve for No 1 COP in P/R found leaking control air from booster relays.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Needs to rectify control air leak","2019-04-30","","Completed","2019-04-25","Yes","No","No","Internal"]
[null,null,null,null,4260,"35_2019-03-08 09:27:11.995","2019-02-26","Defect","Ship Staff","Ship Staff Insp.","COT High level and Low level alarm in Autrocargo tank radar gauging system unable to simulate testing.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.13","Medium","","","Shore technician service report(08aug2018) mentions unable to simulate Hi and Low alarm. System needs upgradation as per technician.","2019-04-30","","Completed","2019-04-25","Yes","No","No","Internal"]
[null,null,null,null,4261,"35_2019-03-09 09:27:11.995","2019-02-28","Defect","Ship Staff","Ship Staff Insp.","Hydraulic valve OT 111 & OT 112 in Cargo system is unable to close fully, 20 % remains open. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.21","High","","","NEED TO INVESTIGATE.","2019-04-30","","Completed","2019-04-25","Yes","No","No","Internal"]
[null,null,null,null,4262,"35_2019-03-10 09:27:11.995","2019-03-03","Defect","Ship Staff","Ship Staff Insp.","1S COT aft programmable COW machine found not working. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.34","High","","","NEED TO OVERHAUL","2019-04-30","","Completed","2019-04-06","No","No","No","Internal"]
[null,null,null,null,4263,"35_2019-03-11 09:27:11.995","2019-03-03","Defect","Ship Staff","Ship Staff Insp.","1S COT fwd programmable COW machine found not working. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.34","High","","","NEED TO OVERHAUL.","2019-04-30","","Completed","2019-04-06","No","No","No","Internal"]
[null,null,null,null,4264,"35_2019-03-12 09:27:11.995","2019-03-03","Defect","Ship Staff","Ship Staff Insp.","6P COT fwd programmable COW machine found not working.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.34","High","","","NEED TO OVERHAUL","2019-04-30","","Completed","2019-04-06","No","No","No","Internal"]
[null,null,null,null,4265,"35_2019-03-13 09:27:11.995","2019-03-03","Defect","Ship Staff","Ship Staff Insp.","5S COT fwd programmable COW machine found not working.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.34","High","","","NEED TO OVERHAUL","2019-04-30","","Completed","2019-04-06","No","No","No","Internal"]
[null,null,null,null,4266,"35_2019-03-14 09:27:11.995","2019-03-03","Defect","Ship Staff","Ship Staff Insp.","Hydraulic valve OP 225 in Cargo system showing 20% open even when it the valve is fully close","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.21","High","",""," Valve position indicator defective. RO raised.","2019-04-30","","Completed","2019-04-25","Yes","No","No","Internal"]
[null,null,null,null,4267,"35_2019-03-15 09:27:11.995","2019-03-03","Defect","Ship Staff","Ship Staff Insp.","IG Branch valve for 6P COT unable to close. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.24","Medium","","","Gear found slipping. Needs to Overhaul.","2019-04-30","","Completed","2019-04-30","No","No","No","Internal"]
[null,null,null,null,4268,"35_2019-03-16 09:27:11.995","2019-03-03","Defect","Ship Staff","Ship Staff Insp.","Draft Gauges are not matching with Actual draft reading. Error in the gauges are not consistent.  ","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","DD specs raised for the same. ","2019-04-30","","Completed","2019-04-25","Yes","No","No","Internal"]
[null,null,null,null,4269,"35_2019-03-17 09:27:11.995","2019-03-03","Defect","Ship Staff","Ship Staff Insp.","Ballast tank level Gauges are not matching with Actual soundings reading. Error in the gauges are not consistent. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.28","Medium","","","DD specs raised for the same. ","2019-04-30","","Completed","2019-04-25","Yes","No","No","Internal"]
[null,null,null,null,4270,"35_2019-03-18 09:27:11.995","2019-03-04","Defect","Ship Staff","Ship Staff Insp.","Valve indication in CCR control panel for AUS No 3 found not movining with respect to actual movement of valve in Pump room. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","NEED TO INVESTIGATE ","2019-04-30","","Completed","2019-04-25","Yes","No","No","Internal"]
[null,null,null,null,4271,"35_2019-03-19 09:27:11.995","2019-03-04","Defect","Ship Staff","Ship Staff Insp.","Needs to be landed for replacement with new Gas meter. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","5.23","Very High","","","Needs to be landed for replacement with new Gas meter.","2019-04-30","","Completed","2019-04-20","No","No","No","Internal"]
[null,null,null,null,4272,"35_2019-03-20 09:27:11.995","2019-03-04","Defect","Ship Staff","Ship Staff Insp.","The scupper plugs in use are of wrong size, Presently cement used for proper sealing.   ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","6.2","High","","","Derusting and painting of Scuppers to be done and RO to be raised for new Scupper plug.","2019-04-30","","Completed","2019-04-26","No","No","No","Internal"]
[null,null,null,null,4273,"35_2019-03-21 09:27:11.995","2019-03-05","Defect","Ship Staff","Ship Staff Insp.","Hydraulic box for Valves near 3W COT steam coils, below pipelines on Main deck Shows traces of leak on deck.  ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.21","High","",""," Needs to investigate further.","2019-04-30","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,4274,"35_2019-03-22 09:27:11.995","2019-03-05","Defect","Ship Staff","Ship Staff Insp.","Hydraulic box for Valves near 4W COT steam coils, below pipelines on Main deck Shows traces of leak on deck","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.21","High","","","Needs to investigate further.","2019-03-30","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,4275,"35_2019-03-23 09:27:11.995","2019-03-05","Defect","Ship Staff","Ship Staff Insp.","Hydraulic box for Valves near 4P WBT tank dome on Main deck Shows traces of leak on deck. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.21","High","","","Needs to investigate further.","2019-04-30","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,4276,"35_2019-03-24 09:27:11.995","2019-03-05","Defect","Ship Staff","Ship Staff Insp.","Hydraulic box for Valves near 2P WBT tank dome on Main deck Shows traces of leak on deck.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.21","High","",""," Needs to investigate further.","2019-04-30","","Completed","2019-04-23","No","No","No","Internal"]
[null,null,null,null,4277,"35_2019-03-25 09:27:11.995","2019-03-05","Defect","Ship Staff","Ship Staff Insp.","Port side Windlass leaking from oil level gauge glass           ","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Temporary repairs done, RO raised .","2019-04-30","RALI180248","Completed","2019-04-19","No","No","No","Internal"]
[null,null,null,null,4278,"35_2019-03-26 09:27:11.995","2019-03-05","Defect","Ship Staff","Ship Staff Insp.","Fwd breast winch leaking from oil level gauge glass ","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Temporary repairs done, RO raised .","2019-04-30","RALI180248","Completed","2019-04-25","No","No","No","Internal"]
[null,null,null,null,4279,"35_2019-03-27 09:27:11.995","2019-03-05","Defect","Ship Staff","Ship Staff Insp.","Port side Windlass Leaking from lock ring for main shaft on the Gear case and vibrates during operation.   ","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Suspect main shaft bearing and bushes wornout needs to replace.","2019-04-30","","Completed","2019-04-17","No","No","No","Internal"]
[null,null,null,null,4280,"35_2019-03-28 09:27:11.995","2019-03-07","Defect","Ship Staff","Ship Staff Insp.","Fwd breast winch leaking from control block   ","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Needs to investigate further.","2019-04-30","","Completed","2019-04-26","No","No","No","Internal"]
[null,null,null,null,4281,"35_2019-03-29 09:27:11.995","2018-03-07","Defect","Ship Staff","Ship Staff Insp.","Stbd side Windlass Leaking from lock ring for main shaft on the Gear case and vibrates during operation. ","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Suspect main shaft bearing and bushes wornout needs to replace.","2019-04-30","","Completed","2019-04-28","No","No","No","Internal"]
[null,null,null,null,4282,"35_2019-03-30 09:27:11.995","2019-03-07","Defect","Ship Staff","Ship Staff Insp.","Fwd spring winch leaking from 2 speed valve  ","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Needs to investigate further.","2019-04-30","","Completed","2019-04-26","No","No","No","Internal"]
[null,null,null,null,4283,"35_2019-03-31 09:27:11.995","2019-03-07","Defect","Ship Staff","Ship Staff Insp.","Stbd side provision crane ramp seal leaking. ","Deck - Machinery","Mooring","Equipment Related","8.76","Medium","","","DD Spec raised for the job.","2019-04-30","","Completed","2019-04-25","Yes","No","No","Internal"]
[null,null,null,null,4284,"35_2019-04-01 09:27:11.995","2019-03-07","Defect","Ship Staff","Ship Staff Insp.","Port side Hose handling crane leaking from Control block.  ","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","8.76","Medium","","","Needs to investigate further.","2019-03-30","","Completed","2019-04-25","No","No","No","Internal"]
[null,null,null,null,4285,"35_2019-04-02 09:27:11.995","2019-03-12","Defect","Ship Staff","Ship Staff Insp.","4 Nos UTI not working (Sr. 9016, 9758 , 8975, G11586) and no Gas tight UTI onboard.     ","Cargo Mach.,Miscellaneous","Cargo / Ballast Systems","Equipment Related","8.12","Medium","","","Total 5nos UTI onboard of which only 1 is working. Non working UTI's Needs to be landed for replacement with working UTI's.","2020-04-30","","Completed","2019-04-26","No","No","No","Internal"]
[null,null,null,null,4286,"35_2019-04-03 09:27:11.995","2018-10-27","Defect","Ship Staff","Ship Staff Insp.","DG FO AUTO FILTER NOT HOLDING ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Change-over valve overhauled fitted with new seals","2019-03-26","RALI180226","Completed","2019-04-23","Yes","No","No","Internal"]
[null,null,null,null,4287,"35_2019-04-04 09:27:11.995","2019-03-13","Defect","Ship Staff","Ship Staff Insp.","Ship side railings at Stern found deformed and broken near Port side fairlead","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Needs to be cropped and renewed. To be included in DD specs.","2019-04-30","","Completed","2019-04-25","Yes","No","No","Internal"]
[null,null,null,null,4288,"35_2019-04-05 09:27:11.995","2019-02-26","Defect","Ship Staff","Ship Staff Insp.","Cargo Tank overfill alarm air horn not working at times.  ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.14","Very High","","","Needs to be renewed with new spare. RO raised.","2019-05-30","RALI190004","Completed","2019-05-05","Yes","No","No","Internal"]
[null,null,null,null,4289,"35_2019-04-06 09:27:11.995","2019-05-05","Defect","Ship Staff","Ship Staff Insp.","Stbd provision crane wire found damged.  ","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","8.76","Medium","","","New wire installed on stbd provision crane.","2019-05-30","","Completed","2019-05-07","No","No","No","Internal"]
[null,null,null,null,4290,"35_2019-04-07 09:27:11.995","2019-04-25","Defect","Ship Staff","Ship Staff Insp.","Steam coil drain valves and steam trap valves to be renewed. ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.15","High","","","All new spare valves received installed on steam coils.","2019-06-15","","Completed","2019-05-28","No","No","No","Internal"]
[null,null,null,null,4291,"35_2019-04-08 09:27:11.995","2019-05-11","Defect","Ship Staff","Ship Staff Insp.","Fire plan box cap cannot be fully closed.  ","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.37","Low","","","New box fabrication done","2019-05-30","","Completed","2019-05-28","No","No","No","Internal"]
[null,null,null,null,4292,"35_2019-04-10 09:27:11.995","2019-02-26","Defect","Ship Staff","Ship Staff Insp.","No 3,4,5 & 6 Fire Isolation valve on deck found passing when in use. ","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.38","High","","","ALL VALVES RENEWED WITH NEW ONES","2019-05-30","","Completed","2019-05-30","No","No","No","Internal"]
[null,null,null,null,4293,"35_2019-04-11 09:27:11.995","2019-02-26","Defect","Ship Staff","Ship Staff Insp.","Stbd side pilot ladder reel unable to shift using air motor. ","Deck - Machinery","General Appearance","Equipment Related","5.47","Medium","","","Wheel chain RENEWED.","2019-05-31","","Completed","2019-05-20","No","No","No","Internal"]
[null,null,null,null,4294,"35_2019-04-09 09:27:11.995","2019-02-26","Defect","Ship Staff","Ship Staff Insp.","No 1,3, 4 & 5, Foam Isolation valve on deck found passing when in use.  ","LSA / FFA","Ice Opns.","Equipment Related","5.38","High","","","ALL VALVES RENEWED WITH NEW ONES","2019-05-31","","Completed","2019-05-30","No","No","No","Internal"]
[null,null,null,null,4295,"35_2019-04-12 09:27:11.995","2019-03-04","Defect","Ship Staff","Ship Staff Insp.","LED indication light for Valves OP 225, OT 107, OT 114 & OT 108) in CCR console not working  ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Needs to replace, RO raised","2019-05-31","RALI190007","Completed","2019-05-14","No","No","No","Internal"]
[null,null,null,null,4296,"35_2019-04-13 09:27:11.995","2019-05-11","Defect","Ship Staff","Ship Staff Insp.","Color coding on extinguishers missing  ","LSA / FFA","LSA / FFA Appliances","Equipment Related","8.55","Low","","","COLOR CODING COMPLETED","2019-05-31","","Completed","2019-05-31","No","No","No","Internal"]
[null,null,null,null,4297,"35_2019-04-14 09:27:11.995","2019-05-11","Defect","Ship Staff","Ship Staff Insp.","Vents open shut welded characters not highlighted. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","ALL CHARACTERS HIGHLIGHTED","2019-06-15","","Completed","2019-05-27","No","No","No","Internal"]
[null,null,null,null,4298,"35_2019-04-15 09:27:11.995","2019-02-26","Defect","Ship Staff","Ship Staff Insp.","Foam monitor No 2, 3, 4 ,5, 6, 7 & 8 found leaking from 360 degree turning bearing assembly and also leaking from Up & down moving bearing assembly","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.38","High","","","Changed all \"O\"rings for the bearing assembly, but still leaking persist. Needs to renew both bearing assembly. RO to be raised.","2019-05-31","","Completed","2019-05-29","No","No","No","Internal"]
[null,null,null,null,4299,"35_2019-04-16 09:27:11.995","2019-04-22","Breakdown","Ship Staff","Ship Staff Insp.","AE NO.1 CRANKSHAFT DAMAGED ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","CRANKSHAFT RENEWED ","2019-05-31","","Completed","2019-06-06","No","No","No","Internal"]
[null,null,null,null,4300,"35_2019-04-17 09:27:11.995","2019-05-12","Defect","Ship Staff","Ship Staff Insp.","No.2 AE Digital tachometer display defective","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","NEW SPARE FITTED","2019-06-02","RALI190187","Completed","2019-06-06","No","No","No","Internal"]
[null,null,null,null,4301,"35_2019-04-18 09:27:11.995","2019-05-16","Breakdown","Ship Staff","Ship Staff Insp.","ME Viscotherm motor found tripping","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","NEW MOTOR FITTED","2019-06-30","RALI190190","Completed","2019-06-09","No","No","No","Internal"]
[null,null,null,null,4302,"35_2019-04-19 09:27:11.995","2019-04-28","Defect","Ship Staff","Ship Staff Insp.","ACONIS  POWER MANAGEMENT SYSTEM FAULT  ","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","11.1","High","","","transducers fitted","2019-06-15","RALI195102","Completed","2019-06-11","No","No","No","Internal"]
[null,null,null,null,4303,"35_2019-04-20 09:27:11.995","2019-04-28","Defect","Ship Staff","Ship Staff Insp.","No.1 O2 ANALYZER defective sensor element   ","Inert Gas","Eng. / Strg. Comp.","Equipment Related","8.26","High","","","new sensor fitted","2019-06-02","RALI190176","Completed","2019-06-15","No","No","No","Internal"]
[null,null,null,null,4304,"35_2019-04-21 09:27:11.995","2019-05-26","Defect","Ship Staff","Ship Staff Insp.","Port side wilden pump leaking from the casing. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","6.2","High","","","Temporary repairs made, needs to be renewed with new wilden pump, RO raised.","2019-06-30","RALI190214","Completed","2019-06-05","No","No","No","Internal"]
[null,null,null,null,4305,"35_2019-04-22 09:27:11.995","2019-05-26","Defect","Ship Staff","Ship Staff Insp.","3 Nos. Foam hydrants found leaking during pressurisation of foam line. ","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.35","Medium","","","LINE REPAIRED AND FITTED BACK","2019-06-07","","Completed","2019-06-05","No","No","No","Internal"]
[null,null,null,null,4306,"35_2019-04-23 09:27:11.995","2019-05-26","Defect","Ship Staff","Ship Staff Insp.","Aft spring winch return hydraullic line found leaking","Deck - Machinery","Mooring","Equipment Related","6.9","Low","","","LINE REPAIRED AND FITTED BACK","2019-06-07","","Completed","2019-06-05","No","No","No","Internal"]
[null,null,null,null,4307,"35_2019-04-24 09:27:11.995","2019-06-08","Defect","Ship Staff","Ship Staff Insp.","Garbage lids found broken","Miscellaneous","General Appearance","External Factors","6.2","High","","","New lids fabricated and fitted back","2019-06-08","","Completed","2019-06-15","No","No","No","Internal"]
[null,null,null,null,4308,"35_2019-04-25 09:27:11.995","2019-06-09","Defect","Ship Staff","Ship Staff Insp.","Stand for extinguisher outside acetylene room found rusted and broken ","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.35","Medium","","","New stand fabricated and fitted back","2019-07-15","","Completed","2019-06-11","No","No","No","Internal"]
[null,null,null,null,4309,"35_2019-04-26 09:27:11.995","2019-06-07","Defect","Ship Staff","Ship Staff Insp.","no.2 EGB circulating pump drawing high current. Overhauled both pumps","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Overhauled both pumps","2019-06-20","","Completed","2019-06-18","No","No","No","Internal"]
[null,null,null,null,4310,"35_2019-04-27 09:27:11.995","2019-04-28","Defect","Ship Staff","Ship Staff Insp.","07 in nos HEEM -II unit  for st by pump starting faulty ","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","11.1","High","","","new spares fitted on defective units","2019-06-15","RALI190149","Completed","2019-06-24","No","No","No","Internal"]
[null,null,null,null,4311,"35_2019-04-28 09:27:11.995","2019-06-22","Defect","Ship Staff","Ship Staff Insp.","Vaccum system for sanitory found leaking from CO cabin ","Accommodation","General Appearance","Equipment Related","","","","","Vacuum unit overhauled and diaphragms renewed","2019-06-23","","Completed","2019-06-23","No","No","No","Internal"]
[null,null,null,null,4312,"35_2019-06-12 09:27:11.995","2019-08-23","Defect","Ship Staff","Ship Staff Insp.","Stbd boiler Flange leaking, between Circulating pump suction and Boiler. ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To renew packing","2019-09-30","","Completed","2019-09-01","No","No","No","Internal"]
[null,null,null,null,4313,"35_2019-06-13 09:27:11.995","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","FWG SW Inlet pipe leaking. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To fabricate new pipe","2019-09-15","","Completed","2019-09-01","No","No","No","Internal"]
[null,null,null,null,4314,"35_2019-06-14 09:27:11.995","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","hFO purifier No.2 leaking. ","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To carry out service. Communication with office regarding fault. Overhauled, running satisfactory till now, under obsevation.","2019-08-31","","Completed","2019-09-03","No","No","No","Internal"]
[null,null,null,null,4315,"35_2019-06-15 09:27:11.995","2019-09-03","Defect","Ship Staff","Ship Staff Insp.","FWG production low. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To clean fresh water generator","2019-09-15","","Completed","2019-09-06","No","No","No","Internal"]
[null,null,null,null,4316,"35_2019-06-16 09:27:11.995","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","Purifier room has large opening from ER store open for trunking.      ","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.32","High","","","CO2 system separate for purifier room.To fill with foam sealant, same to be ordered","2019-09-30","","Completed","2019-09-05","No","No","No","Internal"]
[null,null,null,null,4317,"35_2019-06-17 09:27:11.995","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","HFO purifier No.1 leaking. ","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To carry out service. Communication with office regarding fault 20/08/2019 : Build up sliding bowl surface by welding, fitted and tested","2019-08-31","","Completed","2019-09-06","No","No","No","Internal"]
[null,null,null,null,4318,"35_2019-06-18 09:27:11.995","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","ME LO purifier leaking.    ","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Service carried out, awaiting sludge transfer to Slop. Once sludge tank lower will test. Ran for almost 24 hours, were running during day hours.  Oflowed to be inspected, lost ME sump oil (2500 ltrs)","2019-09-15","","Completed","2019-09-07","No","No","No","Internal"]
[null,null,null,null,4319,"35_2019-06-19 09:27:11.995","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","IG scrubber guage glass has leaks","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To carry out repairs. 31/08/2019 : Leaking from guage glass, metal face completely wasted. To repair the face. 04/09/2019, A new plate fabricated and installed.","2019-09-10","","Completed","2019-09-06","No","No","No","Internal"]
[null,null,null,null,4320,"35_2019-06-20 09:27:11.995","2019-08-20","Defect","Ship Staff","Ship Staff Insp.","Service air compressor cutting in cutting off quite regularly unable to press up.      ","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Investigation in progress. In contact with office.08/09/2019 : Cooler cleaned internally and fitted working satisfactory.","2019-09-15","","Completed","2019-09-08","No","No","No","Internal"]
[null,null,null,null,4321,"35_2019-06-21 09:27:11.995","2019-08-10","Defect","Ship Staff","Ship Staff Insp.","No.2 Boiler fuel oil temperature control not working, boiler tripping at Low temperature alarm.          ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To change controller spare ordered","2019-09-30","RALI190246","Completed","2019-09-25","No","No","No","Internal"]
[null,null,null,null,4322,"35_2019-06-23 09:27:11.995","2019-09-13","Defect","Ship Staff","Ship Staff Insp.","Main engine puncture valve top cover breaking off. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","In consultation with office, thicker gasket to fit. Spare bolts ordered . Thicker gasket replaced with new bolts","2019-09-30","RALI190295","Completed","2019-09-27","No","No","No","Internal"]
[null,null,null,null,4323,"35_2019-06-22 09:27:11.995","2019-08-23","Defect","Ship Staff","Ship Staff Insp.","Pressure and temperature template, gauges to renew.           ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To renew damaged gauges or order. 15/09/2019: changed damaged guages, work in progress. Thermometer requested","2019-09-30","RALI190287","Completed","2019-09-27","No","No","No","Internal"]
[null,null,null,null,4324,"35_2019-06-24 09:27:11.995","2019-09-13","Defect","Ship Staff","Ship Staff Insp.","Fuse blowing off for Engine control console DC Distribution circuit F26. Fuse blows off not instantly, some times twice a day sometimes after week.               ","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","11.1","High","","","Investigation in progress, carrying out as per Mr. Kamlesh Solanki advise. Checked system all found normal","2019-09-30","","Completed","2019-09-27","No","No","No","Internal"]
[null,null,null,null,4325,"35_2019-06-25 09:27:11.995","2019-08-01","Defect","Ship Staff","Ship Staff Insp.","2P COT radar readings for ullage in CCR are erratic due deck radar electronic unit faulty.           ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.22","Very High","","","RO raised. 25/09/2019: as advised connection made and tried out working satisfactory.","2019-09-30","RALI190249","Completed","2019-09-25","No","No","No","Internal"]
[null,null,null,null,4326,"35_2019-06-26 09:27:11.995","2019-09-17","Defect","Ship Staff","Ship Staff Insp.","Boiler feed pump No.1 not taking suction.       ","E/R - Aux. Mach.,E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To inspect and check. Valve housing removed and found rags on suction pipe, same removed and tried out during Loading RasLaffan","2019-09-30","","Completed","2019-09-27","No","No","No","Internal"]
[null,null,null,null,4327,"35_2019-06-27 09:27:11.995","2019-09-18","Defect","Ship Staff","Ship Staff Insp.","MAC No.1 coupling pad damaged.       ","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Damaged coupling renewed, HP piston and con rod renewed, valve renewed","2019-09-30","","Completed","2019-09-21","No","No","No","Internal"]
[null,null,null,null,4328,"35_2019-06-28 09:27:11.995","2019-09-26","Defect","Ship Staff","Ship Staff Insp.","AE No.1 Unit exhaust temperature high to renew head.          ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Replaced cylinder head with spare","2019-09-30","","Completed","2019-09-26","No","No","No","Internal"]
[null,null,null,null,4329,"35_2019-06-29 09:27:11.995","2019-08-01","Defect","Ship Staff","Ship Staff Insp.","IG panel in CCR and ECR analog unit not working. ","Inert Gas","Cargo / Ballast Systems","Equipment Related","8.25","Very High","","","RO raised. Replaced with spares rec'd","2019-09-30","RALI190227","Completed","2019-09-25","No","No","No","Internal"]
[null,null,null,null,4330,"35_2019-06-30 09:27:11.995","2019-09-15","Defect","Ship Staff","Ship Staff Insp.","Deck seal pump No.1 inoperational for long time, not reported. To overhaul.               ","E/R - Aux. Mach.,Inert Gas","Cargo / Ballast Systems","Equipment Related","8.27","Medium","","","Pump overhauled and tested","2019-09-30","","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,4331,"35_2019-07-01 09:27:11.995","2019-10-01","Defect","Ship Staff","Ship Staff Insp.","No.2 (Port) Boiler manhole door leaking. ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To change gasket","2019-10-04","","Completed","2019-10-02","No","No","No","Internal"]
[null,null,null,null,4332,"35_2019-07-02 09:27:11.995","2019-08-01","Defect","Ship Staff","Ship Staff Insp.","SI lights on main deck not found intrinsically safe.     ","LSA / FFA","LSA / FFA Appliances","Equipment Related","5.47","Medium","","","RO raised for intrinsically type SI lights in PAL. RO number RALI190243.","2019-09-30","RALI190243","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,4333,"35_2019-07-03 09:27:11.995","2019-08-02","Defect","Ship Staff","Ship Staff Insp.","Two units of Impact Pro cannot be charged due to batteries on board are permanently discahrged. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.7","High","","","IMM informed regarding the same and they will be supplying new set of batteries for both units of impact pro.","2019-09-30","","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,4334,"35_2019-07-04 09:27:11.995","2019-09-14","Defect","Ship Staff","Ship Staff Insp.","Gyro No.1 not in sync with Gyro No.2 and showing error of 5º.  ","Navigation - Others","Navigation","Equipment Related","4.9","Medium","","","Message sent to company regarding the problem. Shore Techinician Rectified the problem","2019-09-30","","Completed","2019-09-24","No","No","No","Internal"]
[null,null,null,null,4335,"35_2019-07-05 09:27:11.995","2019-05-27","Other","Ship Staff","Ship Staff Insp.","Unable to take print out from PAL using computers other than Master PC","Miscellaneous","Communication","Equipment Related","","","",""," IT Dept informed, awaiting solution. 03/10/2019, tried out in bridge","2019-10-31","","Completed","2019-10-03","No","No","No","Internal"]
[null,null,null,null,4336,"35_2019-07-06 09:27:11.995","2019-03-03","Defect","Ship Staff","Ship Staff Insp.","6S & 3S COT fwd programmable COW machine found missing in dry dock.   ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.34","High","","","6S & 3S COT fwd programmable COW machine installation completed","2019-10-31","RALI195126","Completed","2019-10-07","No","No","No","Internal"]
[null,null,null,null,4337,"35_2019-07-07 09:27:11.995","2019-06-08","Defect","Ship Staff","Ship Staff Insp.","Temperature sensor of 3S COT showing faulty readings. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.13","Medium","","","RO raised for new temperature sensor, 30/09/2019 Rec'd spares at Khorfakkan, will carry out at Ballast passage","2019-10-31","RALI190219","Completed","2019-10-10","No","No","No","Internal"]
[null,null,null,null,4338,"35_2019-07-08 09:27:11.995","2019-06-08","Defect","Ship Staff","Ship Staff Insp.","Aft hydraulic section of SW pipe above generator has soft patch repair.  ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","09/8/19, 2 section of pipe renewed. More pipe to renew, pipe to be ordered. 30/09/2019: Spare rec'd will renew soon","2019-10-31","RALI190266","Completed","2019-10-15","No","No","No","Internal"]
[null,null,null,null,4339,"35_2019-07-09 09:27:11.995","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","LT cooler No.1 dirty.             ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To clean cooler, valves not holding. 31/08/2019: bolts eased up, inlet valve found but with smaller hole and pipes to be modified. Outlet valve RO raised. 30/09/2019: Valve rec'd will replace in ballast passage. 15/10/2019 : Valves renewed in passage and cooler ","2019-10-31","RALI190266","Completed","2019-10-13","No","No","No","Internal"]
[null,null,null,null,4340,"35_2019-07-10 09:27:11.995","2019-10-05","Defect","Ship Staff","Ship Staff Insp.","Port boiler Uptake temperature sensor showing very less reading.  ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Temperature sensor checked, wiring checked and checked with callibrator. Port boiler uptake sensor was kept out, fault rectified and put back in use","2019-10-31","","Completed","2019-10-09","No","No","No","Internal"]
[null,null,null,null,4341,"35_2019-07-11 09:27:11.995","2019-10-05","Defect","Ship Staff","Ship Staff Insp.","No.1 boiler circulating pump leaking. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pump overhauled","2019-10-31","","Completed","2019-10-12","No","No","No","Internal"]
[null,null,null,null,4342,"35_2019-07-12 09:27:11.995","2019-10-01","Defect","Ship Staff","Ship Staff Insp.","GE LO PURIFIER INOPERATIONAL.   ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Purifier cleaned, inspected, water manifold replaced with Main LO purifier. Pressure switch replaced. Purifier put in use","2019-10-15","","Completed","2019-10-11","No","No","No","Internal"]
[null,null,null,null,4343,"35_2019-07-13 09:27:11.995","2019-10-20","Defect","Ship Staff","Ship Staff Insp.","Boiler fuel oil supply pump No.1 leaking. ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","To overhaul pump, 22/10/2019, Pump overhauled and put in use","2019-10-31","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,null,"35_2019-08-02 01:10:23.000","2019-08-01","Defect","Ship Staff","Ship Staff Insp.","UTI No. 9758 on off switch found broken and UTI found inoperational.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.1199999999999992,"Medium","Not Applicable","Not Applicable","RO raised on 03/10/2019. On/Off switch changed with new one recieved.","2019-10-31","RALI190308","Completed","2019-11-05","No",null,null,"Internal"]
[null,null,null,null,null,"35_2019-08-11 01:10:23.000","2019-09-14","Defect","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Pressure reading for COT 4P and 5P showing wrong","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.1199999999999992,"Medium","Not Applicable","Not Applicable","RO raised. 15/10/2019: Sensor changed on 04-NOV-2019. Now pressure reading showing correct for COT 4P and 5P.","2019-10-31","RALI190298","Completed","2019-11-04","No",null,null,"External"]
[null,null,null,null,null,"35_14/01/2020 10:25:07 PM","2019-04-12","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The Printer for IG Line Pressure Marker Stylus was found low on ink and the marking was barely readble.","Inert Gas","Cargo / Ballast Systems","Equipment Related",8.25,"Very High","Not Applicable","Not Applicable","Immediately  stylus for IG line pressure changed & the marking on the printer found readable.","2019-04-19",null,"Completed","2019-04-12","No",null,null,"Internal"]
[null,null,null,null,null,"35_2019-08-03 01:10:23.000","2019-08-02","Defect","Ship Staff","Ship Staff Insp.","Aux.feed pump No.2 seal leaking and noise.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","Aux Feed pump #2 completely overhauled and fitted back on 24/10/2019","2019-10-30","RALI190197","Completed","2019-10-24","No",null,null,"Internal"]
[null,null,null,null,null,"35_2019-08-04 01:10:23.000","2019-08-09","Defect","Ship Staff","Ship Staff Insp.","IG fan water wash drain line leaking.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",8.3000000000000007,"Very High","Not Applicable","Not Applicable","fabricated new pipe line and fitted back on 30/10/2019","2019-10-31",null,"Completed","2019-10-30","No",null,null,"Internal"]
[null,null,null,null,null,"35_2019-08-07 01:10:23.000","2019-08-10","Defect","Ship Staff","Ship Staff Insp.","Provision fridge system has gas leakage.","E/R - Aux. Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","new provision compressor unit installed on 10/01/2020 and kept in service","2019-10-31","RALI190286","Completed","2020-01-10","No",null,null,"Internal"]
[null,null,null,null,null,"35_2019-08-06 01:10:23.000","2019-08-10","Defect","Ship Staff","Ship Staff Insp.","ME viscotherm seal leaking.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","MA visco therm mechanical seal renewed on 01/11/2019 working satisfactory","2019-10-31","RALI190259","Completed","2019-11-01","No",null,null,"Internal"]
[null,null,null,null,null,"35_2019-08-09 01:10:23.000","2019-08-30","Defect","Ship Staff","Ship Staff Insp.","ME fuel oil No.1 circulating pump leaking.","E/R - Aux. Engine,E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","ME FO Circ pump #1 mechanical seal renewed, tried out and kept in service working satisfactory, no leak","2019-11-30",null,"Completed","2019-11-02","No",null,null,"Internal"]
[null,null,null,null,null,"35_2019-05-25 09:27:11.995","2019-08-18","Defect","Ship Staff","Ship Staff Insp.","Temperature and pressure callibrator annual certification overdue.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","certificate received","2019-11-15",null,"Completed","2019-08-27","No",null,null,"Internal"]
[null,null,null,null,null,"35_15/01/2020 4:02:54 PM","2019-04-12","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Lamptest on CCR Panel indicated that Indication bulbs for 2 Port ballast tank and Ballast Eductor suction valve had fused.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.8000000000000007,"Medium","Not Applicable","Not Applicable","bulbs changes. OIC instructed to carry out lamp test frequently","2019-04-19",null,"Completed","2019-04-12","No",null,null,"Internal"]
[null,null,null,null,null,"35_14/01/2020 10:28:30 PM","2019-04-12","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The forward grating on the Port Manifold drip tray was found bent and not secured.","Deck - Pipe / Fittings","General Appearance","Equipment Related",8.25,"Very High","Not Applicable","Not Applicable","MAINTENANCE OF FOREWARD GRATING ON THE PORTSIDE  MANIFOLD  CARRIED OUT. DEFECT RECTIFIED & SECURED BACK ON THE DRIP TRAY.","2019-04-19",null,"Completed","2019-04-19","No",null,null,"Internal"]
[null,null,null,null,null,"35_14/01/2020 10:34:49 PM","2019-04-12","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","3rd Mate was not able to demonstrate calibertaion of Portable MultGas Detector","Miscellaneous","Cargo / Ballast Systems","Knowledge Based",5.23,"Very High","Not Applicable","Not Applicable","PROCEDURE FOR CALIBRATIONS OF PORTABLE MULTIGAS DETECTOR EXPLANED TO ALL OFFICER. INSIST THEM TO REFER THE MANUALS IF ANY DOUBT REGARDING OPERATIONS OF GAS METERS.","2019-04-19",null,"Completed","2019-04-19","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 9:39:48 PM","2019-01-25","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME UNITS NO. 2, 3, 4 & 6 TO BE DECARBED DURING DD","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","ALL 4 UNITS DECARB CARRIED OUT DURING DD","2019-04-25",null,"Completed","2019-04-15","Yes",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 6:51:55 PM","2019-01-22","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","COPT No 3 and water ballast pump turbine casing drain valve found leaking from flange ends","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",8.11,"Medium","Not Applicable","Not Applicable","gasket  renewed. leakage rectified.","2019-02-06",null,"Completed","2019-01-30","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 6:58:15 PM","2019-01-23","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","STBD side gangway found difficult to haul in, on investigation found Fwd roller to the inward side not rotating ","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related",11.3,"Medium","Not Applicable","Not Applicable","eased up and greasing carried out. now rotating freely.","2019-02-20",null,"Completed","2019-01-31","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:02:35 PM","2019-01-23","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","A/E #2 centrifugal oil max filter support stand on crank case door cracked","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","crank case door repair work carried out and fitted back","2019-02-07",null,"Completed","2019-01-30","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:07:03 PM","2019-01-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","OWS sight glass near 3way valve found loosened out of place.","Miscellaneous","MARPOL Related","Equipment Related",6.17,"Very High","Not Applicable","Not Applicable","sight glass removed and cleaned and tightened, found satisfactory","2019-01-31",null,"Completed","2019-01-31","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:16:07 PM","2019-01-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","port side LT fresh water cooler sea water inlet reducer connection leaking","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","renewed gasket. boxed back found satisfactory","2019-02-23",null,"Completed","2019-02-11","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:20:12 PM","2018-01-23","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LT fresh water cooler (port side) sea water inlet pressure gauge faulty","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","pressure gauge with new one","2019-02-07",null,"Completed","2019-02-11","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:24:13 PM","2019-01-22","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aux engine (1,2&3) exhaust gas drain pipes water seal pot pipes wasted/partialy broken","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","repaired and fitted back","2019-02-20",null,"Completed","2019-02-11","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:28:02 PM","2019-01-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","fire line is having an insert near no 4 foam monitor, same to be renewed with new pipe line","LSA / FFA","LSA / FFA Appliances","Equipment Related",5.38,"High","Not Applicable","Not Applicable","new pipe line fabricated and boxed back.","2019-02-22",null,"Completed","2019-02-14","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:35:06 PM","2019-01-24","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","section of grating at the entrance of port side hose handling crane platform found wasted","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related",11.3,"Medium","Not Applicable","Not Applicable","grating  renewed","2019-02-22",null,"Completed","2019-02-14","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:37:49 PM","2019-01-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","STBD side gangway motor found not working, needs to be overhauled","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","motor overhauled and fitted back","2019-02-23",null,"Completed","2019-01-24","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:41:23 PM","2019-01-22","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","doppler main display unit not operational to renew in DD","Navigation - GMDSS & Communication","Navigation","Equipment Related","4.7.17","High","Not Applicable","Not Applicable","job completed in DD","2019-04-22",null,"Completed","2019-04-15","Yes",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:44:34 PM","2018-01-24","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","one no of stud in unit no 3 gets loos during operation, same to be repaired with sleeve insert/ helicert on entablature in DD","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","job completed in DD","2019-04-24",null,"Completed","2019-04-15","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:47:41 PM","2019-01-23","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","overhaul of both ME turbocharger is planed for DD","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","both T/C are overhauled in DD","2019-04-23",null,"Completed","2019-04-15","No",null,null,"Internal"]
[null,null,null,null,null,"35_20/01/2020 7:11:48 PM","2019-01-23","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","incinerator DO inlet pipe connection to the pressure switch found partialy leaking","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","fabricated new connection and fitted back","2019-02-07",null,"Completed","2019-02-08","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["LSA / FFA Appliances",8]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":427,"n_cols":3,"rows_kept":427,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",8243]
["1.10","Low",8252]
["1.11","Low",8253]
["1.12","Low",8254]
["1.13","Low",8255]
["1.14","Low",8256]
["1.15","Low",8257]
["1.16","Low",8259]
["1.17","Low",8260]
["1.18","Low",8261]
["1.19","Low",8262]
["1.2","Low",8244]
["1.20","Low",8263]
["1.21","Low",8265]
["1.22","Low",8266]
["1.23","Low",8267]
["1.24","Low",8268]
["1.25","Low",8269]
["1.26","Low",8270]
["1.3","Low",8245]
["1.4","Low",8246]
["1.5","Low",8247]
["1.6","Low",8248]
["1.7","Low",8249]
["1.8","Low",8250]
["1.9","Low",8251]
["1.99","High",11258]
["10.1","Medium",8461]
["10.10","High",8470]
["10.11","Medium",8471]
["10.12","Very High",8472]
["10.13","Very High",8473]
["10.14","Medium",8474]
["10.15","Low",8475]
["10.16","Very High",8476]
["10.17","Very High",8477]
["10.18","High",8478]
["10.19","Very High",8479]
["10.2","Low",8462]
["10.20","High",8480]
["10.21","Medium",8481]
["10.22","Low",8482]
["10.23","Medium",8483]
["10.24","Low",8484]
["10.25","Very High",8485]
["10.26","High",8486]
["10.27","Medium",8487]
["10.28","Low",8488]
["10.29","Medium",8489]
["10.3","Medium",8463]
["10.30","High",8490]
["10.31","Very High",8491]
["10.32","Very High",8492]
["10.33","High",8493]
["10.34","High",8494]
["10.35","Very High",8495]
["10.36","Very High",8496]
["10.37","Medium",8497]
["10.38","Medium",8498]
["10.39","High",8499]
["10.4","High",8464]
["10.40","Medium",8500]
["10.41","Medium",8501]
["10.42","Medium",8502]
["10.43","Medium",8503]
["10.44","Medium",8504]
["10.45","Very High",8505]
["10.46","High",8506]
["10.47","Medium",8507]
["10.48","High",8508]
["10.49","Medium",8509]
["10.5","Low",8465]
["10.50","High",8510]
["10.51","Low",8511]
["10.52","Medium",8512]
["10.53","Medium",8513]
["10.54","High",8514]
["10.55","Low",8515]
["10.6","Very High",8466]
["10.7","Medium",8467]
["10.8","Medium",8468]
["10.9","Medium",8469]
["10.99","High",8516]
["11.1","High",8420]
["11.10","Medium",8429]
["11.11","Very High",8430]
["11.12","Low",8431]
["11.13","Low",8432]
["11.14","Medium",8433]
["11.15","Low",8434]
["11.16","Low",8435]
["11.17","Low",8436]
["11.2","Medium",8421]
["11.3","Medium",8422]
["11.4","Very High",8423]
["11.5","Medium",8424]
["11.6","Medium",8425]
["11.7","High",8426]
["11.8","Low",8427]
["11.9","Low",8428]
["11.99","High",8437]
["12.1","High",8438]
["12.10","High",8448]
["12.11","High",8449]
["12.12","High",8450]
["12.13","High",8451]
["12.14","High",8452]
["12.15","High",8453]
["12.16","High",8454]
["12.17","High",8455]
["12.18","High",8456]
["12.19","High",8457]
["12.2","High",8439]
["12.20","High",8458]
["12.21","High",8459]
["12.3","High",8441]
["12.4","High",8442]
["12.5","High",8443]
["12.6","High",8444]
["12.7","High",8445]
["12.8","High",8446]
["12.9","High",8447]
["12.99","High",8460]
["2.1","Very High",8296]
["2.1.9","Very High",11259]
["2.10","Medium",8304]
["2.11","Medium",8305]
["2.12","Low",8306]
["2.13","Low",8307]
["2.14","Low",8308]
["2.15","Low",8309]
["2.16","Medium",8310]
["2.2","Medium",8297]
["2.3","High",8295]
["2.4","Medium",8298]
["2.5","Medium",8299]
["2.6","Low",8300]
["2.7","High",8301]
["2.8","High",8302]
["2.9","Medium",8303]
["2.99","High",8311]
["3.1","High",8312]
["3.2","Very High",8313]
["3.3","High",8314]
["3.4","Low",8294]
["3.5","Medium",8315]
["3.6","High",8316]
["3.7","Very High",8317]
["3.8","Very High",8318]
["3.99","High",8319]
["4.1","High",8320]
["4.10","High",8329]
["4.11","Medium",8330]
["4.12","Very High",8331]
["4.13","Very High",8332]
["4.14","Very High",8333]
["4.15","Very High",8334]
["4.16","Very High",8335]
["4.17","Very High",8336]
["4.18","Very High",8337]
["4.19","Low",8338]
["4.2","Medium",8321]
["4.20","Very High",8339]
["4.21","High",8340]
["4.22","Low",8341]
["4.23","High",8342]
["4.24","High",8343]
["4.25","Low",8344]
["4.26","Low",8345]
["4.27","High",8346]
["4.3","Medium",8322]
["4.4","High",8323]
["4.5","Very High",8324]
["4.6","Medium",8325]
["4.7","High",8326]
["4.8","Medium",8327]
["4.9","Medium",8328]
["4.99","High",8347]
["5.1","Very High",8517]
["5.10","High",8526]
["5.11","Low",8527]
["5.12","Medium",8528]
["5.13","High",8529]
["5.14","Very High",8530]
["5.15","Medium",8531]
["5.16","Very High",8532]
["5.17","Very High",8533]
["5.18","High",8534]
["5.19","Medium",8535]
["5.2","Very High",8518]
["5.20","Medium",8536]
["5.21","Medium",8537]
["5.22","High",8539]
["5.23","Very High",8540]
["5.24","Very High",8541]
["5.25","Medium",8542]
["5.26","Medium",8543]
["5.27","Medium",8544]
["5.28","Very High",8545]
["5.29","High",8546]
["5.3","Low",8519]
["5.30","High",8547]
["5.31","High",8548]
["5.32","High",8549]
["5.33","High",8550]
["5.34","Low",8551]
["5.35","Medium",8552]
["5.36","Low",8553]
["5.37","Low",8554]
["5.38","High",8555]
["5.39","Very High",8556]
["5.4","High",8520]
["5.40","Very High",8557]
["5.41","Very High",8558]
["5.42","Medium",8559]
["5.43","High",8560]
["5.44","High",8561]
["5.45","Medium",8564]
["5.46","Medium",8565]
["5.47","Medium",8566]
["5.48","Medium",8567]
["5.5","Low",8521]
["5.6","Low",8522]
["5.7","Medium",8523]
["5.8","Medium",8524]
["5.9","Very High",8525]
["5.99","High",8568]
["6.1","Medium",8348]
["6.10","Low",8357]
["6.11","High",8358]
["6.12","Medium",8359]
["6.13","Low",8360]
["6.14","High",8361]
["6.15","High",8362]
["6.16","Very High",8363]
["6.17","Very High",8364]
["6.18","Medium",8365]
["6.19","Low",8366]
["6.2","High",8349]
["6.20","Medium",8367]
["6.21","High",8368]
["6.22","Medium",8369]
["6.3","Low",8350]
["6.4","High",8351]
["6.5","Medium",8352]
["6.6","Medium",8353]
["6.7","High",8354]
["6.8","High",8355]
["6.9","Low",8356]
["6.99","High",8370]
["7.1","High",8371]
["7.10","High",8380]
["7.11","High",8381]
["7.12","High",8382]
["7.13","Medium",8383]
["7.14","Medium",8384]
["7.15","High",8385]
["7.16","High",8386]
["7.17","High",8387]
["7.2","High",8372]
["7.3","Low",8373]
["7.4","Low",8374]
["7.5","Low",8375]
["7.6","Medium",8376]
["7.7","Low",8377]
["7.8","High",8378]
["7.9","High",8379]
["7.99","High",8388]
["8.1","Very High",8569]
["8.10","Very High",8578]
["8.100","Low",11227]
["8.101","Medium",11228]
["8.102","Low",11229]
["8.103","Low",11230]
["8.104","Low",11231]
["8.105","Medium",11232]
["8.106","Medium",11233]
["8.107","Low",11234]
["8.108","High",11235]
["8.109","Very High",11236]
["8.11","Medium",8579]
["8.110","High",11237]
["8.111","Medium",11238]
["8.112","High",11239]
["8.113","Medium",11240]
["8.114","Low",11241]
["8.115","High",11242]
["8.116","Medium",11243]
["8.117","Medium",11244]
["8.118","Medium",11245]
["8.119","High",11246]
["8.12","Medium",8580]
["8.120","High",11247]
["8.121","Medium",11248]
["8.122","High",11249]
["8.123","High",11250]
["8.124","Low",11251]
["8.125","High",11252]
["8.126","Medium",11253]
["8.127","Medium",11254]
["8.13","Medium",8581]
["8.14","Very High",8582]
["8.15","High",8583]
["8.16","Very High",8584]
["8.17","Low",8585]
["8.18","High",8586]
["8.19","High",8587]
["8.199","High",11255]
["8.2","Medium",8570]
["8.20","Medium",8588]
["8.21","High",8589]
["8.22","Very High",8590]
["8.23","Medium",8591]
["8.24","Medium",8592]
["8.25","Very High",8593]
["8.26","High",8594]
["8.27","Medium",8595]
["8.28","Medium",8596]
["8.29","High",8598]
["8.3","Very High",8571]
["8.30","High",8599]
["8.31","High",8600]
["8.32","Low",8601]
["8.33","Medium",8602]
["8.34","High",8603]
["8.35","Medium",8604]
["8.36","Medium",8605]
["8.37","High",8607]
["8.38","Medium",8608]
["8.39","Medium",8609]
["8.4","Medium",8572]
["8.40","High",8610]
["8.41","Medium",8611]
["8.42","Medium",8612]
["8.43","Very High",8613]
["8.44","High",8615]
["8.45","High",8616]
["8.46","Very High",8617]
["8.47","Very High",8618]
["8.48","Medium",8619]
["8.49","High",8620]
["8.5","Very High",8573]
["8.50","Medium",8621]
["8.51","Low",8622]
["8.52","Low",8623]
["8.53","Low",8624]
["8.54","High",8625]
["8.55","Low",11182]
["8.56","Medium",11183]
["8.57","Medium",11184]
["8.58","High",11185]
["8.59","High",11186]
["8.6","Medium",8574]
["8.60","High",11187]
["8.61","Medium",11188]
["8.62","Very High",11189]
["8.63","High",11190]
["8.64","Medium",11191]
["8.65","Low",11192]
["8.66","High",11193]
["8.67","High",11194]
["8.68","High",11195]
["8.69","Medium",11196]
["8.7","High",8575]
["8.70","Medium",11197]
["8.71","Very High",11198]
["8.72","Medium",11199]
["8.73","Medium",11200]
["8.74","High",11201]
["8.75","Medium",11202]
["8.76","Medium",11203]
["8.77","Medium",11204]
["8.78","Medium",11205]
["8.79","Medium",11206]
["8.8","Medium",8576]
["8.80","Medium",11207]
["8.81","Low",11208]
["8.82","Medium",11209]
["8.83","Low",11210]
["8.84","Low",11211]
["8.85","Medium",11212]
["8.86","Medium",11213]
["8.87","Medium",11214]
["8.88","Low",11215]
["8.89","High",11216]
["8.9","High",8577]
["8.90","High",11217]
["8.91","High",11218]
["8.92","Medium",11219]
["8.93","Low",11220]
["8.94","Low",11221]
["8.95","Medium",11222]
["8.96","Medium",11223]
["8.97","Low",11224]
["8.98","High",11225]
["8.99","Medium",11226]
["9.1","Low",8390]
["9.10","Medium",8399]
["9.11","Medium",8400]
["9.12","Medium",8401]
["9.13","Low",8402]
["9.14","Medium",8403]
["9.15","Medium",8404]
["9.16","High",8405]
["9.17","High",8406]
["9.18","Low",8407]
["9.19","Low",8408]
["9.2","Very High",8391]
["9.20","Medium",8409]
["9.21","Medium",8410]
["9.22","Low",8411]
["9.23","Low",8412]
["9.24","Medium",8413]
["9.25","Low",8414]
["9.26","Low",8415]
["9.27","Low",8416]
["9.28","Medium",8417]
["9.29","Low",8418]
["9.3","Very High",8392]
["9.4","High",8393]
["9.5","High",8394]
["9.6","Low",8395]
["9.7","Medium",8396]
["9.8","Medium",8397]
["9.9","Medium",8398]
["9.99","High",8419]

{"sheet":"Equipment_list","index":7,"n_rows":27,"n_cols":3,"rows_kept":27,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation ",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["35","RIDGEBURY ALINA L (19-12-2019)","35_1577777429712.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":10,"n_cols":2,"rows_kept":10,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]