## Mainsheet
Defect - Damage Monitoring Sheet
|  |  | Date of Report | 23-Apr-2020 |  |  | Ship Name | MING LONG
VERSION : 2.0
ID | UNIQUE ID | Date Recorded | Type of Deficiency | Observer code | Type of Inspection | Description of Deficiency | Equipment Categories | Area of Observation | Deficiency Cause | VIQ Ref Number | Risk Value of Obs | PSC Ref Number | PSC MOU ID | Action Taken or Required | Target Date | PO Ref No. | Status Code | Date Completed | Drydock | Info Sharing | Critical Item | Audit Type | Superintendent Remarks
| 73_29/4/2020 3:48:09 PM | 2020-04-28 | Defect | Ship Staff | Ship Staff Insp. | All three DG and ME /BLR exhaust pipe insulation in poor condition. | E/R - Aux. Engine | Eng. / Strg. Comp. | Equipment Related | 10.19 | Very High | Not Applicable | Not Applicable | Office arranged “Kaizen Offshore & Marine Solutions Pte Ltd" technician to Measurments awaiting their feed back | 2020-07-01 |  | Not Started |  | No |  |  | Internal
| 73_29/4/2020 3:57:45 PM | 2020-04-28 | Observation | Ship Staff | Ship Staff Insp. | Numerous steam/Fuel pipes in ER insulation damaged and in poor condition | E/R - Pipes/ valves & fittings | Eng. / Strg. Comp. | Equipment Related | 10.32 | Very High | Not Applicable | Not Applicable | Office arranged technician from “Kaizen Offshore & Marine Solutions Pte Ltd" and has been taken dimension for damaged insulation awaiting for feed back and fresh insulation | 2020-07-27 |  | Waiting spare |  | No |  |  | Internal
| 73_30/4/2020 1:25:38 PM | 2020-04-30 | Defect | Ship Staff | Ship Staff Insp. | Bunker tank FOT 2(C) high Level not working | Hull & Tanks | Eng. / Strg. Comp. | Equipment Related | 10.8 | Medium | Not Applicable | Not Applicable | Spares to order after troubleshoot | 2020-07-01 |  | Not Started |  | No |  |  | Internal
| 73_30/4/2020 1:37:19 PM | 2020-04-30 | Defect | Ship Staff | Ship Staff Insp. | Ballast tank remote sounding Tank no 1P,After peak,3&4S are showing sensor failure and midship draft gauge port and stbd incorrect sounding. | Hull & Tanks | Cargo / Ballast Systems | Equipment Related | 8.19 | Very High | Not Applicable | Not Applicable | Vessel has few spare sensor but vessel always engaged in cargo operationlooking for suitable oppurtunity to troublr shoot and renew sensors as required. | 2020-07-01 |  | Not Started |  | No |  |  | Internal
[19 empty] | No |  |  | Internal

## Completed
Defect - Damage Monitoring Sheet
|  |  | Date of Report | 23-Apr-2020 |  |  | Ship Name | MING LONG
VERSION : 2.0
ID | UNIQUE ID | Date Recorded | Type of Deficiency | Observer code | Type of Inspection | Description of Deficiency | Equipment Categories | Area of Observation | Deficiency Cause | VIQ Ref Number | Risk Value of Obs | PSC Ref Number | PSC MOU ID | Action Taken or Required | Target Date | PO Ref No. | Status Code | Date Completed | Drydock | Info Sharing | Critical Item | Audit Type | Superintendent Remarks

## Calc (hidden)
Def_type | Def_cause | Equipments | VIQrefno | Observer_code
Dim itemSele As Long
dim startRow as integer
startRow=1
For itemSele = 0 To ListBox1.ListCount - 1
If ListBox1.Selected(itemSele) = True Then
Worksheets("WorksheetName").Range("A" & startRow).Value = ListBox1.List(itemSele)
startRow = startRow + 1
End If
Next
Dim LastRowA As String
Dim itemSele As Long
Dim startRow as integer
LastRowA = ActiveSheet.Cells(Rows.count, "A").End(xlUp).row
startQue = 0
For itemSele = 0 To ListBox1.ListCount - 1
For startRow = 1 To LastRowA
If Worksheets("WorksheetName").Range("A" & startRow).Value = ListBox1.List(itemSele) Then
ListBox1.Selected(itemSele) = True
Exit For
End If
Next j
Next
End If

## Areaofobs (hidden)
TITLE | ID
Cargo / Ballast Systems | 11
Cert. & Docu. | 2
Communication | 6
Crew Management | 3
Emgcy. Systems | 13
Eng. / Strg. Comp. | 14
General Appearance | 15
Ice Opns. | 17
ISM Related | 7
ISPS Related | 10
MARPOL Related | 9
MLC Related | 4
Mooring | 12
Navigation | 5
Safety / LSA / FFA | 8
Structural Condn. / WT integrity | 16

## Vessel_type (hidden)
Vessel_type | ID

## Deficiency_type (hidden)
TITLE | Type of deficiency_description | ID
Breakdown |  | 6
Critical Equipment |  | 4
Defect |  | 1
Guarantee Claim |  | 8
Non Conformity |  | 2
Observation |  | 3
Other |  | 7

## VIQrefno (hidden)
VIQ_ref_no | Risk Value of observation | ID
1.1 | Low | 10160
1.10 | Low | 10169
1.11 | Low | 10170
1.12 | Low | 10171
1.13 | Low | 10172
1.14 | Low | 10173
1.15 | Low | 10174
1.16 | Low | 10176
1.17 | Low | 10177
1.18 | Low | 10178
1.19 | Low | 10179
1.2 | Low | 10161
1.20 | Low | 10180
1.21 |  | 10181
1.22 | Low | 10183
1.23 | Low | 10184
1.24 | Low | 10185
1.25 | Low | 10186
1.26 | Low | 10187
1.3 | Low | 10162
1.4 | Low | 10163
1.5 | Low | 10164
1.6 | Low | 10165
1.7 | Low | 10166
1.8 | Low | 10167
1.9 | Low | 10168
1.99 | High | 16296
10.1 | Medium | 10354
10.10 | High | 10363
10.11 | Medium | 10364
10.12 | Very High | 10365
10.13 | Very High | 10366
10.14 | Medium | 10367
10.15 | Low | 10368
10.16 | Very High | 10369
10.17 | Very High | 10370
10.18 | High | 10371
10.19 | Very High | 10372
10.2 | Low | 10355
10.20 | High | 10373
10.21 | Medium | 10374
10.22 | Low | 10375
10.23 | Medium | 10376
10.24 | Low | 10377
10.25 | Very High | 10378
10.26 | High | 10379
10.27 | Medium | 10380
10.28 | Low | 10381
10.29 | Medium | 10382
10.3 | Medium | 10356
10.30 | High | 10383
10.31 | Very High | 10384
10.32 | Very High | 10385
10.33 | High | 10386
10.34 | High | 10387
10.35 | Very High | 10388
10.36 | Very High | 10389
10.37 | Medium | 10390
10.38 | Medium | 10391
10.39 | High | 10392
10.4 | High | 10357
10.40 | Medium | 10393
10.41 | Medium | 10394
10.42 | Medium | 10395
10.43 | Medium | 10396
10.44 | Medium | 10397
10.45 | Very High | 10398
10.46 | High | 10399
10.47 | Medium | 10400
10.48 | High | 10401
10.49 | Medium | 10402
10.5 | Low | 10358
10.50 | High | 10403
10.51 | Low | 10404
10.52 | Medium | 10405
10.53 | Medium | 10406
10.54 | High | 10407
10.55 | Low | 10408
10.6 | Very High | 10359
10.7 | Medium | 10360
10.8 | Medium | 10361
10.9 | Medium | 10362
10.99 | High | 10409
11.1 | High | 10313
11.10 | Medium | 10322
11.11 | Very High | 10323
11.12 | Low | 10324
11.13 | Low | 10325
11.14 | Medium | 10326
11.15 | Low | 10327
11.16 | Low | 10328
11.17 | Low | 10329
11.2 | Medium | 10314
11.3 | Medium | 10315
11.4 | Very High | 10316
11.5 | Medium | 10317
11.6 | Medium | 10318
11.7 | High | 10319
11.8 | Low | 10320
11.9 | Low | 10321
11.99 | High | 10330
12.1 | High | 10331
12.10 | High | 10341
12.11 | High | 10342
12.12 | High | 10343
12.13 | High | 10344
12.14 | High | 10345
12.15 | High | 10346
12.16 | High | 10347
12.17 | High | 10348
12.18 | High | 10349
12.19 | High | 10350
12.2 | High | 10332
12.20 | High | 10351
12.21 | High | 10352
12.3 | High | 10334
12.4 | High | 10335
12.5 | High | 10336
12.6 | High | 10337
12.7 | High | 10338
12.8 | High | 10339
12.9 | High | 10340
12.99 | High | 10353
2.1 | Very High | 10190
2.1.9 | Very High | 16297
2.10 | Medium | 10198
2.11 | Medium | 10199
2.12 | Low | 10200
2.13 | Low | 10201
2.14 | Low | 10202
2.15 | Low | 10203
2.16 | Medium | 10204
2.2 | Medium | 10191
2.3 | High | 10189
2.4 | Medium | 10192
2.5 | Medium | 10193
2.6 | Low | 10194
2.7 | High | 10195
2.8 | High | 10196
2.9 | Medium | 10197
2.99 | High | 10205
3.1 | High | 10206
3.2 | Very High | 10207
3.3 | High | 10208
3.4 | Low | 10188
3.5 | Medium | 10209
3.6 | High | 10210
3.7 | Very High | 10211
3.8 | Very High | 10212
3.99 | High | 10213
4.1 | High | 10214
4.10 | High | 10223
4.11 | Medium | 10224
4.12 | Very High | 10225
4.13 | Very High | 10226
4.14 | Very High | 10227
4.15 | Very High | 10228
4.16 | Very High | 10229
4.17 | Very High | 10230
4.18 | Very High | 10231
4.19 | Low | 10232
4.2 | Medium | 10215
4.20 | Very High | 10233
4.21 | High | 10234
4.22 | Low | 10235
4.23 | High | 10236
4.24 | High | 10237
4.25 | Low | 10238
4.26 | Low | 10239
4.27 | High | 10240
4.3 | Medium | 10216
4.4 | High | 10217
4.5 | Very High | 10218
4.6 | Medium | 10219
4.7 | High | 10220
4.8 | Medium | 10221
4.9 | Medium | 10222
4.99 | High | 10241
5.1 | Very High | 10410
5.10 | High | 10419
5.11 | Low | 10420
5.12 | Medium | 10421
5.13 | High | 10422
5.14 | Very High | 10423
5.15 | Medium | 10424
5.16 | Medium | 10425
5.17 | Very High | 10426
5.18 | High | 10427
5.19 | Medium | 10428
5.2 | Very High | 10411
5.20 | Medium | 10429
5.21 | Medium | 10430
5.22 | High | 10432
5.23 | Very High | 10433
5.24 | Very High | 10434
5.25 | Medium | 10435
5.26 | Medium | 10436
5.27 | Medium | 10437
5.28 | Very High | 10438
5.29 | High | 10439
5.3 | Low | 10412
5.30 | High | 10440
5.31 | High | 10441
5.32 | High | 10442
5.33 | High | 10443
5.34 | Low | 10444
5.35 | Medium | 10445
5.36 | Low | 10446
5.37 | Low | 10447
5.38 | High | 10448
5.39 | Very High | 10449
5.4 | High | 10413
5.40 | Very High | 10450
5.41 | Very High | 10451
5.42 | Medium | 10452
5.43 | High | 10453
5.44 | High | 10454
5.45 | Medium | 10457
5.46 | Medium | 10458
5.47 | Low | 10459
5.48 | Medium | 10460
5.5 | Low | 10414
5.6 | Low | 10415
5.7 | Medium | 10416
5.8 | Medium | 10417
5.9 | Very High | 10418
5.99 | High | 10461
6.1 | Medium | 10242
6.10 | Low | 10251
6.11 | High | 10252
6.12 | Medium | 10253
6.13 | Low | 10254
6.14 | High | 10255
6.15 | High | 10256
6.16 | Very High | 10257
6.17 | Very High | 10258
6.18 | Medium | 10259
6.19 | Low | 10260
6.2 | High | 10243
6.20 | Medium | 10261
6.21 | High | 10262
6.22 | Medium | 10263
6.3 | Low | 10244
6.4 | High | 10245
6.5 | Low | 10246
6.6 | Medium | 10247
6.7 | High | 10248
6.8 | High | 10249
6.9 | Low | 10250
6.99 | High | 10264
7.1 | High | 10265
7.10 | High | 10274
7.11 | High | 10275
7.12 | High | 10276
7.13 | Medium | 10277
7.14 | Medium | 10278
7.15 | High | 10279
7.16 | High | 10280
7.17 | High | 10281
7.2 | High | 10266
7.3 | Low | 10267
7.4 | Low | 10268
7.5 | Low | 10269
7.6 | Medium | 10270
7.7 | Low | 10271
7.8 | High | 10272
7.9 | High | 10273
7.99 | High | 10282
8.1 | Very High | 10462
8.10 | Very High | 10471
8.11 | Very High | 10472
8.12 | Medium | 10473
8.13 | High | 10474
8.14 | Very High | 10475
8.15 | Medium | 10476
8.16 | Medium | 10477
8.17 | Very High | 10478
8.18 | High | 10479
8.19 | Very High | 10480
8.2 | Medium | 10463
8.20 | Very High | 10481
8.21 | Very High | 10482
8.22 | High | 10483
8.23 | Medium | 10484
8.24 | High | 10485
8.25 | High | 10486
8.26 | Medium | 10487
8.27 | Medium | 10488
8.28 | High | 10489
8.29 | Medium | 10491
8.3 | Medium | 10464
8.30 | Very High | 10492
8.31 | Very High | 10493
8.32 | High | 10494
8.33 | High | 10495
8.34 | Very High | 10496
8.35 | Very High | 10497
8.36 | Very High | 10498
8.37 | Very High | 10500
8.38 | Very High | 10501
8.39 | Very High | 10502
8.4 | Medium | 10465
8.40 | Very High | 10503
8.41 | Very High | 10504
8.42 | Very High | 10505
8.43 | Very High | 10506
8.44 | Medium | 10508
8.45 | High | 10509
8.46 | High | 10510
8.47 | Medium | 10511
8.48 | Very High | 10512
8.49 | Medium | 10513
8.5 | Medium | 10466
8.50 | High | 10514
8.51 | Very High | 10515
8.52 | Very High | 10516
8.53 | Very High | 10517
8.54 | High | 10518
8.55 | High | 16222
8.56 | Very High | 16223
8.57 | Very High | 16224
8.58 | Very High | 16225
8.59 | Medium | 16226
8.6 | Very High | 10467
8.60 | Medium | 16227
8.61 | Medium | 16228
8.62 | Very High | 16229
8.63 | Very High | 16230
8.64 | High | 16231
8.65 | Very High | 16232
8.66 | Medium | 16233
8.67 | Medium | 16234
8.68 | Medium | 16235
8.69 | Very High | 16236
8.7 | High | 10468
8.70 | Very High | 16237
8.71 | Medium | 16238
8.72 | Very High | 16239
8.73 | Medium | 16240
8.74 | High | 16241
8.75 | High | 16242
8.76 | Medium | 16243
8.77 | Medium | 16244
8.78 | Medium | 16245
8.79 | Very High | 16246
8.8 | High | 10469
8.9 | Very High | 10470
8.99 | High | 16266
9.1 | Low | 10283
9.10 | Medium | 10292
9.11 | Medium | 10293
9.12 | Medium | 10294
9.13 | Low | 10295
9.14 | Medium | 10296
9.15 | Medium | 10297
9.16 | High | 10298
9.17 | High | 10299
9.18 | Low | 10300
9.19 | Low | 10301
9.2 | Very High | 10284
9.20 | Medium | 10302
9.21 | Medium | 10303
9.22 | Low | 10304
9.23 | Low | 10305
9.24 | Medium | 10306
9.25 | Low | 10307
9.26 | Low | 10308
9.27 | Low | 10309
9.28 | Medium | 10310
9.29 | Low | 10311
9.3 | Very High | 10285
9.4 | High | 10286
9.5 | High | 10287
9.6 | Low | 10288
9.7 | Medium | 10289
9.8 | Medium | 10290
9.9 | Medium | 10291
9.99 | High | 10312

## Equipment_list (hidden)
TITLE | Equipment_list_description | ID
Accommodation |  | 12
Cargo Mach. |  | 13
Critical Equip. |  | 16
Deck - Machinery |  | 18
Deck - Mooring Machinery |  | 15
Deck - Pipe / Fittings |  | 20
Documentation |  | 21
E/R - Air Comp. |  | 8
E/R - Aux. Engine |  | 4
E/R - Aux. Mach. |  | 7
E/R - Boiler |  | 5
E/R - Main Engine |  | 3
E/R - Pipes/ valves & fittings |  | 9
E/R - Pumps |  | 32
E/R - Purifier |  | 6
Elect. Mach. & Equip. |  | 10
Hull & Tanks |  | 19
Inert Gas |  | 14
LSA / FFA |  | 17
Miscellaneous |  | 22
Navigation - DGPS / EPFS / AIS |  | 28
Navigation - ECDIS |  | 25
Navigation - Echo Sounder / Speed Log |  | 26
Navigation - GMDSS & Communication |  | 23
Navigation - Others |  | 11
Navigation - RADAR |  | 24
Navigation - VDR / BNWAS |  | 30

## PSC_MOU (hidden)
TITLE | PSC_MOU_description | ID
Asia and the Pacific |  | 2
Caribbean |  | 4
Europe and the North Atlantic |  | 1
Latin America |  | 3
The Black Sea region |  | 6
The Indian Ocean |  | 8
The Mediterranean |  | 7
The Riyadh MoU |  | 9
USCG |  | 10
West and Central Africa |  | 5

## Inspection_type (hidden)
TITLE | ID
Bunkering Audit | 14
Cargo Audit | 17
Engineering Audit | 16
ISM Audit | 2
ISPS Audit | 3
IT Audit | 10
MLC Audit | 1
Mooring Audit | 9
Nav Audit / Verification | 8
Ship Staff Insp. | 15
Suptd. Insp. | 13

## Deficiency_Cause (hidden)
TITLE | Deficiency_Cause_description | ID
Behaviour Based |  | 1
Equipment Related |  | 4
External Factors |  | 5
Human Error |  | 7
Inappropriate Procedure |  | 8
Industry Issue |  | 6
Knowledge Based |  | 3

## Observer_code (hidden)
TITLE | Observer_code_description | ID
Owner / Marine / Tech. Suptd. |  | 3
Ship Staff |  | 2

## Status_code (hidden)
TITLE | Status_code_description | ID
Completed |  | 6
Deferred to D D |  | 5
In progress |  | 3
Not Started |  | 2
Waiting spare |  | 4

## PSC_ref_no (hidden)
TITLE | ID
Alarms | 9
Cargo operations including equipment | 7
Certificates & Documentation | 2
Dangerous Goods | 13
Emergency Systems | 5
Fire safety | 8
ISM | 16
ISPS | 17
Life saving appliances | 12
MLC, 2006 | 18
Other | 19
Pollution Prevention | 15
Propulsion and auxiliary machinery | 14
Radio communication | 6
Safety of Navigation | 11
Structural condition | 3
Water/Weathertight condition | 4
Working and Living Conditions | 10

## Risk_value_of_obs (hidden)
Risk Value of observation | ID

## Year (hidden)
Year
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
2028
2029
2030

## Month (hidden)
Month
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec

## Date_ (hidden)
Date
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31

## Sheet1 (hidden)
| ID | E | Date Recorded | 1
| UNIQUE ID | F | Type of Deficiency | 2
1 | Date Recorded | G | Observer code | 3
ignore | Vessel Type | H | Type of Inspection | 4
| Internal / External | I | Description of Deficiency | 5
| Drydock | J | Equipment Categories | 6
| Information Sharing | K | Area of Observation | 7
| Critical_item | L | Deficiency Cause | 8
| Deficiency Type | M | VIQ Ref Number | 9
| Deficiency Cause | N | Risk Value of Obs | 10
| Inspection Type | O | PSC Ref Number | 11
| Equipments | P | PSC MOU ID | 12
| VIQ Reference Number | Q | Action Taken or Required | 13
| Risk Value of the observation | R | Target Date | 14
| PSC Reference Number | S | PO Ref No. | 15
| PSC MOU | T | Status Code | 16
| Observer Code | U | Date Completed | 17
| Target Date | V | Drydock | 18
| Status Code | W | Info Sharing | 19
| Description of Deficiency | X | Critical Item Flag | 20
| Action taken / required | Y | Audit Type | 21
| PO ref no | Z
| Date completed | AA

## Ship_information (hidden)
Ship_ID | Ship_Name | FILE_NAME
73 | MING LONG | 73_1587633350210.xlsm

## External_Deficiency_type (hidden)
TITLE | Type of deficiency_description | ID
Condn of Class / Memo |  | 5
Defect |  | 1
Non Conformity |  | 2
Observation |  | 3

## External_Inspection_type (hidden)
TITLE | ID
Cargo Audit | 17
Flag State Insp. | 5
ISM Audit | 2
ISPS Audit | 3
MLC Audit | 1
Nav Audit / Verification | 8
OM Insp. (Eg. SIRE / CDI etc.) | 6
Others (Eg. Insurance etc.) | 12
PSC Inspection | 4
Terminal Insp. | 11

## External_Observer_code (hidden)
TITLE | Observer_code_description | ID
Class Surveyor |  | 4
FSC Inspector |  | 5
Others (Eg. Insurance etc.) |  | 9
PSC Insp. |  | 6
SIRE / CDI Insp. |  | 8
Terminal Insp. |  | 7

## Sheet Version (hidden)
Version | Title
2.0 | Version 2.0