{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":29,"n_cols":28,"rows_kept":29,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","15-May-2020",null,null,"Ship Name","AQUARIUS (06-04-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,11330,"26_2020-03-17 1:47:19 PM","2020-03-16","Defect","Ship Staff","Ship Staff Insp.","Port And Stbd Lifeboat floating blocks and links are corroded and thinned down, same required to be changed.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Requsition Raised","2022-02-22","AQUA200047","Deferred to D D",null,"Yes","No","No","Internal","PICTURES OF FLOATING BLOCKS AFTER DE-RUSTING INSPECTED, FOUND TO BE IN ORDER.\nJOB OF FLOATING BLOCK RENEWAL TO BE CARRIED OUT DURING NEXT SPECIAL SURVEY."]
[null,null,null,null,10809,"26_2020-01-26 6:15:41 AM","2020-04-15","Defect","Ship Staff","Ship Staff Insp.","Hose Handling crane Luffing Cylinder Seal Leaking.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.73","Medium","","","Seal to be changed in Dry Dock","2020-07-30","","Deferred to D D",null,"Yes","No","No","Internal","DD SPEC INCLUDE SUBJECT REPAIRS AND WILL BE COMPLETED DURING DD."]
[null,null,null,null,4135,"26_2019-10-24 05:22:01.000","2020-04-30","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Few of the bunker/ballast tanks sounding caps are not fitting tightly; repairs needed to redress threads for better fit.","Miscellaneous","Cargo / Ballast Systems","Equipment Related","10.35","Very High","","","Temporary repairs with soft patch work done.Necessary permanent repairs to be carried out in DD.","2020-07-30","","Deferred to D D",null,"Yes","No","No","Internal","Noted."]
[null,null,null,null,9726,"26_15 Jan 2020 7:11:46 PM","2020-04-30","Observation","Ship Staff","Ship Staff Insp.","Provision crane limit switchs found not working.","Deck - Machinery","Eng. / Strg. Comp.","Equipment Related",10.28,"Low","Not Applicable","Not Applicable","Received spare at singapore 08.05.20. in progress","2020-07-30","AQUA205016","In progress",null,"Yes","No","No","Internal","Limit switches are ordered and connected on board. To complete repairs at DD."]
[null,null,null,null,9727,"26_15 Jan 2020 7:14:13 PM","2020-04-30","Observation","Ship Staff","Ship Staff Insp.","Hose handling crane luffing limit switch found erratic","Deck - Machinery","Eng. / Strg. Comp.","Equipment Related","8.73","Medium","","","Tourbleshooting in progress","2020-07-30","","In progress",null,"Yes","No","No","Internal","Complete health check up and repairs to complete during DD."]
[null,null,null,null,10818,"26_2020-01-30 11:35:51 AM","2020-05-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Stub pieces on the cargo lines for Air blowing connection are thinned down and rusted\n\nrequire renewal","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Presently soft patched with Devcon carried out.","2020-07-31","","Deferred to D D",null,"Yes","No","No","Internal","Noted and will be arranged during DD."]
[null,null,null,null,10814,"26_2020-01-30 11:57:03 AM","2020-05-15","Critical Equipment","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo lines flanges and various line flanges hydro blasting to be carried out.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Hydro Blasting Machine Hose and Union coupling ordered to reach to Manifold area.","2020-08-15","AQUA200006","In progress",null,"No","No","No","Internal","SPARES ORDERED AND SUPPLIED ON BOARD.   Target date has increased. Please ensure planning and execution to complete job in target period."]
[null,null,null,null,10817,"26_10 Mar 2020 1:32:05 PM","2020-05-15","Observation","Ship Staff","Ship Staff Insp.","X Band Radar Performance monitor Echo not clear. Maker suggested to renew PM Module","Navigation - RADAR","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","Received PM MOdule at singapore 08.05.20. ","2020-08-15","AQUA200042","Deferred to D D",null,"No","No","No","Internal","SPARES ORDERED AND JOB WILL BE CARRIED OUT AT NEXT SUITABLE OPPORTUNITY."]
[null,null,null,null,11329,"26_2020-03-17 1:14:13 PM","2020-05-15","Defect","Ship Staff","Ship Staff Insp.","Slop (P) Cargo Pump, Cargo Seal leaking.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Seal to be changed.","2020-08-15","","Deferred to D D",null,"Yes","No","No","Internal","Job to plan and complete during docking. Ensure spares are available ."]
[null,null,null,null,null,"26_5 Jun 2020 11:00:51 AM","2020-05-18","Observation","Ship Staff","Ship Staff Insp.","Fixed Gas Dtection system Detector Fault Alarm Received on Main control panel.","Miscellaneous","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Troubleshooting carried out, found detector fault, message sent to office, waiting for office reply.","2020-06-18",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"26_5 Jun 2020 5:51:18 PM","2020-05-26","Defect","Ship Staff","Ship Staff Insp.","Starboard Anchor Cable 6 Links bent and 1 link found elongated between No7 & No.8 Kenter Shackle.","Deck - Mooring Machinery","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable","Requsition raised for 1 shackle and 2 kenter shackle, same to be renewed during drydock.","2020-07-31",null,"Deferred to D D",null,"No",null,null,"Internal"]
[null,null,null,null,null,"26_5 Jun 2020 7:40:48 PM","2020-05-27","Observation","Ship Staff","Ship Staff Insp.","Mooring Winch drum brake band to be derusted.","Deck - Mooring Machinery","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable","Work in Progress. Aft Spring , Port and Starboard Stern line mooring winch drum brake band derusted, Brake Liners changed and Brake rendering test carried out.","2020-06-30",null,"In progress",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":122,"n_cols":28,"rows_kept":122,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","15-May-2020",null,null,"Ship Name","AQUARIUS (06-04-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,10816,"26_30 Jan 2020 3:27:32 PM",null,"Defect","Ship Staff","Suptd. Insp.","IGG Scrubber Tower  sight glass seal leaking.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Requisition raised for sight glass and gasket to renew","2020-04-30","AQUA200022","Completed",null,"No","No","No","Internal","As per update from vessel, complete glass was removed and fitted back correctly to prevent leakage."]
[null,null,null,null,4158,"26_2019-10-24 04:25:56.999","2018-09-21","Breakdown","Ship Staff","Ship Staff Insp.","Remote control for winches from remote stands are not operating","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Remote stand not in use and not required.To be removed in dry dock if possible.","2019-07-19","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,4159,"26_2019-10-24 03:01:35.000","2018-09-21","Defect","Ship Staff","Ship Staff Insp.","No canvas covers for mooring ropes on drums.To be stitiched and put in use.","Deck - Mooring Machinery","General Appearance","Human Error","","","","","Mooring ropes covered with canvas.","2019-06-11","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,4160,"26_2019-10-24 04:34:46.000","2018-09-27","Non Conformity","Ship Staff","Ship Staff Insp.","Canvas cover for magnetic compass missing.","Navigation - Others","Navigation","Equipment Related","","","","","Canvas cover stitched and covered.","2019-11-06","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,4168,"26_2019-10-24 05:15:47.999","2018-12-22","Defect","Ship Staff","Ship Staff Insp.","Safety latch for lifting hook missing.","Deck - Pipe / Fittings","Cargo / Ballast Systems","External Factors","","","","","Same rectified and replaced.","2019-11-30","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,8651,"26_Wed Dec 04 2019 09:10:14 GMT+0000 (Coordinated Universal Time)","2019-01-12","Breakdown","Ship Staff","Ship Staff Insp.","Framo / Mooring Winch System Hydraulic Main High Pressure Pipeline busted ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Both High & Low Pressure pipelines drained into system tank, High Pressure pipeline removed and transfered to E/Room workshop and repaired with dubbler. High Pressure line fitted back in place after repairs Both pipelines filled with Hydraulic oil and system pressure tested.","2019-02-12","","Completed","2019-02-12","No","No","No","Internal"]
[null,null,null,null,8669,"26_Sat Dec 21 2019 09:49:29 GMT+0000 (Coordinated Universal Time)","2019-01-18","Defect","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","One synthetic Mooring ropes used as an aft spring had broken strands at lengths,","Miscellaneous","Mooring","Inappropriate Procedure","9.17","High","","","Mooring Ropes renewed with spares available onboard. ","2019-01-18","","Completed","2019-01-20","No","No","No","External"]
[null,null,null,null,8670,"26_Sat Dec 21 2019 10:00:33 GMT+0000 (Coordinated Universal Time)","2019-01-18","Defect","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Printer to Engine room Alarm monitoring system was out of order. ","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","New printer already recieved onboard which had a wrong typr of connector. Same ordered and rectified prior departing the port. ","2019-02-22","","Completed","2019-01-19","No","No","No","External"]
[null,null,null,null,8671,"26_Sat Dec 21 2019 10:04:56 GMT+0000 (Coordinated Universal Time)","2019-01-18","Defect","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Fresh water was observed leaking through a hole. IWO slop port tank.","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related","11.4","Very High","","","Leaking section of FW Pipe overhauled & drction renewed leak stopped. ","2019-02-18","","Completed","2019-01-21","No","No","No","External"]
[null,null,null,null,8672,"26_Sat Dec 21 2019 10:08:27 GMT+0000 (Coordinated Universal Time)","2019-01-18","Defect","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Two Flood lights ( one on port Bridge wing & other on midship post were found out of order.","Elect. Mach. & Equip.","General Appearance","Equipment Related","11.9","Low","","","Rectified during the inspection.","2019-01-19","","Completed","2019-01-18","No","No","No","External"]
[null,null,null,null,10821,"26_30 Jan 2020 7:12:54 AM","2019-02-02","Observation","FSC Inspector","PSC Inspection","Chemical dosing pump of sewage treatment plant not give out discharge","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","6.14","High","Pollution Prevention",2,"Chemical dosing pump overhauled and all connection and pipe removed and cleaned.Pump tried out working satisfactory","2019-02-15","","Completed","2019-02-02","No","No","No","External"]
[null,null,null,null,8673,"26_Sat Dec 21 2019 11:47:28 GMT+0000 (Coordinated Universal Time)","2019-02-02","Defect","PSC Insp.","PSC Inspection","No identification check was carried out when PSCO boarded the vessel.","Miscellaneous","ISPS Related","Human Error","","","ISPS","","Crew was trained and strict security implementation completed prior the inspector left the vessel.","2019-02-25","","Completed","2019-11-02","No","No","No","External"]
[null,null,null,null,8674,"26_Sat Dec 21 2019 11:52:30 GMT+0000 (Coordinated Universal Time)","2019-02-02","Defect","FSC Inspector","PSC Inspection","RPM meter of Main Engine on Local manoevvuring platform was showing around 10 rpm ahead when M/E was stopped.","E/R - Main Engine","Emgcy. Systems","Equipment Related","","","Propulsion and auxiliary machinery","","Rectified before the ispector left the vessel. ","2019-02-28","","Completed","2019-02-14","No","No","No","External"]
[null,null,null,null,8675,"26_Sat Dec 21 2019 11:56:01 GMT+0000 (Coordinated Universal Time)","2019-02-02","Defect","PSC Insp.","PSC Inspection","Spoiled food was found in vegetable room","Miscellaneous","General Appearance","Human Error","","","Propulsion and auxiliary machinery","","Same shifted quickly nto garbage area and vegetable room cleaned","2019-02-27","","Completed","2019-11-02","No","No","No","External"]
[null,null,null,null,8652,"26_Fri Dec 20 2019 14:22:18 GMT+0000 (Coordinated Universal Time)","2019-03-12","Breakdown","Ship Staff","Ship Staff Insp.","Leak on 5P cargo pipeline in a place where stripping line of 5P Framo Pump connects to 5P Main Cargo line.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Cold work carried out with devcon and corddo bond","2019-06-12","","Completed","2019-12-05","No","No","No","Internal"]
[null,null,null,null,4166,"26_2019-10-24 19:33:00.000","2019-05-08","Defect","Ship Staff","Ship Staff Insp.","Air cooler cleaning line from pump to nozzles and drain back chocked","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pipe removed and nozzzle cleaned","2019-09-30","","Completed","2019-09-19","No","No","No","Internal"]
[null,null,null,null,4144,"26_2019-10-24 08:32:28.000","2019-05-09","Defect","Ship Staff","Ship Staff Insp.","Scupper no.A2 damaged","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related","","","","","Scupper replaced","2019-06-11","AQUA190245","Completed","2020-01-03","No","No","No","Internal","to be arranged at Singapore call."]
[null,null,null,null,8653,"26_Fri Dec 20 2019 14:33:11 GMT+0000 (Coordinated Universal Time)","2019-05-12","Breakdown","Ship Staff","Ship Staff Insp.","Main Deck air Line leaking at 6 W COT","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Deck air line isolated, line removed and transferrd to E/Room for Hot work and fitted back after carrying out hort work","2019-07-12","","Completed","2019-12-07","No","No","No","Internal"]
[null,null,null,null,8668,"26_Sat Dec 21 2019 09:43:48 GMT+0000 (Coordinated Universal Time)","2019-05-21","Defect","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Records of Engine Room (Part I) ORBs were only available since 02 OCT 2019. Records of earlier ORB part I entries ( for last 3 years required by marpol Annex1, Chapter 3C - Reg 17) were not available.","Miscellaneous","Cert. & Docu.","Industry Issue","2.1","Very High","","","Master advised that the ORB's for that period was not retained & handed over by the last operator. After taken over all ORB's were maintained & retained onboard.","2019-06-21","","Completed","2019-05-22","No","No","No","External"]
[null,null,null,null,8660,"26_Sat Dec 21 2019 07:40:38 GMT+0000 (Coordinated Universal Time)","2019-06-06","Defect","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","Second Engineer national certificate of competency was Marine Engineer Oficer Class II, however as per liberian Flag endorsement for his national COC.he was allowed to serve in capacity of Chief Engineer.","Miscellaneous","Cert. & Docu.","Industry Issue","4.3","Medium","","","Flag state informed & his Liberian endorsement was corrected. ","2019-06-07","","Completed","2019-07-06","No","No","No","External"]
[null,null,null,null,8661,"26_Sat Dec 21 2019 07:58:17 GMT+0000 (Coordinated Universal Time)","2019-06-06","Defect","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","On Wharf ladder which was in use, the load tested to,maximum angle of inclination and date of load test was not marked.","Deck - Machinery","MLC Related","Human Error","","","","","All markings such as load tested/max inclination angle were stencilled on the wharf ladder platform.","2019-07-07","","Completed","2019-06-07","No","No","No","External"]
[null,null,null,null,8662,"26_Sat Dec 21 2019 08:06:48 GMT+0000 (Coordinated Universal Time)","2019-06-06","Defect","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","Engine room 1st deck fire zone was noted isolated and disabled.","Elect. Mach. & Equip.","Emgcy. Systems","Inappropriate Procedure","5.35","Medium","","","Immediately rectificed the zone enabled. And log started when this gets isolated for Hot work in E/Rm workshop.","2019-07-06","","Completed","2019-06-07","No","No","No","External"]
[null,null,null,null,8663,"26_Sat Dec 21 2019 08:10:01 GMT+0000 (Coordinated Universal Time)","2019-06-06","Defect","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","In emergency generator room on 220V emergency switchboard ow isulation of 0.0 Megaohm was noted.","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","","","","","Same check & corrected","2019-07-07","","Completed","2019-06-07","No","No","No","External"]
[null,null,null,null,8664,"26_Sat Dec 21 2019 07:50:04 GMT+0000 (Coordinated Universal Time)","2019-06-06","Defect","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","The Carbon Monoxide (CO) low level alarm setting on portable multi gas meters was set at 30 PPM whereas the TLV TWA of CO was 25 PPM. ","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","Correction made on personal gas meters as required druing the next shore servicing. ","2019-06-07","","Completed","2019-07-06","No","No","No","External"]
[null,null,null,null,8665,"26_Sat Dec 21 2019 08:17:22 GMT+0000 (Coordinated Universal Time)","2019-06-06","Other","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","Vessel had cargo hose fro portable framo pump of size 30 m x 8\" x1 no. which was last tested to 5.0 bar on 27-dec-2-18 howerver elongation test & electrical contimnuity test was not carried out and no record was available.","Miscellaneous","Cargo / Ballast Systems","Inappropriate Procedure","","","","","Electirical continuity & elongation test completed & entries made accordingly. ","2019-07-07","","Completed","2019-06-15","No","No","No","External"]
[null,null,null,null,8666,"26_Sat Dec 21 2019 08:24:39 GMT+0000 (Coordinated Universal Time)","2019-06-06","Defect","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","1.Soft patch was noted on steam branch heating line(size 150mm) located on main deck midship area and straub coupling was put to arrest leak. 2. At various places on main deck rust sposts on pipe work","Miscellaneous","General Appearance","Equipment Related","","","","","Steam line renewed with spare pipe available. And continous fabric maintenance upgrade is in progress. ","2019-07-07","","Completed","2019-07-07","No","No","No","External"]
[null,null,null,null,4167,"26_2019-10-24 08:00:46.000","2019-07-18","Defect","Ship Staff","Ship Staff Insp.","Manifold valve port an stbd including the reducer 14''x16'' require dersuting and attention.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Dersuting/painting completed.","2019-06-11","","Completed","2019-10-25","No","No","No","Internal"]
[null,null,null,null,4161,"26_2019-10-24 08:18:49.000","2019-07-22","Defect","Ship Staff","Ship Staff Insp.","Main and branches of steam line  inlet and return leaking and corroded at places.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","All necessary repairs/replacement/painting of all Cargo tank steam lines completed.","2019-11-30","","Completed","2019-10-23","No","No","No","Internal"]
[null,null,null,null,8658,"26_Sat Dec 21 2019 07:12:21 GMT+0000 (Coordinated Universal Time)","2019-08-04","Defect","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","The item garbage treatment plant in the certificate of the satement compliance with the equipments for the prevention of pollution by garbage was not selected. Actually one communitor in galley was used.","Miscellaneous","Cert. & Docu.","Industry Issue","2.1","Very High","","","Statement of compliance new issued by class BV","2019-09-04","","Completed","2019-07-08","No","No","No","External"]
[null,null,null,null,8659,"26_Sat Dec 21 2019 07:26:36 GMT+0000 (Coordinated Universal Time)","2019-08-04","Defect","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Onreview of Oil record book Part II, ODME was fault in measure cell on 21 July 2019, and the system has been made operational on 23 july 2019, but the time of this system operational was not recorded in Oil Record Book again. ","Cargo Mach.","Cargo / Ballast Systems","Human Error","6.13","Low","","","Relevant entries made in the ORB Part II. ","2019-04-09","","Completed","2019-08-05","No","No","No","External"]
[null,null,null,null,8734,"26_Sun Dec 22 2019 14:11:30 GMT+0000 (Coordinated Universal Time)","2019-08-05","Defect","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","No ECDIS repeater panel in Masters cabin","Navigation - ECDIS","Navigation","Equipment Related","","","","","ECDIS Repeater to be fitted in masters cabin","2019-07-06","","Completed","2019-06-05","No","No","No","Internal"]
[null,null,null,null,8735,"26_Sun Dec 22 2019 14:19:22 GMT+0000 (Coordinated Universal Time)","2019-08-05","Defect","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","Magnetic compass deviation more than 15 deg in some heading. ","Navigation - Others","Navigation","Equipment Related","","","","","Magnetic deviation card by shore compass adjustor ","2019-06-30","","Completed","2019-06-20","No","No","No","Internal"]
[null,null,null,null,4163,"26_2019-10-25 11:01:06.000","2019-08-30","Defect","Ship Staff","Ship Staff Insp.","No fresh water supply on deck.Fresh water main line leaking /block and corroded near 1W,3W,5W,6W COT area.","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","All fresh water lines opened /repaired/fabricated & painted.Fresh water supply reinsted right upto forecastle.","2019-10-30","","Completed","2019-10-23","No","No","No","Internal"]
[null,null,null,null,4149,"26_2019-10-24 19:42:09.000","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Air conditioning compressor drier not replaced since take over.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Air condition plant performance checked found good, No sign of moisture found in system.Requistion raised to maintain ROB onboard.","2020-03-30","AQUA190255","Completed","2020-01-25","No","No","No","Internal","noted"]
[null,null,null,null,4150,"26_2019-10-24 19:44:22.000","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Provision plant drier not been replaced since take over.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Ref. plant performance checked found satisfactory, No visiual sign of moisture found in system.Requistion raised to maintain ROB onboard. ","2020-03-30","AQUA190256","Completed","2020-01-27","No","No","No","Internal","noted."]
[null,null,null,null,4151,"26_2019-10-24 19:47:10.000","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ECR telegraph misalignment alarm active.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","10.33","High","","","Telegraph chain worn out an needs replacement. Requistion raised .","2019-11-30","AQUA190218","Completed","2019-12-05","No","No","No","Internal"]
[null,null,null,null,4152,"26_2019-10-24 19:49:44.000","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port side grey water line has minor leak\t","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","OB valve to be renewed with the spare received at Singapore. Awaitng suitable opportunity for vessel in Ballast.","2019-11-30","","Completed","2020-01-15","No","No","No","Internal","noted."]
[null,null,null,null,4153,"26_2019-10-24 19:52:46.000","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pressure regulating valve for ME FO line leaking","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","Will be renewed in DD while system in MGO","2020-04-30","AQUA190234","Completed","2020-04-30","No","No","No","Internal","Job completion noted."]
[null,null,null,null,4169,"26_2019-10-24 19:38:43.000","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No record of steering gear filter replaced since take over","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Filter replaced and record for same maintained near the steering gear.","2019-09-30","","Completed","2019-09-20","No","No","No","Internal"]
[null,null,null,null,4156,"26_2019-10-25 10:52:12.000","2019-09-05","Defect","Ship Staff","Ship Staff Insp.","Port & stbd manifold wheel valves badly corooded.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Manifold Valve Wheels replaced","2019-11-30","AQUA190245","Completed","2019-11-04","No","No","No","Internal","Arranging supply at Singapore call."]
[null,null,null,null,8644,"26_Thu Oct 24 2019 08:32:28 GMT+0000 (Coordinated Universal Time)","2019-09-05","Defect","Ship Staff","Ship Staff Insp.","Scupper no.A2 damaged","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related","","","","","Replaced with New Scupper","2019-11-06","AQUA190245","Completed","2019-10-11","No","No","No","Internal"]
[null,null,null,null,8736,"26_Sun Dec 22 2019 14:45:23 GMT+0000 (Coordinated Universal Time)","2019-09-08","Defect","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","DGPS antenna securing arrangement needs maintenance, Vibration at High RPM coupled with strong winds have toppled the antenna.","Navigation - DGPS / EPFS / AIS","Navigation","Equipment Related","","","","","Antenna resecured in place properly","2019-11-11","","Completed","2019-08-10","No","No","No","Internal"]
[null,null,null,null,8655,"26_Fri Dec 20 2019 14:39:46 GMT+0000 (Coordinated Universal Time)","2019-09-12","Defect","Ship Staff","Ship Staff Insp.","Starboard Windlass Hydraulic Pipeline section badly corroded.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","New Pipeline fabricated and replaced the fabricated section.","2019-12-12","","Completed","2019-12-11","No","No","No","Internal","noted"]
[null,null,null,null,4145,"26_2019-10-24 08:36:33.000","2019-09-17","Defect","Ship Staff","Ship Staff Insp.","Fwd mooring winches hydraulic line connectors for inlet line leaking.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Fittings replaced","2019-11-11","","Completed","2019-12-28","No","No","No","Internal","Fittings supplied."]
[null,null,null,null,8645,"26_Thu Oct 24 2019 08:47:52 GMT+0000 (Coordinated Universal Time)","2019-10-02","Defect","Ship Staff","Ship Staff Insp.","2 Fresh water valve  near 2W & 3W COT area found leaking.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Replaced Valves","2019-11-06","AQUA190245","Completed","2019-01-11","No","No","No","Internal","Noted FW valves replaced"]
[null,null,null,null,8738,"26_Sun Dec 22 2019 14:55:11 GMT+0000 (Coordinated Universal Time)","2019-10-08","Defect","Owner / Marine / Tech. Suptd.","Mooring Audit","Brake band on Stbd Windlass needs renewal","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Brake bands renewed ","2019-08-11","","Completed","2019-09-16","No","No","No","Internal"]
[null,null,null,null,8739,"26_Sun Dec 22 2019 15:00:56 GMT+0000 (Coordinated Universal Time)","2019-10-08","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","PV Breaker level gauge transparent cover dirty- same needs to be cleaned/ renewed.","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","Level gauge glass renewed.","2019-08-11","","Completed","2019-09-08","No","No","No","Internal"]
[null,null,null,null,8740,"26_Sun Dec 22 2019 15:04:41 GMT+0000 (Coordinated Universal Time)","2019-10-08","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Ballast water record log book not used for record keeping.REcords filled in printed forms.","Documentation,Miscellaneous","Cargo / Ballast Systems","Inappropriate Procedure","","","","","New record books started & information transfered into log book from forms. ","2019-10-09","","Completed","2019-08-14","No","No","No","Internal","Noted"]
[null,null,null,null,8741,"26_Sun Dec 22 2019 15:19:06 GMT+0000 (Coordinated Universal Time)","2019-10-08","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Manifold reducres needs maintenance & inspection. ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Fabric maintenance completed on all manifold reducres. A few new ones ordered. ","2019-10-11","","Completed","2019-11-09","No","No","No","Internal"]
[null,null,null,null,4164,"26_2019-10-24 20:02:19.000","2019-10-10","Defect","Ship Staff","Ship Staff Insp.","Main Engine fuel valve testing machine FO container cracked","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Acrylic sheet cover created for same.","2019-10-25","","Completed","2019-10-23","No","No","No","Internal","Noted."]
[null,null,null,null,4162,"26_2019-10-24 09:12:04.999","2019-10-24","Defect","Ship Staff","Ship Staff Insp.","Fire line no.2 port side near fwd spring winch found leaking from 2 places due to pin hole.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","New pipe fabricated and put in place.","2019-10-24","","Completed","2019-10-25","No","No","No","Internal","Noted"]
[null,null,null,null,8646,"26_Fri Nov 15 2019 17:38:00 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","VRCS auto start and stop of Pump No 2 not working","Deck - Machinery","Mooring","Equipment Related","","","","","Requiasiton raised","2019-11-20","AQUA 190278","Completed","2019-11-15","No","No","No","Internal","Noted"]
[null,null,null,null,8647,"26_Fri Nov 15 2019 17:44:25 GMT+0000 (Coordinated Universal Time)","2019-11-06","Defect","Ship Staff","Ship Staff Insp.","LT cooler SW inlet pipe leaking","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Pipe renewed","2019-11-20","","Completed","2019-11-12","No","No","No","Internal","Noted"]
[null,null,null,null,8641,"26_Fri Nov 15 2019 08:43:41 GMT+0000 (Coordinated Universal Time)","2019-11-11","Defect","Ship Staff","Ship Staff Insp.","Deck Seak SW Filling line found to be leaking","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","SW filling pump to be stopped, SW filling line to be removed and new SW filling line to be fabricated.","2019-11-13","","Completed","2019-11-14","No","No","No","Internal"]
[null,null,null,null,8642,"26_Fri Nov 15 2019 09:20:14 GMT+0000 (Coordinated Universal Time)","2019-11-11","Defect","Ship Staff","Ship Staff Insp.","Fire Branch Line on 6w COT found Leaking.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Fire Branch line to be removed and transfered to E/Room workshop to carry out Hot Work","2019-11-14","","Completed","2019-11-14","No","No","No","Internal","Noted"]
[null,null,null,null,8638,"26_Fri Nov 15 2019 17:54:08 GMT+0000 (Coordinated Universal Time)","2019-11-12","Defect","Ship Staff","Ship Staff Insp.","AE No 3 LO temperature rising during operation.\t","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","To renew thermostatic valve. Requisition raised.","2019-12-25","AQUA 190247","Completed","2020-01-06","No","No","No","Internal","Will be supplied at coming port call."]
[null,null,null,null,8643,"26_Fri Nov 15 2019 09:35:52 GMT+0000 (Coordinated Universal Time)","2019-11-14","Defect","Ship Staff","Ship Staff Insp.","Fire Branch Line at 2w COT found leaking","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Fire branch line to be removed and transfered to E/room Workshop to carry out hot work","2019-11-16","","Completed","2019-11-16","No","No","No","Internal","Noted"]
[null,null,null,null,8639,"26_Sat Nov 23 2019 06:33:36 GMT+0000 (Coordinated Universal Time)","2019-11-20","Defect","Ship Staff","Ship Staff Insp.","SOME OF NATURAL VENT FLAPS FOR ACCOMODATION ARE CORRODED AND WASTED.","Accommodation","Structural Condn. / WT integrity ","Equipment Related","","","","","Wasted areas repaired with inserts by taking the vent flaps in E/Room Workshop","2019-12-05","","Completed","2019-12-23","No","No","No","Internal","noted and pls send details so that we can ask ashore for fabrication."]
[null,null,null,null,8648,"26_Sat Nov 23 2019 06:43:54 GMT+0000 (Coordinated Universal Time)","2019-11-21","Breakdown","Ship Staff","Ship Staff Insp.","Steam Line leaking on 2 sections of Main Steam line.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Main Steam line Isolated, Main Steam Line removed from place and taken to E/Room, 1 section Fabricated with new Pipeline and other line repaired.","2019-11-22","","Completed","2019-11-22","No","No","No","Internal","Noted"]
[null,null,null,null,4133,"26_2019-10-24 05:07:30.000","2019-11-25","Defect","Ship Staff","Ship Staff Insp.","Pipelines on main deck require cosmetic upgradation","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Dersuting and painting works for main deck pipelines & steam line in progress.","2020-04-26","","Completed","2020-04-15","No","No","No","Internal","This is ongoing job."]
[null,null,null,null,8657,"26_Wed Dec 04 2019 06:34:02 GMT+0000 (Coordinated Universal Time)","2019-11-26","Breakdown","Ship Staff","Ship Staff Insp.","Ballast tank vent covers of 1S, 1P & 2P WBT are corroded and wasted.","Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related","","","","","New covers fabricated and replaced the wasted covers.","2019-06-12","","Completed","2019-06-12","No","No","No","Internal","Noted"]
[null,null,null,null,8737,"26_Sun Dec 22 2019 14:51:32 GMT+0000 (Coordinated Universal Time)","2019-12-08","Defect","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","The Ships Bell required on forward section of the vessel is missing. Required as per Colregs","Navigation - Others","Navigation","Equipment Related","","","","","Ships bell fitted back in place on teh forward mast. ","2019-11-09","","Completed","2019-08-15","No","No","No","Internal"]
[null,null,null,null,8640,"26_Fri Dec 20 2019 16:19:13 GMT+0000 (Coordinated Universal Time)","2019-12-17","Breakdown","Ship Staff","Ship Staff Insp.","Main Steam Line Section at 2W CoT is Leaking","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Section removed and taken to E/Room for fabrication of new steam line","2019-12-22","","Completed","2019-12-22","No","No","No","Internal","Noted that pipe section fabricated and completed. Pls check other lines too and report."]
[null,null,null,null,8654,"26_Fri Dec 20 2019 14:54:12 GMT+0000 (Coordinated Universal Time)","2019-12-17","Breakdown","Ship Staff","Ship Staff Insp.","Port Windlass Hydraulic Pipe line leaking","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Hydraulic PipeLine removed transfered to E/Room carried out hot work and and fitted back","2019-12-19","","Completed","2019-12-18","No","No","No","Internal","Noted. Please completely check all other hydraulic lines closely to ensure the health is good."]
[null,null,null,null,8656,"26_Fri Dec 20 2019 16:13:20 GMT+0000 (Coordinated Universal Time)","2019-12-17","Breakdown","Ship Staff","Ship Staff Insp.","Main Deck Air Pipeline at 5W COT's  Leaking","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Deck air isolated, Leaking section of Main deck air pipeline removed, New pipeline fabricated and replaced.","2019-12-20","","Completed","2019-12-19","No","No","No","Internal","Noted. Please check the complete deck air line and rectify any other leaks."]
[null,null,null,null,10820,"26_2020-01-27 3:26:12 AM","2020-01-14","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mooring Winch Hydraulic Brake hoses to be renewed.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Mooring Winch Hydraulic Brake hoses checked and found in good condition. vessel has 1 spare hose.","2020-02-25","","Completed","2020-01-16","No","No","No","Internal"]
[null,null,null,null,10833,"26_2020-01-27 2:02:31 PM","2020-01-14","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","port anchor Bow Stopper pin has thinned down same to be ordered and renewed.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","New Pin Fabricated","2020-02-24","","Completed","2020-02-18","No","No","No","Internal"]
[null,null,null,null,10812,"26_2020-01-28 4:31:04 AM","2020-01-16","Defect","Ship Staff","Ship Staff Insp.","Mooring Winch Hydraulic Brake cylinder head seal is leaking, Same required to be changed.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","All Leaking Hydraulic brake cylinder seals changed.","2020-03-25","AQUA200024","Completed","2020-03-25","No","No","No","Internal","Hoses were already supplied and renewed  by staff. As well  as seals were renewed. \nNow few ones, relief valves need replacement., we will supply once requisition is raised. \nManual breaks are in good order."]
[null,null,null,null,10828,"26_2020-01-30 12:05:43 PM","2020-01-21","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Manifold Flanges and Reducers to be De-Rusted and Painted","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Manifold Flanges and Reducers  De-Rusted and Painted","2020-01-22","","Completed","2020-01-22","No","No","No","Internal"]
[null,null,null,null,10810,"26_2020-01-26 7:49:49 AM","2020-01-24","Observation","Ship Staff","Ship Staff Insp.","Grating on Catwalk and PV Valve stands are badly corroded.","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Gratings on Catwalk changed. Changing of gratings on PV Valves Stands and Access to Catwalk in progress","2020-04-15","AQUA200005","Completed","2020-04-15","No","No","No","Internal","NOTED THAT GRATINGS RENEWAL DONE WITH SUPPLIED UNITS."]
[null,null,null,null,10825,"26_30 Jan 2020 3:37:18 PM","2020-01-24","Defect","Ship Staff","Ship Staff Insp.","Deck seal sea water line internal diameter reduced due to scale deposits  ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Deck seal sea water line to renew from pump to Deck Seal Tank  ","2020-03-01","","Completed","2020-02-04","No","No","No","Internal"]
[null,null,null,null,10819,"26_2020-01-26 7:53:16 AM","2020-01-25","Defect","Ship Staff","Ship Staff Insp.","Aft Spring Mooring winch hydraulic return pipeline found leaking.","Deck - Pipe / Fittings","Mooring","Equipment Related","","","","","New pipeline to be fabricated and replaced the damaged pipeline.","2020-01-28","","Completed","2020-01-28","No","No","No","Internal"]
[null,null,null,null,10831,"26_30 Jan 2020 3:31:37 PM","2020-01-25","Defect","Ship Staff","Ship Staff Insp.","Scrubber cooling sea water inlet pipe from scrubber pump to Tower section thinned down. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Pipe renewed","2020-03-04","","Completed","2020-03-10","No","No","No","Internal"]
[null,null,null,null,10813,"26_2020-01-30 11:40:51 AM","2020-01-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main deck area bays - COT 2w, 3w, 4w and under manifold areas has scattered rust on\n\nthe deck, Transverse beams and under pipeline supports.","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Hydro-Blasting to be carried out followed by Buffing / Primer / Painting","2020-04-30","","Completed","2020-04-30","No","No","No","Internal","NOTED VIA WEEKLY WORK DONE REPORT. ENSURE DECK AREAS ARE MAINTAINED RUST FREE ."]
[null,null,null,null,10815,"26_2020-01-30 12:11:38 PM","2020-01-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aft superstructure to be de-rusted and panted. All Primered areas to be final coated. Funnel deck and other accommodation decks to be painted.","Accommodation ","General Appearance","Equipment Related","","","","","Superstructure Aft From Bridge Deck to A-Deck De-Rusted, Buffing Carried out followed by 1st Coat Primer and 2nd Coat Primer. Bridge Deck Full Coat carried out for Bulkhead and Exterior Deck.","2020-04-15","","Completed","2020-04-15","No","No","No","Internal","JOB WELL DONE!"]
[null,null,null,null,10822,"26_2020-01-30 11:45:23 AM","2020-01-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hydro blasting of mooring winches on Forecastle to be completed.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Hydro Blasting Followed by Buffing / 1st Coat Primer/ 2nd Coat Primer Carried out. Ful l coat painting carried out.","2020-02-13","","Completed","2020-01-02","No","No","No","Internal"]
[null,null,null,null,10834,"26_2020-01-30 12:01:29 PM","2020-01-29","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steam Supply Line for 5W COT Required to be fabricated.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","New Steam Pipeline fabricated and replaced the damged sections.","2020-02-13","","Completed","2020-05-03","No","No","No","Internal"]
[null,null,null,null,10823,"26_9 Feb 2020 7:38:47 AM","2020-02-03","Defect","Ship Staff","Ship Staff Insp.","Main Deck Air pipeline at 5W CoT Leaking.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Main Deck air pipeline section removed and replaced with new fabricated pipeline,","2020-02-09","","Completed","2020-02-08","No","No","No","Internal"]
[null,null,null,null,11336,"26_4 Apr 2020 1:11:45 PM","2020-02-03","Breakdown","Ship Staff","Ship Staff Insp.","Boiler water Circulating Pump leaking No.2","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pump overhauled and put in service","2020-03-29","AQUA205008","Completed","2020-03-28","No","No","No","Internal"]
[null,null,null,null,10824,"26_9 Feb 2020 7:43:38 AM","2020-02-05","Defect","Ship Staff","Ship Staff Insp.","No. 4 Foam Monitor found ceased and not rotating 360 Deg.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Foam Monitor overhauled and greased.","2020-02-08","","Completed","2020-02-07","No","No","No","Internal"]
[null,null,null,null,10832,"26_10 Mar 2020 1:42:31 PM","2020-02-08","Breakdown","Ship Staff","Ship Staff Insp.","STP Plant blower motor winding got damaged and giving low insulation.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Motor renewed along with blower","2020-02-29","","Completed","2020-03-02","No","No","No","Internal"]
[null,null,null,null,10826,"26_2020-02-19 11:43:56 AM","2020-02-19","Defect","Ship Staff","Ship Staff Insp.","Hose Handling Crane Jib Head Sheavs found Not moving.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Sheaves revomed and overhauled and greased.","2020-03-15","","Completed","2020-02-29","No","No","No","Internal"]
[null,null,null,null,10827,"26_2020-02-19 11:47:35 AM","2020-02-19","Defect","Ship Staff","Ship Staff Insp.","Port Side Ballast Pump Deck Air priming line found leaking.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Pipe sections removed and transfered to Engine room  work shop, new sections fabricated and replaced the damaged sections.","2020-02-21","","Completed","2020-02-21","No","No","No","Internal"]
[null,null,null,null,10829,"26_1 Mar 2020 6:47:05 AM","2020-02-23","Defect","Ship Staff","Ship Staff Insp.","Fwd Steam By-Pass pile line section found leaking","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Pipeline section removed and transferred to Engine room workshop, New pipeline fabricated and replaced the damaged section.","2020-02-29","","Completed","2020-02-29","No","No","No","Internal"]
[null,null,null,null,10830,"26_1 Mar 2020 6:49:31 AM","2020-02-23","Defect","Ship Staff","Ship Staff Insp.","3S Steam Manifold Pipeline Section found Leaking.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Pipeline section removed and transferred to Engine room workshop, New pipeline fabricated and replaced the damaged section.","2020-02-29","","Completed","2020-02-29","No","No","No","Internal"]
[null,null,null,null,10835,"26_1 Mar 2020 6:52:31 AM","2020-02-24","Defect","Ship Staff","Ship Staff Insp.","4W Steam branch pipeline leaking.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","4W Steam Branch Pipeline Repaired.","2020-03-03","","Completed","2020-03-03","No","No","No","Internal"]
[null,null,null,null,null,"26_2020-01-27 3:13:14 AM","2020-02-28","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Temperature Sensor of 2P COT Showing erratic.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","2P COT Temprature sensor Renewed.","2020-05-30","AQUA205006","Completed","2020-05-15","No",null,null,"Internal"]
[null,null,null,null,11337,"26_4 Apr 2020 1:18:05 PM","2020-03-11","Breakdown","Ship Staff","Ship Staff Insp.","Scrubber pump suction line T section leaking,pipe holed","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.31","Very High","","","new pipe fabricated and fixed.","2020-03-14","","Completed","2020-03-19","No","No","No","Internal"]
[null,null,null,null,11332,"26_2020-03-17 8:51:38 AM","2020-03-13","Defect","Ship Staff","Ship Staff Insp.","Sbtd mooring winch Hydraulic pipeline on Poop deck found leaking.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","New sections fabricated and replaced the old leaking sections.","2020-03-16","","Completed","2020-03-15","No","No","No","Internal"]
[null,null,null,null,11338,"26_2020-03-17 8:34:38 AM","2020-03-13","Defect","Ship Staff","Ship Staff Insp.","3 Sections of Deck Air line for Stbd Ballast pump found  leaking. ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","1 Section fabricated and renewed, Fabrication of 2 new sections in progress.","2020-03-20","","Completed","2020-03-20","No","No","No","Internal"]
[null,null,null,null,11331,"26_2020-03-17 8:43:51 AM","2020-03-14","Defect","Ship Staff","Ship Staff Insp.","Deck Air Pipeline for Port and Stbd gangway and badly corroded. ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","New Sections fabricated and changed the corroded sections for port and Stbd deck air supply pipeline.","2020-03-15","","Completed","2020-03-15","No","No","No","Internal"]
[null,null,null,null,4136,"26_2019-10-24 05:25:49.999","2020-03-15","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Supports for conduit/pipes to de-rust and paint soon; rust on deck is mainly spreading due to rusty tray","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Work in progress","2020-05-15","","Completed","2020-04-15","No","No","No","Internal","THIS IS REGULAR MAINTENANCE JOB AND NEEDS CONTINUOUS MONITORING AND MAINTENANCE."]
[null,null,null,null,11333,"26_2020-03-17 8:57:12 AM","2020-03-15","Defect","Ship Staff","Ship Staff Insp.","Slop Steam Supply pipeline section found leaking.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","New section fabricated and replaced the leaking section.","2020-03-18","","Completed","2020-03-16","No","No","No","Internal"]
[null,null,null,null,null,"26_2020-03-17 10:14:53 AM","2020-03-16","Defect","Ship Staff","Ship Staff Insp.","Aft Spring Mooring winch Hydraulic brake relief valve badly corroded and found leaking.","Deck - Mooring Machinery","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable","Hydraulic Brake control block changed","2020-05-31",null,"Completed","2020-05-15","No",null,null,"Internal"]
[null,null,null,null,11335,"26_4 Apr 2020 1:06:47 PM","2020-03-18","Breakdown","Ship Staff","Ship Staff Insp.","Fresh Water Generator sea water line leaking at various Locations.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.31","Very High","","","All leaking pipe lines renewed with fabricated new lines.","2020-03-25","","Completed","2020-03-24","No","No","No","Internal"]
[null,null,null,null,11334,"26_29 Mar 2020 2:39:43 AM","2020-03-20","Defect","Ship Staff","Ship Staff Insp.","Main Steam Pipeline section aft of Midship crane found leaking.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Pipeline section removed and transfered to Engine room workshop, Fabricated New section and replaced old leaking section.","2020-03-22","","Completed","2020-03-22","No","No","No","Internal"]
[null,null,null,null,11328,"26_4 Apr 2020 3:39:49 PM","2020-03-30","Breakdown","Ship Staff","Ship Staff Insp.","Fwd LT Cooler Sea Water outlet line leaking","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.31","Very High","","","New pipe line fabrication in progress.","2020-04-30","","Completed","2020-04-30","No","No","No","Internal","PIPELINE IS FABRICATED AS PER WEEKLY REPORT, PLEASE CLOSE THE OBSERVATION. SUGGEST TO MAKE ONE SPARE/STANDBY ADDITIONAL OUTLET LINE SECTION."]
[null,null,null,null,null,"26_2019-10-24 19:55:33.000","2020-03-30","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Exhaust truncking below the EGB having leak","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.19,"Very High","Not Applicable","Not Applicable","Economizer gas leak, permanent repair carried out.","2020-07-30",null,"Completed","2020-05-26","Yes",null,null,"Internal"]
[null,null,null,null,11326,"26_2020-04-03 2:37:42 AM","2020-03-31","Defect","Ship Staff","Ship Staff Insp.","Main Steam Pipeline section at 4 W COT found leaking.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Pipeline Section removed and transfered to Engine room workshop for fabricating New Pipline.","2020-04-20","","Completed","2020-04-15","No","No","No","Internal","PIPELINE IS RENEWED AS PER WEEKLY REPORT, PLEASE UPDATE THE RECORD."]
[null,null,null,null,11327,"26_2020-04-04 9:32:16 AM","2020-04-01","Defect","Ship Staff","Ship Staff Insp.","Port and Starboard gangway spring for pawl found broken.","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related","","","","","As no Spares available onboard, New Spring fabricated and replaced. Requisition Raised","2020-05-31","AQUA200053","Completed","2020-04-30","No","No","No","Internal","SPARES ORDERED AS PER AQUA200053. WILL BE CONNECTED TO VESSEL ONCE READY. \nHOWEVER ACTION TAKEN BY STAFF IS SUFFICIENT AND OBSERVATION IS CONSIDERED CLOSED."]
[null,null,null,null,null,"26_2020-05-23 11:04:35 AM","2020-04-13","Defect","Ship Staff","Ship Staff Insp.","Slop (S) Tank Cleaning Machine found not operational.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Worn out parts replaced with newly received spares.","2020-05-31",null,"Completed","2020-05-18","No",null,null,"Internal"]
[null,null,null,null,null,"26_2020-05-23 11:13:02 AM","2020-05-14","Defect","Ship Staff","Ship Staff Insp.","Aft Spring Mooring winch both Brake bands found badly corroded and thinned down.","Deck - Mooring Machinery","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable","repaired with hot work","2020-05-21",null,"Completed","2020-05-19","No",null,null,"Internal"]
[null,null,null,null,null,"26_5 Jun 2020 12:37:44 PM","2020-05-20","Observation","Ship Staff","Ship Staff Insp.","No.1 Boiler Water Circulating pump shaft sleeve leaking","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","No.1 Boiler Water Circulating pump Mechanical seal and shaft sleeve renewed.","2020-06-10",null,"Completed","2020-05-31","No",null,null,"Internal"]
[null,null,null,null,null,"26_5 Jun 2020 12:40:58 PM","2020-05-24","Observation","Ship Staff","Ship Staff Insp.","Main Engine Back Wash Filter change over unit leaking","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Main Engine Back Wash Filter change over unit overhauled, all O rings and bearings renewed","2020-06-05",null,"Completed","2020-06-01","No",null,null,"Internal"]
[null,null,null,null,9729,"26_2020-01-15 3:31:43 PM","2020-11-01","Observation","Ship Staff","Ship Staff Insp.","Slop S Steam Supply branch line found leaking.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Slop S Steam Manifold isolated form Main stem line, Defective section removed and transferred to E/Room, hot work carried out and fitted back in place.","2020-01-14","","Completed","2020-01-14","No","No","No","Internal","Noted."]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":427,"n_cols":3,"rows_kept":427,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",8243]
["1.10","Low",8252]
["1.11","Low",8253]
["1.12","Low",8254]
["1.13","Low",8255]
["1.14","Low",8256]
["1.15","Low",8257]
["1.16","Low",8259]
["1.17","Low",8260]
["1.18","Low",8261]
["1.19","Low",8262]
["1.2","Low",8244]
["1.20","Low",8263]
["1.21","Low",8265]
["1.22","Low",8266]
["1.23","Low",8267]
["1.24","Low",8268]
["1.25","Low",8269]
["1.26","Low",8270]
["1.3","Low",8245]
["1.4","Low",8246]
["1.5","Low",8247]
["1.6","Low",8248]
["1.7","Low",8249]
["1.8","Low",8250]
["1.9","Low",8251]
["1.99","High",11258]
["10.1","Medium",8461]
["10.10","High",8470]
["10.11","Medium",8471]
["10.12","Very High",8472]
["10.13","Very High",8473]
["10.14","Medium",8474]
["10.15","Low",8475]
["10.16","Very High",8476]
["10.17","Very High",8477]
["10.18","High",8478]
["10.19","Very High",8479]
["10.2","Low",8462]
["10.20","High",8480]
["10.21","Medium",8481]
["10.22","Low",8482]
["10.23","Medium",8483]
["10.24","Low",8484]
["10.25","Very High",8485]
["10.26","High",8486]
["10.27","Medium",8487]
["10.28","Low",8488]
["10.29","Medium",8489]
["10.3","Medium",8463]
["10.30","High",8490]
["10.31","Very High",8491]
["10.32","Very High",8492]
["10.33","High",8493]
["10.34","High",8494]
["10.35","Very High",8495]
["10.36","Very High",8496]
["10.37","Medium",8497]
["10.38","Medium",8498]
["10.39","High",8499]
["10.4","High",8464]
["10.40","Medium",8500]
["10.41","Medium",8501]
["10.42","Medium",8502]
["10.43","Medium",8503]
["10.44","Medium",8504]
["10.45","Very High",8505]
["10.46","High",8506]
["10.47","Medium",8507]
["10.48","High",8508]
["10.49","Medium",8509]
["10.5","Low",8465]
["10.50","High",8510]
["10.51","Low",8511]
["10.52","Medium",8512]
["10.53","Medium",8513]
["10.54","High",8514]
["10.55","Low",8515]
["10.6","Very High",8466]
["10.7","Medium",8467]
["10.8","Medium",8468]
["10.9","Medium",8469]
["10.99","High",8516]
["11.1","High",8420]
["11.10","Medium",8429]
["11.11","Very High",8430]
["11.12","Low",8431]
["11.13","Low",8432]
["11.14","Medium",8433]
["11.15","Low",8434]
["11.16","Low",8435]
["11.17","Low",8436]
["11.2","Medium",8421]
["11.3","Medium",8422]
["11.4","Very High",8423]
["11.5","Medium",8424]
["11.6","Medium",8425]
["11.7","High",8426]
["11.8","Low",8427]
["11.9","Low",8428]
["11.99","High",8437]
["12.1","High",8438]
["12.10","High",8448]
["12.11","High",8449]
["12.12","High",8450]
["12.13","High",8451]
["12.14","High",8452]
["12.15","High",8453]
["12.16","High",8454]
["12.17","High",8455]
["12.18","High",8456]
["12.19","High",8457]
["12.2","High",8439]
["12.20","High",8458]
["12.21","High",8459]
["12.3","High",8441]
["12.4","High",8442]
["12.5","High",8443]
["12.6","High",8444]
["12.7","High",8445]
["12.8","High",8446]
["12.9","High",8447]
["12.99","High",8460]
["2.1","Very High",8296]
["2.1.9","Very High",11259]
["2.10","Medium",8304]
["2.11","Medium",8305]
["2.12","Low",8306]
["2.13","Low",8307]
["2.14","Low",8308]
["2.15","Low",8309]
["2.16","Medium",8310]
["2.2","Medium",8297]
["2.3","High",8295]
["2.4","Medium",8298]
["2.5","Medium",8299]
["2.6","Low",8300]
["2.7","High",8301]
["2.8","High",8302]
["2.9","Medium",8303]
["2.99","High",8311]
["3.1","High",8312]
["3.2","Very High",8313]
["3.3","High",8314]
["3.4","Low",8294]
["3.5","Medium",8315]
["3.6","High",8316]
["3.7","Very High",8317]
["3.8","Very High",8318]
["3.99","High",8319]
["4.1","High",8320]
["4.10","High",8329]
["4.11","Medium",8330]
["4.12","Very High",8331]
["4.13","Very High",8332]
["4.14","Very High",8333]
["4.15","Very High",8334]
["4.16","Very High",8335]
["4.17","Very High",8336]
["4.18","Very High",8337]
["4.19","Low",8338]
["4.2","Medium",8321]
["4.20","Very High",8339]
["4.21","High",8340]
["4.22","Low",8341]
["4.23","High",8342]
["4.24","High",8343]
["4.25","Low",8344]
["4.26","Low",8345]
["4.27","High",8346]
["4.3","Medium",8322]
["4.4","High",8323]
["4.5","Very High",8324]
["4.6","Medium",8325]
["4.7","High",8326]
["4.8","Medium",8327]
["4.9","Medium",8328]
["4.99","High",8347]
["5.1","Very High",8517]
["5.10","High",8526]
["5.11","Low",8527]
["5.12","Medium",8528]
["5.13","High",8529]
["5.14","Very High",8530]
["5.15","Medium",8531]
["5.16","Very High",8532]
["5.17","Very High",8533]
["5.18","High",8534]
["5.19","Medium",8535]
["5.2","Very High",8518]
["5.20","Medium",8536]
["5.21","Medium",8537]
["5.22","High",8539]
["5.23","Very High",8540]
["5.24","Very High",8541]
["5.25","Medium",8542]
["5.26","Medium",8543]
["5.27","Medium",8544]
["5.28","Very High",8545]
["5.29","High",8546]
["5.3","Low",8519]
["5.30","High",8547]
["5.31","High",8548]
["5.32","High",8549]
["5.33","High",8550]
["5.34","Low",8551]
["5.35","Medium",8552]
["5.36","Low",8553]
["5.37","Low",8554]
["5.38","High",8555]
["5.39","Very High",8556]
["5.4","High",8520]
["5.40","Very High",8557]
["5.41","Very High",8558]
["5.42","Medium",8559]
["5.43","High",8560]
["5.44","High",8561]
["5.45","Medium",8564]
["5.46","Medium",8565]
["5.47","Medium",8566]
["5.48","Medium",8567]
["5.5","Low",8521]
["5.6","Low",8522]
["5.7","Medium",8523]
["5.8","Medium",8524]
["5.9","Very High",8525]
["5.99","High",8568]
["6.1","Medium",8348]
["6.10","Low",8357]
["6.11","High",8358]
["6.12","Medium",8359]
["6.13","Low",8360]
["6.14","High",8361]
["6.15","High",8362]
["6.16","Very High",8363]
["6.17","Very High",8364]
["6.18","Medium",8365]
["6.19","Low",8366]
["6.2","High",8349]
["6.20","Medium",8367]
["6.21","High",8368]
["6.22","Medium",8369]
["6.3","Low",8350]
["6.4","High",8351]
["6.5","Medium",8352]
["6.6","Medium",8353]
["6.7","High",8354]
["6.8","High",8355]
["6.9","Low",8356]
["6.99","High",8370]
["7.1","High",8371]
["7.10","High",8380]
["7.11","High",8381]
["7.12","High",8382]
["7.13","Medium",8383]
["7.14","Medium",8384]
["7.15","High",8385]
["7.16","High",8386]
["7.17","High",8387]
["7.2","High",8372]
["7.3","Low",8373]
["7.4","Low",8374]
["7.5","Low",8375]
["7.6","Medium",8376]
["7.7","Low",8377]
["7.8","High",8378]
["7.9","High",8379]
["7.99","High",8388]
["8.1","Very High",8569]
["8.10","Very High",8578]
["8.100","Low",11227]
["8.101","Medium",11228]
["8.102","Low",11229]
["8.103","Low",11230]
["8.104","Low",11231]
["8.105","Medium",11232]
["8.106","Medium",11233]
["8.107","Low",11234]
["8.108","High",11235]
["8.109","Very High",11236]
["8.11","Medium",8579]
["8.110","High",11237]
["8.111","Medium",11238]
["8.112","High",11239]
["8.113","Medium",11240]
["8.114","Low",11241]
["8.115","High",11242]
["8.116","Medium",11243]
["8.117","Medium",11244]
["8.118","Medium",11245]
["8.119","High",11246]
["8.12","Medium",8580]
["8.120","High",11247]
["8.121","Medium",11248]
["8.122","High",11249]
["8.123","High",11250]
["8.124","Low",11251]
["8.125","High",11252]
["8.126","Medium",11253]
["8.127","Medium",11254]
["8.13","Medium",8581]
["8.14","Very High",8582]
["8.15","High",8583]
["8.16","Very High",8584]
["8.17","Low",8585]
["8.18","High",8586]
["8.19","High",8587]
["8.199","High",11255]
["8.2","Medium",8570]
["8.20","Medium",8588]
["8.21","High",8589]
["8.22","Very High",8590]
["8.23","Medium",8591]
["8.24","Medium",8592]
["8.25","Very High",8593]
["8.26","High",8594]
["8.27","Medium",8595]
["8.28","Medium",8596]
["8.29","High",8598]
["8.3","Very High",8571]
["8.30","High",8599]
["8.31","High",8600]
["8.32","Low",8601]
["8.33","Medium",8602]
["8.34","High",8603]
["8.35","Medium",8604]
["8.36","Medium",8605]
["8.37","High",8607]
["8.38","Medium",8608]
["8.39","Medium",8609]
["8.4","Medium",8572]
["8.40","High",8610]
["8.41","Medium",8611]
["8.42","Medium",8612]
["8.43","Very High",8613]
["8.44","High",8615]
["8.45","High",8616]
["8.46","Very High",8617]
["8.47","Very High",8618]
["8.48","Medium",8619]
["8.49","High",8620]
["8.5","Very High",8573]
["8.50","Medium",8621]
["8.51","Low",8622]
["8.52","Low",8623]
["8.53","Low",8624]
["8.54","High",8625]
["8.55","Low",11182]
["8.56","Medium",11183]
["8.57","Medium",11184]
["8.58","High",11185]
["8.59","High",11186]
["8.6","Medium",8574]
["8.60","High",11187]
["8.61","Medium",11188]
["8.62","Very High",11189]
["8.63","High",11190]
["8.64","Medium",11191]
["8.65","Low",11192]
["8.66","High",11193]
["8.67","High",11194]
["8.68","High",11195]
["8.69","Medium",11196]
["8.7","High",8575]
["8.70","Medium",11197]
["8.71","Very High",11198]
["8.72","Medium",11199]
["8.73","Medium",11200]
["8.74","High",11201]
["8.75","Medium",11202]
["8.76","Medium",11203]
["8.77","Medium",11204]
["8.78","Medium",11205]
["8.79","Medium",11206]
["8.8","Medium",8576]
["8.80","Medium",11207]
["8.81","Low",11208]
["8.82","Medium",11209]
["8.83","Low",11210]
["8.84","Low",11211]
["8.85","Medium",11212]
["8.86","Medium",11213]
["8.87","Medium",11214]
["8.88","Low",11215]
["8.89","High",11216]
["8.9","High",8577]
["8.90","High",11217]
["8.91","High",11218]
["8.92","Medium",11219]
["8.93","Low",11220]
["8.94","Low",11221]
["8.95","Medium",11222]
["8.96","Medium",11223]
["8.97","Low",11224]
["8.98","High",11225]
["8.99","Medium",11226]
["9.1","Low",8390]
["9.10","Medium",8399]
["9.11","Medium",8400]
["9.12","Medium",8401]
["9.13","Low",8402]
["9.14","Medium",8403]
["9.15","Medium",8404]
["9.16","High",8405]
["9.17","High",8406]
["9.18","Low",8407]
["9.19","Low",8408]
["9.2","Very High",8391]
["9.20","Medium",8409]
["9.21","Medium",8410]
["9.22","Low",8411]
["9.23","Low",8412]
["9.24","Medium",8413]
["9.25","Low",8414]
["9.26","Low",8415]
["9.27","Low",8416]
["9.28","Medium",8417]
["9.29","Low",8418]
["9.3","Very High",8392]
["9.4","High",8393]
["9.5","High",8394]
["9.6","Low",8395]
["9.7","Medium",8396]
["9.8","Medium",8397]
["9.9","Medium",8398]
["9.99","High",8419]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["26","AQUARIUS (06-04-2020)","26_1589541826424.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]