{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":20,"n_cols":28,"rows_kept":20,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","2020-06-16",null,null,"Ship Name","A SYMPHONY (06-06-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,4349,"85_25/10/2019 8:17:50 PM","2019-09-16","Defect","Ship Staff","Ship Staff Insp.","Manifold Spill tank gratings - Port and Stbd are in poor condition, require renewal.","Deck - Pipe / Fittings","MARPOL Related","Human Error",6.6,"Medium","Not Applicable","Not Applicable","New Gratings received and renewal of Grating in Progress.","2020-06-30","ASYM190187","In progress",null,"No","No","No","Internal","New grating supplied to vessel, kindly update once renewed."]
[null,null,null,null,4354,"85_25/10/2019 9:40:00 PM","2019-09-23","Defect","Ship Staff","Nav Audit / Verification","Simultaneous comparison of GPS position on ECDIS cannot be done since only one GPS feed is available at any time. Changeover switch is provided for 2nd GPS.","Navigation - ECDIS","Navigation","Equipment Related",4.17,"Very High","Not Applicable","Not Applicable","Vessel require buffer unit to complete this job, which is still not received from the office.","2020-06-30",null,"In progress",null,"No","No","No","Internal","Service will be arranged during Class annuals."]
[null,null,null,null,12140,"85_28/2/2020 6:55:52 PM","2020-02-14","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","The UKHO Security Chart related to vessel trading area (Mediterranean Area) was not provided onboard.","Documentation","ISPS Related","Human Error",7.13,"Medium","Not Applicable","Not Applicable","Requested for local purchase through agent, Awaiting supply.","2020-06-30",null,"Waiting spare",null,"No","No","No","External","Refer to mail from Mr Deepak dated 19th Feb'20 for procuring it directly from local agent, kindly confirm query was sent to agent for sourcing."]

{"sheet":"Completed","index":1,"n_rows":136,"n_cols":28,"rows_kept":136,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","09-Jun-2020",null,null,"Ship Name","A SYMPHONY (06-06-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,9880,"85_4/1/2020 4:56:50 PM","2019-05-23","Observation","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","Echo sounder was not marked as required by pre arrival tests","Documentation","Navigation","Human Error","4.19","Low","","","Rectified","2019-05-24","","Completed","2019-05-23","No","No","No","Internal"]
[null,null,null,null,9881,"85_4/1/2020 5:01:24 PM","2019-05-23","Observation","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","Aldis Lamp bulb was found fused during testing.","Navigation - Others","Navigation","Equipment Related","","","","","Rectified","2019-05-24","","Completed","2019-05-23","No","No","No","Internal"]
[null,null,null,null,9882,"85_4/1/2020 5:05:46 PM","2019-05-23","Observation","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","The Master Pilot exchange for the last port was not signed by Master.","Documentation","Navigation","Human Error","4.3","Medium","","","Rectified","2019-05-24","","Completed","2019-05-23","No","No","No","Internal"]
[null,null,null,null,9891,"85_4/1/2020 5:09:29 PM","2019-05-23","Observation","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","During testing of the navigation lights it was found that stbd lower light had fused and was giving an alarm on the panel.","Navigation - Others","Navigation","Equipment Related","4.8","Medium","","","Rectified","2019-05-31","","Completed","2019-05-30","No","No","No","Internal"]
[null,null,null,null,9908,"85_19/1/2020 8:53:39 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Accomodation superstructure needs to be attended to at anchorages as has rust spots.","Accommodation ","General Appearance","External Factors","11.13","Low","","","Accomodation superstructure derusted and painted","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9909,"85_19/1/2020 8:59:58 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Electric cable clamp fittings for supports and penetrations on bridge and other accomodation decks have been wasted and require renewal during next docking.","Elect. Mach. & Equip.","Structural Condn. / WT integrity ","Equipment Related","10.37","Medium","","","Wasted cable fittings renwed in drydock.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9911,"85_19/1/2020 9:03:28 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Some cabins and common spaces toilets, taps, hot and cold mixers in some cabins will need renewal.","Accommodation ","MLC Related","Equipment Related","11.13","Low","","","Defective fittings renewed.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9912,"85_19/1/2020 9:09:02 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine room ventilation ducts for all fans are in poor condition with rust/waste of material on flaps, which require immediate attention.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","11.13","Low","","","Duct spaces for all engine room fans derusted and painted. Wasted parts renewed.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9913,"85_19/1/2020 9:12:34 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Certain mattresses are worn out with age and require renewal.","Accommodation ","MLC Related","Industry Issue","11.13","Low","","","Mattresses renewed.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9914,"85_19/1/2020 9:30:39 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Linoleum flooring for CCR, officer & crew smoke room is in poor condition, needs renewal.","Accommodation ","MLC Related","External Factors","11.13","Low","","","Flooring renewed in drydock.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9915,"85_19/1/2020 9:45:58 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Some garbage bins in accomodation are without lids as required. New bins will have to be ordered.","Accommodation ","MARPOL Related","Knowledge Based","6.2","High","","","Old bins have been replaced with new bins which are having lids.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9916,"85_19/1/2020 9:50:01 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Lifeboat grating fitting on canopy wasted.","LSA / FFA","ISM Related","Equipment Related","5.29","High","","","Wasted fitting renewd.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9917,"85_19/1/2020 9:52:23 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mooring winches brake lining thinned.","Deck - Mooring Machinery","Mooring","Equipment Related","9.15","Medium","","","Brake lining changed.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9918,"85_19/1/2020 10:03:14 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Manifold grating found in poor condition.","Deck - Pipe / Fittings","General Appearance","Equipment Related","11.3","Medium","","","Grating renewed.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9919,"85_19/1/2020 10:48:39 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","deck hydraulics box hinges & channels wasted.","Deck - Pipe / Fittings","General Appearance","Equipment Related","11.5","Medium","","","Wasted hinges and channels renewed.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9920,"85_19/1/2020 10:56:08 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Tank dome cover lips found rusted at edges.","Deck - Pipe / Fittings","General Appearance","Equipment Related","11.5","Medium","","","Rusted cover lips derusted and painted.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9921,"85_19/1/2020 10:59:19 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Many pumps near bottom flat of Er are not fitted with guards.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","All pumps are now fitted with guards.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9922,"85_19/1/2020 9:23:09 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Gangway reel drums, pump room davit, fwd davit and aft davit reel drums require derusting.","Accommodation ","MLC Related","Industry Issue","11.13","Low","","","Gangway reel drums, pump room davit, fwd and aft davit reel drums derusted.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,9923,"85_19/1/2020 11:01:40 AM","2019-05-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ER lube oil cooler slightly leaking from plates, complete stack to be renewed.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","All cooler plates and gaskets renewed in drydock.","2019-06-27","","Completed","2019-06-17","No","No","No","Internal"]
[null,null,null,null,4380,"85_25/10/2019 1:59:04 PM","2019-06-06","Non Conformity","Ship Staff","Ship Staff Insp.","EM Log not working, as result Speed indicator on the wheel house and bridge wings also not working.","Navigation - Echo Sounder / Speed Log","Navigation","Equipment Related","","","","","Rectified","2019-09-06","ASYM190034","Completed","2019-09-03","No","No","No","Internal"]
[null,null,null,null,9886,"85_9/1/2020 8:29:26 PM","2019-06-15","Non Conformity","Ship Staff","Ship Staff Insp.","1 Unit SCBA Set Un-usable - Demand Valve Leaking and Pressure Gauge Hose Leaking.","LSA / FFA","Safety / LSA / FFA","Equipment Related","5.43","High","","","Defect rectified.","2019-06-30","","Completed","2019-06-27","No","No","No","Internal"]
[null,null,null,null,4345,"85_25/10/2019 8:00:28 PM","2019-07-14","Defect","Ship Staff","Ship Staff Insp.","AIS is showing “RX3 channel 3 malfunction”. Alarm not resetting","Navigation - DGPS / EPFS / AIS","Navigation","Equipment Related","","","","","AIS Technician attended and defect rectified.","2020-01-31","ASYM190192","Completed","2020-01-28","No","No","No","Internal","Based on VFF, order have been supplied on obard at Malta on 18/11/2019. Via a seperate message, pls advice Mr. Kamlesh Solanki that vessel have received the ordered parts and how to proceed further.\nPls amend target date as the current date is already overdue."]
[null,null,null,null,4362,"85_24/10/2019 5:47:21 PM","2019-07-17","Defect","Ship Staff","Ship Staff Insp.","Air Vents for ballast Tanks - 10 pcs heavy corroded internally","Deck - Pipe / Fittings","Cargo / Ballast Systems","Human Error","1.17","Low","","","All 10 Pcs vent heads renewed with new ones.","2019-08-30","","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,null,"85_25/10/2019 8:06:41 PM","2019-07-17","Defect","Ship Staff","Ship Staff Insp.","VECS System working with only two sensors.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.17,"Low","Not Applicable","Not Applicable","Both defective sensors renewed with new ones. System working satisfactory now.","2020-07-15","ASYM205006","Completed","2020-06-13","No",null,null,"Internal"]
[null,null,null,null,4359,"85_24/10/2019 4:59:53 PM","2019-07-20","Defect","Ship Staff","Ship Staff Insp.","Port and Stbd Ligeboats Air Bottle Pressure Less than the required working pressure","LSA / FFA","Safety / LSA / FFA","Human Error","5.28","Very High","","","Both Lifeboats air bottle (Total 6 Btls) topped up to working pressure of 200 bars.","2019-07-22","","Completed","2019-07-22","No","No","No","Internal"]
[null,null,null,null,4363,"85_24/10/2019 8:08:48 PM","2019-07-20","Non Conformity","Ship Staff","Ship Staff Insp.","Port Side Lifeboat Deck PA Announcement Speaker Not Working.","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","11.1","High","","","PA Announcement Speaker received and renewed.","2019-08-30","ASYM190151","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,4360,"85_24/10/2019 5:24:07 PM","2019-07-22","Defect","Ship Staff","Ship Staff Insp.","Mooring Wires and Fire Wires Lubrication not adequate, dust accumulated on wires, carried over from Dry Dock. ","Deck - Mooring Machinery","Mooring","Human Error","9.17","High","","","All Mooring Wires, Fire wires Greasing and Inspection completed","2019-08-30","","Completed","2019-08-07","No","No","No","Internal"]
[null,null,null,null,4381,"85_25/10/2019 2:25:58 PM","2019-07-22","Defect","Ship Staff","Ship Staff Insp.","Deck Hydraulic boxes packing missing.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","8.11","Medium","","","Packings received as per PO and Renewed.","2019-09-15","ASYM190144","Completed","2019-09-15","No","No","No","Internal"]
[null,null,null,null,4356,"85_24/10/2019 4:37:41 PM","2019-08-01","Defect","Ship Staff","Ship Staff Insp.","Safety rings are missing for fresh water tank ladders","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Inappropriate Procedure","5.47","Medium","","","Safety rings to be fabricated","2019-10-30","","Completed","2019-10-03","No","No","No","Internal"]
[null,null,null,null,4357,"85_24/10/2019 5:15:04 PM","2019-08-01","Defect","Ship Staff","Ship Staff Insp.","Stbd Windlass Speed Switch High Pressure Line Holed.","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Line renewed. Rectified.","2019-08-30","","Completed","2019-08-08","No","No","No","Internal"]
[null,null,null,null,4358,"85_24/10/2019 5:19:08 PM","2019-08-01","Defect","Ship Staff","Ship Staff Insp.","Mooring Winch MW2 Pressure constant valve observed with pin hole leakage.","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Valve opened and O-rings renewed","2019-08-30","","Completed","2019-08-07","No","No","No","Internal"]
[null,null,null,null,4361,"85_24/10/2019 5:37:24 PM","2019-08-01","Defect","Ship Staff","Ship Staff Insp.","Air Vent Mesh Covers Of FW Tk (P), DW Tk (P) and DW Tk (S) wasted. Mesh condition Poor.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Human Error","11.17","Low","","","Vent Mesh Covers fabricated and fitted, Mesh renewed.","2019-08-30","","Completed","2019-08-06","No","No","No","Internal"]
[null,null,null,null,4347,"85_25/10/2019 8:10:20 PM","2019-08-08","Defect","Ship Staff","Ship Staff Insp.","1 Number Mooring Wire W2-P Eye found damaged with broken strands.","Deck - Mooring Machinery","Mooring","Equipment Related","9.17","High","","","Mooring wire renewed - RO raised. No Spare onboard","2019-12-15","ASYM190159","Completed","2019-12-02","No","No","No","Internal","Based on VFF, requisition is still under processing stage. Pls amend target date to 15th Dec 2019."]
[null,null,null,null,4364,"85_24/10/2019 8:16:26 PM","2019-08-16","Defect","Ship Staff","Ship Staff Insp.","WBT 3S - 128 - Hydraulic soenoid valve block not working. Unable to operate from CCR.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","Valve Block opened and overhauled. However, started leaking after repairs. Leak to be rectified.\n\nCompleted 20th Aug 2019.","2019-08-30","","Completed","2019-08-20","No","No","No","Internal"]
[null,null,null,null,4365,"85_24/10/2019 8:27:53 PM","2019-08-25","Defect","Ship Staff","Ship Staff Insp.","Elbow for Emergency Inerting Equipments for WBTs to be prepared for Stand Pipe connection to Breather Valve","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.3","Very High","","","Fabricated and Kept in Midship Store","2019-09-30","","Completed","2019-09-03","No","No","No","Internal"]
[null,null,null,null,4367,"85_24/10/2019 8:32:45 PM","2019-08-25","Defect","Ship Staff","Ship Staff Insp.","Foc'le Deck 2 Nos Deck Stand Rollers and Fwd 1 no. horizontal roller difficult to rotate with hand.\t","Deck - Mooring Machinery","Mooring","Equipment Related","9.18","Low","","","Same Freed up and Greasing done","2019-09-06","","Completed","2019-09-02","No","No","No","Internal"]
[null,null,null,null,9885,"85_9/1/2020 8:21:48 PM","2019-08-26","Non Conformity","Ship Staff","Ship Staff Insp.","Chief Engineer's (Safety Officer) Certificate for Ship's Safety Officer Course Not available.","Miscellaneous","Crew Management","Human Error","5.3","Low","","","FPD Department notified and chief engineer's certificate received via E-mail. Original Certificate Dispatched from office to be connected on board.","2019-08-31","","Completed","2019-08-28","No","No","No","Internal"]
[null,null,null,null,4366,"85_24/10/2019 9:00:28 PM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","IT Audit","Gangway not having Lifebuoy fitted with light and line","LSA / FFA","Safety / LSA / FFA","Knowledge Based","5.47","Medium","","","Portable 1 set of lifebuoy prepared with light and line to comply with VIQ requirement","2019-11-30","","Completed","2019-09-02","No","No","No","Internal"]
[null,null,null,null,4368,"85_24/10/2019 11:28:32 PM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","Course Recorder Rudder angle indicator stylus not printing on the recording paper","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Rectified","2019-11-30","","Completed","2019-09-01","No","No","No","Internal"]
[null,null,null,null,4369,"85_24/10/2019 11:33:21 PM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","Safety Contours setting not correctly mentioned in passage plan sheet - B considering Company's UKC policy for ocean and coastal waters","Navigation - Others","Navigation","Human Error","4.15","Very High","","","Correct Settings mentioned in Passage plan - Rectified","2019-11-30","","Completed","2019-09-01","No","No","No","Internal"]
[null,null,null,null,4370,"85_24/10/2019 11:40:21 PM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","Risk assessment not prepared for entering Port for the first time (Port Sudan, Suez canal Transit)","Navigation - Others","Navigation","Human Error","7.9","High","","","RA Prepared and discussed.","2019-11-30","","Completed","2019-09-01","No","No","No","Internal"]
[null,null,null,null,4371,"85_24/10/2019 11:43:49 PM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","Conn changeover from Master to OOW not entered for arrival Suez anchorage on 22.08.2019","Navigation - Others","Navigation","Human Error","4.2","Medium","","","Entry made - Rectified","2019-11-30","","Completed","2019-09-01","No","No","No","Internal"]
[null,null,null,null,4372,"85_24/10/2019 11:53:48 PM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","IT Audit","Oxygen and Acetylene bottles to have indications for \"In use\", \"Full\" and \"Empty\"","Miscellaneous","Eng. / Strg. Comp.","Human Error","5.26","Medium","","","Completed","2019-11-30","","Completed","2019-09-01","No","No","No","Internal"]
[null,null,null,null,4373,"85_25/10/2019 12:02:38 AM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","IT Audit","Eyepads in Pump room not highlighted and marked with SWL","Deck - Pipe / Fittings","Cargo / Ballast Systems","Human Error","8.5","Very High","","","Pump room eyepads highlighted and marked with SWL, Foc'le and E/R to be done","2019-09-30","","Completed","2019-09-04","No","No","No","Internal"]
[null,null,null,null,4374,"85_24/10/2019 11:49:11 PM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","IT Audit","Gymnasium to be cleaned and cleared of all stores and spares kept in it.","Accommodation","General Appearance","Human Error","11.13","Low","","","All these stores received in suez just before the audit. All items cleaned and gymnasium squarred up after dep suez","2019-11-30","","Completed","2019-09-02","No","No","No","Internal"]
[null,null,null,null,4375,"85_25/10/2019 12:07:35 AM","2019-08-31","Defect","Ship Staff","Ship Staff Insp.","Angle Indicator For gangway to be placed at the fwd end so that it is visible from deck level. Current indicator placed at middle level of the gangway","Deck - Machinery","ISM Related","Equipment Related","5.47","Medium","","","New Gangway angle indicators being fabricated to put at ends.","2019-09-30","","Completed","2019-09-03","No","No","No","Internal"]
[null,null,null,null,4376,"85_25/10/2019 12:10:41 AM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","IT Audit","MSDS Missing for newly received paint for suez","Documentation","Cert. & Docu.","Human Error","5.46","Medium","","","MSDS not provided by supplier. Request has been made\t","2019-11-30","","Completed","2019-09-03","No","No","No","Internal"]
[null,null,null,null,4377,"85_25/10/2019 12:15:44 AM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","IT Audit","Foc'le door weathertight door dog bolts to be freed up and some external W/T doors not having Open / Shut marking on the dog bolts","Deck - Pipe / Fittings","ISM Related","Human Error","11.6","Medium","","","Foc'le door doglegs freed up and markings in progress","2019-11-30","","Completed","2019-09-04","No","No","No","Internal"]
[null,null,null,null,4378,"85_25/10/2019 1:37:38 PM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","Time and Position for changeover to hand steering from auto pilot and vice versa for 22.08.2019 Arrival Suez anchorage, 24.08.2019 Dep Suez anchorage and 24.08.2019 Dep Suez transit not entered in bridge bell book","Navigation - Others","Navigation","Human Error","4.1","High","","","Entry made and corrected","2019-11-30","","Completed","2019-09-01","No","No","No","Internal"]
[null,null,null,null,4379,"85_25/10/2019 1:40:51 PM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","IT Audit","Provision stores (Wet and Dry) requires cleaning, tidying up and arrangemnt of provisions","Accommodation","General Appearance","Human Error","11.13","Low","","","New provision received in Suez being arranged.","2019-11-30","","Completed","2019-09-04","No","No","No","Internal"]
[null,null,null,null,4386,"85_25/10/2019 3:08:29 PM","2019-08-31","Non Conformity","Owner / Marine / Tech. Suptd.","IT Audit","Many pumps near bottom flat of engine room not fitted with guards","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.27","Medium","","","Job done","2019-11-30","","Completed","2019-09-04","No","No","No","Internal"]
[null,null,null,null,4389,"85_25/10/2019 3:48:04 PM","2019-08-31","Non Conformity","Owner / Marine / Tech. Suptd.","IT Audit","Pumproom Blowers, mastriser ladders more than 3 mtrs in heighty with no Safety rings","Deck - Pipe / Fittings","ISM Related","Equipment Related","5.47","Medium","","","Safety rings fabricated and fitted.","2019-11-30","","Completed","2019-10-02","No","No","No","Internal"]
[null,null,null,null,9887,"85_9/1/2020 9:08:16 PM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Hazardous material inventory to be prepared","Documentation","Cert. & Docu.","Human Error","","","","","Rectified","2019-11-29","","Completed","2019-10-07","No","No","No","Internal"]
[null,null,null,null,9888,"85_9/1/2020 11:41:29 PM","2019-08-31","Observation","Ship Staff","IT Audit","Restricted areas to be marked as per 06.02 of SSP","Miscellaneous","General Appearance","Human Error","7.4","Low","","","Restricted Areas on deck marked as per 06.02 of SSP","2019-11-29","","Completed","2019-09-16","No","No","No","Internal"]
[null,null,null,null,9889,"85_9/1/2020 11:46:24 PM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Indicator light for Slop (P) valve and low pressure indicator for Hydraulic power unit fused in CCR","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","Indicator light for Slop (P) valve and low pressure indicator for Hydraulic power unit replaced with spare units.","2019-11-29","","Completed","2019-09-20","No","No","No","Internal"]
[null,null,null,null,9890,"85_9/1/2020 11:50:25 PM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Steam lines and valves on deck covered by think salt deposits ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Human Error","8.15","High","","","Steam lines and valves covered with salt deposits hosed down and cleaned with hot water.","2019-11-29","","Completed","2019-09-10","No","No","No","Internal"]
[null,null,null,null,9892,"85_9/1/2020 11:54:22 PM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Cargo sample log not maintained ","Documentation","Cert. & Docu.","Human Error","8.17","Low","","","Cargo sample log prepared and put in use.","2019-11-29","","Completed","2019-10-07","No","No","No","Internal"]
[null,null,null,null,9893,"85_9/1/2020 11:58:17 PM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Posters / procedures not posted as per Cargo audit c/l nr. 3.22","Documentation","Cert. & Docu.","Human Error","8.1","Very High","","","Missing Posters/ Procedures prepared and posted in CCR.","2019-11-29","","Completed","2019-09-27","No","No","No","Internal"]
[null,null,null,null,9894,"85_10/1/2020 12:01:37 AM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Few Horizontal rollers and pedestal dead man rollers found frozen at forward and aft of vessel","Deck - Pipe / Fittings","Mooring","Human Error","9.18","Low","","","All Horizontal rollers and pedestal dead man rollers greased and made free.","2019-11-29","","Completed","2019-09-02","No","No","No","Internal"]
[null,null,null,null,9895,"85_10/1/2020 12:12:36 AM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Poop deck anti skid paint worn down i.w.o. mooring winch barrels ","Miscellaneous","Mooring","Human Error","9.13","Low","","","Anti-skid paint applied to the weather deck area where required.","2019-11-29","","Completed","2019-10-04","No","No","No","Internal"]
[null,null,null,null,9896,"85_10/1/2020 12:16:28 AM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Striking direction arrow for releasing anchor Bitter end not clearly marked in the vicinity of bitter end","Deck - Mooring Machinery","Mooring","Human Error","9.22","Low","","","Striking direction stencil painted near the bitter end of the anchor.","2019-11-29","","Completed","2019-09-16","No","No","No","Internal"]
[null,null,null,null,9897,"85_10/1/2020 12:19:37 AM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Spares & Stores sighted in the Gymnasium - to be removed and Gym restored back to its original glory ","Accommodation ","General Appearance","Human Error","11.13","Low","","","Spares and stores secured back in their respective store rooms. ","2019-11-29","","Completed","2019-09-02","No","No","No","Internal"]
[null,null,null,null,9898,"85_10/1/2020 12:22:20 AM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","All common toilets to be provided with hand wash, toilet rolls and paper towels & deodorizes","Accommodation ","General Appearance","Human Error","11.13","Low","","","All common toilets stocked with hand wash, toilet rolls, paper towels & deodorizers","2019-11-29","","Completed","2019-08-31","No","No","No","Internal"]
[null,null,null,null,9899,"85_10/1/2020 12:24:09 AM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Dry & wet provision stores: Tidying up, last in first out arranging of provisions based on expiry date ","Accommodation ","General Appearance","Human Error","11.13","Low","","","Provision stores cleaned and arranged as per expiry dates. First-in First-out method of store keeping explained to galley staff.","2019-11-29","","Completed","2019-09-08","No","No","No","Internal"]
[null,null,null,null,9900,"85_10/1/2020 12:26:23 AM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Energy Efficiency  measures and action plan to be customized and made ships specific","Documentation","Cert. & Docu.","Human Error","2.14","Low","","","Ships specific Energy Efficiency measures and action plan made ship specific.","2019-11-29","","Completed","2019-09-23","No","No","No","Internal"]
[null,null,null,null,9901,"85_10/1/2020 12:28:26 AM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","ENERGY Best Management practice posters to be displayed to ensure awareness across all departments  ","Documentation","Cert. & Docu.","Human Error","2.14","Low","","","ENERGY Best Management practice posters prepared & displayed in common areas and near essential electrical equipment.","2019-11-29","","Completed","2019-09-26","No","No","No","Internal"]
[null,null,null,null,9902,"85_10/1/2020 12:06:08 AM","2019-08-31","Observation","Owner / Marine / Tech. Suptd.","IT Audit","Snap back zone stencil at various locations found faded  ","Miscellaneous","General Appearance","Human Error","9.8","Medium","","","SNAP-BACK ZONE stencils on deck re-stenciled.","2019-11-29","","Completed","2019-09-03","No","No","No","Internal"]
[null,null,null,null,4348,"85_25/10/2019 8:13:22 PM","2019-08-31","Defect","Owner / Marine / Tech. Suptd.","IT Audit","Fresh water testing kit onboard is from the previous management and some chemical used for testing has expired.","Miscellaneous","MLC Related","External Factors","","","","","New Fresh water test received and onboard test carried out","2019-11-30","ASYM190157","Completed","2019-11-03","No","No","No","Internal","Based on VFF, order have been delivered on board at Malta on 18/11/2019. Pls close-out this observation."]
[null,null,null,null,9883,"85_9/1/2020 8:08:32 PM","2019-09-01","Non Conformity","Ship Staff","Ship Staff Insp.","During routine inspection of Stbd Lifeboat engine found that the engine was not starting with no 1 Battery alone.","LSA / FFA","Safety / LSA / FFA","Equipment Related","5.28","Very High","","","Rectified","2019-09-08","","Completed","2019-09-04","No","No","No","Internal"]
[null,null,null,null,4382,"85_25/10/2019 2:37:13 PM","2019-09-03","Defect","Ship Staff","Ship Staff Insp.","Branch Return Line for Mooring Winch MW3 found pin holed and leaking","Deck - Pipe / Fittings","Mooring","Equipment Related","11.4","Very High","","","Hydraulic branch Line for MW3 renewed with New one fabricated onboard","2019-09-15","","Completed","2019-09-05","No","No","No","Internal"]
[null,null,null,null,4383,"85_25/10/2019 3:00:15 PM","2019-09-03","Defect","Ship Staff","Ship Staff Insp.","MW No 2 Gratings damaged and not secured to the platform","Deck - Pipe / Fittings","Mooring","Equipment Related","11.3","Medium","","","Railing repaired and Securing arrangement made","2019-09-15","","Completed","2019-09-05","No","No","No","Internal"]
[null,null,null,null,4384,"85_25/10/2019 3:02:43 PM","2019-09-03","Defect","Ship Staff","Ship Staff Insp.","Hydraulic Returm Line near Hose handling Crane found leaking  with pin hole","Deck - Pipe / Fittings","Mooring","Equipment Related","11.4","Very High","","","Line Renewed Flange to Flange","2019-09-15","","Completed","2019-09-05","No","No","No","Internal"]
[null,null,null,null,4387,"85_25/10/2019 3:19:03 PM","2019-09-04","Defect","Ship Staff","Ship Staff Insp.","Hawse Pipe Covers partially wasted - Hinges and locks not fixing in position correctly","Deck - Mooring Machinery","Mooring","Equipment Related","9.2","Very High","","","Port & Stbd side Hawse Pipe cover and Hinges renewed, primered & painted.","2019-09-30","","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,9903,"85_15/1/2020 5:02:15 PM","2019-09-05","Observation","Ship Staff","Ship Staff Insp.","Fish room temperature not maintaining.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Expansion valve replaced.","2019-09-05","","Completed","2019-09-05","No","No","No","Internal"]
[null,null,null,null,9924,"85_19/1/2020 11:12:35 AM","2019-09-06","Defect","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Insulation resistance of the 110 volt Emergency Feeder Panel in the\n\nEmergency Diesel Generator Room was 1.0 megaohm at the time of inspection","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","10.38","Medium","","","It was found that the low insulation was\n\ndue to a cracked holder of the emergency light located on the sunken deck, leading to the low\n\ninsulation on the panel. After completion of STS operation the holder for\n\nthe Emergency light fitting was replaced with new holder from on board stock.","2019-09-15","","Completed","2019-09-08","No","No","No","External"]
[null,null,null,null,9925,"85_19/1/2020 11:17:45 AM","2019-09-06","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Although the vessel was discharging in closed condition, the vessel\n\nwas provided restricted type 3 pcs MMC Model D-2401-2.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.16","Very High","","","As per the regulations\n\nthese MMC's can be used on Oil Tankers provided the vessel's are fitted with Vapour Control\n\nValves on Gauging Stations as is the case onboard this vessel.","2019-10-05","","Completed","2019-09-06","No","No","No","External"]
[null,null,null,null,9910,"85_15/1/2020 4:57:29 PM","2019-09-07","Observation","Ship Staff","Ship Staff Insp.","Aeration blower motor making abnormal noise.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Motor and blower overhauled.","2019-09-07","","Completed","2019-09-07","No","No","No","Internal"]
[null,null,null,null,4385,"85_25/10/2019 3:05:01 PM","2019-09-12","Defect","Ship Staff","Ship Staff Insp.","Hydraulic Return Line for Deck Machinery found leaking and holed at No 7 COT area below U-clamp. ","Deck - Pipe / Fittings","Mooring","Equipment Related","11.4","Very High","","","\tRetuen Line Straight section and connecting Elbow section renewed with new one","2019-09-15","","Completed","2019-09-12","No","No","No","Internal"]
[null,null,null,null,4388,"85_25/10/2019 3:25:19 PM","2019-09-16","Defect","Ship Staff","Ship Staff Insp.","Foam Hydrant - 2 Nos leaking near No 7 And No 6 Isolation valves","LSA / FFA","Safety / LSA / FFA","Equipment Related","5.4","High","","","Hydrants overhauled & tested. No leaks found.","2019-09-30","","Completed","2019-09-30","No","No","No","Internal"]
[null,null,null,null,4393,"85_25/10/2019 7:41:29 PM","2019-09-16","Defect","Ship Staff","Ship Staff Insp.","No.2 COP governor is not responding from CCR at times. To be inspected & rectified","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.8","Medium","","","Job completed","2019-09-30","","Completed","2019-10-07","No","No","No","Internal"]
[null,null,null,null,4395,"85_25/10/2019 7:38:52 PM","2019-09-16","Defect","Ship Staff","Ship Staff Insp.","Few cargo & ballast tank valve indicators in CCR panel hunting. To be inspected and rectified","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","Job completed","2019-11-30","","Completed","2019-10-05","No","No","No","Internal"]
[null,null,null,null,4351,"85_25/10/2019 8:20:34 PM","2019-09-16","Defect","Ship Staff","Ship Staff Insp.","Hydraulic pipeline for deck machinery is thinned down near the U-clamps in several places and requires renewal","Deck - Machinery","Mooring","Equipment Related","11.4","Very High","","","3nos section of hydraulic lines near 5S renewed.","2019-12-15","ASYM190185","Completed","2019-12-12","No","No","No","Internal","Pls continue to update this office as the repairs progresses."]
[null,null,null,null,9905,"85_15/1/2020 5:09:41 PM","2019-09-24","Other","Ship Staff","Ship Staff Insp.","FWG generator not producing water.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Condenser and evaporator plates cleaned.","2019-09-26","","Completed","2019-09-24","No","No","No","Internal"]
[null,null,null,null,4355,"85_24/10/2019 4:26:00 PM","2019-09-27","Defect","Ship Staff","Ship Staff Insp.","No.2 Boiler main feed pump pressure regulating line leaking and temporarily repaired.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Need to be removed from the place and fabricate the segment of the pipe.","2019-10-30","","Completed","2019-10-05","No","No","No","Internal"]
[null,null,null,null,4390,"85_25/10/2019 7:46:43 PM","2019-09-27","Defect","Ship Staff","Ship Staff Insp.","Steam Main inlet valve for 6P COT found frozen in open condition.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.15","High","","","Valve replaced with spare available onboard","2019-11-30","","Completed","2019-10-15","No","No","No","Internal"]
[null,null,null,null,4392,"85_25/10/2019 7:35:23 PM","2019-09-27","Defect","Ship Staff","Ship Staff Insp.","No.2 Boiler Main Feed pump pressure regulating line leaking and temporarily repaired.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","New pipe fabricated the leaking segment of the pipe renewed.","2019-10-30","","Completed","2019-10-05","No","No","No","Internal"]
[null,null,null,null,9904,"85_15/1/2020 5:05:58 PM","2019-09-27","Defect","Ship Staff","Ship Staff Insp.","FWG ejector pump not building up pressure.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","New pump installed.","2019-09-30","","Completed","2019-09-27","No","No","No","Internal"]
[null,null,null,null,null,"85_25/10/2019 8:27:40 PM","2019-09-27","Defect","Ship Staff","Ship Staff Insp.","No 4 Steam coil for 5S COT tank heating found leaking.","Hull & Tanks","Cargo / Ballast Systems","Equipment Related",8.15,"High","Not Applicable","Not Applicable","Heating coil pressure tested and no leak observed.","2020-06-30",null,"Completed","2020-06-16","No",null,null,"Internal"]
[null,null,null,null,4353,"85_25/10/2019 8:32:14 PM","2019-09-28","Defect","Ship Staff","Ship Staff Insp.","Mono rail crane both hooks not operational.","Deck - Machinery","ISM Related","Equipment Related","8.5","Very High","","","Voltage module rectifier replaced.","2019-10-30","ASYM190199","Completed","2019-11-19","No","No","No","Internal","Based on VFF, order was supplied on board at Malta on 18/11/2019. When do you plan to commence replacement of the supplied rectifier? Pls amend target date based on  your job plan."]
[null,null,null,null,4344,"85_24/10/2019 4:12:11 PM","2019-09-28","Defect","Ship Staff","Ship Staff Insp.","Aft ETA Brake band support found corroded ","Deck - Mooring Machinery","Emgcy. Systems","Equipment Related","9.28","Medium","","","Aft ETA brake band supports renewed.","2019-11-30","ASYM190208","Completed","2019-11-15","No","No","No","Internal","Based on VFF, order was supplied on board @ Malta on 01/11/2019.  Pls revert with update on progress of said job."]
[null,null,null,null,4394,"85_25/10/2019 7:43:57 PM","2019-10-11","Defect","Ship Staff","Ship Staff Insp.","Main engine jacket cooling water pump no.1 mechanical seal found leaking","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","Renewed the seal","2019-10-16","","Completed","2019-10-15","No","No","No","Internal"]
[null,null,null,null,4391,"85_25/10/2019 7:55:59 PM","2019-10-16","Defect","Ship Staff","Ship Staff Insp.","Pump room blower no.2 making abnormal sound\t","Elect. Mach. & Equip.","ISM Related","Equipment Related","5.18","High","","","Checked and overhauled.","2019-10-20","","Completed","2019-10-18","No","No","No","Internal"]
[null,null,null,null,4396,"85_25/10/2019 7:54:06 PM","2019-10-16","Defect","Ship Staff","Ship Staff Insp.","Pump room blower no.1 making abnormal sound","Elect. Mach. & Equip.","ISM Related","Equipment Related","5.18","High","","","Checked and overhauled.","2019-10-20","","Completed","2019-10-17","No","No","No","Internal"]
[null,null,null,null,9906,"85_15/1/2020 5:16:05 PM","2019-10-18","Defect","Ship Staff","Ship Staff Insp.","Pump room exhaust fan no.2 making abnormal noise and vibration.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","10.32","Very High","","","Pump room exhaust fan dismantled bearing found damanged, same renewed.","2019-10-18","","Completed","2019-10-18","No","No","No","Internal"]
[null,null,null,null,null,"85_Wed Dec 11 2019 06:17:44 GMT+0000","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","MF/HF switched off due to lightning. When tried switching on after weather improved, however didn't turn on.","Navigation - GMDSS & Communication","Communication","Equipment Related",4.21,"High","Not Applicable","Not Applicable","MF/HF Radio unit not working. Checked the antenna unit on the compass deck and Shore technician attended the vessel for repair and rectified the MF/HF Unit. ","2020-01-30","ASYM195096, ASYM190211","Completed","2020-02-14","No",null,null,"Internal"]
[null,null,null,null,9884,"85_9/1/2020 7:54:28 PM","2019-11-11","Non Conformity","Ship Staff","Ship Staff Insp.","MLC Work Rest Hour requirement for Master and Chief Mate not complied with due to operational requirement of vessel.","Miscellaneous","Crew Management","Human Error","3.2","Very High","","","Compensatory rest given after operations","2019-11-15","","Completed","2019-11-15","No","No","No","Internal"]
[null,null,null,null,8164,"85_15/11/2019 6:57:14 PM","2019-11-13","Breakdown","Ship Staff","Ship Staff Insp.","Aux. Boiler burner No3 not firing.Flame trouble alarm is activated.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Flame eye replaced for No3 burner, tested and found working satisfactory.","2019-11-20","","Completed","2019-11-14","No","No","No","Internal"]
[null,null,null,null,8165,"85_Tue Feb 12 2019 10:45:00 GMT+0000 (Coordinated Universal Time)","2019-11-16","Other","Ship Staff","Ship Staff Insp.","One steam tracing line near the AE area was leaking.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pipe removed and leak rectified.","2019-11-20","","Completed","2019-11-17","No","No","No","Internal"]
[null,null,null,null,8167,"85_Mon Dec 02 2019 23:35:14 GMT+0000 (Coordinated Universal Time)","2019-11-19","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steam line insulation on pumproom entrance found damaged, to be rectified.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","11.4","Very High","","","Damaged Steam Insulations renewed","2019-11-19","","Completed","2019-11-23","No","No","No","Internal"]
[null,null,null,null,8168,"85_Mon Dec 02 2019 23:47:14 GMT+0000 (Coordinated Universal Time)","2019-11-19","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aft navigation light switch box missing\n\nthe Flap.","Miscellaneous","General Appearance","Equipment Related","11.1","High","","","New flap fabricated and fixed.","2019-11-19","","Completed","2019-11-23","No","No","No","Internal"]
[null,null,null,null,8166,"85_Mon Dec 02 2019 16:22:01 GMT+0000 (Coordinated Universal Time)","2019-11-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency fire pump was leaking from the gland.","Critical Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Gland packing renewed.","2019-11-25","","Completed","2019-11-22","No","No","No","Internal"]
[null,null,null,null,8169,"85_Wed Dec 04 2019 15:03:56 GMT+0000 (Coordinated Universal Time)","2019-11-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","One drain pipe in the funnel has got a pin hole.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pipe removed, repaired and put back.","2019-12-10","","Completed","2019-12-02","No","No","No","Internal"]
[null,null,null,null,8170,"85_Fri Apr 12 2019 15:06:33 GMT+0000 (Coordinated Universal Time)","2019-11-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Drain pipe in the ER vent fan (port aft) compartment has got several pin holes.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pipe fabricated and renewed.","2019-12-10","","Completed","2019-12-03","No","No","No","Internal"]
[null,null,null,null,9907,"85_18/1/2020 10:04:12 AM","2020-01-15","Observation","Ship Staff","Ship Staff Insp.","Fresh water hydrophore pump #1 was found leaking from the seal.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","Pump overhauled and mechanical seal replaced with new one.","2020-01-20","","Completed","2020-01-16","No","No","No","Internal"]
[null,null,null,null,12141,"85_28/2/2020 6:25:55 PM","2020-02-14","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","The ESP folder related to last special survey was not updated, the Continuous   Evaluation report was not available.","Documentation","Cert. & Docu.","Human Error","2.15","Low","","","Soft copy received from office.","2020-03-14","","Completed","2020-02-14","No","No","No","External"]
[null,null,null,null,12142,"85_28/2/2020 8:30:39 PM","2020-02-14","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","The following areas on main deck were noticed to corroded, ii. the hydraulic oil piping system (supply and return lines) of the fwd mooring winch No.1.\n\nmooring winch No.1, \n\n","Deck - Pipe / Fittings","General Appearance","Human Error","11.4","Very High","","","Hydraulic pipeline Renewed with newly fabricated section.","2020-03-14","","Completed","2020-03-16","No","No","No","External"]
[null,null,null,null,12143,"85_28/2/2020 8:21:59 PM","2020-02-14","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","The following areas on main deck were noticed to corroded, \n\ni.e.: i. the cargo lines between port and starboard manifold area were noticed to\n\nbe rusted, approximately 10 % of spot heavy rust with soft patches.","Deck - Pipe / Fittings","General Appearance","Human Error","11.4","Very High","","","cargo lines between port and starboard manifold area derusted and painted.","2020-03-30","","Completed","2020-03-26","No","No","No","External"]
[null,null,null,null,12144,"85_28/2/2020 8:34:06 PM","2020-02-14","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","The following areas on main deck were noticed to corroded, iii, the 20 % of piping service U-bolts and supports were noticed to be heavy rusted and fresh painted on the top.","Deck - Pipe / Fittings","General Appearance","Human Error","11.4","Very High","","","Piping service U-bolts renewed and de rusting of bolted area & Supports done.","2020-05-31","","Completed","2020-05-14","No","No","No","External"]
[null,null,null,null,12149,"85_28/2/2020 6:43:44 PM","2020-02-14","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","The MF/HF Equipment noticed to be Malfunctioning, the transmission was non operative. However, shore technician attendance was in progress.","Navigation - GMDSS & Communication","Communication","Equipment Related","4.21","High","","","Shore technician attended the vessel for repair and rectified the MF/HF Unit.Transmission and receiption working. acknowledgement received.","2020-03-14","","Completed","2020-02-14","No","No","No","External"]
[null,null,null,null,12150,"85_28/2/2020 7:02:07 PM","2020-02-14","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","A minor Hydraulic leakage was noticed at the Cargo and Ballast valves solenoid cabinet, from related Hydraulic piping system Connections.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","Leak rectified.","2020-03-14","","Completed","2020-02-14","No","No","No","External"]
[null,null,null,null,12145,"85_11/3/2020 10:45:36 AM","2020-03-05","Defect","Ship Staff","Ship Staff Insp.","IG flue gas inlet pipe to scrubber is corroded and holed due to which the O2 content was fluctuating with black smoke","Inert Gas","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pipe repaired by welding a doubler plate on the holed and corroded section.","2020-03-15","","Completed","2020-03-10","No","No","No","Internal"]
[null,null,null,null,12146,"85_15/3/2020 11:13:52 PM","2020-03-12","Defect","Ship Staff","Ship Staff Insp.","IG flue gas line to scrubber near the sealing air line is corroded and holed.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Doubler plate to be welded on the damaged area.","2020-03-20","","Completed","2020-03-16","No","No","No","Internal"]
[null,null,null,null,12147,"85_13/4/2020 4:50:18 PM","2020-04-08","Defect","Ship Staff","Ship Staff Insp.","No. 1 Line master valve (no 312) found Leaking, same confirmed during pressure testing (found liquid Passing even when the valve is closed).","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.3","Very High","","","Vessel renewed damaged Seat ring with new spare seat ring. Manually operated and found operating freely.Cargo system Pressure tested to MAWP (12bars) and all found satisfactory.","2020-04-13","","Completed","2020-04-12","No","No","No","Internal"]
[null,null,null,null,12148,"85_30/4/2020 11:00:36 AM","2020-04-16","Defect","Ship Staff","Ship Staff Insp.","MGPS inlet valve found leaking.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Valve replaced with new one.","2020-04-25","","Completed","2020-04-17","No","No","No","Internal"]
[null,null,null,null,null,"85_Wed Dec 11 2019 06:26:10 GMT+0000","2020-04-17","Breakdown","Ship Staff","Ship Staff Insp.","Accomodation A/C fan found tripping frequently.","Accommodation","Eng. / Strg. Comp.","Equipment Related",10.3,"Medium","Not Applicable","Not Applicable","Motor relay renewed with new one. Working satisfactory now.","2020-07-31",null,"Completed","2020-06-08","No",null,null,"External"]
[null,null,null,null,12151,"85_30/4/2020 11:04:26 AM","2020-04-18","Defect","Ship Staff","Ship Staff Insp.","Both ProvRefer & deck seal pump discharge valves were not holding. Same to be overhauled.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Both the valves removed from the place and overhauled.Valves put back and found working satisfactory.","2020-04-28","","Completed","2020-04-21","No","No","No","Internal"]
[null,null,null,null,12152,"85_22/5/2020 3:20:52 PM","2020-05-14","Observation","Owner / Marine / Tech. Suptd.","Bunkering Audit","\"12.04.08.011.02 STATUS OF TANKS NOT BEING BUNKERED\" - Trim of vessel prior and immediately after completion of bunkering not recorded.","Documentation","Cert. & Docu.","Human Error","10.7","Medium","","","Amend the checklist with corrective and preventive action","2020-05-25","","Completed","2020-05-22","No","No","No","Internal"]
[null,null,null,null,12153,"85_21/5/2020 3:13:26 PM","2020-05-16","Observation","Ship Staff","Ship Staff Insp.","Pressure gauge of Main engine fuel oil heater #1  was defective. Same need to be replaced.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.34","High","","","Pressure gauge renewed.","2020-05-23","","Completed","2020-05-20","No","No","No","Internal"]
[null,null,null,null,null,"85_15/6/2020 3:50:33 PM","2020-06-01","Defect","Ship Staff","Ship Staff Insp.","No. 3 Drop valve (no 317) found Leaking, same confirmed during pressure testing (found liquid Passing even when the valve is closed).","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related",8.3000000000000007,"Very High","Not Applicable","Not Applicable","Vessel renewed damaged Seat ring with new spare seat ring. Manually operated and found operating freely.Cargo system Pressure tested to MAWP (12bars) and all found satisfactory.","2020-06-10",null,"Completed","2020-06-05","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":427,"n_cols":3,"rows_kept":427,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",8243]
["1.10","Low",8252]
["1.11","Low",8253]
["1.12","Low",8254]
["1.13","Low",8255]
["1.14","Low",8256]
["1.15","Low",8257]
["1.16","Low",8259]
["1.17","Low",8260]
["1.18","Low",8261]
["1.19","Low",8262]
["1.2","Low",8244]
["1.20","Low",8263]
["1.21","Low",8265]
["1.22","Low",8266]
["1.23","Low",8267]
["1.24","Low",8268]
["1.25","Low",8269]
["1.26","Low",8270]
["1.3","Low",8245]
["1.4","Low",8246]
["1.5","Low",8247]
["1.6","Low",8248]
["1.7","Low",8249]
["1.8","Low",8250]
["1.9","Low",8251]
["1.99","High",11258]
["10.1","Medium",8461]
["10.10","High",8470]
["10.11","Medium",8471]
["10.12","Very High",8472]
["10.13","Very High",8473]
["10.14","Medium",8474]
["10.15","Low",8475]
["10.16","Very High",8476]
["10.17","Very High",8477]
["10.18","High",8478]
["10.19","Very High",8479]
["10.2","Low",8462]
["10.20","High",8480]
["10.21","Medium",8481]
["10.22","Low",8482]
["10.23","Medium",8483]
["10.24","Low",8484]
["10.25","Very High",8485]
["10.26","High",8486]
["10.27","Medium",8487]
["10.28","Low",8488]
["10.29","Medium",8489]
["10.3","Medium",8463]
["10.30","High",8490]
["10.31","Very High",8491]
["10.32","Very High",8492]
["10.33","High",8493]
["10.34","High",8494]
["10.35","Very High",8495]
["10.36","Very High",8496]
["10.37","Medium",8497]
["10.38","Medium",8498]
["10.39","High",8499]
["10.4","High",8464]
["10.40","Medium",8500]
["10.41","Medium",8501]
["10.42","Medium",8502]
["10.43","Medium",8503]
["10.44","Medium",8504]
["10.45","Very High",8505]
["10.46","High",8506]
["10.47","Medium",8507]
["10.48","High",8508]
["10.49","Medium",8509]
["10.5","Low",8465]
["10.50","High",8510]
["10.51","Low",8511]
["10.52","Medium",8512]
["10.53","Medium",8513]
["10.54","High",8514]
["10.55","Low",8515]
["10.6","Very High",8466]
["10.7","Medium",8467]
["10.8","Medium",8468]
["10.9","Medium",8469]
["10.99","High",8516]
["11.1","High",8420]
["11.10","Medium",8429]
["11.11","Very High",8430]
["11.12","Low",8431]
["11.13","Low",8432]
["11.14","Medium",8433]
["11.15","Low",8434]
["11.16","Low",8435]
["11.17","Low",8436]
["11.2","Medium",8421]
["11.3","Medium",8422]
["11.4","Very High",8423]
["11.5","Medium",8424]
["11.6","Medium",8425]
["11.7","High",8426]
["11.8","Low",8427]
["11.9","Low",8428]
["11.99","High",8437]
["12.1","High",8438]
["12.10","High",8448]
["12.11","High",8449]
["12.12","High",8450]
["12.13","High",8451]
["12.14","High",8452]
["12.15","High",8453]
["12.16","High",8454]
["12.17","High",8455]
["12.18","High",8456]
["12.19","High",8457]
["12.2","High",8439]
["12.20","High",8458]
["12.21","High",8459]
["12.3","High",8441]
["12.4","High",8442]
["12.5","High",8443]
["12.6","High",8444]
["12.7","High",8445]
["12.8","High",8446]
["12.9","High",8447]
["12.99","High",8460]
["2.1","Very High",8296]
["2.1.9","Very High",11259]
["2.10","Medium",8304]
["2.11","Medium",8305]
["2.12","Low",8306]
["2.13","Low",8307]
["2.14","Low",8308]
["2.15","Low",8309]
["2.16","Medium",8310]
["2.2","Medium",8297]
["2.3","High",8295]
["2.4","Medium",8298]
["2.5","Medium",8299]
["2.6","Low",8300]
["2.7","High",8301]
["2.8","High",8302]
["2.9","Medium",8303]
["2.99","High",8311]
["3.1","High",8312]
["3.2","Very High",8313]
["3.3","High",8314]
["3.4","Low",8294]
["3.5","Medium",8315]
["3.6","High",8316]
["3.7","Very High",8317]
["3.8","Very High",8318]
["3.99","High",8319]
["4.1","High",8320]
["4.10","High",8329]
["4.11","Medium",8330]
["4.12","Very High",8331]
["4.13","Very High",8332]
["4.14","Very High",8333]
["4.15","Very High",8334]
["4.16","Very High",8335]
["4.17","Very High",8336]
["4.18","Very High",8337]
["4.19","Low",8338]
["4.2","Medium",8321]
["4.20","Very High",8339]
["4.21","High",8340]
["4.22","Low",8341]
["4.23","High",8342]
["4.24","High",8343]
["4.25","Low",8344]
["4.26","Low",8345]
["4.27","High",8346]
["4.3","Medium",8322]
["4.4","High",8323]
["4.5","Very High",8324]
["4.6","Medium",8325]
["4.7","High",8326]
["4.8","Medium",8327]
["4.9","Medium",8328]
["4.99","High",8347]
["5.1","Very High",8517]
["5.10","High",8526]
["5.11","Low",8527]
["5.12","Medium",8528]
["5.13","High",8529]
["5.14","Very High",8530]
["5.15","Medium",8531]
["5.16","Very High",8532]
["5.17","Very High",8533]
["5.18","High",8534]
["5.19","Medium",8535]
["5.2","Very High",8518]
["5.20","Medium",8536]
["5.21","Medium",8537]
["5.22","High",8539]
["5.23","Very High",8540]
["5.24","Very High",8541]
["5.25","Medium",8542]
["5.26","Medium",8543]
["5.27","Medium",8544]
["5.28","Very High",8545]
["5.29","High",8546]
["5.3","Low",8519]
["5.30","High",8547]
["5.31","High",8548]
["5.32","High",8549]
["5.33","High",8550]
["5.34","Low",8551]
["5.35","Medium",8552]
["5.36","Low",8553]
["5.37","Low",8554]
["5.38","High",8555]
["5.39","Very High",8556]
["5.4","High",8520]
["5.40","Very High",8557]
["5.41","Very High",8558]
["5.42","Medium",8559]
["5.43","High",8560]
["5.44","High",8561]
["5.45","Medium",8564]
["5.46","Medium",8565]
["5.47","Medium",8566]
["5.48","Medium",8567]
["5.5","Low",8521]
["5.6","Low",8522]
["5.7","Medium",8523]
["5.8","Medium",8524]
["5.9","Very High",8525]
["5.99","High",8568]
["6.1","Medium",8348]
["6.10","Low",8357]
["6.11","High",8358]
["6.12","Medium",8359]
["6.13","Low",8360]
["6.14","High",8361]
["6.15","High",8362]
["6.16","Very High",8363]
["6.17","Very High",8364]
["6.18","Medium",8365]
["6.19","Low",8366]
["6.2","High",8349]
["6.20","Medium",8367]
["6.21","High",8368]
["6.22","Medium",8369]
["6.3","Low",8350]
["6.4","High",8351]
["6.5","Medium",8352]
["6.6","Medium",8353]
["6.7","High",8354]
["6.8","High",8355]
["6.9","Low",8356]
["6.99","High",8370]
["7.1","High",8371]
["7.10","High",8380]
["7.11","High",8381]
["7.12","High",8382]
["7.13","Medium",8383]
["7.14","Medium",8384]
["7.15","High",8385]
["7.16","High",8386]
["7.17","High",8387]
["7.2","High",8372]
["7.3","Low",8373]
["7.4","Low",8374]
["7.5","Low",8375]
["7.6","Medium",8376]
["7.7","Low",8377]
["7.8","High",8378]
["7.9","High",8379]
["7.99","High",8388]
["8.1","Very High",8569]
["8.10","Very High",8578]
["8.100","Low",11227]
["8.101","Medium",11228]
["8.102","Low",11229]
["8.103","Low",11230]
["8.104","Low",11231]
["8.105","Medium",11232]
["8.106","Medium",11233]
["8.107","Low",11234]
["8.108","High",11235]
["8.109","Very High",11236]
["8.11","Medium",8579]
["8.110","High",11237]
["8.111","Medium",11238]
["8.112","High",11239]
["8.113","Medium",11240]
["8.114","Low",11241]
["8.115","High",11242]
["8.116","Medium",11243]
["8.117","Medium",11244]
["8.118","Medium",11245]
["8.119","High",11246]
["8.12","Medium",8580]
["8.120","High",11247]
["8.121","Medium",11248]
["8.122","High",11249]
["8.123","High",11250]
["8.124","Low",11251]
["8.125","High",11252]
["8.126","Medium",11253]
["8.127","Medium",11254]
["8.13","Medium",8581]
["8.14","Very High",8582]
["8.15","High",8583]
["8.16","Very High",8584]
["8.17","Low",8585]
["8.18","High",8586]
["8.19","High",8587]
["8.199","High",11255]
["8.2","Medium",8570]
["8.20","Medium",8588]
["8.21","High",8589]
["8.22","Very High",8590]
["8.23","Medium",8591]
["8.24","Medium",8592]
["8.25","Very High",8593]
["8.26","High",8594]
["8.27","Medium",8595]
["8.28","Medium",8596]
["8.29","High",8598]
["8.3","Very High",8571]
["8.30","High",8599]
["8.31","High",8600]
["8.32","Low",8601]
["8.33","Medium",8602]
["8.34","High",8603]
["8.35","Medium",8604]
["8.36","Medium",8605]
["8.37","High",8607]
["8.38","Medium",8608]
["8.39","Medium",8609]
["8.4","Medium",8572]
["8.40","High",8610]
["8.41","Medium",8611]
["8.42","Medium",8612]
["8.43","Very High",8613]
["8.44","High",8615]
["8.45","High",8616]
["8.46","Very High",8617]
["8.47","Very High",8618]
["8.48","Medium",8619]
["8.49","High",8620]
["8.5","Very High",8573]
["8.50","Medium",8621]
["8.51","Low",8622]
["8.52","Low",8623]
["8.53","Low",8624]
["8.54","High",8625]
["8.55","Low",11182]
["8.56","Medium",11183]
["8.57","Medium",11184]
["8.58","High",11185]
["8.59","High",11186]
["8.6","Medium",8574]
["8.60","High",11187]
["8.61","Medium",11188]
["8.62","Very High",11189]
["8.63","High",11190]
["8.64","Medium",11191]
["8.65","Low",11192]
["8.66","High",11193]
["8.67","High",11194]
["8.68","High",11195]
["8.69","Medium",11196]
["8.7","High",8575]
["8.70","Medium",11197]
["8.71","Very High",11198]
["8.72","Medium",11199]
["8.73","Medium",11200]
["8.74","High",11201]
["8.75","Medium",11202]
["8.76","Medium",11203]
["8.77","Medium",11204]
["8.78","Medium",11205]
["8.79","Medium",11206]
["8.8","Medium",8576]
["8.80","Medium",11207]
["8.81","Low",11208]
["8.82","Medium",11209]
["8.83","Low",11210]
["8.84","Low",11211]
["8.85","Medium",11212]
["8.86","Medium",11213]
["8.87","Medium",11214]
["8.88","Low",11215]
["8.89","High",11216]
["8.9","High",8577]
["8.90","High",11217]
["8.91","High",11218]
["8.92","Medium",11219]
["8.93","Low",11220]
["8.94","Low",11221]
["8.95","Medium",11222]
["8.96","Medium",11223]
["8.97","Low",11224]
["8.98","High",11225]
["8.99","Medium",11226]
["9.1","Low",8390]
["9.10","Medium",8399]
["9.11","Medium",8400]
["9.12","Medium",8401]
["9.13","Low",8402]
["9.14","Medium",8403]
["9.15","Medium",8404]
["9.16","High",8405]
["9.17","High",8406]
["9.18","Low",8407]
["9.19","Low",8408]
["9.2","Very High",8391]
["9.20","Medium",8409]
["9.21","Medium",8410]
["9.22","Low",8411]
["9.23","Low",8412]
["9.24","Medium",8413]
["9.25","Low",8414]
["9.26","Low",8415]
["9.27","Low",8416]
["9.28","Medium",8417]
["9.29","Low",8418]
["9.3","Very High",8392]
["9.4","High",8393]
["9.5","High",8394]
["9.6","Low",8395]
["9.7","Medium",8396]
["9.8","Medium",8397]
["9.9","Medium",8398]
["9.99","High",8419]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["85","A SYMPHONY (06-06-2020)","85_1591682707386.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]