{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":45,"n_cols":28,"rows_kept":45,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","26-Jun-2020",null,null,"Ship Name","MOJO (08-06-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,7557,"93_Tue Feb 12 2019 09:44:01 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","All MS pipe lines on deck including hydraulic lines & electric conduit pipes show heavy corrosion at many places. ","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","To be hydroblasted & painted 03 coats. Wasted areas of pipes to be cropped & renewed. Awaiting hydroblaster.","2020-06-30","","Waiting spare",null,"Yes","No","No","Internal"]
[null,null,null,null,7571,"93_Tue Feb 12 2019 10:25:27 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Aux. Engine fuel oil auto filter not in use.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Awaiting Spares to make it operational","2020-08-31","004 E / 19,  New RO- MOJO205038","Waiting spare",null,"No","No","No","Internal","Spares supplied during docking, confirm equipment is operational now. Update job accordingly."]
[null,null,null,null,7579,"93_Tue Feb 12 2019 10:43:06 GMT+0000 (Coordinated Universal Time)","2019-08-20","Defect","Ship Staff","Ship Staff Insp.","Air btl safety valve for QCV in fire fighting station is leaking continuously.","LSA / FFA","Eng. / Strg. Comp.","Equipment Related","","","","","Valve needs to be replaced, awaiting spares","2020-08-31","MOJO200132","Waiting spare",null,"Yes","No","No","Internal","This defect is from time of takeover, trust it has been rectified. Update job accordingly."]
[null,null,null,null,7586,"93_Tue Feb 12 2019 11:33:09 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","No.03 WBT (P) remote shut indication light on ballast panel malfuntioning. Sensor to be checked at the actual v/v body in pipe duct. .","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Sensors checked by attending technician from Kuidatech and as per his advise we have raised requisition for the actuator and reed limit switch.","2020-08-31","MOJO200093","Waiting spare",null,"No","No","No","Internal","Spares will be connected at next convenient port."]
[null,null,null,null,7587,"93_Tue Feb 12 2019 11:35:19 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","All hatch coamings stiffeners on deck show heavy rusting","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","To be derusted, primered & painted accordingly.","2020-08-31","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,7601,"93_Tue Feb 12 2019 12:04:43 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","No.1 HFO bunker tank port & stbd level gauge defective.","Hull & Tanks","Eng. / Strg. Comp.","Equipment Related","","","","","Level transmitters checked by attending technician from Kuidatech and as per his instructions requisition raised for the same","2020-08-31","MOJO200098","Waiting spare",null,"No","No","No","Internal","Vessel to update \"Action Taken or Required\" as this was attended during DOCKING & insert comments accordingly. PO REF NO missing"]
[null,null,null,null,7616,"93_Tue Mar 12 2019 07:50:03 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","All CH entrance booby hatches to be legibly stencilled following - \"Restricted Area, No unauthorized Access / Caution: Danger of Oxygen depletion\".","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","Vessel endevours to do this job in ballast voyage as currently we are concentrating on Accomodation and Engine room block De-rusting & Painting","2020-08-31","","Not Started",null,"No","No","No","Internal","Revert with progress of it as still STATUS CODE shows NOT STARTED."]
[null,null,null,null,7620,"93_Tue Mar 12 2019 08:03:04 GMT+0000 (Coordinated Universal Time)","2019-08-24","Defect","Ship Staff","Ship Staff Insp.","Main Engine Running Hour meter not working","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Need to replace the running hour meter.","2020-08-31","MOJO200101","Waiting spare",null,"No","No","No","Internal","PO no not mentioned, insert correct PO reference no."]
[null,null,null,null,7629,"93_Tue Mar 12 2019 08:52:43 GMT+0000 (Coordinated Universal Time)","2019-08-28","Defect","Ship Staff","Ship Staff Insp.","Some W/T doors not sealing properly on closure. Also packing retaining channel seems corroded.","Accommodation","Structural Condn. / WT integrity ","Equipment Related","","","","","All W/T doors checked for proper sealing. Packing retaining channel will be derusted & painted accordingly, wasted sections will be repaired by ship staff.","2020-08-31","","In progress",null,"No","No","No","Internal","This job was completed in DD, kindly update."]
[null,null,null,null,7635,"93_Tue Mar 12 2019 09:18:51 GMT+0000 (Coordinated Universal Time)","2019-08-29","Defect","Ship Staff","Ship Staff Insp.","Fresh water expansion tank have some oil trace, A/E fuel injector is being cooled by fresh water.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Upon investigation found, Unit #2 of AE 3 was leaking through the noozle cooing line and oil finding its way to the expansion tank. Chemical 'SEACLEAN' was added as per instructions to collect the oil from the line and thereby collecing at the expansion tank.","2020-07-31",null,"In progress",null,"No","No","No","Internal","Vsl to update job progress by mail ."]
[null,null,null,null,7656,"93_Tue Mar 12 2019 11:07:15 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","ME fuel oil auto filter running hour meter not operational.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Requisition raised for the hour meter,awaiting spares","2020-08-31","MOJO200102","Waiting spare",null,"No","No","No","Internal","Confirm vessel has new hour meter, same to be attended on priority."]
[null,null,null,null,7661,"93_Tue Mar 12 2019 11:35:12 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","All hatch cover cleats have no record of last overhauling.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","overhauling of hatch 1 in progress","2020-07-30",null,"In progress",null,"No","No","No","Internal","This job has been completed in DD by shipstaff, kindly update it."]
[null,null,null,null,7666,"93_Wed Dec 04 2019 02:15:30 GMT+0000 (Coordinated Universal Time)","2019-12-04","Defect","Ship Staff","Ship Staff Insp.","The control block and reduction gear of the Bunker Davit Port side are damaged & missing. The davits were not in use for a long time by previous crew.","Miscellaneous","MARPOL Related","Equipment Related","","","","","Overhaul the Bunker davits and check the condition of the bearings. New control block and reduction gear to be fitted on port side Bunker davit.","2020-08-31","MOJO200037","Waiting spare",null,"Yes","No","No","Internal","Insert PO reference no as same missing."]
[null,null,null,null,null,"93_30/6/2020 12:25:49 PM","2020-05-04","Defect","Ship Staff","Ship Staff Insp.","Main Engine Unit # 4 FWD – Bearing sensor is defective and upon investigation found sensor wire broken from sensor end. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Vessel awaiting spare to rectify the same.","2020-07-31","MOJO200142","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,12134,"93_17/5/2020 11:37:28 AM","2020-05-10","Defect","Ship Staff","Ship Staff Insp.","Galley Fridge and Dish washers are inoperational and need to be replaced.","Miscellaneous","MLC Related","Equipment Related","","","","","Vessel raised requisition for the same and need to be supplied.","2020-07-30","MOJO200127","Not Started",null,"No","No","No","Internal","PO reef no missing, to insert same."]
[null,null,null,null,12135,"93_17/5/2020 12:04:08 PM","2020-05-10","Defect","Ship Staff","Ship Staff Insp.","All Accommodation Natural vents hinges are rusted and seized.","Accommodation","Structural Condn. / WT integrity ","External Factors","","","","","All Accommodation Natural vent hinges to be De-rusted and made free.","2020-07-30","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,12136,"93_17/5/2020 11:55:16 AM","2020-05-10","Defect","Ship Staff","Ship Staff Insp.","Elevator shaft access & Maintenance top hatch packing channel is badly De-rusted.","Accommodation","Structural Condn. / WT integrity ","Equipment Related","","","","","Elevator shaft access & Maintenance top hatch packing channel to be builtup and packing to be changed.","2020-07-30","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,12137,"93_17/5/2020 12:08:41 PM","2020-05-10","Defect","Ship Staff","Ship Staff Insp.","Engine room skylight supports are wasted and corroded","Miscellaneous","Structural Condn. / WT integrity ","External Factors","","","","","Wasted skylight support areas to be built up and Corroded areas to be De-rusted and paint.","2020-07-30","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,null,"93_30/6/2020 10:31:43 PM","2020-05-14","Defect","Ship Staff","Ship Staff Insp.","Galley Hot plate not working - 2 & 4.","Accommodation","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Upon checking , found the cables and switches damaged and vessel had raised an R.O to rectify and put the same in use.","2020-07-31","MOJO200120","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"93_29/6/2020 10:46:57 PM","2020-06-19","Non Conformity","Ship Staff","Ship Staff Insp.","Stbd side Life boat Magnetic Compass is highly erratic & has no match with the ship’s Magnetic compass","LSA / FFA","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","vsl to raise req","2020-08-25",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"93_29/6/2020 10:59:02 PM","2020-06-19","Observation","Ship Staff","Ship Staff Insp.","Bridge Clock back light Not working & cannot see time in night time","Navigation - Others","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","awaiting office advise","2020-07-30",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"93_29/6/2020 11:04:23 PM","2020-06-19","Observation","Ship Staff","Ship Staff Insp.","1 No GMDSS walkie talkie has slight issue with rotary switch","LSA / FFA","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","awaiting office advise","2020-07-30",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"93_29/6/2020 10:56:36 PM","2020-06-20","Observation","Ship Staff","Ship Staff Insp.","Auto Pilot Course Alteration knob does not work","Navigation - Others","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","awaiting office advise","2020-07-30",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"93_30/6/2020 12:22:13 PM","2020-06-20","Defect","Ship Staff","Ship Staff Insp.","Main Engine – Unit # 5 Fuel Pump puncture O-rings are found to be leakin slightly. O-rings to be renewed. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","O-rings to be renewed. Job to be undertake when vessel is in port / anchorage. ","2020-07-20",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"93_29/6/2020 10:53:06 PM","2020-06-22","Observation","Ship Staff","Ship Staff Insp.","Fire line drain valves seized","LSA / FFA","Safety / LSA / FFA","External Factors",null,null,"Not Applicable","Not Applicable","to overhaul","2020-07-10",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"93_29/6/2020 10:36:49 PM","2020-06-23","Observation","Ship Staff","Ship Staff Insp.","hold no. 3 main water ingress alarm not working ","Miscellaneous","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","defected sensor. requisition raised for the same  ","2020-08-31","MOJO190013","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"93_29/6/2020 10:40:42 PM","2020-06-24","Non Conformity","Ship Staff","Ship Staff Insp.","Fire line has a hole aft of No. 6 hold","LSA / FFA","Safety / LSA / FFA","External Factors",null,null,"Not Applicable","Not Applicable","VSL will take hot work permit for carrying out repairs","2020-07-04",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"93_29/6/2020 10:43:40 PM","2020-06-25","Non Conformity","Ship Staff","Ship Staff Insp.","Accomodation block  Fire Hydrants found seized","LSA / FFA","Safety / LSA / FFA","Human Error",null,null,"Not Applicable","Not Applicable","lubrication in progress","2020-07-10",null,"In progress",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":172,"n_cols":28,"rows_kept":172,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","26-Jun-2020",null,null,"Ship Name","MOJO (08-06-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,7555,"93_Tue Feb 12 2019 09:40:32 GMT+0000 (Coordinated Universal Time)","2019-01-15","Defect","Ship Staff","Ship Staff Insp.","Hull stress monitor is already decommissioned, all fittings on deck & bridge to be removed at DD","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","HSMS fittings cropped from the deck and removed by Ship tard.","2020-03-31","","Completed","2020-04-07","Yes","No","No","Internal"]
[null,null,null,null,7542,"93_Mon Dec 02 2019 19:23:23 GMT+0000 (Coordinated Universal Time)","2019-08-14","Defect","Ship Staff","Ship Staff Insp.","Hull Paint in Poor Condition, especially topsides all around. ","Hull & Tanks","Structural Condn. / WT integrity ","External Factors","","","","","Hull painted in Dry dock after high pressure wash and sand blasting.","2020-01-31","","Completed","2020-01-19","Yes","No","No","Internal"]
[null,null,null,null,7543,"93_Tue Feb 12 2019 19:27:34 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","Both ECDIS UPS, expiring in jan 2020","Navigation - ECDIS","Navigation","Equipment Related","","","","","ECDIS UPS changed by ETO. ","2020-03-31","007D/19","Completed","2020-03-10","No","No","No","Internal"]
[null,null,null,null,7544,"93_Tue Feb 12 2019 21:08:57 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","Elevator to be recommissioned as per flag state requirements.","Miscellaneous","General Appearance","Equipment Related","","","","","Invetor and the PCB renewed by the shore technician, elevator made operational.","2020-03-31","","Completed","2020-03-31","Yes","No","No","Internal"]
[null,null,null,null,7545,"93_Tue Feb 12 2019 08:49:02 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","All Cargo holds show heavy rusting, including but not limited to CH booby hatch access, rubber packing retaining channel, Australian ladders / straight ladders & guard pipes show heavy corrosion & total wasting at many places. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","All cargo holds, Cleaned with high pressure fresh water wash and grit blasted. The cargo holds, along with the Australian and Vertical ladders, Pipes and supports, Upperstool areas were painted with 2 coats of cargo hold paint as per specification.","2020-03-31","","Completed","2020-04-01","Yes","No","No","Internal"]
[null,null,null,null,7546,"93_Tue Feb 12 2019 08:51:39 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","All hatch cover packings & CH access hatch packings are hardened & grooved (Loss of resilience) & also  understand have few leakages. Also packing retaining channel totally wasted at many places. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","All hatch cover & hatch access lid packings  renewed & packing retaining channel full derusted, cropped & renewed & painted as required.","2020-03-31","","Completed","2020-04-13","Yes","No","No","Internal"]
[null,null,null,null,7547,"93_Tue Feb 12 2019 08:53:08 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","Both windlass brake bands worn out by 70%. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Both windlass brake bands renewed in DD. ","2020-03-31","","Completed","2020-04-13","Yes","No","No","Internal"]
[null,null,null,null,7548,"93_Tue Feb 12 2019 08:56:34 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","Bridge sofa, Crew Mess Room, completely torn & upholstery held in place with tapes. Bridge radio station chair, ship's office chair, ECR chair to be replaced. ","Miscellaneous","General Appearance","Equipment Related","","","","","All sofas and chairs mentioned re-upholstered and attended in DD.","2020-03-31","","Completed","2020-04-08","Yes","No","No","Internal"]
[null,null,null,null,7549,"93_Tue Feb 12 2019 09:30:42 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","On stbd side stern frame, steering gear room bulkhead shows an indentation & slight bending of longitudinal (area about 02m x 02m)","Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related","","","","","Class surveyor and Owners are satisfied with the condition. Hence the job has been cancelled.","2020-01-31","","Completed","2020-01-10","Yes","No","No","Internal"]
[null,null,null,null,7550,"93_Tue Feb 12 2019 09:32:41 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","There is no solid fairlead on forecastle deck P&S side to pass tug boat towing lines. Similarly no solid centre lead on poop deck. It was observed vessel passes tug towing lines on forecastle deck & poop deck via roller fairleads, which are not designed for tug pulling stress. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Owners are satisfied with the mooring arrangement onboard. hence no modifications are required. job cancelled.","2020-01-31","","Completed","2020-01-10","Yes","No","No","Internal"]
[null,null,null,null,7551,"93_Mon Dec 02 2019 09:34:21 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","Aft P side stern rope winch on poop dk & spring rope mooring winch between hatch no.08 & 09 - Control lever unit trickle leaking oil, also for aft breast line, stern lines, spring mooring winch gear engaging clutch lever base welding to main body has come off. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Control lever checked for leaking seal & all control blocks overhauled and serviced by attending technicians in DD.","2020-03-31","","Completed","2020-04-13","No","No","No","Internal"]
[null,null,null,null,7553,"93_Tue Feb 12 2019 09:37:17 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","Mooring winches hydraulic motor gearbox oil filling cap  frozen stiff in place & suspect to be wasted. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","All filling caps in good condition and oil renewed in windlass and gangway gear box.","2020-03-31","","Completed","2020-04-13","Yes","No","No","Internal"]
[null,null,null,null,7554,"93_Tue Feb 12 2019 09:38:52 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","Spare anchor to be off landed in DD.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Spare anchor is in good condition. De-rusted and painted by Yard. Owners did not approve for landing the spare anchor. Hence the job is cancelled.","2020-01-31","","Completed","2020-01-10","Yes","No","No","Internal"]
[null,null,null,null,7672,"93_Mon Dec 02 2019 21:02:39 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","Gyro Compass Annual servicing over due since July 2019","Navigation - Others","Navigation","Equipment Related","","","","","Gyro Compass servicing & gyrosphere replaced with reconditioned gyrosphere at Xiamen.","2019-09-15","002D/19","Completed","2019-11-13","No","No","No","Internal"]
[null,null,null,null,null,"93_Tue Feb 12 2019 09:35:52 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","All mooring winches hydraulic motor gearbox oil seems to be curdled, no record of renewal.","Deck - Mooring Machinery","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable"," 6 winches oil renewed. ","2020-08-31",null,"Completed","2020-06-09","Yes",null,null,"Internal"]
[null,null,null,null,7556,"93_Tue Feb 12 2019 09:42:18 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Almost all hatch cover not sitting on resting pads. Hatch cover lip resting on hatch coaming at many places","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Resting pads rebuilt as required & all hatch cover packings renewed. Chalk test carried out and found satisfactory.","2020-03-31","","Completed","2020-04-13","Yes","No","No","Internal"]
[null,null,null,null,7558,"93_Tue Feb 12 2019 09:46:37 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Many hatch cover hydraulic lifting jack leaking from seal. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","All flexible hoses & seals of hatch cover lifting jacks renewed. Lifting jacks removed from location for servicing and rechroming  by ship yard. All seals renewed. ","2020-03-31","","Completed","2020-04-13","Yes","No","No","Internal"]
[null,null,null,null,7559,"93_Tue Feb 12 2019 09:49:56 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","All cargo holds hatch cover natural vents flame arrestors badly painted over","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Wire mesh renewed once the new louvers were fitted back by the yard. ","2020-03-31","","Completed","2020-04-08","Yes","No","No","Internal"]
[null,null,null,null,7560,"93_Tue Feb 12 2019 09:51:46 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","X band RADARS Magnetron due for renewal. (Last renewal in Nov 2017). S Band Radar PM not working","Navigation - RADAR","Navigation","Equipment Related","","","","","X band magnetron renewed on 19-Jan-2020 and S Band PM renewed and replaced with new one and now working satisfactory.","2020-03-31","","Completed","2020-03-13","Yes","No","No","Internal"]
[null,null,null,null,7561,"93_Mon Dec 02 2019 09:53:55 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Hatch cover drawing chains of following hatch covers full wasted & narrowed down (# 01PA, 02P&SF, 03, 04F, 05F, 07","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","",""," All wasted hatch cover drawing chains replaced with new ones as required. ","2020-03-31","","Completed","2020-05-15","Yes","No","No","Internal"]
[null,null,null,null,7562,"93_Tue Feb 12 2019 09:55:56 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","No.04 & 02 hatch covers drawing hydraulic motor is leaking oil continuously from flexible pipe joint. ","Deck - Mooring Machinery","Cargo / Ballast Systems","Equipment Related","","","","","All hatch cover hydraulic drawing chain motor bushes, bearings & seal renewed as required.","2020-03-31","017E/19","Completed","2020-04-13","No","No","No","Internal"]
[null,null,null,null,7563,"93_Tue Feb 12 2019 09:58:13 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","04 nos. Drinking water fountains in accommodation to be made operational. ","Accommodation","MLC Related","Equipment Related","","","","","Drinking water fountain has no filter and candle for purifying. It is a simple water cooler. Water coolers working satisfactorily.","2020-03-31","","Completed","2020-04-13","Yes","No","No","Internal"]
[null,null,null,null,7564,"93_Mon Dec 02 2019 10:02:33 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","All cabins porthole curtains found dirty & velcro tape has lost resilience, unable to completely block out light. ","Miscellaneous","MLC Related","Equipment Related","","","","","All curtains to be washed & cleaned. Velcro issue not needed.Navigation at night is not impeded. ","2020-08-31","","Completed","2020-04-13","No","No","No","Internal"]
[null,null,null,null,7565,"93_Mon Dec 02 2019 10:12:12 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Many cabins clocks not synchronizing with bridge slave clock & requires manual adjustment. For eg: Owner's cabin. ","Miscellaneous","MLC Related","Equipment Related","","","","","Owners cancelled the job.","2020-03-31","","Completed","2020-04-13","Yes","No","No","Internal"]
[null,null,null,null,7566,"93_Tue Feb 12 2019 10:14:00 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","No additional locking arrangement on the inside of accommodation alleyways exit doors abv A deck, for piracy prone areas. Same to be attended in DD as per company discretion.","Miscellaneous","ISPS Related","Equipment Related","","","","","To be done according to the trading area of the vessel.","2020-08-31","","Completed","2020-04-13","Yes","No","No","Internal","Docking is over, update job accordingly."]
[null,null,null,null,7567,"93_Mon Dec 02 2019 10:16:35 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","FWG Ejector pump casing and motor in place,shaft, impeller, mechanical seal and coupling missing.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","",""," The shaft , impeller, mechanical seal and the coupling assembled and fitted back in place.The Pump tried out , found working satisfactory.The discharge pressure and amps found normal.","2020-01-31","003E/19","Completed","2020-01-25","No","No","No","Internal"]
[null,null,null,null,7568,"93_Mon Dec 02 2019 10:18:06 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Aft Hydraulic Power Unit Oil  cooler sea water leaking from end cover","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","The section of the leaking pipe at the end cover renewed, leak rectified","2020-03-31","","Completed","2020-02-26","Yes","No","No","Internal"]
[null,null,null,null,7569,"93_Mon Dec 02 2019 10:20:04 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Emergency air driven diesel oil pump leaking. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Pump overhauled, the oil seal and O rings renewed and boxed back.","2020-03-31","006E/19","Completed","2020-03-29","Yes","No","No","Internal"]
[null,null,null,null,7570,"93_Tue Feb 12 2019 10:22:13 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","It was observed Boiler burner unit is being held by chain block, whilst at sea","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","The burner unit pulled out and inspection carried out, found satisfactory. The burner unit need not be held by chain block","2020-03-31","","Completed","2020-02-02","Yes","No","No","Internal"]
[null,null,null,null,7572,"93_Tue Feb 12 2019 10:27:32 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Main Engine fuel oil line pressure regulator not working","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","",""," Pressure regulator renewed with new spare, now working satisfactory.","2020-03-31","005E/19","Completed","2020-02-26","Yes","No","No","Internal"]
[null,null,null,null,7573,"93_Tue Feb 12 2019 10:29:31 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Main Engine fuel oil viscometer fuel oil leaking from seal. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Fuel Oil Viscometer overhauled , shaft seal, O rings and bearings renewed. Now working satisfactory.","2020-03-31","007E/19","Completed","2020-04-20","No","No","No","Internal"]
[null,null,null,null,7574,"93_Mon Dec 02 2019 10:31:42 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","DW Sterlizer not working.","E/R - Aux. Mach.","MLC Related","Equipment Related","","","","","  Germicidal lamp and the ballast renewed with new spare, found working satisfactory.","2020-03-31","MOJO 190002","Completed","2020-02-04","Yes","No","No","Internal"]
[null,null,null,null,7575,"93_Tue Feb 12 2019 10:33:17 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","STBD side sea chest both CU & AL anodes need to be renewed. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","The CU and Al anodes of Stbd. sea chest renewed with new spare anodes.","2020-01-31","","Completed","2020-01-18","Yes","No","No","Internal"]
[null,null,null,null,7576,"93_Tue Feb 12 2019 10:35:22 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Aft ICCP display showing module/system fault","Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related","","","","","Aft ICCP Module renewed with new spare, now working satisfactory.","2020-03-31","","Completed","2020-02-22","Yes","No","No","Internal"]
[null,null,null,null,7577,"93_Mon Dec 02 2019 10:37:02 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","Control air dryer not working properly","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Control air dryer inspected, filters cleaned,found working satisfactory.","2020-03-31","013E/19","Completed","2020-03-05","Yes","No","No","Internal"]
[null,null,null,null,7671,"93_Tue Feb 12 2019 10:00:13 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","AIS still showing fault in vessel speed feed.","Navigation - DGPS / EPFS / AIS","Navigation","Equipment Related","","","","","Newly received AIS installed by Shore technician at Xiamen.","2019-11-05","","Completed","2019-11-10","No","No","No","Internal"]
[null,null,null,null,8951,"93_Tue Feb 12 2019 10:31:42 GMT+0000 (Coordinated Universal Time)","2019-08-19","Defect","Ship Staff","Ship Staff Insp.","DW Sterlizer not working.","E/R - Aux. Mach.","MLC Related","Equipment Related","","","","","The germicidal lamp of the sterilizer renewed with new spare , working satisfactory.","2020-03-31","","Completed","2020-03-07","Yes","No","No","Internal"]
[null,null,null,null,7578,"93_Tue Feb 12 2019 10:41:05 GMT+0000 (Coordinated Universal Time)","2019-08-20","Defect","Ship Staff","Ship Staff Insp.","Hatch cover opening / closing control lever boxes many corroded & wasted. For eg: No.02 & 05","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","",""," New boxes fabricated & corroded ones cropped & renewed by yard in DD","2020-03-31","","Completed","2020-04-11","Yes","No","No","Internal"]
[null,null,null,null,7580,"93_Tue Feb 12 2019 10:50:43 GMT+0000 (Coordinated Universal Time)","2019-08-20","Defect","Ship Staff","Ship Staff Insp.","Yard supplied many cooking apparatus inoperational in galley. Only hot plates, one small kneader & one baking oven shelf working.","Miscellaneous","MLC Related","Equipment Related","","","","","Hot plates supplied and installed in location.","2020-06-30","","Completed","2020-05-13","Yes","No","No","Internal","Will be supplied at next convenient port as delivery time is 27 days. This defect has been attended by ship staff after receipt of spare during docking so Date Recorded has to be amended  accordingly."]
[null,null,null,null,7581,"93_Tue Feb 12 2019 11:24:58 GMT+0000 (Coordinated Universal Time)","2019-08-20","Defect","Ship Staff","Ship Staff Insp.","Water leaking from Main engine jacket temperature controler 3-way valve spindle. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","O rings renewed , leak rectifed .","2020-03-31","","Completed","2020-04-06","No","No","No","Internal"]
[null,null,null,null,7673,"93_Mon Dec 02 2019 10:53:17 GMT+0000 (Coordinated Universal Time)","2019-08-20","Defect","Ship Staff","Ship Staff Insp.","Main Engine oil mist detector was showing error E014 which is negative pressure/air flow too low & the alarm is kept in off-scan condition.The alarm is in offscan condition. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Same was rectified by ship staff after take over","2020-01-31","015E/19","Completed","2019-11-10","Yes","No","No","Internal"]
[null,null,null,null,7582,"93_Tue Feb 12 2019 11:26:24 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Fwd winches & windlass power pack, temp. control sensor by-passed to avoid frequent overheating trip. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Fwd winches & windlass power pack, temp. control sensor working satisfactory and cooling water is able to control the temperature of the power pack.","2020-03-31","","Completed","2020-04-08","Yes","No","No","Internal"]
[null,null,null,null,7584,"93_Tue Feb 12 2019 11:29:46 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Fire & G/S pump alone not efficient for ballast tank eductor operation. Onboard C/O using 02 pumps for WBT final eduction","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Eductors renewed in dry dock and efficiency checked in richard's bay while loading. Single pump used for educting and found satisfactory.","2020-03-31","","Completed","2020-05-23","Yes","No","No","Internal"]
[null,null,null,null,7585,"93_Tue Feb 12 2019 11:31:48 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","All remote sounding gauges, draft gauges in ship's office not operational. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Remote gauges were attended by the shore technician from IMA.","2020-03-31","","Completed","2020-04-13","Yes","No","No","Internal"]
[null,null,null,null,7588,"93_Tue Feb 12 2019 11:36:58 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Both lifeboat - falls, self lowering wires & gripes due for renewal in next DD. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Lifeboat falls, self lowering wire and Gripes renewed .","2020-03-31","","Completed","2020-05-11","Yes","No","No","Internal"]
[null,null,null,null,7589,"93_Mon Dec 02 2019 11:41:30 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","All 3 A/E's are capable of taking only 340kW and below  with exhaust temperatures at around 480 degree celcius.(rated capacity 730 kW)resulting in breakage of exhaust valves\n\nSUSPECT: wrong timing and use of non genuine spares like inlet valve,s,exhaust valves,fuel valve nozzles,coolers and the turbochargers.Also appears that the lube oil used are in excess of 2000 running hours and not purified. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","All the three AEs overhauled in DD. Performance test carried out at 75% , found satifactory.","2020-03-31","016E/19","Completed","2020-03-22","Yes","No","No","Internal"]
[null,null,null,null,7590,"93_Tue Feb 12 2019 11:43:47 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Bilge fire & GS pump overboard valve gland leaking","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Gland Packing renewed , leak rectified","2020-01-31","","Completed","2020-01-18","No","No","No","Internal"]
[null,null,null,null,7591,"93_Tue Feb 12 2019 11:46:14 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","No.3 HFO bunker tank Stbd, minor fuel oil leakage from the tank gauging system sensor","E/R - Aux. Engine","MARPOL Related","Equipment Related","","","","","Gasket renewed, leak rectified","2020-01-31","","Completed","2020-01-15","No","No","No","Internal"]
[null,null,null,null,7592,"93_Tue Feb 12 2019 11:47:36 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Main engine unit No.2 cylinder oil lubricator inlet line Y-filter leaking form the plug","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Gasket renewed, leak rectifed","2020-01-31","","Completed","2020-01-08","No","No","No","Internal"]
[null,null,null,null,7593,"93_Tue Feb 12 2019 11:52:16 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Loadicator Computer is 15 yrs old. Same should be renewed to a newer computer & get Class approved. ","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","Job cancelled by the owners.","2020-03-31","","Completed","2020-04-13","No","No","No","Internal"]
[null,null,null,null,7594,"93_Tue Feb 12 2019 11:54:11 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Both sides bridge wing, bridge front glass & its frame not clear & corroded & wasted respectively ","Navigation - Others","Navigation","Equipment Related","","","","","Glass and frames of portholes were attended in DD. Frames renewed and glass cleaned thoroughly.","2020-03-31","","Completed","2020-03-20","Yes","No","No","Internal"]
[null,null,null,null,7595,"93_Tue Feb 12 2019 11:56:09 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Fwd winches & windlass power pack have drip hydraulic oil leakage from its pipe. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Leakage rectified.","2020-03-31","","Completed","2020-05-15","No","No","No","Internal"]
[null,null,null,null,7596,"93_Mon Dec 02 2019 11:50:50 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Cargo hold bilge eductor & ballast tank eductor were with doubler plate & jubilee clip repairs respectively, Now the doubler plate has been replaced with soft patch repair & some hot repair. ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Both eductors renewed in DD by Ship's staff.","2020-03-31","34DD/19","Completed","2020-04-11","Yes","No","No","Internal"]
[null,null,null,null,7597,"93_Tue Feb 12 2019 11:57:53 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Vessel unable to compact garbage volume & hence leading to garbage accumulation onboard. ","Miscellaneous","MARPOL Related","Equipment Related","","","","","Vessel received Garbage compactor in DD and compaction is done regularly.","2020-03-31","","Completed","2020-04-20","Yes","No","No","Internal"]
[null,null,null,null,7598,"93_Tue Feb 12 2019 11:59:53 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","MLC Audit","All cabin portholes on accommodation super structure are in poor condition & on outside show heavy rusting on the edges thus causing water ingress. ","Accommodation","MLC Related","Equipment Related","","","","","All porthole edges thoroughly derusted & sealed properly & then primered & painted. Portholes frames were sealed with silicon by attending team in DD.","2020-03-31","","Completed","2020-03-20","Yes","No","No","Internal"]
[null,null,null,null,7599,"93_Tue Feb 12 2019 12:01:24 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Bridge Wings underside rusted at many unaccessible places. ","Accommodation","Structural Condn. / WT integrity ","Equipment Related","","","","","Both Bridge wing underside derusted, and painted with two coats primer and full finish coat in DD by Ship's staff.","2020-03-31","","Completed","2020-03-04","Yes","No","No","Internal"]
[null,null,null,null,7600,"93_Tue Feb 12 2019 12:02:54 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Emergency generator radiator damaged badly and water leaking. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Radiator of the emergency generator renewed with new spare, the generator tried out , found working satisfactory with no leaks.","2020-01-31","","Completed","2019-12-16","No","No","No","Internal"]
[null,null,null,null,7602,"93_Tue Feb 12 2019 12:06:46 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Rescue boat(port) battery expiring on May 2020. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Battery renewed with new spare battery.","2020-03-31","","Completed","2020-04-05","No","No","No","Internal"]
[null,null,null,null,8952,"93_Tue Feb 12 2019 11:50:50 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Cargo hold bilge eductor & ballast tank eductor were with doubler plate & jubilee clip repairs respectively, Now the doubler plate has been replaced with soft patch repair & some hot repair. ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Both Eductors renewed in DD by ship's staff.","2020-03-31","","Completed","2020-04-11","Yes","No","No","Internal"]
[null,null,null,null,7674,"93_Mon Dec 02 2019 11:49:26 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","Topping up compressor is not being used, as it is not building up pressure","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Ship staff has put the compressor in use after take over.","2020-01-31","","Completed","2019-11-15","No","No","No","Internal"]
[null,null,null,null,null,"93_Tue Feb 12 2019 11:27:53 GMT+0000 (Coordinated Universal Time)","2019-08-21","Defect","Ship Staff","Ship Staff Insp.","All W/T door dogs on deck not free","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable"," All W/T door dogs  overhauled.","2020-07-31",null,"Completed","2020-06-06","Yes",null,null,"Internal"]
[null,null,null,null,7687,"93_Tue Mar 12 2019 07:53:21 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Vacuum toilet pump No.1 minor leakage. ","E/R - Aux. Mach.","MLC Related","Equipment Related","","","","","O ring of the casing renewed, leak rectified.","2020-01-31","","Completed","2019-12-13","No","No","No","Internal"]
[null,null,null,null,7688,"93_Tue Dec 03 2019 07:55:32 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","FWG feed water line chemical dosing pump not running","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","",""," The chemical dosing pump tried out and put in use, found working satisfactory","2020-01-31","","Completed","2019-12-10","No","No","No","Internal"]
[null,null,null,null,7693,"93_Tue Dec 03 2019 06:30:55 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Master's cabin entrance door curtain in poor condition. ","Miscellaneous","MLC Related","Equipment Related","","","","","Replaced with new one.","2020-01-31","001D/19","Completed","2020-01-05","No","No","No","Internal"]
[null,null,null,null,7603,"93_Tue Mar 12 2019 06:14:55 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Excessive condemned material in forecastle store. .","Miscellaneous","MARPOL Related","Equipment Related","","","","","Condemned material landed at Jin Hai ship yard.","2020-03-31","","Completed","2020-04-13","No","No","No","Internal"]
[null,null,null,null,7604,"93_Tue Mar 12 2019 06:22:19 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Vessel has 03 pcs pneumatic de-mucking davits in defunct condition. Same to be made operational.","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","2 De-mucking winch are operational and vessel is using them for cargo hold cleaning.","2020-08-31","","Completed","2020-04-13","Yes","No","No","Internal","This observation was raised in 2019 during takeover, revert what vessel has found reason for not operation of it ."]
[null,null,null,null,7605,"93_Tue Mar 12 2019 06:24:47 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Fwd P side Windlass motor gear engaging hydraulic mechanism has been removed from place & manual engagament used. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","As per Owners instructions, the gear engaging mechanism is operational and does not require any modification. Hence job is cancelled.","2020-03-31","","Completed","2020-01-10","Yes","No","No","Internal"]
[null,null,null,null,7606,"93_Tue Mar 12 2019 06:26:03 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Fwd S side Windlass motor gear engaging hydraulic mechanism full corroded & about to break anytime. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","As per Owners instructions, the gear engaging mechanism is operational and does not require any modification. Hence job is cancelled.","2020-01-31","","Completed","2020-01-10","Yes","No","No","Internal"]
[null,null,null,null,7607,"93_Tue Mar 12 2019 06:27:59 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Fwd & Midship draft guage hydraulic purge v/v looks poorly maintained","Cargo Mach.,Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Gauges attended in DD by technician and are operational. The purge valve maintained in DD.","2020-03-31","","Completed","2020-03-30","Yes","No","No","Internal"]
[null,null,null,null,7608,"93_Tue Mar 12 2019 06:29:22 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Both FWTks & DWTk cleaning & washing not done in the last 06 months. ","Hull & Tanks","MLC Related","Equipment Related","","","","","All fresh water tanks and Drinking water tank cleaned in Dry dock by ship's crew..","2020-03-31","","Completed","2020-03-20","Yes","No","No","Internal"]
[null,null,null,null,7609,"93_Tue Mar 12 2019 06:33:14 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Atmospheric condensor 14 Nos of tubes has been plugged. ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Complete atmospheric condensor renewed","2020-03-31","012E/19","Completed","2020-02-19","No","No","No","Internal"]
[null,null,null,null,7610,"93_Tue Mar 12 2019 06:35:20 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Boiler feed water controller erratic and leaking from the gland.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","The gland leak rectified","2020-03-31","","Completed","2020-03-08","No","No","No","Internal"]
[null,null,null,null,7611,"93_Tue Mar 12 2019 06:38:53 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Main Engine unit no.2,3 & 6 minor fuel oil leakage from shock absorber flange","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","All units fuel pump shock absorber oveerhauled and fitted with new gaskets, leaks rectified.","2020-03-31","","Completed","2020-04-02","No","No","No","Internal"]
[null,null,null,null,7612,"93_Tue Mar 12 2019 06:45:15 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Main engine unit no.6  minor fuel oil leakage from aft high pressure pipe. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","High pressure pipe renewed.","2020-03-31","","Completed","2020-03-18","No","No","No","Internal"]
[null,null,null,null,7613,"93_Tue Mar 12 2019 06:47:01 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Fwd Liferaft launching instructions poster in poor condition. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Replaced with new one.","2020-01-31","","Completed","2020-01-02","No","No","No","Internal"]
[null,null,null,null,7614,"93_Tue Mar 12 2019 06:49:17 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","All hatch cover opening chain drawing hydraulic motor open to shipping seas & thus prone to heavy seas & water damage.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Owners did not approve the job.","2020-03-31","","Completed","2020-04-13","Yes","No","No","Internal"]
[null,null,null,null,7615,"93_Tue Mar 12 2019 07:48:12 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","WBTks remote hydraulic v/v operating power pack pumps always kept 'ON' & pumps running continuously to maintain pressure. ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","After investigation, the pumps need to be kept on only during the period of operation and hence is being used accordingly.","2020-01-31","","Completed","2020-01-24","No","No","No","Internal"]
[null,null,null,null,7617,"93_Tue Mar 12 2019 07:56:56 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Main engine unit no.3 aft fuel injector leaking. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Injector renewed with spare overhauled injector.The engine tried out , found no leaks","2020-01-31","","Completed","2020-01-02","No","No","No","Internal"]
[null,null,null,null,8953,"93_Tue Mar 12 2019 07:55:32 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","FWG feed water line chemical dosing pump not running","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","",""," The chemical dosing pump inspected and put in use, found working satisfactory.","2020-01-31","","Completed","2019-12-10","No","No","No","Internal"]
[null,null,null,null,7675,"93_Tue Dec 03 2019 06:13:11 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Overside painting stage is in poor condition. Bos'n chair with hook also not available onboard. ","Miscellaneous","General Appearance","Equipment Related","","","","","Received at Xiamen.","2020-01-31","008D/19","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,7676,"93_Tue Dec 03 2019 07:51:45 GMT+0000 (Coordinated Universal Time)","2019-08-22","Defect","Ship Staff","Ship Staff Insp.","Helicopter Landing FFE- Fireman's Outfit Suit (02 pcs) completely worn out, helmets broken & unwearable. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Received at Xiamen","2020-01-31","","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,7618,"93_Tue Mar 12 2019 07:59:22 GMT+0000 (Coordinated Universal Time)","2019-08-24","Defect","Ship Staff","Ship Staff Insp.","Main engine unit no.3 fwd stbd cooling water connection pipe leaking","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","O rings renewed , leak rectified","2020-03-31","","Completed","2020-03-18","No","No","No","Internal"]
[null,null,null,null,7619,"93_Tue Mar 12 2019 08:01:02 GMT+0000 (Coordinated Universal Time)","2019-08-24","Defect","Ship Staff","Ship Staff Insp.","Main engine camshaft lube oil inlet low pressure shutdown broken. Alarm showing in Safety system unit and alarm monitor. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Card on the SSU panel renewed, broken alarm found normal","2020-03-31","","Completed","2020-03-18","No","No","No","Internal"]
[null,null,null,null,7692,"93_Tue Mar 12 2019 08:07:37 GMT+0000 (Coordinated Universal Time)","2019-08-26","Defect","Ship Staff","Ship Staff Insp.","Fireman's outfit suit & SCBAs visor in Fire Station looks worn out. One Safety helmet visor is missing. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","New Fireman's outfit & SCBA visors to be requisitioned along with one safety helmet with visor & neck protection","2020-01-31","004D/19","Completed","2019-11-30","No","No","No","Internal"]
[null,null,null,null,7621,"93_Tue Dec 03 2019 08:05:32 GMT+0000 (Coordinated Universal Time)","2019-08-26","Defect","Ship Staff","Ship Staff Insp.","Actual location of Fireman's outfit not in compliance with Ship's Fire Safety Plan. Ship's Fire Safety Plan modified as per ship's convenience. But not all are updated. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Actual location of Fireman's outfit made in compliance with Fire Safety Plan.","2020-03-31","","Completed","2020-04-13","No","No","No","Internal"]
[null,null,null,null,8954,"93_Tue Dec 03 2019 08:07:37 GMT+0000 (Coordinated Universal Time)","2019-08-26","Defect","Ship Staff","Ship Staff Insp.","Fireman's outfit suit & SCBAs visor in Fire Station looks worn out. One Safety helmet visor is missing. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","New Fireman's outfit & SCBA visors to be received along with one safety helmet with visor & neck protection","2020-03-31","004D/19","Completed","2020-04-13","No","No","No","Internal"]
[null,null,null,null,7677,"93_Tue Dec 03 2019 08:09:25 GMT+0000 (Coordinated Universal Time)","2019-08-26","Defect","Ship Staff","Ship Staff Insp.","Spare foam liquid in Fire Station stored in unlabelled water bottles. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Spare foam charges receive at Xiamen","2020-01-31","011D/19","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,7622,"93_Tue Mar 12 2019 08:14:21 GMT+0000 (Coordinated Universal Time)","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","Main engine exhaust pipe above the funnel exhaust platform welding is completely gone in fwd both port and stbd support frame. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Section of the plate cropped and new supports welded","2020-03-31","","Completed","2020-03-08","Yes","No","No","Internal"]
[null,null,null,null,7623,"93_Tue Mar 12 2019 08:15:51 GMT+0000 (Coordinated Universal Time)","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","All 3 Aux Engine exhaust pipe above the funnel exhaust platform completely rusted and holed. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","The exhaust pipes of all the 3 Aux Engine above the funnel cropped and new pipes fitted and supports welded","2020-03-31","","Completed","2020-04-01","Yes","No","No","Internal"]
[null,null,null,null,7624,"93_Tue Mar 12 2019 08:17:49 GMT+0000 (Coordinated Universal Time)","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","Incinerator exhaust pipe above the funnel exhaust platform rusted. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Incinerator exhaust pipe cropped and new pipe fitted.","2020-03-31","","Completed","2020-03-08","Yes","No","No","Internal"]
[null,null,null,null,7625,"93_Tue Mar 12 2019 08:20:26 GMT+0000 (Coordinated Universal Time)","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","Funnel hatch cover completely rusted","Hull & Tanks","Eng. / Strg. Comp.","Equipment Related","","","","","The hatch cover renewed.","2020-03-31","","Completed","2020-03-08","Yes","No","No","Internal"]
[null,null,null,null,7626,"93_Tue Mar 12 2019 08:31:38 GMT+0000 (Coordinated Universal Time)","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","Sewage discharge pump delivery line two section of pipes is holed in many places. Need to renewe the pipe.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","The pipe renewed with newly fabricated pipe","2020-03-31","","Completed","2020-04-03","No","No","No","Internal"]
[null,null,null,null,7627,"93_Tue Mar 12 2019 08:33:16 GMT+0000 (Coordinated Universal Time)","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","Main engine unit No.1 port side FWD and AFT cooling water connection pipe minor leakage. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Cooling water connection O rings renewed , leak rectified","2020-03-31","","Completed","2020-03-18","No","No","No","Internal"]
[null,null,null,null,7628,"93_Tue Mar 12 2019 08:50:35 GMT+0000 (Coordinated Universal Time)","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","Main engine fuel oil auto filter running hour meter is not working.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Job captured in duplication previously.","2020-06-30","","Completed","2020-06-07","No","No","No","Internal","This observation is captured two times, delete one observation."]
[null,null,null,null,7679,"93_Tue Dec 03 2019 08:12:22 GMT+0000 (Coordinated Universal Time)","2019-08-27","Defect","Ship Staff","Ship Staff Insp.","VDR data never downloaded by ship staff.","Navigation - VDR / BNWAS","Navigation","Equipment Related","","","","","Data downloaded by shore technician during re-programming at Xiamen","2020-01-31","","Completed","2019-11-10","No","No","No","Internal"]
[null,null,null,null,7630,"93_Tue Mar 12 2019 08:54:24 GMT+0000 (Coordinated Universal Time)","2019-08-28","Defect","Ship Staff","Ship Staff Insp.","All 03 embarkation ladders for both lifeboats & fwd liferafts, the shackle end thimble area & exposed ladder parts shows Sunrays / SW damage. .","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","New embarkation ladder received and other Embarkation ladders checked for wear & found in satisfactory condition.","2020-03-31","013D/19","Completed","2020-02-13","No","No","No","Internal"]
[null,null,null,null,7631,"93_Tue Mar 12 2019 08:56:50 GMT+0000 (Coordinated Universal Time)","2019-08-28","Defect","Ship Staff","Ship Staff Insp.","Boiler fuel oil pump No.2 shaft seal leaking. ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Pump overhauled , seal renewed","2020-03-31","","Completed","2020-03-11","No","No","No","Internal"]
[null,null,null,null,7632,"93_Tue Mar 12 2019 09:00:41 GMT+0000 (Coordinated Universal Time)","2019-08-28","Defect","Ship Staff","Ship Staff Insp.","No.1 HFO Purifier Fuel oil leaking from the inlet/outlet pipe flange. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","The gaskets of the inlet and outlet pipe flanges renewed, leak rectified","2020-01-31","","Completed","2019-12-03","No","No","No","Internal"]
[null,null,null,null,7633,"93_Tue Mar 12 2019 09:04:37 GMT+0000 (Coordinated Universal Time)","2019-08-28","Defect","Ship Staff","Ship Staff Insp.","A/E No.3 lube oil inlet pipe to turbocharger leaking. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Turbocharger overhauled, O ring renewed, leak rectified","2020-03-31","","Completed","2020-03-25","No","No","No","Internal"]
[null,null,null,null,7634,"93_Tue Dec 03 2019 09:10:15 GMT+0000 (Coordinated Universal Time)","2019-08-28","Defect","Ship Staff","Ship Staff Insp.","A/E ACONICS PMS system need to check as A/E synchronizing is being done manually. .","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","AE ACONIS PMS tried out , all the three generators are able to take on load on auto","2019-11-30","","Completed","2019-11-20","No","No","No","Internal"]
[null,null,null,null,7689,"93_Tue Mar 12 2019 09:20:59 GMT+0000 (Coordinated Universal Time)","2019-08-29","Defect","Ship Staff","Ship Staff Insp.","Boiler burner unit attached fuel oil pump leaking from shaft seal. ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","The fuel pump renewed with new spare pump, leak rectified","2020-01-31","20000000000000000000","Completed","2019-12-01","No","No","No","Internal"]
[null,null,null,null,7636,"93_Tue Mar 12 2019 09:24:31 GMT+0000 (Coordinated Universal Time)","2019-08-29","Defect","Ship Staff","Ship Staff Insp.","Sea chest both Low & High and Cooling sea water overboard valves have remote operating option(From 2nd Deck) but not working. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Hydraulic oil topped up,tried out the remote operation , operating satisfactory.","2020-01-31","","Completed","2019-12-03","No","No","No","Internal"]
[null,null,null,null,8955,"93_Tue Dec 03 2019 09:20:59 GMT+0000 (Coordinated Universal Time)","2019-08-29","Defect","Ship Staff","Ship Staff Insp.","Boiler burner unit attached fuel oil pump leaking from shaft seal. ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","The fuel oil pump renewed with new spare pump, tried out, working satisfactory with no leaks","2020-01-31","20000000000000000000","Completed","2020-12-01","No","No","No","Internal"]
[null,null,null,null,7678,"93_Tue Dec 03 2019 09:16:17 GMT+0000 (Coordinated Universal Time)","2019-08-29","Defect","Ship Staff","Ship Staff Insp.","Portable extinguishers spare charges not in compliance with Ship's Fire Safety Plan or even SOLAS or flag requirement. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Spare charges for portable extinguishers received at Xiamen","2019-11-30","","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,7637,"93_Tue Mar 12 2019 09:27:12 GMT+0000 (Coordinated Universal Time)","2019-08-30","Defect","Ship Staff","Ship Staff Insp.","Bridge wings - Anti skid walking mats in worn out condition. ","Accommodation","General Appearance","Equipment Related","","","","","New mats installed in location on bridge wings.","2020-03-31","","Completed","2020-06-03","Yes","No","No","Internal"]
[null,null,null,null,7680,"93_Tue Dec 03 2019 09:32:14 GMT+0000 (Coordinated Universal Time)","2019-09-02","Defect","Ship Staff","Ship Staff Insp.","SI lights on lifebuoys on deck looks worn out. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","New SI lights received at Xiamen","2020-01-31","011D/19","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,7681,"93_Tue Dec 03 2019 09:34:49 GMT+0000 (Coordinated Universal Time)","2019-09-02","Defect","Ship Staff","Ship Staff Insp.","EPIRB HRU expiring in Nov 2019. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","New HRU ordered & installed.","2019-11-05","011D/19","Completed","2019-11-10","No","No","No","Internal"]
[null,null,null,null,7682,"93_Tue Dec 03 2019 09:37:02 GMT+0000 (Coordinated Universal Time)","2019-09-02","Defect","Ship Staff","Ship Staff Insp.","Helicopter FFE foam concentrate stock is manufactured 2013 / 2014. More than 05 years old. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Replaced with new stock, received at Xiamen.","2019-11-30","011D/19","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,7691,"93_Tue Dec 03 2019 09:39:49 GMT+0000 (Coordinated Universal Time)","2019-09-02","Defect","Ship Staff","Ship Staff Insp.","No.2 main air compressor oil is getting emulsification. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","The main air compressor crankcase inspected , find no leaks , the sump oil drained and replenished with fresh oil. ","2019-12-30","","Completed","2019-12-03","No","No","No","Internal"]
[null,null,null,null,7638,"93_Tue Mar 12 2019 09:29:34 GMT+0000 (Coordinated Universal Time)","2019-09-02","Defect","Ship Staff","Ship Staff Insp.","Vessel hawse pipes have no covering arrangement on forecastle deck for anti pilferage measure. Hawse pipe covers stowed in FPK store. ","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","New Hawse pipe covers installed on forecastle deck & put in use.","2020-03-31","","Completed","2020-05-15","No","No","No","Internal"]
[null,null,null,null,7639,"93_Tue Mar 12 2019 09:42:44 GMT+0000 (Coordinated Universal Time)","2019-09-02","Defect","Ship Staff","Ship Staff Insp.","Soft patch in STBD grey water overboard pipe line in bottom platform. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Pipe renewed at Dry Dock","2020-03-31","","Completed","2020-02-24","No","No","No","Internal"]
[null,null,null,null,8956,"93_Tue Mar 12 2019 09:39:49 GMT+0000 (Coordinated Universal Time)","2019-09-02","Defect","Ship Staff","Ship Staff Insp.","No.2 main air compressor oil is getting emulsification. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","The cooler gasket renewed, the crankcase inspected, the old oil drained and replenished with fresh oil.","2019-12-30","","Completed","2019-12-03","No","No","No","Internal"]
[null,null,null,null,7541,"93_Tue Mar 12 2019 09:53:04 GMT+0000 (Coordinated Universal Time)","2019-09-04","Defect","Ship Staff","Ship Staff Insp.","A/E lube oil settling tank is filled with 8.45 m3 of sludge and water. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","The contents of the tank disposed to barge, tank cleaned.","2020-01-31","","Completed","2019-12-26","No","No","No","Internal"]
[null,null,null,null,7640,"93_Tue Mar 12 2019 09:50:42 GMT+0000 (Coordinated Universal Time)","2019-09-04","Defect","Ship Staff","Ship Staff Insp.","Steam pipe in purifier room is leaking from the flange. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Gasket renewed , leak rectified","2020-03-31","","Completed","2020-02-12","No","No","No","Internal"]
[null,null,null,null,7641,"93_Tue Mar 12 2019 09:55:25 GMT+0000 (Coordinated Universal Time)","2019-09-04","Defect","Ship Staff","Ship Staff Insp.","M/E lube oil settling tank is filled with 6.5 m3 of used oil. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","The contents of the tank disposed to barge, the tank cleaned","2020-01-31","","Completed","2019-12-26","No","No","No","Internal"]
[null,null,null,null,7642,"93_Tue Mar 12 2019 10:00:30 GMT+0000 (Coordinated Universal Time)","2019-09-04","Defect","Ship Staff","Ship Staff Insp.","Pressure and temperature gauges of various pumps not working. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Defective gauges renewed.","2020-01-31","011E/19","Completed","2020-03-26","No","No","No","Internal"]
[null,null,null,null,7669,"93_Tue Dec 03 2019 09:45:42 GMT+0000 (Coordinated Universal Time)","2019-09-04","Defect","Ship Staff","Ship Staff Insp.","Understand from ship staff, vessel has water ingress issue from No.02 CH Tank top","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","NO.2 CH tanktop repaired with insert plate in presence of class surveyor at Putian berth.","2020-01-31","","Completed","2019-11-01","No","No","No","Internal"]
[null,null,null,null,7670,"93_Tue Mar 12 2019 09:48:54 GMT+0000 (Coordinated Universal Time)","2019-09-04","Defect","Ship Staff","Ship Staff Insp.","All Garbage collection receptacles to be colour coded as per Company GMP","Miscellaneous","MARPOL Related","Equipment Related","","","","","Garbage Receptacles colour coded as per the Garbage Management Plan","2020-01-31","","Completed","2019-12-03","No","No","No","Internal"]
[null,null,null,null,7643,"93_Tue Mar 12 2019 10:02:35 GMT+0000 (Coordinated Universal Time)","2019-09-09","Defect","Ship Staff","Ship Staff Insp.","Both lifeboats, fwd & aft hooks engaged & locked position yellow marking is missing. ","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Both Lifeboat hooks marked as per instructions.","2020-03-05","","Completed","2020-02-24","No","No","No","Internal"]
[null,null,null,null,7644,"93_Tue Mar 12 2019 10:04:14 GMT+0000 (Coordinated Universal Time)","2019-09-10","Defect","Ship Staff","Ship Staff Insp.","Both Boiler feed water pump discharge line holes repaired with soft patch","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","The feed water pump discharge lines renewed.","2020-03-31","","Completed","2020-02-24","No","No","No","Internal"]
[null,null,null,null,7645,"93_Tue Mar 12 2019 10:11:44 GMT+0000 (Coordinated Universal Time)","2019-09-10","Defect","Ship Staff","Ship Staff Insp.","Oily bilge pump discharge line to OWS many places corroded and have trace of leakage. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","The entire discharge line from the Oily bilge pump to OWS renewed with newly fabricated pipe line.","2020-03-31","","Completed","2020-02-24","No","No","No","Internal"]
[null,null,null,null,7646,"93_Tue Mar 12 2019 10:14:14 GMT+0000 (Coordinated Universal Time)","2019-09-10","Defect","Ship Staff","Ship Staff Insp.","Oxygen cylinder room closing valve have soft patch. .","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","The Oxygen Cylinder room closing valve renewed.","2020-03-31","009E/19","Completed","2020-03-25","No","No","No","Internal"]
[null,null,null,null,7647,"93_Tue Dec 03 2019 10:31:12 GMT+0000 (Coordinated Universal Time)","2019-10-18","Defect","Ship Staff","Ship Staff Insp.","No.03 hatch cover chain drawing hydraulic motor in not working condition & lying defunct.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Existing hydraulic Drawing chain motor was overhauled and bearing , bushes and seal renewed by the Vendor. No.3 Hatch cover motor is working satisfactory.","2020-03-31","017E/19","Completed","2020-04-12","No","No","No","Internal"]
[null,null,null,null,7648,"93_Tue Mar 12 2019 10:33:09 GMT+0000 (Coordinated Universal Time)","2019-10-26","Defect","Ship Staff","Ship Staff Insp.","All hatch cover chain drawing hydraulic motors to be overhauled. (09 pcs) ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","All hatch cover hydraulic drawing chain motoroverhauled, bearings, bushes and seals renewed as required by the ship yard.","2020-03-31","","Completed","2020-04-12","Yes","No","No","Internal"]
[null,null,null,null,7683,"93_Tue Dec 03 2019 10:45:09 GMT+0000 (Coordinated Universal Time)","2019-10-31","Defect","Ship Staff","Ship Staff Insp.","No.02 CH straight ladder bottom platform is damaged during present discharging operation at Luoyu port. ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Repaired by shore staff at Putian berth","2020-11-05","","Completed","2019-11-01","No","No","No","Internal"]
[null,null,null,null,7649,"93_Tue Mar 12 2019 10:35:18 GMT+0000 (Coordinated Universal Time)","2019-10-31","Defect","Ship Staff","Ship Staff Insp.","Fire & G/S pump No.2 leaking from shaft seal. .","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","The Pump overhauled, the mechanical seal renewed.","2020-03-31","","Completed","2020-03-19","No","No","No","Internal"]
[null,null,null,null,7650,"93_Tue Mar 12 2019 10:37:26 GMT+0000 (Coordinated Universal Time)","2019-10-31","Defect","Ship Staff","Ship Staff Insp.","A/E fuel oil heater found slightly leaking from the end cover flange. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","The heater cleaned and pressure tested , the gasket renewed, leak rectified.","2020-01-31","","Completed","2020-02-21","No","No","No","Internal"]
[null,null,null,null,7651,"93_Tue Mar 12 2019 10:39:44 GMT+0000 (Coordinated Universal Time)","2019-10-31","Defect","Ship Staff","Ship Staff Insp.","FWG observed to be producing only 10 to 12 MT/day                   (capacity :- 25 MT) ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Evaporatorcleaned , the choked tubes cleared and pressure tested. The condenser and the demister cleaned.","2020-03-31","","Completed","2020-03-28","Yes","No","No","Internal"]
[null,null,null,null,7652,"93_Tue Mar 12 2019 10:42:12 GMT+0000 (Coordinated Universal Time)","2019-10-31","Defect","Ship Staff","Ship Staff Insp.","All stained steam laggings in purifier room/Generators/Boilers/ME/General laggings in Engine Room. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","All the stained laggings renewed.","2020-03-31","","Completed","2020-04-05","Yes","No","No","Internal"]
[null,null,null,null,7684,"93_Tue Dec 03 2019 10:54:26 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","Blr feed water salinometer in alarm condition. ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Rectified by ship staff after take over","2020-01-31","","Completed","2019-11-17","No","No","No","Internal"]
[null,null,null,null,7685,"93_Tue Mar 12 2019 11:29:39 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","Vessel has no spare mooring ropes, other than those on drums. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Vessel supplied with 02 spare mooring ropes at Xiamen","2020-11-05","012D/19","Completed","2019-11-08","No","No","No","Internal"]
[null,null,null,null,7686,"93_Tue Dec 03 2019 11:14:58 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","Emergency generator abnormal alarm existing/not in ready to start position. ","Critical Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Inspected & rectified","2020-01-31","","Completed","2019-11-20","No","No","No","Internal"]
[null,null,null,null,7690,"93_Tue Dec 03 2019 11:13:14 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","WMFF system in alarm condition/panel abnormal alarm. ","Critical Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","All the flame sensors and the smoke sensors of the WMFSS checked , the faulty smoke sensors renewed with new sensors and now the system is back to normal with no alarms in the panel","2020-01-31","","Completed","2019-12-08","No","No","No","Internal"]
[null,null,null,null,7653,"93_Tue Mar 12 2019 10:48:43 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","All WB TSTs & DBTs onboard need thorough demucking, UT guaging & rerusting & painiting as required. ","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","All ballast tanks UT gauging done by attending team and demucking cancelled by the Owners. Maintenance to be carried out in ballast tank on Owner's instructions.","2020-03-31","","Completed","2020-04-12","Yes","No","No","Internal"]
[null,null,null,null,7654,"93_Tue Mar 12 2019 10:52:24 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","All lifting cranes & davit main wires + ancillary wires wires on board due for renewal in DD. (01 prov. Crane, 01 E/R o/h crane, 02 bunker davits, 02 gangways). ","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related","","","","","New wires received and installed in location. certificates updated in file.","2020-03-31","","Completed","2020-05-13","Yes","No","No","Internal"]
[null,null,null,null,7655,"93_Tue Mar 12 2019 10:56:11 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","Few  exhaust temperature guages for the AE are faulty and few are missing. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","The exhaust temperature guages of all the three AEs fitted with new temperature guages.","2020-03-31","","Completed","2020-03-22","No","No","No","Internal"]
[null,null,null,null,7657,"93_Tue Mar 12 2019 11:22:33 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","Main Engine Lubricators for all the units leaking. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","O rings of Main Engine lubricator indicators renewed.","2020-03-31","","Completed","2020-02-20","No","No","No","Internal"]
[null,null,null,null,7658,"93_Tue Mar 12 2019 11:25:17 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","No.02 HFO (P) bunker tank is not used for bunkering atleast in the last 11 months. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","No.2 HFO (P) bunker tank cleaned at DD and put in use","2020-03-31","","Completed","2020-02-22","No","No","No","Internal"]
[null,null,null,null,7659,"93_Tue Mar 12 2019 11:27:16 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","10 nos. mooring ropes put in use since 2014 / 2015 & are already 05 years old & in moderate condition.  ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","8 mooring ropes received in dry dock put in use and old wasted and damged mooring ropes removed and kept separately marked as condemned ropes.","2020-03-31","","Completed","2020-04-20","No","No","No","Internal"]
[null,null,null,null,7660,"93_Tue Mar 12 2019 11:32:11 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","All roller fairleads have no record of overhauling & all are not rotating easily. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","All roller fairleads overhauled in DD. Bushes and shaft renewed for 18 pieces of fair leads.","2020-03-31","","Completed","2020-04-08","No","No","No","Internal"]
[null,null,null,null,8957,"93_Tue Mar 12 2019 11:13:15 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","WMFF system in alarm condition/panel abnormal alarm. ","Critical Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","All the flame sensors and the smoke sensors of WMFF system checked, the faulty smoke sensors renewed with new sensors.The panel is normal without any alarms ","2020-01-31","","Completed","2019-12-08","No","No","No","Internal"]
[null,null,null,null,8958,"93_Tue Dec 03 2019 11:35:12 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","All hatch cover cleats have no record of last overhauling.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Duplication of previous job.","2020-08-31","","Completed","2020-06-05","No","No","No","Internal","This job is recorded twice, kindly keep only one job in report."]
[null,null,null,null,7662,"93_Fri Apr 12 2019 00:05:32 GMT+0000 (Coordinated Universal Time)","2019-11-22","Defect","Ship Staff","Ship Staff Insp.","Stbd anchor, one fluke shows a bend & anchor not used since last 08 months by the previous management","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Dye test of anchors carried out and found satisfactory.Owners and Class surveyor are satisfied with the Anchor and hence the job is cancelled.","2020-01-31","","Completed","2020-01-19","Yes","No","No","Internal"]
[null,null,null,null,7663,"93_Wed Dec 04 2019 00:09:37 GMT+0000 (Coordinated Universal Time)","2019-11-22","Defect","Ship Staff","Ship Staff Insp.","Gangway Starboard side ladderstep guard is broken at various places .\t","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related","","","","","Gangway step guard repaired by Shipyard.","2020-03-31","","Completed","2020-04-06","Yes","No","No","Internal"]
[null,null,null,null,7664,"93_Fri Apr 12 2019 00:13:38 GMT+0000 (Coordinated Universal Time)","2019-11-22","Defect","Ship Staff","Ship Staff Insp.","Gangway Stanchions are corroded and wasted.\t","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related","","","","","Gangway stanchions repaired.","2020-03-31","","Completed","2020-05-13","No","No","No","Internal"]
[null,null,null,null,7665,"93_Wed Dec 04 2019 00:18:34 GMT+0000 (Coordinated Universal Time)","2019-11-22","Defect","Ship Staff","Ship Staff Insp.","Cargo hold bilge sounding pipe of cargo hold No.3 Port side, No.4 stbd side and No.9 Port side are broken and sounding the Bilges are not possible.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Cargo Hold Bilges sounding pipes renewed in Dry dock after hydroblasting and painted 2 coats epoxy.","2020-03-31","","Completed","2020-04-10","Yes","No","No","Internal"]
[null,null,null,null,7667,"93_15/12/2019 10:53:13 AM","2019-12-08","Breakdown","Ship Staff","Ship Staff Insp.","Boiler not firing in auto as well as in manual mode.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","On inspection, the heater found choked, the heater cleaned and fitted back. The boiler tried out and is found working in both auto and manual mode.","2019-12-26","MOJO 190039","Completed","2020-12-26","No","No","No","Internal"]
[null,null,null,null,7668,"93_15/12/2019 10:59:20 AM","2019-12-11","Breakdown","Ship Staff","Ship Staff Insp.","The motor of the primary blower of the incinerator showing zero insulation, the blower impeller and the coupling damaged","Miscellaneous","MARPOL Related","Equipment Related","","","","","The primary blower, impeller and the coupling renewed with new spares , tried out working satisfactory. ","2020-03-31","MOJO 190037","Completed","2020-03-25","No","No","No","Internal"]
[null,null,null,null,10316,"93_30/1/2020 8:00:25 PM","2020-01-27","Breakdown","Ship Staff","Ship Staff Insp.","Diesel Generator No.1 ACB linkage found broken and unable to take DG#1  on load","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","ACB renewed with new spare ACB, tried out , working satisfactory","2020-03-31","MOJO200052 ","Completed","2020-03-05","No","No","No","Internal"]
[null,null,null,null,10317,"93_31/1/2020 9:05:26 AM","2020-01-27","Defect","Ship Staff","Ship Staff Insp.","Upper stool space access hatch W/T lid rubber packing channel fully corroded & wasted.","Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related","","","","","Upper stool space access hatch W/T lid rubber packing channel de-rusted, built up with flat bars & rubber packing renewed. ","2020-03-31","","Completed","2020-03-08","Yes","No","No","Internal"]
[null,null,null,null,12138,"93_17/5/2020 11:32:40 AM","2020-05-03","Defect","Ship Staff","Ship Staff Insp.","All hatch cover stoppers are rusted and siezed. Stoppers to be made free.","Cargo Mach.","Cargo / Ballast Systems","External Factors","","","","","Hatch cover stoppers  made free and lubrication carried out.","2020-05-31","","Completed","2020-05-13","No","No","No","Internal"]
[null,null,null,null,12139,"93_17/5/2020 11:44:57 AM","2020-05-04","Observation","Ship Staff","Ship Staff Insp.","Garbage drums are leaking and need to be replaced.","Miscellaneous","General Appearance","External Factors","","","","","Leaking garbage drums replaced with new ones.","2020-05-30","","Completed","2020-05-16","No","No","No","Internal"]
[null,null,null,null,null,"93_30/6/2020 12:44:17 PM","2020-06-22","Defect","Ship Staff","Ship Staff Insp.","AE 3 - Unit #1 - Fuel Pump delivery valve assembly was found cracked and oil leaking from the seating face of the delivery valve. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","AE was immediately stopped and delivery valve assembly replaced by old genuine spare. ","2020-06-22",null,"Completed","2020-06-22","No",null,null,"Internal"]
[null,null,null,null,null,"93_29/6/2020 10:50:02 PM","2020-06-23","Observation","Ship Staff","Ship Staff Insp.","Port side embarkation ladder shackles seized ","LSA / FFA","Safety / LSA / FFA","External Factors",null,null,"Not Applicable","Not Applicable","derusting & lubrication done","2020-06-26",null,"Completed","2020-06-24","No",null,null,"Internal"]
[null,null,null,null,null,"93_30/6/2020 12:31:56 PM","2020-06-25","Defect","Ship Staff","Ship Staff Insp.","MAC 1 & 2 - Cooling water inlet magnetic solenoid valve was found always in open condition thereby leading to excessive cooling of compressor as standstill condition.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Upon investigation , found the timer for magentic solenoid valve operation was defetive and same was replaced with new spare. Compressor test run and found satisfactory.","2020-06-30",null,"Completed","2020-06-29","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["93","MOJO (08-06-2020)","93_1593151682601.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]