{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":21,"n_cols":28,"rows_kept":21,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","2020-04-30",null,null,"Ship Name","Kalamazoo"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,null,"94_23/11/2020 5:39:35 PM","2020-11-23","Defect","Ship Staff","Ship Staff Insp.","Burnt PCB of marine master clock.","Elect. Mach. & Equip.","Communication","Equipment Related",null,null,"Not Applicable","Not Applicable","Informed office. Waiting for PO. To replace damage PCB.","2020-12-30",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"94_12/15/2020 3:30:36 PM","2020-09-12","Defect","Ship Staff","Ship Staff Insp.","GPD Antenna Cable defective ","Navigation - DGPS / EPFS / AIS","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","Awating supply Cable antenna /connector","2021-01-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"94_22/12/2020 2:41:28 PM","2020-12-21","Defect","Ship Staff","Ship Staff Insp.","Axial damper AFT side oil pressure switch was defective broken wire.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace new pressure switch ,awaiting supply spare.","2021-01-15",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"94_29/12/2020 8:35:39 AM","2020-12-29","Defect","Ship Staff","Ship Staff Insp.","NO.3A S.W.B. TANK (S) Heeeling tank  observed reading is zero ,try to cleaned the sensor and noticed same no reading.Confirmed the sensor was defective.","Hull & Tanks","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace new sensor ,Request sensor at PAL  by January 2021.","2021-01-15",null,"Waiting spare",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":203,"n_cols":28,"rows_kept":203,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","2020-04-30",null,null,"Ship Name","KALAMAZOO (26-12-2019)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,6816,"94_Wed Dec 11 2019 08:49:23 GMT+0000 (Coordinated Universal Time)","2018-02-04","Defect","Ship Staff","Ship Staff Insp.","Ballast sensors 23 pcs to renew","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Received  8 pcs ballast sensors  and 8 pcs.  already installed.","2019-09-30","Kala 190066","Completed","2019-09-27","No","No","No","Internal"]
[null,null,null,null,6767,"94_Mon Nov 11 2019 17:17:29 GMT+0000 (Coordinated Universal Time)","2018-07-26","Defect","Ship Staff","Ship Staff Insp.","No UV lamp therefore the UVK sterilizer unoperational ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","To replace UV lamp ( Rcvd spares KALA180140)Need more spare re-order ( UV Lamp)","2018-08-30","KALA185102-KALA180174","Completed","2019-02-27","No","No","No","Internal"]
[null,null,null,null,6814,"94_Wed Dec 11 2019 08:41:53 GMT+0000 (Coordinated Universal Time)","2018-09-24","Defect","Ship Staff","Ship Staff Insp.","Defective No. 1& 2  HFO service tank sensor","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Cleaned sensor and retighten the wirings. To be order next year due to tight budget.","2019-09-30","Kala190066","Completed","2019-08-26","No","No","No","Internal"]
[null,null,null,null,6737,"94_Mon Nov 11 2019 18:50:56 GMT+0000 (Coordinated Universal Time)","2019-01-01","Defect","Ship Staff","Ship Staff Insp.","Main SW pump no. 1 leaking mechanical seal","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","renew mechanical seal with new spare received","2019-11-30","KALA190009","Completed","2019-11-23","No","No","No","Internal","Based on VFF, order was supplied to vessel at Pusan on 07th October 2019. When do you plan to carry out replacement of the mechanical seal?"]
[null,null,null,null,6759,"94_Wed Dec 11 2019 04:52:07 GMT+0000 (Coordinated Universal Time)","2019-01-04","Defect","Ship Staff","Ship Staff Insp.","Leaking mechanical seal of MSW pump no.1 ","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Rectified leaking / replaced new spare mechanical seal of Main Sea water p/p no.1 ","2019-01-05","","Completed","2019-01-05","No","No","No","Internal"]
[null,null,null,null,6760,"94_Mon Nov 11 2019 16:09:46 GMT+0000 (Coordinated Universal Time)","2019-01-04","Defect","Ship Staff","Ship Staff Insp.","Rectify Balalst Water treatment pump no.1 wiping \"timeout alarm\" ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","To rectified alarmed of BWT no.1 found position switch defective -restored magnet to detect the system,Replaced 4 pcs UV lamp/ 2 pcs quarts jacket.","2019-01-15","","Completed","2019-01-05","No","No","No","Internal"]
[null,null,null,null,6761,"94_Mon Nov 11 2019 16:15:19 GMT+0000 (Coordinated Universal Time)","2019-01-04","Defect","Ship Staff","Ship Staff Insp.","Defective flame detector at incinerator area ","Elect. Mach. & Equip.","Safety / LSA / FFA","Equipment Related","","","","","To replace with new spare  flame detector ","2019-01-15","KALA190005","Completed","2019-01-20","No","No","No","Internal"]
[null,null,null,null,6803,"94_Wed Dec 11 2019 08:02:37 GMT+0000 (Coordinated Universal Time)","2019-01-14","Defect","Ship Staff","Ship Staff Insp.","Cargo hold fan No:08 -3GS5  -port side burned -out motor wiring ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","To be replace new motor assembly both casargo hold supply fan 3GS5","2019-04-30","","Completed","2019-05-08","No","No","No","Internal"]
[null,null,null,null,6813,"94_Wed Dec 11 2019 08:39:26 GMT+0000 (Coordinated Universal Time)","2019-01-14","Defect","Ship Staff","Ship Staff Insp.","Cargo hold fan NO.11 3GS4 port side burned -out motor wiring ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","To replace new motor assembly hold supply fan no. 11 3GS4.","2019-09-30","KALA190121","Completed","2019-08-21","No","No","No","Internal"]
[null,null,null,null,6762,"94_Mon Nov 11 2019 16:18:48 GMT+0000 (Coordinated Universal Time)","2019-01-21","Defect","Ship Staff","Ship Staff Insp.","Rcvd newBallast sensor from supplier to install to 3B SWB tk. port side defective sensor reading.","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","To renewed new rcvd ballast sensor 3B SWB port side and back to normal reading.","2019-01-21","","Completed","2019-01-21","No","No","No","Internal"]
[null,null,null,null,6798,"94_Mon Nov 11 2019 18:44:01 GMT+0000 (Coordinated Universal Time)","2019-01-21","Defect","Ship Staff","Ship Staff Insp.","HFO Purifier feed pump no.1 & 2 Leaking oil seal ","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","To renew oil seal leaking of HFO feed pump no.1 & 2","2019-01-31","","Completed","2019-04-07","No","No","No","Internal"]
[null,null,null,null,6766,"94_Mon Nov 11 2019 17:12:28 GMT+0000 (Coordinated Universal Time)","2019-01-22","Defect","Ship Staff","Ship Staff Insp.","Galley oven burned -out transformer ","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","To be replace new transformer ","2019-01-31","KALA190035","Completed","2019-02-20","No","No","No","Internal"]
[null,null,null,null,6763,"94_Mon Nov 11 2019 16:23:21 GMT+0000 (Coordinated Universal Time)","2019-01-26","Defect","Ship Staff","Ship Staff Insp.","Aux. Boiler burner oil pump broken driving shaft gear.and no pressure build up due to broken gear","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Rectified and repaired take the old pump driving shaft and gear  fixed it and testing pressure come-up and back to normal and testted firing and working satisfactory.","2019-01-26","","Completed","2019-01-26","No","No","No","Internal"]
[null,null,null,null,6764,"94_Mon Nov 11 2019 16:28:48 GMT+0000 (Coordinated Universal Time)","2019-02-03","Defect","Ship Staff","Ship Staff Insp.","Heat Defector on paint store defector fault appearing on panel during testing ","Elect. Mach. & Equip.","Safety / LSA / FFA","Equipment Related","","","","","Rectified changed new spare heat detector / back to normal working.","2019-02-03","","Completed","2019-02-03","No","No","No","Internal"]
[null,null,null,null,6765,"94_Mon Nov 11 2019 16:30:55 GMT+0000 (Coordinated Universal Time)","2019-02-04","Defect","Ship Staff","Ship Staff Insp.","Leaking Gasket of Main steam valve of aux. boiler","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Rectified laeaking changed new fabricated gasket and observed after no more leaking exist.","2019-02-04","","Completed","2019-02-04","No","No","No","Internal"]
[null,null,null,null,6815,"94_Wed Dec 11 2019 08:43:56 GMT+0000 (Coordinated Universal Time)","2019-02-23","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Rescue Boat Davit Accumulator press gauge to order & check for hose coupling for charging nitrogen","LSA / FFA","MLC Related","Equipment Related","","","","","To raise RO for Charging Hose of Accumulator","2019-09-30","KALA190089","Completed","2019-06-30","No","No","No","Internal"]
[null,null,null,null,6768,"94_Mon Nov 11 2019 17:20:41 GMT+0000 (Coordinated Universal Time)","2019-02-26","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emg gen fuel storage tank doesn't have marking on gauge glass of min fuel required to RUN for 18hours of operation as required by SOLAS regulations","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","To stencil FO tank level of 18hrs continous running","2019-03-01","","Completed","2019-03-06","No","No","No","Internal"]
[null,null,null,null,6805,"94_Wed Dec 11 2019 08:13:16 GMT+0000 (Coordinated Universal Time)","2019-02-26","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emg fire p/p priming pump clutch lining was not touching the pump lining during stop condition, same to be adjusted","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","To check the clutch of priming unit","2019-05-31","KALA190088","Completed","2019-06-03","No","No","No","Internal"]
[null,null,null,null,6769,"94_Mon Nov 11 2019 17:33:02 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","WS grinding m/c making noise, motor to o'haul","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To overhaul/changed bearing","2019-03-14","KALA190035","Completed","2019-03-06","No","No","No","Internal"]
[null,null,null,null,6770,"94_Mon Nov 11 2019 17:36:26 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ER logbook reading were written only once a day, to be written twice a day.","Documentation","Cert. & Docu.","Equipment Related","","","","","To comply as required","2019-02-28","","Completed","2019-02-28","No","No","No","Internal"]
[null,null,null,null,6771,"94_Mon Nov 11 2019 17:41:19 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pneumatic air regulators for BWTS control 3 way vv to be drained everyday, same to be stencilled","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To drain everyday and stencilled \"Drain Everyday\"","2019-03-01","","Completed","2019-03-01","No","No","No","Internal"]
[null,null,null,null,6772,"94_Mon Nov 11 2019 17:44:43 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Near OWS ovbd v/v notice to put \"NOT TO BE OPERATED WITHOUT PERMISSION OF MASTER & CHIEF ENGINEER\"","Documentation","Cert. & Docu.","Equipment Related","","","","","To post poster near OWS valve","2019-03-14","","Completed","2019-03-07","No","No","No","Internal"]
[null,null,null,null,6773,"94_Mon Nov 11 2019 17:47:22 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No. 2 steering gear space heater bulb fused to renew","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","ETO to check","2019-03-04","","Completed","2019-03-07","No","No","No","Internal"]
[null,null,null,null,6774,"94_Mon Nov 11 2019 17:49:44 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sewage plant 2 in no. transparent hose to be replaced with new as part of 3 monthly routines.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To replace with new transparent hose","2019-03-14","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6776,"94_Mon Nov 11 2019 17:54:30 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No. 2 Lube oil purifier top cover seal leaking, to replace with new","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","To check/Renewed o-ring","2019-03-09","","Completed","2019-03-08","No","No","No","Internal"]
[null,null,null,null,6777,"94_Mon Nov 11 2019 17:56:36 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo hold space smoke detector both motor to overhaul","Elect. Mach. & Equip.","Safety / LSA / FFA","Equipment Related","","","","","To check for spare ball bearing ","2019-03-30","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6783,"94_Mon Nov 11 2019 18:10:45 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Boiler chloride level is 130 which is on higher side, blow down to be carried out & cooling water nitrate level is too low, to add chemicals. Also testing chemicals have expired, need to order new.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Vessel to raise RO for testing reagent","2019-03-04","","Completed","2019-03-08","No","No","No","Internal"]
[null,null,null,null,6784,"94_Mon Nov 11 2019 18:12:44 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Lagging to fitted on main engine fuel pp no.2 HP pipe outlet. All temp piping to be covered with insulation lagging including ME and Dg T/Cs as it is fire hazard.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To put insulation lagging","2019-03-06","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6786,"94_Mon Nov 11 2019 18:16:32 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Air compressor Lube oil low pressure trip set at very low pressure, to check from manual the cut off pressure & adjust accordingly.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To be check and confirm","2019-03-14","","Completed","2019-03-10","No","No","No","Internal"]
[null,null,null,null,6787,"94_Mon Nov 11 2019 18:18:24 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Vessel fuel oil C/O approved procedures to ECA/SECA to be posted in ECR","Documentation","Cert. & Docu.","Equipment Related","","","","","To be posted at ECR","2019-04-14","","Completed","2019-03-10","No","No","No","Internal"]
[null,null,null,null,6788,"94_Mon Nov 11 2019 18:20:41 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME backwas servo filter differential press coming frequently & both auto backwash & bypass are kept in use, plan backwash filter to clean at every port stay. Check for proper operation of backwash cycle confirming both solenoid are activated. Also check if the frequency of backwash can be reduced","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Cleaned every arrival port the Auto and manual filter","2019-03-06","","Completed","2019-03-12","No","No","No","Internal"]
[null,null,null,null,6789,"94_Mon Nov 11 2019 18:23:16 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Luminance to increase in purifier room, plan to install additional LED ligh","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","ETO to install additional lighting","2019-03-30","","Completed","2019-03-12","No","No","No","Internal"]
[null,null,null,null,6790,"94_Mon Nov 11 2019 18:25:07 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sewage plant metering pp not dosing the chemical to recheck the correct operation from manual.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To check the operating instruction of the Metering pump","2019-03-02","","Completed","2019-03-14","No","No","No","Internal"]
[null,null,null,null,6791,"94_Mon Nov 11 2019 18:27:15 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aux boiler burner hing door limit switch in operational, to replace with new.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","ETO to check","2019-03-14","","Completed","2019-03-14","No","No","No","Internal"]
[null,null,null,null,6792,"94_Mon Nov 11 2019 18:31:37 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All the ER ovbd v/v has no stencilling for identification, same to be stencilled","Documentation","Cert. & Docu.","Equipment Related","","","","","Engine staff to stencile","2019-03-30","","Completed","2019-03-12","No","No","No","Internal"]
[null,null,null,null,6795,"94_Mon Nov 11 2019 18:37:39 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","On funnel 1 DG welding support bracket broken, same to be rewelded. Attach photo","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To weld by engine fitter","2019-04-30","","Completed","2019-03-21","No","No","No","Internal"]
[null,null,null,null,6796,"94_Mon Nov 11 2019 18:39:30 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Many rubber supports for tensioning bolts of exhaust pipe have got hardened & bronken. To order the rubber supports, 4 in no. tensioning rods are broken, same to be rewelded","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To Raise RO/Renewed tensioning bolts and rubber supports","2019-03-30","","Completed","2019-03-27","No","No","No","Internal"]
[null,null,null,null,6800,"94_Mon Nov 11 2019 18:48:06 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel platform boiler/EGE outlet bellow leaking, also some DG bellows leaking, same to be opened during port stay & check for leakages, order the bellows accordingly","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To check and if found leaking to raise RO of same. Retightened loose bolts and nuts.","2019-03-27","","Completed","2019-04-18","No","No","No","Internal"]
[null,null,null,null,6801,"94_Wed Dec 11 2019 07:55:26 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Ship Staff","Ship Staff Insp.","No.3 DG CW high temp sensor wire broken, new temp switch to order & replace","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","To order new temp switch, rectify broken wire","2019-03-14","Kala190074","Completed","2019-04-18","No","No","No","Internal"]
[null,null,null,null,6839,"94_Wed Dec 11 2019 08:46:48 GMT+0000 (Coordinated Universal Time)","2019-02-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME viscotherm unit pressure gauge faulty, to replace. Again check all the gauges & thermometer & replace as required.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Spares received and to be installed","2019-09-30","Office RO","Completed","2019-06-30","No","No","No","Internal"]
[null,null,null,null,6775,"94_Mon Nov 11 2019 17:51:57 GMT+0000 (Coordinated Universal Time)","2019-02-28","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sewage plant air blower spares for motor & pump to order, urgently order for pressure gauge of required range & thread for air blower line","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To raise RO","2019-03-14","Kala190062","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6785,"94_Mon Nov 11 2019 18:14:41 GMT+0000 (Coordinated Universal Time)","2019-02-28","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME fuel pp leak off tank gives alarm when engine running on higher speed. Source of leakage to be identified after opening the tank in port, investigation report report to be forwarded to supt.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Engine staff to check and rectify","2019-03-30","","Completed","2019-03-10","No","No","No","Internal"]
[null,null,null,null,6797,"94_Mon Nov 11 2019 18:41:58 GMT+0000 (Coordinated Universal Time)","2019-02-28","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bilge tank has heavy traces of fuel oil on top, oil to be skimmed & absorbent pad to be laid on top of the tank. Most importantly the source of the oil traces needs to be traced & rectified. Investigation report to be forwarded to supt.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","To open up and remove traces of oil","2019-03-31","","Completed","2019-04-07","No","No","No","Internal"]
[null,null,null,null,6799,"94_Mon Nov 11 2019 18:46:13 GMT+0000 (Coordinated Universal Time)","2019-02-28","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME lube oil servo auto backwash filter is used in conjunction with bypass filter as candle filters get chocked when only on auto backwash filter. Auto backwash filter operation, its solenoid v/vs to be check for its correct operation. Investigation report to be forwarded to supt & spares to be ordered as required","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To be checked for proper operation","2019-03-15","","Completed","2019-04-12","No","No","No","Internal"]
[null,null,null,null,6778,"94_Mon Nov 11 2019 17:58:35 GMT+0000 (Coordinated Universal Time)","2019-03-06","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MSDS for paints & chemicals are old edition to renew with new edition","Documentation","Cert. & Docu.","Equipment Related","","","","","MSDS Renewed with new edition","2019-03-06","","Completed","2019-03-06","No","No","No","Internal"]
[null,null,null,null,6779,"94_Mon Nov 11 2019 18:00:28 GMT+0000 (Coordinated Universal Time)","2019-03-06","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering room entrance door  rubber seal gasket damaged, to renew","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Rubber seal gasket renewed","2019-03-09","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6780,"94_Mon Nov 11 2019 18:02:53 GMT+0000 (Coordinated Universal Time)","2019-03-06","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Missing IMO symbols for fire hoses, embarkation level, embarkation etc. to be renew with new as required, raise RO if required.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","IMO symbols renewed ","2019-03-06","","Completed","2019-03-06","No","No","No","Internal"]
[null,null,null,null,6781,"94_Mon Nov 11 2019 18:05:50 GMT+0000 (Coordinated Universal Time)","2019-03-06","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","On board Complaint box/suggestion box to be fabricated in Crew smoke room as part of MLC survey.","Miscellaneous","MLC Related","Equipment Related","","","","","Fabricate On Board Complaint/Suggestion box in crew smoke room  as part of MLC","2019-03-09","","Completed","2019-03-09","No","No","No","Internal"]
[null,null,null,null,6782,"94_Mon Nov 11 2019 18:08:25 GMT+0000 (Coordinated Universal Time)","2019-03-06","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All the deck machineries where greasing is required including LB davits etc., need to be marked with yellow paint for easy identification.","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","All the deck machineries where greasing is required including LB davits etc, Marked with yellow paint for easy identification.","2019-03-07","","Completed","2019-03-06","No","No","No","Internal"]
[null,null,null,null,6793,"94_Mon Nov 11 2019 18:33:45 GMT+0000 (Coordinated Universal Time)","2019-03-06","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both pilot ladders were supplied in yard & not in accordance with IMO resolution A.1024. To order new ladder  ","Deck - Machinery","General Appearance","Equipment Related","","","","","New pilot ladders supplied in accordance with IMO 1045 A(27)","2019-03-16","","Completed","2019-03-16","No","No","No","Internal"]
[null,null,null,null,6794,"94_Mon Nov 11 2019 18:35:39 GMT+0000 (Coordinated Universal Time)","2019-03-06","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Duct keel bottom platform has rust spots ,same to power tooled & painted","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Duct keel bottom platform has rust spots, De rusting, power tooled & painted.","2019-03-31","","Completed","2019-03-20","No","No","No","Internal"]
[null,null,null,null,6806,"94_Wed Dec 11 2019 08:21:39 GMT+0000 (Coordinated Universal Time)","2019-04-06","Defect","Ship Staff","Ship Staff Insp.","Defective Galvanic Isolator of Cargo Hold Smoke Detector","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Office Informed and RO Raised","2019-06-30","KALA190086","Completed","2019-06-21","No","No","No","Internal"]
[null,null,null,null,6802,"94_Wed Dec 11 2019 07:59:59 GMT+0000 (Coordinated Universal Time)","2019-04-24","Defect","Ship Staff","Ship Staff Insp.","Defective float switch for bilge alarms","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Replaced Float level switch","2019-04-24","","Completed","2019-04-24","No","No","No","Internal"]
[null,null,null,null,6804,"94_Wed Dec 11 2019 08:04:45 GMT+0000 (Coordinated Universal Time)","2019-04-28","Defect","Ship Staff","Ship Staff Insp.","Defective engine room blower  gauze wire screen.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To replace with new wire screen.","2019-05-31","KALA190105","Completed","2019-05-31","No","No","No","Internal"]
[null,null,null,null,null,"94_Thu Dec 12 2019 12:34:06 GMT+0000 (Coordinated Universal Time)","2019-05-12","Defect","Ship Staff","Ship Staff Insp.","Defective crewmess exhaust fan.","Accommodation,Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Inform office and raise RO","2020-07-30","KALA190254","Completed","2020-06-25","No",null,null,"Internal"]
[null,null,null,null,6809,"94_Tue Nov 12 2019 08:30:12 GMT+0000 (Coordinated Universal Time)","2019-05-31","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp."," No.1 DG CW high temp sensor wire broken, new temp switch to order & replace","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Checked broken wire and same problem persist. Report sent and awaiting instruction from maker regarding the defect/alarm.","2019-07-31","KALA190124","Completed","2019-07-28","No","No","No","Internal"]
[null,null,null,null,6810,"94_Wed Dec 11 2019 08:32:54 GMT+0000 (Coordinated Universal Time)","2019-07-15","Defect","Ship Staff","Ship Staff Insp.","Defective Valve Block","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","RO Raised","2019-08-15","KALA190073","Completed","2019-08-05","No","No","No","Internal"]
[null,null,null,null,6811,"94_Wed Dec 11 2019 08:35:48 GMT+0000 (Coordinated Universal Time)","2019-07-15","Defect","Ship Staff","Ship Staff Insp.","Defective Bonded Stator of Incinerator Dosing Pump","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","RO Raised","2019-08-15","Kala190137","Completed","2019-08-02","No","No","No","Internal"]
[null,null,null,null,6817,"94_Wed Dec 11 2019 08:51:31 GMT+0000 (Coordinated Universal Time)","2019-07-15","Defect","Ship Staff","Ship Staff Insp.","Sluggish movement of LT Actuator Control Valve","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","RO raised for o-ring and seals, spares received","2019-10-15","KALA190136","Completed","2019-10-10","No","No","No","Internal"]
[null,null,null,null,6812,"94_Wed Dec 11 2019 08:37:36 GMT+0000 (Coordinated Universal Time)","2019-07-25","Defect","Ship Staff","Ship Staff Insp.","Defective Impeller of Incinerator Circulating Pump","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","RO raised for Impeller and O-rings","2019-08-15","KALA190139","Completed","2019-08-05","No","No","No","Internal"]
[null,null,null,null,7735,"94_Fri Dec 06 2019 11:08:49 GMT+0000 (Coordinated Universal Time)","2019-07-30","Defect","PSC Insp.","PSC Inspection","Ceiling Light in Battery - not turned on","Miscellaneous","General Appearance","Equipment Related","","","Other",2,"Rectified light before departure","2019-07-30","","Completed","2019-07-30","No","No","No","External"]
[null,null,null,null,7736,"94_Fri Dec 06 2019 11:12:49 GMT+0000 (Coordinated Universal Time)","2019-07-30","Defect","PSC Insp.","PSC Inspection","Emergency light near liferaft (both sides) - not turned on","Miscellaneous","Emgcy. Systems","Equipment Related","","","Emergency Systems",2,"Rectified both emergency lights before departure","2019-07-30","","Completed","2019-07-30","No","No","No","External"]
[null,null,null,null,6807,"94_Wed Dec 11 2019 08:25:36 GMT+0000 (Coordinated Universal Time)","2019-07-30","Defect","PSC Insp.","PSC Inspection","Ceiling light in Battery room- not turned on","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","Other","","Replaced immediately with new spare","2019-07-30","","Completed","2019-07-30","No","No","No","External"]
[null,null,null,null,6808,"94_Wed Dec 11 2019 08:27:50 GMT+0000 (Coordinated Universal Time)","2019-07-30","Defect","PSC Insp.","PSC Inspection","Emergency  light near life raft ,PS SS - Not turned on","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","","","Emergency Systems","","Replaced immediately with new spare","2019-07-30","","Completed","2019-07-30","No","No","No","External"]
[null,null,null,null,6738,"94_Tue Nov 12 2019 10:17:24 GMT+0000 (Coordinated Universal Time)","2019-08-15","Defect","Ship Staff","Ship Staff Insp.","Defective bridge wing thruster controller/ starboard SIDE","Navigation - Others","Navigation","Equipment Related","","","","","renewed with new spare","2019-11-15","KALA190143","Completed","2019-11-18","No","No","No","Internal","Based on VFF, the order is currently awaiting readiness.  Pls amend target date as same is already overdue."]
[null,null,null,null,6820,"94_Wed Dec 11 2019 10:01:39 GMT+0000 (Coordinated Universal Time)","2019-08-18","Defect","Ship Staff","Ship Staff Insp.","Defective safety interlock switch/ Door lock for incinerator","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Ro raised ","2019-10-30","KALA 190146","Completed","2019-10-17","No","No","No","Internal"]
[null,null,null,null,6818,"94_Wed Dec 11 2019 10:13:58 GMT+0000 (Coordinated Universal Time)","2019-08-29","Defect","Ship Staff","Ship Staff Insp.","Defective control transformer for accom. Ladder port side","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","RO raised","2019-10-15","KALA 190154","Completed","2019-10-06","No","No","No","Internal"]
[null,null,null,null,6822,"94_Wed Dec 11 2019 10:06:29 GMT+0000 (Coordinated Universal Time)","2019-09-07","Defect","Ship Staff","Ship Staff Insp.","Defective life boat battery charger","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Replaced new battery charger","2019-10-30","KALA 190165","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,7737,"94_Wed Jun 12 2019 11:18:00 GMT+0000 (Coordinated Universal Time)","2019-09-09","Defect","PSC Insp.","PSC Inspection","Fireman's outfit in bosun store - Firemans cloth was missing ( crew forgot bring back after last fire fighting drill)","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","Fire safety",2,"Return back firemans cloth at fwd bosun store before departure.","2019-09-09","","Completed","2019-09-09","No","No","No","External"]
[null,null,null,null,7738,"94_Wed Jun 12 2019 11:21:28 GMT+0000 (Coordinated Universal Time)","2019-09-09","Defect","PSC Insp.","PSC Inspection","Copy of DMLC part I & II - Not posted at conspicuous place\t","Documentation","Cert. & Docu.","Equipment Related","","","Certificates & Documentation",2,"Posted DMLC part I & II at messroom alleyway before departure","2019-09-09","","Completed","2019-09-09","No","No","No","External"]
[null,null,null,null,7739,"94_Wed Jun 12 2019 11:25:00 GMT+0000 (Coordinated Universal Time)","2019-09-09","Defect","PSC Insp.","PSC Inspection","Accumulator launching appliance for R/B and L/R - not ready to use due to no pressure","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","Life saving appliances",2,"Pressure was increase and rectified before departure.","2019-09-09","","Completed","2019-09-09","No","No","No","External"]
[null,null,null,null,6741,"94_Wed Dec 11 2019 12:18:49 GMT+0000 (Coordinated Universal Time)","2019-09-11","Defect","Ship Staff","Ship Staff Insp.","Hfo purifier no.1 defective water valve block.","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","renewed with new spare recieved ","2019-11-15","KALA 190160","Completed","2019-11-21","No","No","No","Internal","Based on VFF, the order was supplied on board @ Pusan on 14/11/2019. Pls revert with updated status for replacement of the water valve block. Pls amend target date as same is already overdue."]
[null,null,null,null,6739,"94_Wed Dec 11 2019 12:13:44 GMT+0000 (Coordinated Universal Time)","2019-09-13","Defect","Ship Staff","Ship Staff Insp.","Wasted  anode of low and high sea chest","Hull & Tanks","General Appearance","Equipment Related","","","","","RO raised","2019-12-31","KALA 190175","Completed","2019-12-17","No","No","No","Internal","Based on VFF, order is awaiting readiness. We recommend that the target date be revised as it is now showing as overdue."]
[null,null,null,null,6740,"94_Wed Dec 11 2019 12:16:14 GMT+0000 (Coordinated Universal Time)","2019-09-13","Defect","Ship Staff","Ship Staff Insp.","Defective  engine room  crane limit switch","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","renew with new spare tested found working satisfactory","2019-10-30","KALA 190174","Completed","2019-11-17","No","No","No","Internal","Despite difference in design, is the new limit switch servicing it's purpose? If yes, you should consider closing out this defect."]
[null,null,null,null,6819,"94_Wed Dec 11 2019 09:59:22 GMT+0000 (Coordinated Universal Time)","2019-09-13","Defect","Ship Staff","Ship Staff Insp."," Rescue boat davit defective shut-off valve.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","RO raised","2019-10-15","KALA 190171","Completed","2019-10-14","No","No","No","Internal"]
[null,null,null,null,9288,"94_23/12/2019 12:23:22 PM","2019-09-14","Defect","Ship Staff","Ship Staff Insp.","Clock not synchronize on Bridge engine movement order","Navigation - Others","Communication","Equipment Related","","","","","Immediately synchronized clock at bridge engine movement to local time and utc.","2019-09-14","","Completed","2019-09-14","No","No","No","Internal"]
[null,null,null,null,6743,"94_Wed Dec 11 2019 12:26:57 GMT+0000 (Coordinated Universal Time)","2019-09-16","Defect","Ship Staff","Ship Staff Insp.","7pcs Ballast tank Sensors to be renewed.","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","received spares & Closed the defect","2019-12-31","KALA190182","Completed","2020-01-15","No","No","No","Internal",""]
[null,null,null,null,null,"94_Wed Dec 11 2019 12:24:05 GMT+0000 (Coordinated Universal Time)","2019-09-30","Defect","Ship Staff","Ship Staff Insp.","Bunkering davit port and stbd hard to turn","Deck - Machinery","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","we will renew the bearing once the weather condition clear/bearing have been received","2020-01-31","KALA190193","Completed","2019-12-25","No",null,null,"Internal"]
[null,null,null,null,6746,"94_Wed Dec 11 2019 12:36:30 GMT+0000 (Coordinated Universal Time)","2019-10-03","Defect","Ship Staff","Ship Staff Insp.","Non working davit(bunker davit Port & stbd)","Deck - Machinery","General Appearance","Equipment Related","","","","","same item previous report  raw 18","2019-12-31","KALA190193","Completed","2019-12-25","No","No","No","Internal","Based on VFF, said RO is currently in the procesing stage. Recommend that you amend the target date as the current date is already overdue."]
[null,null,null,null,6736,"94_Wed Dec 11 2019 12:38:47 GMT+0000 (Coordinated Universal Time)","2019-10-06","Defect","Ship Staff","Ship Staff Insp.","Defective FCM front module","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Replaced defective FCM front module of AELO purifier","2019-12-31","KALA190194","Completed","2019-12-19","No","No","No","Internal","Based on VFF, said RO is still in the processing stage.\nPls amend the target date as the current date is already overdue."]
[null,null,null,null,6744,"94_Wed Dec 11 2019 12:31:08 GMT+0000 (Coordinated Universal Time)","2019-10-09","Defect","Ship Staff","Ship Staff Insp.","Defective pressure gauge","Miscellaneous","General Appearance","Equipment Related","","","","","renewed with new spare","2019-12-31","KALA190198","Completed","2019-12-18","No","No","No","Internal","Based on VFF, the new presure gauge ws supplied on board on 14/11/2019 @ Pusan. Pls update status for replacement of the defective gauge as the target date is already overdue."]
[null,null,null,null,6752,"94_Wed Dec 11 2019 12:46:42 GMT+0000 (Coordinated Universal Time)","2019-10-10","Defect","Ship Staff","Ship Staff Insp.","BALLAST COMPUTER AT SHIP'S OFFICE MALFUNCTION/NO POWER","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Replaced defective berg computer on cargo office","2019-12-31","OFFICE PO","Completed","2019-12-18","No","No","No","Internal","Understand from Tech. Supt. Aneet that the replacement unit is ready & will be supplied on board in due time. Recommend to amend the target date since this is already overdue."]
[null,null,null,null,6821,"94_Wed Dec 11 2019 10:04:22 GMT+0000 (Coordinated Universal Time)","2019-10-10","Defect","Ship Staff","Ship Staff Insp.","Gyro failure alarm","Elect. Mach. & Equip.","Navigation","Equipment Related","","","","","Service technician will attend","2019-11-15","KALA195037","Completed","2019-10-17","No","No","No","Internal"]
[null,null,null,null,6823,"94_Wed Dec 11 2019 10:09:05 GMT+0000 (Coordinated Universal Time)","2019-10-10","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Replaced damage lighting fixture at A-deck","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Replaced lighting fixture","2019-11-15","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,6824,"94_Wed Dec 11 2019 10:11:34 GMT+0000 (Coordinated Universal Time)","2019-10-10","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","To repair PS crane limit switch not working","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Limit switch operational. Problem in the electrical connection.","2019-11-15","KALA190201","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,6826,"94_Wed Dec 11 2019 10:15:49 GMT+0000 (Coordinated Universal Time)","2019-10-10","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Remove/hide LAN and sockets in A-deck","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Removed cables","2019-11-15","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,6827,"94_Wed Dec 11 2019 10:17:55 GMT+0000 (Coordinated Universal Time)","2019-10-10","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Repair bao of hoisting in PS crane","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Renewed limit switch and overhaul bao","2019-11-15","","Completed","2019-10-25","No","No","No","Internal"]
[null,null,null,null,null,"94_Wed Dec 11 2019 12:44:07 GMT+0000 (Coordinated Universal Time)","2019-10-10","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port side blower vent flap closure limit switch to replace with new.","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","RENEW WITH NEW SPARE","2020-02-15","KALA190201","Completed","2020-01-31","No",null,null,"Internal"]
[null,null,null,null,6745,"94_Wed Dec 11 2019 12:33:36 GMT+0000 (Coordinated Universal Time)","2019-10-14","Defect","Ship Staff","Ship Staff Insp.","Defective solenoid valve","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","renewed with new spare","2019-11-15","KALA190204","Completed","2019-11-19","No","No","No","Internal","Based on VFF, this order was supplied on board on 14/11/2019 @ Pusan.  Pls revert with update on status for replacement of the defective solenoid valve. If require, pls amend target date as this is already overdue."]
[null,null,null,null,6825,"94_Wed Dec 11 2019 10:13:48 GMT+0000 (Coordinated Universal Time)","2019-10-14","Defect","Ship Staff","Ship Staff Insp.","Replaced damage lighting fixture at ships name","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Replaced lighting fixture","2019-11-15","","Completed","2019-10-25","No","No","No","Internal"]
[null,null,null,null,6747,"94_Wed Dec 11 2019 10:47:58 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Wilden pp kept in port side duct keel to be flushed & clean & keep in steering flat ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Wilden pump flushed & clean & keep in steering flat. ","2019-10-24","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,6748,"94_Wed Dec 11 2019 10:50:56 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Crane/davit hook missing for life raft davit, all small davits, same to fabricate","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Fabricated missing latch forhooks at crane davit, life raft davit, all small davits.","2019-10-28","","Completed","2019-10-28","No","No","No","Internal"]
[null,null,null,null,6750,"94_Tue Nov 12 2019 10:56:53 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bunker tank  high level alarm panel portside buzzer fused & STBD side all light glowing ,to rectify prior USCG inspection","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Checked electrical connections","2019-10-28","","Completed","2019-10-28","No","No","No","Internal"]
[null,null,null,null,6828,"94_Wed Dec 11 2019 10:20:07 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NOX file records for ALL DG & ME to be updated.","Documentation","Cert. & Docu.","Equipment Related","","","","","NOX files updated","2019-10-24","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,6829,"94_Wed Dec 11 2019 10:22:30 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel flap mainly STBD side has slight gap, Not 100% close, to make it free to close fully","E/R - Aux. Mach.","Structural Condn. / WT integrity ","Equipment Related","","","","","Fixed and adjusted funnel flap","2019-10-25","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,6830,"94_Wed Dec 11 2019 10:25:29 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Marpol sample for last 1 year to be kept in chronological order.","Miscellaneous","MARPOL Related","Equipment Related","","","","","Marpol sample last 1 year separetely keep","2019-10-24","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,6831,"94_Wed Dec 11 2019 10:27:47 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bridge PC to activate for navtracker & update the ENPs on it as well","Navigation - Others","Navigation","Equipment Related","","","","","install and activate navtracker at Bridge PC","2019-11-21","","Completed","2019-10-21","No","No","No","Internal"]
[null,null,null,null,6832,"94_Wed Dec 11 2019 10:30:21 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","New washing machine to be fitted in laundry","Accommodation","MLC Related","Equipment Related","","","","","Washing machine installed at Laundry room","2019-10-26","","Completed","2019-10-26","No","No","No","Internal"]
[null,null,null,null,6833,"94_Wed Dec 11 2019 10:32:58 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LT cooler auto electrical operating unit to fit back & check the system.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Fitted back & checked LT cooler auto electrical operating unit","2019-10-26","","Completed","2019-10-22","No","No","No","Internal"]
[null,null,null,null,6834,"94_Wed Dec 11 2019 10:35:27 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","One of the drain in galley is chocked ,same to be cleared ","Accommodation","General Appearance","Equipment Related","","","","","Unblocked and decloged galley drain","2019-10-28","","Completed","2019-10-28","No","No","No","Internal"]
[null,null,null,null,6835,"94_Wed Dec 11 2019 10:37:56 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Suez cabin to be cleared of garbage & galley materials, toilet is in shabby condition, to be arranged & light changed.","Accommodation","General Appearance","Equipment Related","","","","","Organize and cleaned Suez cabin, transfer some stores to cabin locker","2019-10-26","","Completed","2019-10-26","No","No","No","Internal"]
[null,null,null,null,6837,"94_Wed Dec 11 2019 10:43:09 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","EAL grease to be applied on the rudder carrier ,Lifeboat davit wire, Life raft wires & aft gangway wires","Miscellaneous","General Appearance","Equipment Related","","","","","Applied EAL grease on rudder carrier, lifeboat, rescue boat/liferaft, gangway wirtes.","2019-10-26","","Completed","2019-10-26","No","No","No","Internal"]
[null,null,null,null,6838,"94_Wed Dec 11 2019 10:45:29 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","BDN for 3 years i.e. till Nov16 carried out ,should be available ","Documentation","Cert. & Docu.","Equipment Related","","","","","BDN for the last 3 years till Nov'16 filed.","2019-10-24","","Completed","2019-10-24","No","No","No","Internal"]
[null,null,null,null,null,"94_Wed Dec 11 2019 12:52:43 GMT+0000 (Coordinated Universal Time)","2019-10-21","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aphoulstry of many cabin not in good condition ,material to order & rectify, damaged shower mixer to order ,also missing toilet flush button to order & replace","Accommodation","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","COMPLETED","2020-02-15","KALA190223","Completed","2020-07-03","No",null,null,"Internal"]
[null,null,null,null,null,"94_17/12/2019 3:36:40 PM","2019-10-21","Defect","Ship Staff","Suptd. Insp.","WIPER TIMEOUT ALARM IN BALLAST NO.1 SYSTEM TO BE CLEANED AND RECTIFIED","E/R - Aux. Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","INSTALLED NEW MAGNET FOR BWT NO. 1 AND O-RINGS. TESTED BALLAST AND DE-BALLASTING IN GOOD CONDITION.","2020-03-31","KALA200025","Completed","2020-03-12","No",null,null,"Internal"]
[null,null,null,null,6749,"94_Wed Dec 11 2019 10:53:44 GMT+0000 (Coordinated Universal Time)","2019-10-22","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency bulb fitting near L/B deck locking bolt stud, broken to be rectified.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Fabricated  locking bolt stud for Emergency bulb ","2019-10-25","","Completed","2019-10-25","No","No","No","Internal"]
[null,null,null,null,6836,"94_Wed Dec 11 2019 10:40:20 GMT+0000 (Coordinated Universal Time)","2019-10-22","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port side Vent head rusted & damaged, need to Refabricate.","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Renew port side vent box","2019-10-26","","Completed","2019-10-25","No","No","No","Internal"]
[null,null,null,null,7740,"94_Fri Dec 06 2019 11:32:53 GMT+0000 (Coordinated Universal Time)","2019-10-28","Defect","PSC Insp.","PSC Inspection","Auxiliary machinery spaces which do not contain machinery having a pressure lubrication system and where storage of combustibles is prohibited, such as; steering gear room. Found bunker fuel samples in the emergency steering space. Samples were moved to forward paint locker.","Miscellaneous","MARPOL Related","Equipment Related","","","Dangerous Goods",10,"All bunker samples were move to fwd paint locker before departure.","2019-10-28","","Completed","2019-10-28","No","No","No","External"]
[null,null,null,null,7741,"94_Wed Jun 12 2019 11:41:54 GMT+0000 (Coordinated Universal Time)","2019-10-28","Defect","PSC Insp.","PSC Inspection","Ventilation ducts shall be of stell or equivalent material. Found a section in the emergency steering space that is corroded through on the ventilation ducts","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related","","","Structural condition",10,"The corroded section of ventilation duct was repaired by fitting/welding with 2mm sheet metal and rectified before departure.","2019-11-28","","Completed","2019-10-30","No","No","No","External"]
[null,null,null,null,6753,"94_Wed Dec 11 2019 12:48:53 GMT+0000 (Coordinated Universal Time)","2019-10-30","Defect","Ship Staff","Ship Staff Insp.","BWTS NO. 1 COOLING SOLENOID VALVE NOT FUNCTIONING WELL","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","","","","","Not closing nor opening then cleaned solenoid valve. After cleaning, it takes time to close the valve causing it to fail first. To replace solenoid valve./renew with new spare ","2019-11-30","KALA190218","Completed","2019-11-18","No","No","No","Internal","Based on VFF, this order was supplied on board on 14/11/2019 @ Pusan. Pls advice when you plan to arrange replacement of same."]
[null,null,null,null,null,"94_Wed Dec 11 2019 12:58:40 GMT+0000 (Coordinated Universal Time)","2019-11-01","Defect","Ship Staff","Ship Staff Insp.","Defective PD controller","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","To replaced defective PD controller/ RO raise KALA200024 kindly approve at your side","2020-03-31","KALA200024","Completed","2020-03-15","No",null,null,"Internal"]
[null,null,null,null,null,"94_Wed Dec 11 2019 12:54:49 GMT+0000 (Coordinated Universal Time)","2019-11-02","Defect","Ship Staff","Ship Staff Insp.","Galley oven not working due to burnt electric parts","Elect. Mach. & Equip.","MLC Related","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace damage components WITH NEW SPARE","2020-01-31","KALA190227","Completed","2020-01-30","No",null,null,"Internal"]
[null,null,null,null,null,"94_Wed Dec 11 2019 12:56:45 GMT+0000 (Coordinated Universal Time)","2019-11-02","Defect","Ship Staff","Ship Staff Insp.","Corroded lighting fixtures around accommodation area","Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Only 3 remaining lighting fixtures to be installed at the moment. Only 3 spares lighting fixture remaining. 9 out of 12 lighting fixtures already installed. ","2020-02-29","KALA190213,KALA190214,  KALA190209","Completed","2020-02-25","No",null,null,"Internal"]
[null,null,null,null,7732,"94_Sun Dec 01 2019 05:06:16 GMT+0000 (Coordinated Universal Time)","2019-11-13","Defect","Ship Staff","Ship Staff Insp.","Defective water boiler in galley equipment","Accommodation","Crew Management","Equipment Related","","","","","request to renew with boiler catle","2019-12-31","KALA190231","Completed","2020-01-15","No","No","No","Internal","to change with big portable cattle"]
[null,null,null,null,7734,"94_Thu Dec 12 2019 12:36:21 GMT+0000 (Coordinated Universal Time)","2019-12-08","Critical Equipment,Defect","Ship Staff","Ship Staff Insp.","Damage throttle cable astern and ahead of rescue boat","Critical Equip.","Emgcy. Systems","Equipment Related","","","","","Raise RO","2019-12-31","KALA190255","Completed","2019-12-21","No","No","No","Internal"]
[null,null,null,null,null,"94_30/01/2020 9:16:51 AM","2019-12-23","Breakdown,Defect","Ship Staff","Ship Staff Insp.","SLUDGE PUMP NOT WORKING","E/R - Pumps","MARPOL Related","Equipment Related",null,null,"Not Applicable","Not Applicable","TO REPLACE ROTOR AND STATOR","2020-02-15","KALA190256","Completed","2020-01-31","No",null,null,"Internal"]
[null,null,null,null,null,"94_25/02/2020 8:55:28 AM","2020-01-01","Defect","Ship Staff","Ship Staff Insp.","To replace LED and corroded  lighting fixtures around accommodation from A- deck to bridge.\t","Accommodation","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","RO raised.","2020-04-30","KALA200009","Completed","2020-04-21","No",null,null,"Internal"]
[null,null,null,null,null,"94_30/01/2020 9:28:10 AM","2020-01-02","Defect","Ship Staff","Ship Staff Insp.","DEFECTIVE LIMIT SWITCH OF SB MIDSHIP LADDER","Deck - Machinery","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","TO REPLACE DEFECTIVE LIMIT SWITCH","2020-02-15","KALA190201","Completed","2020-02-12","No",null,null,"Internal"]
[null,null,null,null,null,"94_30/01/2020 9:25:40 AM","2020-01-02","Breakdown,Defect","Ship Staff","Ship Staff Insp.","CARGO HOLD NO. 14 3GS6 VENTILATION FAN MOTOR BURNT","Deck - Machinery","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","INFORMED OFFICE, RAISE RO AND TO REPLACE BURNT MOTOR","2020-05-15","KALA200022","Completed","2020-05-02","No",null,null,"Internal"]
[null,null,null,null,null,"94_30/01/2020 9:32:58 AM","2020-01-05","Critical Equipment","Ship Staff","Ship Staff Insp.","DEFECTIVE BATTERY CHARGER OF RESCUE BOAT","Critical Equip.","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","REPLACE DEFECTIVE BATTERY CHARGER WITH NEW SPARE","2020-03-15","KALA200015","Completed","2020-03-03","No",null,null,"Internal"]
[null,null,null,null,null,"94_30/01/2020 9:30:52 AM","2020-01-05","Defect","Ship Staff","Ship Staff Insp.","DEFECTIVE BALLAST SENSORS IN NO. 4 DWB TK P AND NO. 3 SWB TK P","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","TO REPLACE DEFECTIVE SENSOR","2020-04-30","KALA200014","Completed","2020-05-15","No",null,null,"Internal"]
[null,null,null,null,null,"94_02/07/2020 5:23:31 AM","2020-01-07","Defect","Ship Staff","Ship Staff Insp.","Defective DOL starter of paint room exhaust fan.","Deck - Machinery","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","replace new DOL starter switch","2020-08-31","KALA200130","Completed","2020-07-31","No",null,null,"Internal"]
[null,null,null,null,null,"94_30/01/2020 9:37:51 AM","2020-01-09","Breakdown,Non Conformity","Ship Staff","Ship Staff Insp.","LEAKING INTERNATIONAL SHORE CONNECTION FOR FIRE LINE","Deck - Pipe / Fittings","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","renew with new spare","2020-02-15","KALA200023","Completed","2020-01-30","No",null,null,"Internal"]
[null,null,null,null,null,"94_30/01/2020 9:35:34 AM","2020-01-09","Non Conformity","Ship Staff","Ship Staff Insp.","BUNKER STATION PORT & STBD VALVE & PRESSURE GAUGE TO BE RENEW WITH NEW SPARE DUE TO CORRODED & BLURRED GAUGE","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","fabricate reducer for new valve and REPLACE pressure gauges with new spare","2020-02-29",null,"Completed","2020-02-19","No",null,null,"Internal"]
[null,null,null,null,null,"94_30/01/2020 9:22:25 AM","2020-01-29","Breakdown","Ship Staff","Ship Staff Insp.","fire line / broken stop valve of paint store springkler due to bad weather","LSA / FFA","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","replace with new spare globe valve","2020-03-15"," KALA200041","Completed","2020-03-03","No",null,null,"Internal"]
[null,null,null,null,null,"94_31/01/2020 4:03:38 PM","2020-01-31","Defect","Ship Staff","Ship Staff Insp.","Defective V-belt of galley aircon\t","Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace defective V-belt","2020-07-30","KALA200044","Completed","2020-06-22","No",null,null,"Internal"]
[null,null,null,null,null,"94_17/02/2020 6:38:20 AM","2020-02-12","Breakdown","Ship Staff","Ship Staff Insp.","leakinglub oil priming pump of Aux no. 2 generator due to rubber tear on shaft seal","E/R - Aux. Engine,E/R - Pumps","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","renew spare and replace WITH NEW ONE","2020-03-30","R.O. KALA200057","Completed","2020-03-03","No",null,null,"Internal"]
[null,null,null,null,null,"94_17/02/2020 6:46:58 AM","2020-02-13","Breakdown","Ship Staff","Ship Staff Insp.","RPM PICK UP FOR dOCTOR AUX NO. 2 NOT WORKING","E/R - Aux. Engine","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","ORDER NEW SPARE AND REPLACE WITH NEW SPARE","2020-03-30","R.O. KALA200058","Completed","2020-03-03","No",null,null,"Internal"]
[null,null,null,null,null,"94_17/02/2020 6:43:45 AM","2020-02-13","Breakdown","Ship Staff","Ship Staff Insp.","EXHAUST TEMPERATURE OF OUTLET TURBO CAHRGER OF AUX NO. 3 NOT WORKING","E/R - Aux. Engine","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","ORDER NEW SPARE AND REPLACE WITH NEW SPARE","2020-04-30","R.O.KALA200059","Completed","2020-04-11","No",null,null,"Internal"]
[null,null,null,null,null,"94_25/02/2020 2:05:04 PM","2020-02-18","Defect","Ship Staff","Ship Staff Insp.","Defective PS freshwater sensor","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","RO raised","2020-04-30","KALA200061","Completed","2020-05-15","No",null,null,"Internal"]
[null,null,null,null,null,"94_25/02/2020 8:57:31 AM","2020-02-24","Defect","Ship Staff","Ship Staff Insp.","Damage v-belt of window wiper.","Navigation - Others","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace defective v-belt.","2020-07-30","KALA200064","Completed","2020-06-30","No",null,null,"Internal"]
[null,null,null,null,null,"94_20/04/2020 1:39:50 PM","2020-03-14","Defect","Ship Staff","Ship Staff Insp.","A/E NO.1 UNIT NO.1 PULL OUT CYL. HEAD @ PISTON FOR O/H","E/R - Aux. Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","A/E NO.1 UNIT NO.1 CHANGE RECOND. SPARE NEW V/V SEAT V/V SPINDLE EXH.INTAKE NEW PISTON @ PISTON RING CONNT ROD BOLLT @ CRANKPIN BOLT.CYL. HEAD GASKET C.W CONNECTOR RUUBER PUST ROD.","2020-03-20",null,"Completed","2020-03-14","No",null,null,"Internal"]
[null,null,null,null,null,"94_15/03/2020 8:13:55 AM","2020-03-15","Defect","Ship Staff","Ship Staff Insp.","DEFECTIVE PS RPM INDICATOR ON BRIDGE WING","Navigation - Others","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","REPLACE DEFECTIVE RPM INDICATOR","2020-04-30","KALA200075","Completed","2020-05-15","No",null,null,"Internal"]
[null,null,null,null,null,"94_20/04/2020 1:51:03 PM","2020-03-24","Defect","Ship Staff","Ship Staff Insp.","A/E NO.1 UNIT NO.2 PULLOUT CYLINDER HEAD FOR O/H","E/R - Aux. Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","A/ENO.1 UNIT NO.2 CHANGE RECOND SPARE CYLINDER HEAD NEW STEM SEAL V/V NEW PISTON @ PISTON RING CONNECTING ROD BOLT@ CRANKPIN BOLT C.W CONNECTOR CYLINDER GASKET RUBBER PUST ROD INKE @EXH.GASKET","2020-03-30",null,"Completed","2020-03-24","No",null,null,"Internal"]
[null,null,null,null,null,"94_14/04/2020 9:27:49 AM","2020-04-14","Breakdown","Ship Staff","Ship Staff Insp.","Burn out electrical motor of Incinerator sludge circulating pump due to bearing wear","E/R - Pumps","MARPOL Related","Equipment Related",null,null,"Not Applicable","Not Applicable","To be replace with new spare office inform and order R.O. No. KALA200095","2020-05-30","KALA200095","Completed","2020-05-13","No",null,null,"Internal"]
[null,null,null,null,null,"94_22/06/2020 11:35:07 AM","2020-04-14","Defect","Ship Staff","Ship Staff Insp.","Defective lub oil pressure transmitter of AE no. 3","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Repalce defective transmitter","2020-05-30",null,"Completed","2020-05-22","No",null,null,"Internal"]
[null,null,null,null,null,"94_15/04/2020 4:48:37 PM","2020-04-15","Defect","Ship Staff","Ship Staff Insp.","main air compressor no.2 change suction valve dleviry valve.","E/R - Air Comp.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","change valve ","2020-04-30",null,"Completed","2020-04-15","No",null,null,"Internal"]
[null,null,null,null,null,"94_15/04/2020 4:56:47 PM","2020-04-15","Defect","Ship Staff","Ship Staff Insp.","main air comp.no.1 discharge unloader dimantle.","E/R - Air Comp.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","cleaning unloader","2020-04-30",null,"Completed","2020-04-15","No",null,null,"Internal"]
[null,null,null,null,null,"94_20/04/2020 5:49:42 AM","2020-04-18","Defect","Ship Staff","Ship Staff Insp.","DUE FOR O/H PISTON AND CYLINDER HEAD @ BEARING A/E NO. UNIT NO.3","E/R - Aux. Engine","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","CHANGE PISTON RING @ BEARING ","2020-04-30",null,"Completed","2020-04-18","No",null,null,"Internal"]
[null,null,null,null,null,"94_20/04/2020 5:56:58 AM","2020-04-20","Defect","Ship Staff","Ship Staff Insp.","CYLINDER HEAD DIMANTLE @ CLEANING A/E SPARE","E/R - Aux. Engine","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","A/E SPARE CLEANING LALLPING VALVE ANG CHANGE VALVE SEAT @ SPINDLE.","2020-04-30",null,"Completed","2020-04-20","No",null,null,"Internal"]
[null,null,null,null,null,"94_22/04/2020 4:45:04 AM","2020-04-21","Defect","Ship Staff","Ship Staff Insp.","A/E NO1 UNIT NO.4 PULL OUT CYL.HEAD @ PISTON","E/R - Aux. Engine","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","A/E NO.1 UNIT NO.4 CHANGE CYL.HEAD @ PISTON RING CRANKPIN BEARING CONNECTING ROD BOLT CRANKPIN BOLT.","2020-04-30",null,"Completed","2020-04-21","No",null,null,"Internal"]
[null,null,null,null,null,"94_23/04/2020 11:50:19 AM","2020-04-22","Defect","Ship Staff","Ship Staff Insp.","A/E SPARE CYLINDER HEAD CLEANING","E/R - Aux. Engine","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","A/E SPARE CYLINDER HEAD CHANGE EXH. V/V SPINDLE @ V/V SEAT @ INTAKE V/V SPINDLE.","2020-04-23",null,"Completed","2020-04-23","No",null,null,"Internal"]
[null,null,null,null,null,"94_26/04/2020 11:26:17 AM","2020-04-24","Defect","Ship Staff","Ship Staff Insp.","H.F.O PUR.NO.2 NOT WORKING  DUE TO THE BOWL SPEED LOW","E/R - Purifier","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","H.F.O PUR.O/H CLEANING USED INTERMIDATE KIT.","2020-04-25",null,"Completed","2020-04-25","No",null,null,"Internal"]
[null,null,null,null,null,"94_2020-04-30 1:32:22 AM","2020-04-24","Defect","Ship Staff","Ship Staff Insp.","CORRODED LIGHTING FIXTURES ","Accommodation","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","TO RAISED RO FOR LIGHTING FIXTURES","2020-07-20","KALA200112","Completed","2020-07-03","No",null,null,"Internal"]
[null,null,null,null,null,"94_22/06/2020 11:21:36 AM","2020-04-29","Defect","Ship Staff","Ship Staff Insp.","Defective sound telephone of ME local side. Replacement of headset on all sound telephones.","Elect. Mach. & Equip.","Communication","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace defective sound telephone and replace all headsets.","2020-06-30","KALA200110","Completed","2020-06-20","No",null,null,"Internal"]
[null,null,null,null,null,"94_06/05/2020 11:21:55 AM","2020-04-30","Defect","Ship Staff","Ship Staff Insp.","BWT no. 2 inlet valve takes time to open and close.\t","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace butterfly valve","2020-05-30","KALA200111","Completed","2020-05-14","No",null,null,"Internal"]
[null,null,null,null,null,"94_02/05/2020 12:28:50 PM","2020-05-02","Defect","Ship Staff","Ship Staff Insp.","PURIFIER NO.1 SPEED BOWL LOW","E/R - Purifier","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","PURIFIER NO.1 DISMANTLE AND CLEANING BOWL.PARTS","2020-05-03",null,"Completed","2020-05-02","No",null,null,"Internal"]
[null,null,null,null,null,"94_06/05/2020 11:17:56 AM","2020-05-04","Defect","Ship Staff","Ship Staff Insp.","BWT booster pump no. 1 mechanical seal leaking.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace mechanical seal","2020-05-15",null,"Completed","2020-05-06","No",null,null,"Internal"]
[null,null,null,null,null,"94_06/05/2020 11:19:33 AM","2020-05-04","Defect","Ship Staff","Ship Staff Insp.","BWT booster pump no. 2 mechanical seal leaking.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace mechanical seal","2020-05-30","KALA200118","Completed","2020-05-07","No",null,null,"Internal"]
[null,null,null,null,null,"94_14/05/2020 8:58:12 AM","2020-05-04","Critical Equipment","Ship Staff","Ship Staff Insp.","UNABLE TO START ENGINE IN BATTERY 2 DUE TO DEFECTIVE BATTERY\t","Critical Equip.","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","REPLACE DEFECTIVE BATTERY","2020-05-15","KALA200117","Completed","2020-05-14","No",null,null,"Internal"]
[null,null,null,null,null,"94_22/06/2020 11:03:43 AM","2020-05-13","Critical Equipment,Defect","Ship Staff","Ship Staff Insp.","Defective MCP floor ecr","Critical Equip.","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace manual call point.","2020-06-30","KALA205038","Completed","2020-06-16","No",null,null,"Internal"]
[null,null,null,null,null,"94_22/06/2020 11:26:57 AM","2020-05-15","Defect","Ship Staff","Ship Staff Insp.","Defective RADIO PC","Miscellaneous","Communication","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace radio PC","2020-06-30",null,"Completed","2020-06-17","No",null,null,"Internal"]
[null,null,null,null,null,"94_02/06/2020 5:26:52 AM","2020-05-30","Defect","Ship Staff","Ship Staff Insp.","CREW HOT WATER THERMOS DEFECTIVE","Miscellaneous","MLC Related","Equipment Related",null,null,"Not Applicable","Not Applicable","ORDER NEW SPARE","2020-07-30",null,"Completed","2020-06-16","No",null,null,"Internal"]
[null,null,null,null,null,"94_22/06/2020 11:09:19 AM","2020-06-04","Defect","Ship Staff","Ship Staff Insp.","Defective SW inlet pressure sensor","E/R - Aux. Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace defective pressure sensor","2020-06-30","KALA205020","Completed","2020-06-19","No",null,null,"Internal"]
[null,null,null,null,null,"94_22/06/2020 11:18:05 AM","2020-06-09","Defect","Ship Staff","Ship Staff Insp.","Damage v-belt of flu gas fan incinerator","E/R - Aux. Mach.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace defective v-belt","2020-06-09",null,"Completed","2020-06-09","No",null,null,"Internal"]
[null,null,null,null,null,"94_22/06/2020 11:29:59 AM","2020-06-11","Defect","Ship Staff","Ship Staff Insp.","Tripping of AHU fan motor. Loose tension of v-belt","Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace defective overload relay and change new v-belt","2020-06-11",null,"Completed","2020-06-11","No",null,null,"Internal"]
[null,null,null,null,null,"94_13/06/2020 4:24:09 PM","2020-06-13","Defect","Ship Staff","Ship Staff Insp.","Defective MCP on loop 9 poop deck","Critical Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Informed offiice","2020-06-30",null,"Completed","2020-06-18","No",null,null,"Internal"]
[null,null,null,null,null,"94_22/06/2020 11:24:00 AM","2020-06-19","Defect","Ship Staff","Ship Staff Insp.","Defective ballast sensor of No. 3B SWB TK (P)","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace defective sensor - Rcvd spare and renewed new sensor and confirmed back to normal reading thru berg monitor.","2020-10-30","KALA200124","Completed","2020-12-09","No",null,null,"Internal"]
[null,null,null,null,null,"94_23/06/2020 2:06:06 PM","2020-06-21","Defect","Ship Staff","Ship Staff Insp.","Defective pressure regulator of ventillation flaps","Critical Equip.","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace pressure regulator valve","2020-09-30","KALA200125","Completed","2020-09-20","No",null,null,"Internal"]
[null,null,null,null,null,"94_15/07/2020 2:46:22 PM","2020-07-13","Defect","Ship Staff","Ship Staff Insp.","NO.2 PURIFIER BIEARING WORM OUT@ FAN @ VERTICAL SHAFT","E/R - Purifier","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","REPLACE DEFECTIVE PARTS","2020-09-30","KALA200143","Completed","2020-09-17","No",null,null,"Internal"]
[null,null,null,null,null,"94_2020-07-15 1:34:31 PM","2020-07-14","Other","Ship Staff","Cargo Audit","Defective ballast sensor of No.3A SWBT (S)","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Cleaned sensor found in good order","2020-08-09",null,"Completed","2020-07-17","No",null,null,"Internal"]
[null,null,null,null,null,"94_20/07/2020 2:03:53 PM","2020-07-19","Defect","Ship Staff","Ship Staff Insp.","Replace defective VRLA battery of Captain's UPS.","Elect. Mach. & Equip.","Communication","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace VRLA battery","2020-08-30","KALA200146","Completed","2020-07-31","No",null,null,"Internal"]
[null,null,null,null,null,"94_2020-07-25 6:46:15 PM","2020-07-25","Defect","Ship Staff","Ship Staff Insp.","DEFECTIVE SWBT 4A PORT BALLAST WATER SENSOR","Miscellaneous","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","TO BE REPAIR OR REPLACE","2020-09-30",null,"Completed","2020-08-14","No",null,null,"Internal"]
[null,null,null,null,null,"94_29/07/2020 10:01:55 AM","2020-07-28","Defect,Non Conformity","Ship Staff","Ship Staff Insp.","Defective sewage blower.","E/R - Aux. Engine","MARPOL Related","Equipment Related",null,null,"Not Applicable","Not Applicable","RO raised and informed office. Replaced new sewage blower motor","2020-09-30","KALA200032","Completed","2020-09-21","No",null,null,"Internal"]
[null,null,null,null,null,"94_06/08/2020 6:48:22 AM","2020-08-01","Critical Equipment","Ship Staff","Ship Staff Insp.","Defective primer bulb of rescue boat.","Critical Equip.","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","RO raised. Replaced primer bulb.","2020-08-31","KALA200147","Completed","2020-09-20","No",null,null,"Internal"]
[null,null,null,null,null,"94_11/08/2020 6:46:41 AM","2020-08-11","Defect","Ship Staff","Ship Staff Insp.","Defective 4A DWB TK (P) ballast sensor.","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Cleaned sensor and pipe but still the same. Reading is full but in actual empty. To raise RO.-Received new spare ballast sensor and renewed after fixed it checked the reading and confirmed back to normal reading.","2020-10-30","KALA200151","Completed","2020-12-10","No",null,null,"Internal"]
[null,null,null,null,null,"94_31/08/2020 9:44:50 AM","2020-08-22","Defect","Ship Staff","Ship Staff Insp.","Defective explosion proof switch of oxygen/acetylen and battery room.","Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Replace defective switch.","2020-09-30","KALA200155","Completed","2020-09-21","No",null,null,"Internal"]
[null,null,null,null,null,"94_31/08/2020 9:38:17 AM","2020-08-22","Defect","Ship Staff","Ship Staff Insp.","Defective limit switch of accommodation ladder motor.","Deck - Machinery","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Replaced new limit switch  completed 28-Oct-2020","2020-10-30","KALA200154","Completed","2020-10-28","No",null,null,"Internal"]
[null,null,null,null,null,"94_31/08/2020 9:52:53 AM","2020-08-22","Defect","Ship Staff","Ship Staff Insp.","Defective CFW temperature switch of Aux engine no. 2.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Replaced defective CFW temp. switch of Aux engine no. 2 ( Completed 30-October -2020)","2020-10-30","KALA200157","Completed","2020-10-30","No",null,null,"Internal"]
[null,null,null,null,null,"94_15/09/2020 10:47:21 AM","2020-09-14","Defect","Ship Staff","Ship Staff Insp.","Defective SB FW tank sensor","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Cleaned sensor but still the same reading full. RO raised. - Received new sensor and replaced and observed reading FW tank STBD  back to normal reading   ","2020-12-10","KALA200151","Completed","2020-12-08","No",null,null,"Internal"]
[null,null,null,null,null,"94_15/09/2020 10:49:47 AM","2020-09-15","Defect","Ship Staff","Ship Staff Insp.","Damage navigational steering light","Navigation - Others","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","Temporary repair. RO raised. Rcvd spare and replaced new unit. Completed 26- October 2020)","2020-10-30","KALA200164","Completed","2020-10-26","No",null,null,"Internal"]
[null,null,null,null,null,"94_12/11/2020 11:21:28 AM","2020-10-11","Defect","Ship Staff","Ship Staff Insp.","Defective GPS antenna of AIS.","Navigation - DGPS / EPFS / AIS","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","Informed office and office will supply GPS antenna as per Sir Kamlesh mail.Received spare and installed new GPS Antenna and no alarm and await advise from Maker. And Cable will be defective.","2020-12-31","KALA205050","Completed","2020-09-12","No",null,null,"Internal"]
[null,null,null,null,null,"94_29/10/2020 1:58:49 PM","2020-10-24","Defect","Ship Staff","Ship Staff Insp.","Replace LED floodlight on SB pilot ladder and SB gangway ladder.","Elect. Mach. & Equip.","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace new LED floodlight. There is still light but need to replace due to less illumination and some damage diode lights.","2020-12-30","KALA200169","Completed","2020-12-13","No",null,null,"Internal"]
[null,null,null,null,null,"94_30/10/2020 8:38:24 AM","2020-10-26","Defect","Ship Staff","Ship Staff Insp.","Observe during testing BWT Solenoid Valve not working properly malfunction opening /closing the valve.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Replaced new Spare Solenoid valve( Completed 27 October 2020.","2020-10-28",null,"Completed","2020-10-27","No",null,null,"Internal"]
[null,null,null,null,null,"94_20/11/2020 7:43:33 AM","2020-11-03","Defect","Ship Staff","Ship Staff Insp.","HFO purifier no.2  Alarm lit on panel Bowl Speed Low/Alarm PT4 Feed back low.","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Awaiting Spare to supply ,Need to replace rectangular ring/ o-ring ,Recvd new spares and renewed o-rings/ seal rings.","2020-12-10","KALA200189","Completed","2020-12-07","No",null,null,"Internal"]
[null,null,null,null,null,"94_07/11/2020 8:40:08 AM","2020-11-06","Defect","Ship Staff","Ship Staff Insp.","Defective LAN switch of berg monitoring system.","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Recieved spares and  replaceD defective LAN switch. ( completed 07 December 2020.","2020-12-30",null,"Completed","2020-12-07","No",null,null,"Internal"]
[null,null,null,null,null,"94_19/11/2020 6:38:43 AM","2020-11-18","Defect","Ship Staff","Ship Staff Insp.","Damage lighting fixture on bridge area due to bad weather","Elect. Mach. & Equip.","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","Replaced damage lighting fixture","2020-12-31","KALA200175","Completed","2020-12-14","No",null,null,"Internal"]
[null,null,null,null,null,"94_20/11/2020 7:51:41 AM","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","DG no.2 observed during on service load ,Exh. gas cylinder unit no.2 dropped temperature outlet.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Stopped gen no.2 and investigated and found plunger /barrel defective.Renewed ready spare FO pump assembly (NEW SPare) After fixed the pump tested and observed in good order.(Noted Updated PAL -unplanned maintenance.)","2020-11-20",null,"Completed","2020-11-19","No",null,null,"Internal"]
[null,null,null,null,null,"94_11/20/2020 7:34:01 AM","2020-11-20","Defect","Ship Staff","Ship Staff Insp.","DG no.2 FW oulet of air cooler temp. gauge defective.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Replaced with spare temp. gauge ( 100 deg)","2020-11-21",null,"Completed","2020-11-20","No",null,null,"Internal"]
[null,null,null,null,null,"94_23/11/2020 10:39:16 AM","2020-11-23","Defect","Ship Staff","Ship Staff Insp.","Steering Gear no.1 motor ,Damaged Flexible Coupling Element Found borken parts","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Need to replace Spare flexible Coupling Element ,Raise Req, order KALA200208 Awaiting to supply.( Temporary repaired fabricate coupling  with hard rubber and fixed it then tested found working in good order.) New coupling supplied and renewed Steering gear motor no.1 & 2 with new rubber couplings ( completed 07 Dec 2020)","2020-12-10","KALA200208","Completed","2020-12-07","No",null,null,"Internal"]
[null,null,null,null,null,"94_26/11/2020 8:00:29 AM","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","During Testing of Lifting Appliances of Free fall lifeboat observed hydraulic hose leaking ","LSA / FFA","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","Replaced new spare haydraulic hose after fixed it tested found working in good order.","2020-11-25",null,"Completed","2020-11-25","No",null,null,"Internal"]
[null,null,null,null,null,"94_26/11/2020 8:07:57 AM","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","Observed STBD side FWD bilge well malfuction alarm ., and checked the unit found the float valve was found have seen tiny pin hole observed.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Repaired tiny pin hole and cleaned the rod and float valve and fixed it back and tested many time and observed working in good order.","2020-11-25",null,"Completed","2020-11-25","No",null,null,"Internal"]
[null,null,null,null,null,"94_02/12/2020 2:25:34 PM","2020-12-01","Critical Equipment","Ship Staff","Ship Staff Insp.","Recue boat engine having hard time to run due to electric starter motor malfunctioning.","Critical Equip.","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","To replace electric starter motor-Recvd starter motor at Yokoham Japan and renewed and tested found working back to normal ( completed 07-dec-2020)","2020-12-31","KALA200210","Completed","2020-12-07","No",null,null,"Internal"]
[null,null,null,null,null,"94_12/12/2020 9:37:23 AM","2020-12-12","Critical Equipment","Ship Staff","Ship Staff Insp.","Saturday check tested fire alarm at engine room /workshop and noticed workahop smoke detector not working.","Critical Equip.,LSA / FFA","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","Checked and cleaned the detector head and found the smoke detector head was busted / defective,Renewed with new spare detector head and tested found working back  in good order.","2020-12-13",null,"Completed","2020-12-12","No",null,null,"Internal"]
[null,null,null,null,null,"94_12/15/2020 3:36:25 PM","2020-12-14","Defect","Ship Staff","Ship Staff Insp.","Accom Aircond Compressor no.2 oil separator copper pipe leaking.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Rectified oil  leaking  copper pipe connector  of Accom Aircond compressor no.","2020-12-14",null,"Completed","2020-12-14","No",null,null,"Internal"]
[null,null,null,null,null,"94_29/12/2020 8:43:27 AM","2020-12-29","Observation","Ship Staff","Ship Staff Insp.","DG no.2 Governor broken plug connector (3-pins) ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Replaced with new recvd spare Plug connector weth 3-pins ","2020-12-29",null,"Completed","2020-12-29","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":12,"n_cols":2,"rows_kept":12,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["94","KALAMAZOO (26-12-2019)","94_1580180356824.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]