{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":6,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":108,"n_cols":28,"rows_kept":108,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","09-Dec-2020",null,null,"Ship Name","CHARM (09-12-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,14801,"108_Tue Nov 17 2020 11:07:47 GMT+0000","2020-10-30","Observation","Ship Staff","Ship Staff Insp.","All 4-engine room blower airline to remote closing flaps is corroded and need replacement.","Miscellaneous","Emgcy. Systems","Equipment Related","","","","","To renew defective lines","2020-12-30","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14815,"108_Tue Nov 17 2020 11:15:28 GMT+0000","2020-10-30","Observation","Ship Staff","Ship Staff Insp.","Ballast educator has large soft patch on the body","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","NEED TO ORDER NEW BALLAST EDUCTOR RO HAS BEEN RAISED","2020-12-30","CHAR200060","Not Started",null,"No","No","No","Internal","Pls  ORDER NEW BALLAST EDUCTOR"]
[null,null,null,null,14817,"108_Tue Nov 17 2020 11:16:56 GMT+0000","2020-10-30","Observation","Ship Staff","Ship Staff Insp.","No 1 FIRE and GS pump discharge line has 5 mm hole","E/R - Pipes/ valves & fittings","","","","","","","REPAIRED WITH SOFT PATCH","2020-12-30","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14848,"108_Wed Nov 18 2020 03:10:10 GMT+0000","2020-11-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering gear entrance from engine room lagging is damaged and need replacement","Miscellaneous","Eng. / Strg. Comp.","External Factors","","","","","LAGGING WILL BE ORDERED IN NEXT ENGINE STORES AND REPALCED ACCORDINGLY. ","2020-12-31","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14851,"108_Wed Nov 18 2020 03:15:45 GMT+0000","2020-11-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Incinerator is not operational All safeties are by passed","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","INCINERATOR IS MADE OPERATIONAL WITH FEW SAPES AVAILABLE ON BOARD. RO RAISED. ","2020-12-18","CHAR200058","Not Started",null,"No","No","No","Internal","Pls  do check and  list down all deficiency to make operational."]
[null,null,null,null,14853,"108_Wed Nov 18 2020 03:20:11 GMT+0000","2020-11-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main Engine FO supply Pump No1 and No 2 both are leaking from mechanical seal and need overhauling","E/R - Pumps","General Appearance","Equipment Related","","","","","SPARES ORDERED. ","2020-12-31","CHAR200020","Not Started",null,"No","No","No","Internal","Pls order spare parts if not available on board."]
[null,null,null,null,14860,"108_Wed Nov 18 2020 03:31:02 GMT+0000","2020-11-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Present control air drier is not effective, need to install new refrigerated control air drier with oil separators","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","NEW CONTROL AIR DRIER ORDERED UNDER PO CHAR200004. ","2020-12-31","CHAR200004","Not Started",null,"No","No","No","Internal","Pls order new control air dryer if required."]
[null,null,null,null,14863,"108_Wed Nov 18 2020 03:35:28 GMT+0000","2020-11-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main Engine LO back wash filter leaking from  spindle seal","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","NEED TO RENEW SEALS. SPARES ORDERED UNDER PO CHAR200019","2020-12-31","CHAR200019","Not Started",null,"No","No","No","Internal","Pls  check spare oil seal and order if not available on board."]
[null,null,null,null,14864,"108_Wed Nov 18 2020 03:37:02 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine Room ship side need cleaning and painting","Miscellaneous","General Appearance","External Factors","","","","","JOB IN PROGRESS. ","2020-12-31","","In progress",null,"No","No","No","Internal","Cosmetic maintenance"]
[null,null,null,null,14866,"108_Wed Nov 18 2020 03:40:06 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency escape door in bottom platform lagging are damaged and need repair","Miscellaneous","Eng. / Strg. Comp.","External Factors","","","","","LAGGING WILL BE ORDERED AT NEXT ENGINE STORES AND REPALCED ACCORDINGLY. ","2020-12-31","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14867,"108_Wed Nov 18 2020 03:41:56 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bilge wells need cleaning, chipping and need painting","Miscellaneous","General Appearance","Human Error","","","","","JOB PLANNED AND WILL  BE DONE ","2020-12-31","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14869,"108_Wed Nov 18 2020 03:48:05 GMT+0000","2020-11-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LT Coolers leaking from plates","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","ORDERED PLATES AND GASKETS. COOLER NEEDS TO BE OPENED AND CLEANED. JOB PLANNED. ","2020-12-31","CHAR200057","Not Started",null,"No","No","No","Internal","Pls order gasket  and repair seal kits"]
[null,null,null,null,14870,"108_Wed Nov 18 2020 03:51:15 GMT+0000","2020-11-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FWG condense /Evaporator required to be cleaned and inspect due to poor performance","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","CONDENCER AND EVOPARATOR CLEANED. STILL AWATING FOR MORE SPARES TO MAKE IT OPERATIONAL TO ITS FULL CAPACITY. ","2020-12-18","CHAR200023","Not Started",null,"No","No","No","Internal","Pls do as soon as possible."]
[null,null,null,null,14872,"108_Wed Nov 18 2020 03:57:32 GMT+0000","2020-11-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","M/E indicator cock body leaking, same to be renewed","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","SPARES ORDERED UNDER PO CHAR200030","2020-12-18","CHAR200030","Not Started",null,"No","No","No","Internal","Pls advise how many indicator valve are leaking and order spare  based on R.O.B"]
[null,null,null,null,14808,"108_Tue Nov 17 2020 11:11:39 GMT+0000","2020-11-01","Observation","Ship Staff","Ship Staff Insp.","Steering gear entrance from engine room lagging is damaged and need replacement","Miscellaneous","Safety / LSA / FFA","External Factors","","","","","LAGGING TO RENEW.","2020-12-30","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14818,"108_Tue Nov 17 2020 11:17:18 GMT+0000","2020-11-01","Observation","Ship Staff","Ship Staff Insp.","Sewage treatment plat is not operational, further investigation is needed. Presently plant is by passed","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","To identify defect & make plant operational","2020-11-30","CHAR200005","Not Started",null,"No","No","No","Internal","To identify defect & make plant operational"]
[null,null,null,null,14766,"108_Tue Nov 17 2020 10:46:05 GMT+0000","2020-11-03","Observation","Ship Staff","Ship Staff Insp.","Several antennae posts rusted/wasted on monkey island.","Navigation - Others","General Appearance","Equipment Related","","","","","Renew the wasted antenae posts","2020-12-15","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14770,"108_Tue Nov 17 2020 10:48:17 GMT+0000","2020-11-03","Observation","Ship Staff","Ship Staff Insp.","Natural vents around accommodation packing needs renewal, Channels rusted.","Accommodation","General Appearance","External Factors","","","","","De-rust channels and renew rubber packing","2020-11-30","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14772,"108_Tue Nov 17 2020 10:50:12 GMT+0000","2020-11-03","Observation","Ship Staff","Ship Staff Insp.","Ramps (Bridges over pipes) on deck are heavily rusted and wasted at places","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","Needs Ram Plate Renewal at various locations.","2020-12-31","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14761,"108_Tue Nov 17 2020 10:38:47 GMT+0000","2020-11-04","Observation","Ship Staff","Ship Staff Insp.","MINOR LEAKS FOUND ON MAIN ENGINE CRAK CASE DOORS","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","DOOR  TIGHTENED AS PER MAKER ADVISE.","2020-11-20","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14807,"108_Tue Nov 17 2020 11:10:25 GMT+0000","2020-11-04","Observation","Ship Staff","Ship Staff Insp.","Present control air drier is not effective, need to install new refrigerated control air drier with oil separators.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","HAVE ORDERED FOR NEW REF. TYPE CONTROL AIR DRIER.","2020-12-30",null,"Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14804,"108_Tue Nov 17 2020 11:09:04 GMT+0000","2020-11-05","Observation","Ship Staff","Ship Staff Insp.","All 3 AE are leaking between flywheel and engine casing.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","SPARES RECEIVED AND JOB IN PROGRESS. ","2020-12-30",null,"Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14799,"108_Tue Nov 17 2020 11:06:22 GMT+0000","2020-11-07","Observation","Ship Staff","Ship Staff Insp.","No 1 Cylinder oil storage tank spring loaded valve leaking from spindle","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","STORAGE TANK HAS OIL AND WILL NEED TO WAIT TILL THE TANK IS EMPTY","2020-12-30",null,"Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14776,"108_Tue Nov 17 2020 10:52:21 GMT+0000","2020-11-08","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No 1 Cargo hold Control block safety relief valve leaking, fittings corroded","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","TEMPORARAY REPAIR CARRIED OUT, NEW BLOCKS ORDERED.","2020-12-07","CHAR200013","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14796,"108_Tue Nov 17 2020 11:04:54 GMT+0000","2020-11-08","Observation","Ship Staff","Ship Staff Insp.","Many laggings in purifier room are soaked in oil. Laggings need renewal.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","WILL ORDER NEW LAGGINGS AT NEXT  ENGINE STORES.","2020-12-30",null,"Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14879,"108_Wed Nov 18 2020 04:13:16 GMT+0000","2020-11-10","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering gear rams no. 1, 2, 3 and 4 rams are leaking through  seal","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","NEED TO RENEW SEAL AT NEXT DD","2020-12-31",null,"Not Started",null,"Yes","No","No","Internal","Pls order spare  if required."]
[null,null,null,null,14810,"108_Tue Nov 17 2020 11:11:55 GMT+0000","2020-11-10","Observation","Ship Staff","Ship Staff Insp.","BILGE PUMP NEED OVERHAULING AS ITS NOT TAKING SUCTION","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","SPARES ORDERED AND WILL OVERHAUL ONCE SPARES ARE RECEIVED ON BOARD.","2020-12-30","CHAR200015","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14876,"108_Wed Nov 18 2020 04:05:14 GMT+0000","2020-11-11","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aux engine No. 1 , 2 & 3 required to be overhauled due to poor performance as  one AE not able to take sea load.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","SPARES ARE ORDERED. DECARB IS PLANNED  AFTER SUPPLYINF OF SPARES. CHAR200001","2020-12-31","CHAR200001","Not Started",null,"No","No","No","Internal","Pls plan and check all the necessary calibration tools to carry out the overhaul"]
[null,null,null,null,14877,"108_Wed Nov 18 2020 04:07:27 GMT+0000","2020-11-11","Critical Equipment","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency fire pump priming pump to be overhauled","E/R - Pumps","Emgcy. Systems","Equipment Related","","","","","SPARES ARE ORDERED. CHAR200002, CHAR200017","2020-11-30","CHAR200002 , CHAR200017","In progress",null,"No","No","No","Internal","PSC items_ Work in progress"]
[null,null,null,null,14878,"108_Wed Nov 18 2020 04:10:39 GMT+0000","2020-11-11","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both HFO purifier and No. 1 LO purifier was not working during vessel take over","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","HFO PURIFIERS MADE OPERATIONAL. LO PURIFIER SPARES ARE ORDERED. ","2020-12-31","CHAR200032","In progress",null,"No","No","No","Internal","Pls order spare parts if required"]
[null,null,null,null,14786,"108_Tue Nov 17 2020 10:58:33 GMT+0000","2020-11-12","Observation","Ship Staff","Ship Staff Insp.","Oil/water leaking from oil outlet valve of OWS.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","SPARES ORDERED UNDER RO CHAR200061","2020-12-30","CHAR200061","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14819,"108_Tue Nov 17 2020 11:21:49 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo hold # 5 stbd side outer packing wasted","Miscellaneous","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Damaged packing to be replaced","2020-12-15",null,"Not Started",null,"No","No","No","Internal","Hatch cover packing  to be order if not available on board."]
[null,null,null,null,14821,"108_Tue Nov 17 2020 11:23:02 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo hold # 5 (fwd) lower platform damaged","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","Damaged area to be repaired, hot work required.","2020-12-15","","Not Started",null,"No","No","No","Internal","To be cropped and renewed."]
[null,null,null,null,14823,"108_Tue Nov 17 2020 11:24:21 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hydraulic leak near hold no. 7 port side","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Temporary repair carried out, Pipe to be renewed","2020-12-15","","Not Started",null,"No","No","No","Internal","Pipe to be renewed"]
[null,null,null,null,14831,"108_Tue Nov 17 2020 11:28:46 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","3.\tAll fairleads frozen and covers wasted","Deck - Mooring Machinery","Mooring","External Factors","","","","","To overhaul fairleads & renew covers","2020-12-15","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14833,"108_Tue Nov 17 2020 11:29:46 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo holds hatch operation platforms as well as hydraulic control lever blocks for opening and closing are rusted","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","New Block on order for renewal","2020-12-15","CHAR200013- HATCH COVER HYDRAULICS.","Not Started",null,"No","No","No","Internal","Spot de-rusting and touch up required."]
[null,null,null,null,14834,"108_Tue Nov 17 2020 11:30:31 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mooring winches, windlass rusted, protection covers wasted, mooring winches brake bands rusted, liners thinned out","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","To de-rust, renew wasted covers.","2021-01-17","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14835,"108_Tue Nov 17 2020 11:31:06 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hatch cover trackway rusted","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","De-rusting and lubrication to be carried out","2020-12-15","","Not Started",null,"No","No","No","Internal","Spot de-rusting and touch up required."]
[null,null,null,null,14837,"108_Tue Nov 17 2020 11:31:59 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mooring winches platforms wasted","Miscellaneous","General Appearance","External Factors","","","","","To renew wasted sections","2020-12-30","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14838,"108_Tue Nov 17 2020 11:32:18 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hatch coamings, Observation platforms, chain guide bars (pipes) rusted and wasted","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Hot work required, Renewal of supports/pipes and chain guide bars","2021-02-15","","Not Started",null,"No","No","No","Internal","Spot-de-rusting / crop and renew"]
[null,null,null,null,14840,"108_Tue Nov 17 2020 11:33:29 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bilge level gauge protection cover/angle bar found wasted","E/R - Pipes/ valves & fittings","","","","","","","","2020-12-15","","Not Started",null,"No","No","No","Internal","To be cropped and renewed"]
[null,null,null,null,14841,"108_Tue Nov 17 2020 11:33:33 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CO2 room top edge plate corroded","Miscellaneous","General Appearance","External Factors","","","","","To de-rust and renew if wasted.","2020-12-22","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14842,"108_Tue Nov 17 2020 11:36:17 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","U-clamps, expansion joints for pipes on main deck rusted, hydraulic lines, fire line, airline, FW line rusted and in several locations","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","To de-rust/paint & renew wasted sections.","2021-02-12","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14777,"108_Tue Nov 17 2020 10:53:37 GMT+0000","2020-11-15","Observation","Ship Staff","Ship Staff Insp.","DO service tank spring loaded vale to sounding column is leaking from gland.","E/R - Pipes/ valves & fittings","","","","","","","CANNOT RECTIFY LEAK AS THE TANK  IS FULL OF DO.","2020-12-30","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14774,"108_Tue Nov 17 2020 10:50:59 GMT+0000","2020-11-16","Observation","Ship Staff","Ship Staff Insp.","MGPS pipelines are corroded and need replacement.","E/R - Pipes/ valves & fittings","","","","","","","WORK IN PROGRESS.","2020-12-30","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14896,"108_19 Nov 2020 1:47:22 AM","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","EJECTOR PUMP SUCTION BUTTER FLY VALVE WORM GEAR DEFECTIVE, NEED VALVE RENEWAL. \t","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","VALVE CAN OBLY BE RENEWED IN DD AS ITS DIRECTLY CONNETED MAIN SEA WATER LINE. ","2021-03-01","","Not Started",null,"Yes","No","No","Internal"]
[null,null,null,null,14749,"108_Tue Nov 17 2020 09:55:43 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Several antennas posts rusted/wasted on Monkey Island.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","ANTENNA POSTS WILL BE REPLACED. MATERIAL WILL BE ORDERED IN STORES. ","2021-01-16","","Not Started",null,"No","No","No","Internal","Spot de-rusting and touch up required"]
[null,null,null,null,14750,"108_Tue Nov 17 2020 09:58:15 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Main mast rusted, to be de-rusted and full painted white","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","DERESTING AND PAITING WILL BE CARRIED OUT.","2021-01-16","","Not Started",null,"No","No","No","Internal","Cosmetic  maintenance  to be carried out"]
[null,null,null,null,14753,"108_Tue Nov 17 2020 10:15:51 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","MH/HF & Satcom antenna danger area to be marked on monkey island with “do not enter”","Miscellaneous","General Appearance","External Factors","","","","","MARKING WORK IN PROGRESS. JOB WILL BE  COMPLETED SOON ALONG WITH OTHER JOBS IN MONKET ISLAND","2020-12-17","","Not Started",null,"No","No","No","Internal","Marking to be done after painting"]
[null,null,null,null,14754,"108_Tue Nov 17 2020 10:18:52 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Stay wires of main mast are wasted and need renewal.","Deck - Pipe / Fittings,Navigation - Others","Navigation","Equipment Related","","","","","WIRES WILL BE ORDERED IN NEXT DECK STORES AND WILL BE RENEWED AFTER SUPPLY. ","2020-12-17","","Not Started",null,"No","No","No","Internal","Condition  of stay wires to be further checked after de-rusting and renewed if required.  R.O.B of spare stay wires to be checked."]
[null,null,null,null,14758,"108_Tue Nov 17 2020 10:30:32 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","D, C, B- Deck weather tight doors port & stbd rusted badly, needs renewal.","Miscellaneous","General Appearance","External Factors","","","","","Door frames are wasted, require full renewal of frames, Full job can be campleted in dry-dock. Temporary repairs to be carried out for time being.","2020-12-17","","Not Started",null,"No","No","No","Internal","Doors actual condition to be checked after  de-rusting."]
[null,null,null,null,14759,"108_Tue Nov 17 2020 10:32:28 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Accommodation paint is peeled of any several places, to be full de-rusted and re-painted.","Accommodation","General Appearance","External Factors","","","","","Full accommodation block hydroblasting and painting to be carried out.","2021-01-16","","Not Started",null,"No","No","No","Internal","Cosmetic maintenance"]
[null,null,null,null,14760,"108_Tue Nov 17 2020 10:37:36 GMT+0000","2020-11-17","Observation,Defect","Ship Staff","Ship Staff Insp.","Natural vents around accommodation needs packing renewal, Channels rusted","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","External Factors","","","","","De-rusting of channels and packing renewal to be carried out.","2021-01-16","","Not Started",null,"No","No","No","Internal","Packing channel to be de-rusted and packing to be renewed"]
[null,null,null,null,14762,"108_Tue Nov 17 2020 10:41:42 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Provisions cranes rusted at various places.","Deck - Machinery","General Appearance","External Factors","","","","","De-rusting/hydroblasting required.","2020-12-17","","Not Started",null,"No","No","No","Internal","Spot derusting and touch up / painting to be carried out."]
[null,null,null,null,14763,"108_Tue Nov 17 2020 10:43:15 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Bunker cranes rusted and wire reels/drums wasted.","Deck - Machinery","General Appearance","Equipment Related","","","","","De-rusting of bunker crane davit, built up on crane reel drum edges","2020-12-31","","Not Started",null,"No","No","No","Internal","Cosmetic maintenance  to be carried out  and wire reels/drums condition to be carried out"]
[null,null,null,null,14764,"108_Tue Nov 17 2020 10:44:59 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Port & Stbd life raft securing areas railings and securing arrangements badly rusted","LSA / FFA","General Appearance","External Factors","","","","","De-rusting and painting of railings to be carried out.","2020-12-17","","Not Started",null,"No","No","No","Internal","Spot de-rusting and renewal  if required"]
[null,null,null,null,14767,"108_Tue Nov 17 2020 10:46:13 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Port & stbd side life boat deck aft area drain pipe is rusted","LSA / FFA","General Appearance","External Factors","","","","","Clogged drain pipe to be cleared and de-rusting & painting to be done on drain pipe","2020-12-31","","Not Started",null,"No","No","No","Internal","Spot de-rusting and touch ups"]
[null,null,null,null,14768,"108_Tue Nov 17 2020 10:47:29 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Switch box port & stbd side muster stations base wasted","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","New base to be fabricated and welded","2020-12-30","","Not Started",null,"No","No","No","Internal","Crop and renew"]
[null,null,null,null,14769,"108_Tue Nov 17 2020 10:47:57 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Ballast Pump No 1 Leaking from mechanical seal.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","SLIGHT LEAKAGE FOUND.  MECHANICAL SEAL ORDERD UNDER RO CHAR200037","2020-12-30","CHAR200037","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14773,"108_Tue Nov 17 2020 10:50:47 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Weather tight door A deck stbd side wasted","Accommodation","Structural Condn. / WT integrity ","External Factors","","","","","Temporary repairs to be carried out on boken sections of the weather tight door","2020-12-31","","Not Started",null,"No","No","No","Internal","Spot de-rusting and renewal if required"]
[null,null,null,null,14779,"108_Tue Nov 17 2020 10:55:04 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Life boat falls port & stbd side rusted, fall wire drums edges wasted, Limit switches to be cleaned, Resting pads to be de-rusted and painted","LSA / FFA","Safety / LSA / FFA","External Factors","","","","","De-rusting and painting of life boat davits and full structure to be carried out","2020-12-31","","Not Started",null,"No","No","No","Internal","PSC- items, to be completed asap."]
[null,null,null,null,14787,"108_Tue Nov 17 2020 10:58:46 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Navigation side lights platforms and casings rusted, to be de-rusted and painted matt black","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","De-rusting and painting to be carried out","2020-12-18","","Not Started",null,"No","No","No","Internal","Cosmetic maintenance"]
[null,null,null,null,14790,"108_Tue Nov 17 2020 11:00:24 GMT+0000","2020-11-17","Observation,Defect","Ship Staff","Ship Staff Insp.","Stbd bunker hose davit gear oil leak, drum coamings wasted","Deck - Machinery","MARPOL Related","External Factors","","","","","OIL LEAKAGE WILL BE INVESIGATED. DRUM MAINTENANCE WILL BE CARREID OUT. ","2020-12-17","","Not Started",null,"No","No","No","Internal","Gear box to be dismantled and required parts to be ordered."]
[null,null,null,null,14793,"108_Tue Nov 17 2020 11:02:34 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Accommodation entrance Port and Stbd side floor is rusted and need to be de-rusted and painted","Accommodation","General Appearance","External Factors","","","","","De-rusting and painting to be carried out","2020-12-17","","Not Started",null,"No","No","No","Internal","cosmetic maintenance"]
[null,null,null,null,14795,"108_Tue Nov 17 2020 11:04:11 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Safety tongue of port side bunker davit hook stuck","Deck - Machinery","General Appearance","Equipment Related","","","","","Safety latch to be repaired.","2020-12-17","","Not Started",null,"No","No","No","Internal","To be checked and made free"]
[null,null,null,null,14800,"108_Tue Nov 17 2020 11:06:51 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Bunker save-all trays& Manifold valves for bunker manifold rusted, Wheels for valves wasted, to be de-rusted and wheels renewed as required.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","De-rusting and painting to be carried out, Wheels to be renewed.","2020-12-31","","Not Started",null,"No","No","No","Internal","To be carried out asap"]
[null,null,null,null,14803,"108_Tue Nov 17 2020 11:08:55 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Port side accommodation gangway lower platform securing eyes grooved and swivel nuts thinned down","Critical Equip.","Safety / LSA / FFA","External Factors","","","","","Swivel nuts to be renewed, Eye grooves to be built up","2020-12-17","","Not Started",null,"No","No","No","Internal","PSC items- to be completed asap"]
[null,null,null,null,14806,"108_Tue Nov 17 2020 11:10:17 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Ramps (Bridges over pipes) on deck are heavily rusted and wasted at places","Miscellaneous","General Appearance","External Factors","","","","","Rusted ramps to be renewed.","2020-12-31","","Not Started",null,"No","No","No","Internal","Crop and renew after de-rusting  if required"]
[null,null,null,null,14816,"108_Tue Nov 17 2020 11:16:53 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","E/R skylight rubber hardened, channels rusted, requires de-rusting and greasing on hinges.","Deck - Pipe / Fittings","Eng. / Strg. Comp.","External Factors","","","","","De-rusting and painting of channel, Rubber renewal required.","2020-12-31","","Not Started",null,"No","No","No","Internal","Spot de-rusting and touchup  job"]
[null,null,null,null,14820,"108_Tue Nov 17 2020 11:22:10 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Several cargo hold natural vents rusted, packings damaged, channel rusted","Deck - Pipe / Fittings","Cargo / Ballast Systems","External Factors","","","","","De-rusting and painting , rubber renewal where required to be carried out","2020-12-30","","Not Started",null,"No","No","No","Internal","Damage packing required to be renewed and touch up maintenance at the packing channel."]
[null,null,null,null,14822,"108_Tue Nov 17 2020 11:24:08 GMT+0000","2020-11-17","Defect","Ship Staff","Suptd. Insp.","Cargo hold # 3 stbd fwd stbd side corner packing damaged","Cargo Mach.","Structural Condn. / WT integrity ","External Factors","","","","","Damaged packing to be renewed","2020-12-31","","Not Started",null,"No","No","No","Internal","Packing spare to be checked and renewed if available on board."]
[null,null,null,null,14825,"108_Tue Nov 17 2020 11:25:30 GMT+0000","2020-11-17","Defect","Ship Staff","Suptd. Insp.","Mooring winch no.7  oil leaking","Deck - Machinery","MARPOL Related","External Factors","","","","","To be investigated and leak ractified","2020-12-17","","Not Started",null,"No","No","No","Internal","Oil seal spare to be checked and ordered if not available"]
[null,null,null,null,14829,"108_Tue Nov 17 2020 11:27:30 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Hatch covers packing channels rusted need maintenance, Hatch covers rollers heavy rusted.","Cargo Mach.","General Appearance","External Factors","","","","","Some rollers heavy rusted to be de-rusted and renewed at few places","2020-12-31","","Not Started",null,"No","No","No","Internal","Hydro blasting and touch up required and rollers  bearing to be  greased up."]
[null,null,null,null,14832,"108_Tue Nov 17 2020 11:29:24 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Cargo holds Australian ladders safety hand railings wasted, to be rectified , vertical ladders in few location found damaged","Deck - Pipe / Fittings","Cargo / Ballast Systems","External Factors","","","","","Fabrication of damaged sections to be carried out, hot work is required","2020-12-31","","Not Started",null,"No","No","No","Internal","To be cropped and renewed."]
[null,null,null,null,14894,"108_Thu Nov 19 2020 09:46:10 GMT+0000","2020-11-18","Breakdown","Ship Staff","Ship Staff Insp.","No 2 STBD Bunker tank steam inlet valve not operational and need renewal","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","valve will be ordered in next engine room stores PO and replaced at next opportunity.","2020-12-31","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14895,"108_Thu Nov 19 2020 09:48:16 GMT+0000","2020-11-18","Defect","Ship Staff","Ship Staff Insp.","Main Engine FO Backwash Filer Leaking from Changeover Spindle","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Spares Ordered and awaiting","2020-12-31","CHAR200007","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14897,"108_19 Nov 2020 1:50:20 AM","2020-11-18","Breakdown","Ship Staff","Ship Staff Insp.","No 2 STBD Bunker tank steam inlet valve not operational and need renewal\t","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","valve will be ordered in next engine room stores PO and replaced at next opertunity. ","2021-03-01","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14898,"108_19 Nov 2020 1:52:19 AM","2020-11-18","Defect","Ship Staff","Ship Staff Insp.","Main Engine FO Backwash Filer Leaking from Changeover Spindle\t","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Spares Ordered and awating ","2021-03-01","CHAR200007","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14908,"108_19 Nov 2020 2:08:33 AM","2020-11-18","Defect","Ship Staff","Ship Staff Insp.","No 1  and No 2 fire pump discharge valve to AFT peak Tank are nt holding and operational(butterfly valve)\t","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Valves need renewal RO RAISED CHAR210006","2021-03-01","CHAR210006","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14856,"108_Wed Nov 18 2020 03:24:38 GMT+0000","2020-11-19","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","HFO purifier No 1 to HFO settling tank valve spindle leaking","E/R - Pipes/ valves & fittings","General Appearance","External Factors","","","","","SETTLING TANK WILL NEED TO EMPTIED. JOB  DEFERED TO DD.","2020-12-30","","Not Started",null,"Yes","No","No","Internal","Pls renew valve gland packing as soon as possible"]
[null,null,null,null,14871,"108_Wed Nov 18 2020 03:53:13 GMT+0000","2020-11-19","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FWG ejector pump required to be overhauled due to poor performance","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","SPARES RECEIVED. FWG IS OPERATIONAL AND PUMP WILL BE RENEWED AT NEXT PORT. ","2020-12-18","CHAR200023","Not Started",null,"No","No","No","Internal","Pls check and order spare parts to overhaul the pump  soonest."]
[null,null,null,null,14880,"108_Wed Nov 18 2020 04:14:59 GMT+0000","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","Both the Main Air Compressor oil carry over into the system -required to be overhauled","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","SPARES ORDERED . NO SPARES AVAILABLE ON BOARD TO CARRY OUT OVERHAULING. ","2020-12-31","CHAR200041","Not Started",null,"No","No","No","Internal","Both the compressor required to be overhaul. pls raise requisition based on present stock on board."]
[null,null,null,null,14900,"108_19 Nov 2020 2:02:20 AM","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","STP both chambers  outlet valve to discharge pump not operational/holding. \t\t","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","vales need to be repalced","2021-03-01","CHAR200005","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14901,"108_19 Nov 2020 2:11:35 AM","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","Sewage over board valve, Galley grey water ovbv valve, boiler blow down valve, are leaking from body and not holding\t","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","valves need to be repalced. need to plug form outside by divers to replace valves. CHAR200062","2021-03-01","CHAR200062","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14902,"108_19 Nov 2020 2:13:02 AM","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","bilge holding tank level sendor is broken and not operational. \t","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","need t repalce sensor with new sensor. ","2021-02-01","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14903,"108_19 Nov 2020 2:14:50 AM","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","ACB for No 2 AE is not winding in auto and needs manual charging","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Spares are ordered shrough shore tech team. need replacement of motor winding mechanism. ","2021-03-01","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14904,"108_19 Nov 2020 2:17:38 AM","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","Hot water circulating pump not operational. motor and pump are seized and need repalcement. \t","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","SPARES ORDERED. ","2021-03-10","CHAR200043","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14905,"108_19 Nov 2020 2:20:38 AM","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","Main Engine Unit No 4 Liner wear reading are over the limit. Piston rings have lot of scuffing markes and need liner replacement on urgent basis. \t","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","liner need replacement. ","2021-03-01","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14906,"108_19 Nov 2020 2:25:14 AM","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","All 3 Aux Engine Sump oil to renew. Oil condition is Bad.\t","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Sump oil to renew during decarb","2021-02-01","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14907,"108_19 Nov 2020 2:26:52 AM","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","AE 1 and AE 2 TC needs overhauling. AE is unable to take load and build sufficiebnt Scavenge pressure. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Overhauling will be carried out during decarb. ","2021-03-05","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14909,"108_19 Nov 2020 2:31:56 AM","2020-11-19","Defect","Ship Staff","Ship Staff Insp.","Main Engine Spare Exhaust Valce - 3 in numbers, 12 spare fuel valves, 1 spare piston and 1 spare fuel pump top cover need overhauling. ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","will check spares and overhaul all items at next voyage. spares will be ordered accordingly. ","2021-02-02","","Not Started",null,"No","No","No","Internal"]

{"sheet":"Completed","index":1,"n_rows":70,"n_cols":28,"rows_kept":70,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","09-Dec-2020",null,null,"Ship Name","CHARM (09-12-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,14861,"108_Wed Nov 18 2020 03:33:04 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main Welding machine missing. There are no welding accessories","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","ITEMS SUPPLIED AND FITTED. ALL IN GOOD ORDER. ","2020-12-30","","Completed","2020-11-04","No","No","No","Internal","Pls  order if required"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:14:40 GMT+0000","2020-10-30","Observation","Ship Staff","Ship Staff Insp.","Suction filters of Main SW pump, TC pump, and fire and GS pump body is corroded and need cleaning and painting.","E/R - Pumps","Structural Condn. / WT integrity ","External Factors",null,null,"Not Applicable","Not Applicable","All sea water pumps suction filers body cleaned and painted.","2020-12-15",null,"Completed","2020-11-12","No",null,null,"Internal"]
[null,null,null,null,null,"108_Thu Nov 19 2020 09:27:57 GMT+0000","2020-10-30","Defect","Ship Staff","Ship Staff Insp.","HFO purifier no.1 to HFO settling tank  valve spindle leaking","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors",null,null,"Not Applicable","Not Applicable","Valve spindle gland nut tightened now no loeak.","2020-12-15",null,"Completed","2020-12-02","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:02:04 GMT+0000","2020-10-30","Observation","Ship Staff","Ship Staff Insp.","Step corroded and need replacement on entry into engine room from china passage.","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","New plate fabricated and welded in palce. ","2020-12-30",null,"Completed","2020-12-27","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:05:31 GMT+0000","2020-10-30","Observation","Ship Staff","Ship Staff Insp.","Steering gear natural mushroom vent spindle is corroded and need complete overhauling","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","de rust carried out. spindle can move freely. sealing tested and found to be in good order. ","2020-12-15","na","Completed","2020-12-03","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:13:42 GMT+0000","2020-10-30","Observation","Ship Staff","Ship Staff Insp.","Main Ballast line butterfly valve leaking from Spidle in bottom platform","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","SPIDLET TIGHTNED AND LEAK RECTIFIED","2020-12-30","NA","Completed","2020-11-05","No",null,null,"Internal"]
[null,null,null,null,14862,"108_Wed Nov 18 2020 03:33:58 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Gas welding torch and accessories missing","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","ITEMS SUPPLIED. ","2020-12-31","","Completed","2020-11-04","No","No","No","Internal","PLs order  if required"]
[null,null,null,null,14865,"108_Wed Nov 18 2020 03:38:53 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No 1 FO bunker tank Stem leaking on inlet line","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","STEAM LEAK RECTIFIED. ","2020-12-31","","Completed","2020-11-07","No","No","No","Internal","Pls rectify leakage."]
[null,null,null,null,14868,"108_Wed Nov 18 2020 03:44:29 GMT+0000","2020-11-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main SW pump Discharge valve leaking from body","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","WAS LEAKING FROM GLAND, AFTER TIGHTENING THE GLAND LEAK STOPPED. ","2020-12-18","","Completed","2020-11-10","No","No","No","Internal","Pls order new valve if not available on board"]
[null,null,null,null,null,"108_Wed Nov 18 2020 03:21:50 GMT+0000","2020-11-01","Observation,Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steam leak on FO settling tank steam return line near steam trap","Miscellaneous","Eng. / Strg. Comp.","External Factors",null,null,"Not Applicable","Not Applicable","Steam leak rectified.","2020-12-31",null,"Completed","2020-12-03","No",null,null,"Internal"]
[null,null,null,null,null,"108_Wed Nov 18 2020 03:18:04 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Purifier room bilges need to be cleaned of oil and need painting on floor and pipelines","Miscellaneous","Eng. / Strg. Comp.","Human Error",null,null,"Not Applicable","Not Applicable","Purifier room cleaned and painted","2020-11-30",null,"Completed","2020-11-25","No",null,null,"Internal"]
[null,null,null,null,null,"108_Wed Nov 18 2020 03:11:32 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering gear entrance from engine room need IMP posters (Entering in to Steering gear room)","Miscellaneous","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","ALL IMO POSTERS POSTED. ","2020-12-31",null,"Completed","2020-11-24","No",null,null,"Internal"]
[null,null,null,null,null,"108_Wed Nov 18 2020 03:12:57 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering gear motors have too much dust and need cleaning","Miscellaneous","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","CLEANING COMPLETED ","2020-12-16",null,"Completed","2020-12-01","No",null,null,"Internal"]
[null,null,null,null,null,"108_Wed Nov 18 2020 03:23:29 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All QCV in Engine room are with full of dust. Valve springs need to be cleaned and check for operation","E/R - Pipes/ valves & fittings","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","CLEANED","2020-12-30",null,"Completed","2020-12-17","No",null,null,"Internal"]
[null,null,null,null,null,"108_Wed Nov 18 2020 03:28:05 GMT+0000","2020-11-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Refer No 2-compressor electric panel cover missing","E/R - Pipes/ valves & fittings","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","COVER FABRICATED AND REPLACED. . ","2020-12-31",null,"Completed","2020-11-28","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:09:29 GMT+0000","2020-11-01","Observation","Ship Staff","Ship Staff Insp.","Funnel casing inside engine room all platforms need cleaning","Miscellaneous","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","CLEANED AND PAINTED. ","2020-12-15",null,"Completed","2020-12-02","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:07:48 GMT+0000","2020-11-06","Observation","Ship Staff","Ship Staff Insp.","All Fire hoses in engine room to be cleaned and pressure tested. All fire hoses to be connected to hydrants and kept ready for use.","LSA / FFA","Safety / LSA / FFA","External Factors",null,null,"Not Applicable","Not Applicable","ALL FIRE HOSES CLEANED, PRESSURE TESTING OF HOSE CARRIED OUT. KEPT IN STATE OF READINESS.","2020-12-30",null,"Completed","2020-11-27","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:03:15 GMT+0000","2020-11-09","Observation","Ship Staff","Ship Staff Insp.","Fire hydrant No 33 on bottom platform  in engine room is leaking","LSA / FFA","Safety / LSA / FFA","Human Error",null,null,"Not Applicable","Not Applicable","Hydrant opened & re-tightened. No leak detected .","2020-12-30",null,"Completed","2020-11-30","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:58:00 GMT+0000","2020-11-10","Observation","Ship Staff","Ship Staff Insp.","Various places on deck need IMO symbols and stencils renewal","LSA / FFA","Safety / LSA / FFA","Human Error",null,null,"Not Applicable","Not Applicable","IMO symbols & stencils renewed.","2020-11-30",null,"Completed","2020-11-24","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:59:49 GMT+0000","2020-11-10","Observation","Ship Staff","Ship Staff Insp.","Stbd side combination ladder in poor condition, to be renewed","Miscellaneous","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","Stbd side ladder renewed.","2020-11-25",null,"Completed","2020-11-15","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:01:53 GMT+0000","2020-11-10","Observation","Ship Staff","Ship Staff Insp.","HOLD cleaning sea water pump discharge valve leaking from gland.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","GLAND PACKING TIGHTENED. LEAK RECTIFIED. ","2020-12-30",null,"Completed","2020-12-04","No",null,null,"Internal"]
[null,null,null,null,14875,"108_Wed Nov 18 2020 04:02:35 GMT+0000","2020-11-11","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main engine unit 1 & 5 fuel injector required to press test","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","PRESSURE TESING DONE AND VALVES REPLACED WITH OVERHAULED FUEL VALVES. SPARES  ARE ALSO ORDERED. ","2020-12-10","CHAR200018","Completed","2020-11-18","No","No","No","Internal","Pls  do at next convenient time"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:00:00 GMT+0000","2020-11-11","Observation","Ship Staff","Ship Staff Insp.","OWS piping are in bad condition and need replacement including valves on urgent basis","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","ALL RUSTED AND DAMAGED SECTIONS RENEWED. ","2020-12-30",null,"Completed","2020-12-05","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:27:02 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","SOPEP Locker dirty/not arranged.","Miscellaneous","Structural Condn. / WT integrity ","External Factors",null,null,"Not Applicable","Not Applicable","SOPEP locker cleaned & arranged.","2020-11-25",null,"Completed","2020-11-21","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:27:15 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","New posters to be posted outside paint locker","Miscellaneous","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","Posters renewed","2020-12-15",null,"Completed","2020-11-24","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:28:32 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Leaking airline valve aft of hold# 7","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",null,null,"Not Applicable","Not Applicable","renewed. ","2020-12-15",null,"Completed","2020-12-07","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:56:57 GMT+0000","2020-11-13","Observation","Ship Staff","Ship Staff Insp.","Incinerator refractory is damaged completely.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","TEMP. REPAIR CARRIED OUT.","2020-12-30",null,"Completed","2020-12-29","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:24:38 GMT+0000","2020-11-13","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Oxygen acetylene room new poster to be pasted, Acetylene room lock eye is wasted to be fabricated","Miscellaneous","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","Poster renewed & Lock eye to be renewed.","2020-11-30",null,"Completed","2020-11-25","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:45:35 GMT+0000","2020-11-14","Observation","Ship Staff","Ship Staff Insp.","Hatch cover drive chain & wire length to be adjusted.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","adjusted. operated and found in good order. ","2020-11-30",null,"Completed","2020-11-15","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:55:32 GMT+0000","2020-11-14","Observation","Ship Staff","Ship Staff Insp.","Steering gear all 4 pressure gauges on the units are in bad situation and need replacement.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","GAUGE RENEWED WITH SPARE GAUGES AVILABLE ON BOARD. ","2020-12-30",null,"Completed","2020-12-28","No",null,null,"Internal"]
[null,null,null,null,14811,"108_Tue Nov 17 2020 11:13:11 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Emergency generator room- poster missing, Fuel oil tank missing the markings for level of oil and time left, Quick closing valve leaking","Miscellaneous","General Appearance","External Factors","","","","","POSTER WILL RELAVENT DATA PASTED IN EMERGENCY GENERATOR ROOM. ","2020-12-31","","Completed","2020-11-19","No","No","No","Internal","PSC items- to be attended asap"]
[null,null,null,null,14836,"108_Tue Nov 17 2020 11:31:47 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Stbd side combination ladder in poor condition, to be renewed","Miscellaneous","General Appearance","External Factors","","","","","Port and stbd side pilot ladders renewed","2020-12-17","","Completed","2020-11-17","No","No","No","Internal","Pls  order new combination ladder if not available onboard."]
[null,null,null,null,14843,"108_Wed Nov 18 2020 02:59:13 GMT+0000","2020-11-17","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine room blower no 1 flap not closing","Miscellaneous","General Appearance","Equipment Related","","","","","GRESING CARRIED OUT AND FLAP MADE FREE. ","2020-12-18","","Completed","2020-11-20","No","No","No","Internal","PSC items- Pls check  flap position internally and rectify problem as soon as possible."]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:28:06 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Battery room IMO poster missing on entrance.","Miscellaneous","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","New IMO sticker pasted","2020-12-17",null,"Completed","2020-11-24","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:53:46 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Fire hoses all around accommodation are in very dirty condition and require washing and cleaning","LSA / FFA","General Appearance","Human Error",null,null,"Not Applicable","Not Applicable","Hoses laid on deck and washed with fresh water.","2020-12-31",null,"Completed","2020-11-26","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:56:17 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Embarkation ladders & life boat painters to be opened and inspected for any damages","Miscellaneous","Safety / LSA / FFA","External Factors",null,null,"Not Applicable","Not Applicable","Embarkation ladders opened, Inspected and washed","2020-12-17",null,"Completed","2020-11-26","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:57:32 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Removable railing in way of life boat lowering area is frozen and will require to be removed by cutting","Deck - Pipe / Fittings","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","De-rusting and painting of base holders carried out","2020-12-31",null,"Completed","2020-12-10","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:33:11 GMT+0000","2020-11-17","Defect,Observation","Ship Staff","Ship Staff Insp.","Forecastle store requires cleaning and housekeeping","Miscellaneous","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","STORE CLEANED AND ARRANGED. ","2020-12-17",null,"Completed","2020-12-05","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:15:10 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Suez cabins in very poor condition. Cleaning, disinfecting, curtains missing on beds, washroom. Shower head missing","Miscellaneous","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","Cleaning done","2020-12-31",null,"Completed","2020-12-15","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 11:05:29 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Tally room is in very poor condition, to be cleaned and floor need to be painted","Accommodation","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","Tally room cleaned","2020-12-31",null,"Completed","2020-12-07","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:52:02 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Lashing on port side provision crane is broken","Deck - Pipe / Fittings","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","LAshing wire  renewed.","2020-12-17",null,"Completed","2020-11-25","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:25:13 GMT+0000","2020-11-17","Defect","Ship Staff","Ship Staff Insp.","Battery room door packing painted over, old and needs renewal, channel is rusted.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","External Factors",null,null,"Not Applicable","Not Applicable","maintenance carried out","2021-01-16",null,"Completed","2020-12-18","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:22:35 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","Battery room floor rusted, needs de-rusting and painting.","Accommodation","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","de rusting  and paiting carrired out","2020-12-17",null,"Completed","2020-12-18","No",null,null,"Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:14:11 GMT+0000","2020-11-17","Observation","Ship Staff","Ship Staff Insp.","All stencils & markings to renew on monkey Island.","Miscellaneous","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","STENCILING CARRIED OUT. ","2021-01-16",null,"Completed","2020-12-15","No",null,null,"Internal"]
[null,null,null,null,null,"108_Wed Nov 18 2020 03:07:53 GMT+0000","2020-11-17","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Aux engine bellow leaking gases near EGB","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors,Equipment Related",null,null,"Not Applicable","Not Applicable","BELLO GASKET RENEWED. ","2020-12-31",null,"Completed","2020-12-13","No",null,null,"Internal"]
[null,null,null,null,null,"108_Wed Nov 18 2020 03:02:43 GMT+0000","2020-11-17","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hot well top cover is corroded, need replacement","E/R - Pipes/ valves & fittings","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","TOP COVER FABRICATED AND RENWED. ","2020-12-18",null,"Completed","2020-12-02","No",null,null,"Internal"]
[null,null,null,null,null,"108_Wed Nov 18 2020 03:04:07 GMT+0000","2020-11-17","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","EGB steam stop valve steam leaking","E/R - Boiler","Eng. / Strg. Comp.","External Factors",null,null,"Not Applicable","Not Applicable","LEAK RECTIFIED AT GANGAVRAM ANCHORAGE. ","2020-12-31",null,"Completed","2020-12-20","No",null,null,"Internal"]
[null,null,null,null,null,"108_Wed Nov 18 2020 03:06:21 GMT+0000","2020-11-17","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Plates near EBG steam stop valves need to be shifted to other location and secure them properly","E/R - Boiler","General Appearance","Human Error",null,null,"Not Applicable","Not Applicable","PLATES SECURED WITH WIRE ROPES. ","2020-11-30",null,"Completed","2020-11-20","No",null,null,"Internal"]
[null,null,null,null,null,"108_19 Nov 2020 1:54:18 AM","2020-11-18","Defect","Ship Staff","Ship Staff Insp.","LT cooler No 1  SW Inlet Valve is not operational. Need valve repalcemnet. \t","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","VALVE RENEWED. ","2021-03-01",null,"Completed","2021-01-02","No",null,null,"Internal"]
[null,null,null,null,14891,"108_Thu Nov 19 2020 09:12:07 GMT+0000","2020-11-19","Observation","Ship Staff","Ship Staff Insp.","After taking over vessel found there was error in the LO tank soundings. \nHad brought issue to owners notice upon take over.  \nTanks                                             Error (in Ltrs)         \n1.\tNo 1 CYL OIL Storage Tank -                 800\n2.\tNo 2 CYL oil Storage Tank -                 2800\n3.\tME LO Storage Tank -                        1400\n4.\tME LO settling Tank -                           800\n5.\tAE LO Storage Tank -                           200","Miscellaneous","Eng. / Strg. Comp.","External Factors","","","","","Action taken","2020-11-19","","Completed",null,"No","No","No","Internal","We have competed zero calibration the tanks listed below and kindly note the errors in each tank soundings. \n\n  Tanks                                             Error (in Ltrs)         \n1.\tNo 1 CYL OIL Storage Tank -                 800\n2.\tNo 2 CYL oil Storage Tank -                 2800\n3.\tME LO Storage Tank -                        1400\n4.\tME LO settling Tank -                           800\n5.\tAE LO Storage Tank -                           200"]
[null,null,null,null,14910,"108_Thu Nov 19 2020 10:02:10 GMT+0000","2020-11-19","Observation","Ship Staff","Ship Staff Insp.","After taking over vessel found there was error in the LO tank soundings. \nHad brought issue to owners notice  upon take over.  \n                            Tanks                                   Error (in Ltrs)         \n1.\tNo 1 CYL OIL Storage Tank  -                 800\n2.\tNo 2 CYL oil Storage Tank -                 2800\n3.\tME  LO Storage Tank -                        1400\n4.\tME LO settling Tank  -                           800\n5.\tAE LO Storage Tank  -                           200","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","We have competed  zero calibration the tanks listed below and kindly note the errors in each tank soundings.",null,"","Completed",null,"No","No","No","Internal"]
[null,null,null,null,null,"108_Tue Nov 17 2020 10:48:53 GMT+0000","2020-11-19","Observation","Ship Staff","Ship Staff Insp.","Several markings, imo symbols in poor condition around accommodation","Accommodation","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","IMO stickers and posters renewed","2020-12-31",null,"Completed","2020-11-24","No",null,null,"Internal"]
[null,null,null,null,null,"108_26/12/2020 6:29:18 AM","2020-12-24","Defect","Ship Staff","Ship Staff Insp.","Provison crane (stbd) magnetic brakes not holding.","Deck - Machinery","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","Magnetic brakes CHANGED AND CRANE MADE OPERATIONAL. ","2021-01-24",null,"Completed","2021-01-03","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["108","CHARM (09-12-2020)","108_1607498740424.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]