{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":42,"n_cols":28,"rows_kept":42,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","14-Jan-2021",null,null,"Ship Name","ANTWERP (31-12-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,14673,"107_Mon Nov 16 2020 11:11:18 GMT+0000","2020-01-12","Observation","Ship Staff","Ship Staff Insp.","Port side windlass brake lining not good condition, required renewal","Deck - Mooring Machinery","General Appearance","Equipment Related","","","","","REPLACE BY DD","2021-03-15","ANTW200013","Deferred to D D",null,"Yes","No","No","Internal","Pls submit requisition for brake lining based on the spare stock onboard."]
[null,null,null,null,14667,"107_Mon Nov 16 2020 10:58:32 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","Main engine Total  running hrs 98251.3  which recorded manually and  M/E tachometer is  not working.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Crew can't do anything. Asked Maker these matter. Pls to ask Maker, then deleted if no need.","2021-03-31","","Deferred to D D",null,"No","No","No","Internal","PLs submit requisition if not yet submitted."]
[null,null,null,null,14671,"107_Mon Nov 16 2020 11:06:02 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","No.1 HFO purifier temp control valve malfunctioning","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","\"UMS\" personals come on board for check & adjust. After sailing, found problem continuous. Inspection job in progress. Keep manual control only.","2021-03-31","","In progress",null,"No","No","No","Internal","Please  do check and  advise  in details what is the problem. on the temp control valve."]
[null,null,null,null,14676,"107_Mon Nov 16 2020 11:15:46 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","ME Lub oil purifier supply pump  are  not working","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Raised spare requisition ANTW-007-2021","2021-01-31",null,"In progress",null,"No","No","No","Internal","Pls do check and plan to overhaul pump if required."]
[null,null,null,null,14679,"107_Mon Nov 16 2020 11:20:54 GMT+0000","2020-11-16","Defect,Observation","Ship Staff","Ship Staff Insp.","Provision crane hydraulic piping  condition not good, required renewal","Deck - Machinery","Eng. / Strg. Comp.","Equipment Related","","","","","Renewed many soft hose by workshop personal & some can't renewed due to old connector welding by previous crew. these hose stay on board for spare.","2021-03-31","ANTW205043","Deferred to D D",null,"No","No","No","Internal","Pls renew if spare pipe available or submit requisition."]
[null,null,null,null,14684,"107_Mon Nov 16 2020 11:28:17 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","Many pumps in ER   auto exchange function  are out of order. Testing in progress","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Found AE FO supply & circulating pump can't auto start. Check & found many pumps only can auto start when power-off. Can't auto changed when pumps stop (found 1# ME j.c.f.w.pump stopped, but 2# no started when ship sailing). Found pressure switchs normal. Rcvd spare ANTW215041 Hyundai HEEM-2 pump changeover control module, Renewed 1pc to ME jacket.c.f.w.pump, but no auto change function continuous.","2021-05-31","ANTW215041 rcvd @ 2021-3-21 Itaguai.","Deferred to D D",null,"No","No","No","Internal","Pls do test all pumps and make require R.O."]
[null,null,null,null,15237,"107_Wed Nov 25 2020 05:57:32 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Topping up air compressor required to be overhauled due to poor performance","E/R - Air Comp.","Eng. / Strg. Comp.","External Factors","","","","","Raised spare requisition excel form \"ANT - 2020006 Spare requisition main air compressor\"  & send e-mail to office Nov.25th already.","2021-01-31","ANTW 205077","Waiting spare",null,"No","No","No","Internal","Compressor to be overhauled. Pls submit R.O for necessary spare parts."]
[null,null,null,null,15239,"107_Wed Nov 25 2020 06:01:46 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","Accommodation A/C compressor sump oil leaking, required to be overhaul","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Plan to do this job when ship D-docking due to compressor working condition well / only slightly leaking.","2021-03-31","ANTW 205045 rcvd on board @ 20201129SIN.","Deferred to D D",null,"No","No","No","Internal","New spare parts received on board at Singapore, pls overhaul the compressor."]
[null,null,null,null,15240,"107_Wed Nov 25 2020 06:04:23 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","Aux engine no. 1 &  2 running hours counter not working","Elect. Mach. & Equip.","Eng. / Strg. Comp.","External Factors","","","","","Waiting spares.","2021-01-31","ANTW 205079","Waiting spare",null,"No","No","No","Internal","Pls submit R.O. for necessary parts."]
[null,null,null,null,15241,"107_Wed Nov 25 2020 06:06:04 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","M/E lube oil purifier supply pump not working","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Raised spare requisition ANTW215019.","2021-01-31",null,"In progress",null,"No","No","No","Internal","Pump to be overhauled."]
[null,null,null,null,15243,"107_Wed Nov 25 2020 06:11:18 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Ballast control  system   04 nos valves are show error from cargo control room","Deck - Pipe / Fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","require renewal in DD.","2021-05-31","Exchanged by ANTW215053.","Deferred to D D",null,"No","No","No","Internal","Service technicians attended at Singapore. Pls test the valves operation and advise."]
[null,null,null,null,15557,"107_Tue Dec 08 2020 07:38:04 GMT+0000","2020-11-28","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel deck  light holder  3 nos supports corroded and wasted, same to be renewed.","Deck - Pipe / Fittings","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","Waiting store ANTW210001 which wrong supplied at Fujairah. Needed re-supplied.","2021-01-15",null,"In progress",null,"No","No","No","Internal"]
[null,null,null,null,15558,"107_Tue Dec 08 2020 07:43:47 GMT+0000","2020-11-28","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Deck hydraulic pipes for hatch cover corroded in various places, all pipes to be press tested and leaky pipes to be renewed.","Deck - Pipe / Fittings","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","Crew renewed some leaking pipe/hose/connector which heavy leaking. Other refer to D-D list 5.07, 5.08 etc.","2021-05-30","ANWT210015.","Deferred to D D",null,"Yes","No","No","Internal"]
[null,null,null,null,15559,"107_Tue Dec 08 2020 07:45:26 GMT+0000","2020-11-28","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Deck air lines sighted corroded in various places, all corroded pipes to be renewed.","Deck - Pipe / Fittings","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","Wii added to D-docking repair list 7.04.","2021-03-30","ANTW210015.","Deferred to D D",null,"Yes","No","No","Internal"]
[null,null,null,null,15562,"107_Tue Dec 08 2020 07:50:58 GMT+0000","2020-11-28","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","A/E F.O. viscosity meter assy removed by UNIMARINE and off landed at Singapore for repair.","E/R - Pumps","Eng. / Strg. Comp.","External Factors,Equipment Related",null,null,"Not Applicable","Not Applicable","The spares delivery on board.We install finish ,System not leaking.Test find the viscosity controller cann't work.The F.O temperature cann't change.","2021-03-31",null,"In progress",null,"No","No","No","Internal","Item landed at Singapore for repair"]
[null,null,null,null,15565,"107_Tue Dec 08 2020 08:21:34 GMT+0000","2020-11-29","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Stbd Windlass: Main shaft bearing is badly worn out which causing excessive shaft movement.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","The manual dwg send to office @ 20201204 already.","2021-03-30","","Deferred to D D",null,"Yes","No","No","Internal","Pls submit R.O. for the spare parts."]
[null,null,null,null,15566,"107_Tue Dec 08 2020 08:23:49 GMT+0000","2020-11-29","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port Windlass: Outer drum bush is badly worn – requires to be renewed soonest to avoid shaft damage. Main shaft bearing is badly worn out which causing excessive shaft movement.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","The manual dwg send to office @ 20201204 already.","2021-03-30","","Deferred to D D",null,"Yes","No","No","Internal","Pls  check spare R.O.B  and submit R.O. for the spare parts if require."]
[null,null,null,null,15568,"107_Tue Dec 08 2020 08:30:11 GMT+0000","2020-11-29","Defect","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","AE LO purifier temperature controller require spare for repairs, same being sourced. Two nos of automatic steam control valve overhauled for HFO purifier as same found erratic.","E/R - Purifier,Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","The inspect job by workshop already. They said ok but can't hold on set point after sailing. Need time to check by crew. Keep manual control only.","2021-03-31","","Deferred to D D",null,"No","No","No","Internal",""]
[null,null,null,null,15569,"107_Tue Dec 08 2020 10:33:21 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Main deck, cross decks, poop decks and forecastle deck sighted scattered spot rust, same to be hydro blasted and painted.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","MAINTENANCE PLAN IN PROGRESS","2021-02-28","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,15571,"107_Tue Dec 08 2020 10:36:12 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel painting faded, same to be painted with designated LOGO.","Deck - Pipe / Fittings","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","Completed forward, portside & stbdside painting jobs.behind side will be complete when D-Docking. ","2021-05-31",null,"Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,15574,"107_Tue Dec 08 2020 10:41:28 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Crew laundry room upper deck common toilets floor tiles rust stained and same required to be renewed.","Accommodation","General Appearance","External Factors","","","","","renewed by D-D","2021-03-31","","Deferred to D D",null,"Yes","No","No","Internal","Pls submit R.O. for required floor tiles."]
[null,null,null,null,15567,"107_Tue Dec 08 2020 08:26:47 GMT+0000","2020-12-08","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Provision Crane (S): Found hoist and slewing limit not working, not able to carry out further trouble shooting due to no platform for the winch limit. Jib slewing limit is badly corroded and jammed, needs to be replace with new. Limit switch cam corroded and need change. Manual control lever not able to return to center upon release, and externally badly corroded. All hoses need to be renewal.  Cylinder Load holding valve requires to be renewed. Internal slewing bearing gear dry and need greasing. Winch standing platform is badly corroded. Spares will be sourced to rectify above mentioned faults.","Deck - Machinery","General Appearance","Equipment Related",null,null,"Not Applicable","Not Applicable","The renewed hoses when D-docking.\r\n\r\nCrew can renewed the Limit switch when receipt.","2021-03-31","ANTW 205083","Deferred to D D",null,"No","No","No","Internal","Pls do check and advise  what jobs can be completed by the ship staffs."]
[null,null,null,null,15242,"107_Wed Nov 25 2020 06:08:16 GMT+0000","2020-12-10","Observation","Ship Staff","Ship Staff Insp.","A/E No.3 fuel injectors to be renewed as it is overdue.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","No found any spare nozzles on board. Pressure test the old injectors & re-use only. Waiting spare ANTW205073, 215034.","2021-01-31",null,"In progress",null,"No","No","No","Internal","Please prepare one sets of fuel injector and replace  all six  units fuel injectors."]
[null,null,null,null,15580,"107_12/13/2020 4:53:59 AM","2020-12-12","Defect","Ship Staff","Ship Staff Insp.","VDR sometimes will display rudder error?timeout on SI17 rudder indicator","Navigation - VDR / BNWAS","Navigation","Equipment Related","","","","","we need shore professional maintenance check (before at singapore has repair, but now again appear error)","2021-01-31","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,16301,"107_31/12/2020 4:22:32 AM","2020-12-29","Observation","Ship Staff","Ship Staff Insp.","No2 FO supply pump for HFO purifier: mech.seal leaking.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Waiting spares antw215016. Anyway, exchanged by old mech.seal & no leaking now.","2021-01-31","ANTW 027-2020 send to office @ 20201228.","Waiting spare",null,"No","No","No","Internal"]

{"sheet":"Completed","index":1,"n_rows":61,"n_cols":28,"rows_kept":61,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","14-Jan-2021",null,null,"Ship Name","ANTWERP (31-12-2020)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,14664,"107_Mon Nov 16 2020 10:52:14 GMT+0000","2020-01-12","Observation","Ship Staff","Ship Staff Insp.","VDR display shows radar alert alarm sometimes.","Navigation - VDR / BNWAS","Communication","Equipment Related","","","","","already completed ","2020-12-15","","Completed","2020-01-12","No","No","No","Internal","Pls do check and find out the cause of alarms on the VDR display  monitor"]
[null,null,null,null,14670,"107_Mon Nov 16 2020 11:04:36 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","Steering gear no. 1& 2 hyd pump oil seal  found leaking excessively","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Shore service engineers on board for repair @ Sgp 2020-11-27~30. Now new problem are leaking from shaft seal of rudder angle. So suugest to close this & writen new.","2020-12-31","ANTW205043","Completed","2020-11-30","No","No","No","Internal","Pls submit requisition for spare parts"]
[null,null,null,null,14675,"107_Mon Nov 16 2020 11:14:20 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","Hatch covers hydraulic pipes corroded and leaking in various locations, required renewal and press test","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Some pipe renewed by crew already.","2020-12-30","","Completed","2020-12-03","No","No","No","Internal","Leaky pipes renewed. Pls  submit RO of the  required pipes & fittings ."]
[null,null,null,null,14677,"107_Mon Nov 16 2020 11:18:05 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","M/E lube oil stand by  pump  found starting auto but no alert alarm activated in ECR panel","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","\"cyclect\" engineers on board for check, test, later supplied 3+7pcs contactor & renewed by crew. Test & found normal, but found some problem after sail again. So closed this & writen other later.","2021-01-15","ANWT205042, 205054.","Completed","2020-11-29","No","No","No","Internal","Pls advise which pump contactor are having problem now."]
[null,null,null,null,14678,"107_Mon Nov 16 2020 11:19:28 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","M/E JCFW  stand by  pump  found starting auto but no alert alarm activated in ECR panel","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Same than ME LO pump","2021-01-15","ANWT205042, 205054","Completed","2020-11-29","No","No","No","Internal","Pls  renew contactor after receiving spare."]
[null,null,null,null,14681,"107_Mon Nov 16 2020 11:24:05 GMT+0000","2020-11-16","Other","Ship Staff","Ship Staff Insp.","There was no ODS & Suphur content record book found on board","Documentation","Cert. & Docu.","Equipment Related","","","","","SI bring 2books - Bunker sample & SECA FCO record book on board 20-Nov-2020 ( Incluclinding S%). Re ODS office have standard \"word\" file.","2020-12-16","","Completed","2020-11-30","No","No","No","Internal",""]
[null,null,null,null,14682,"107_Mon Nov 16 2020 11:25:29 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","Aux boiler feed water automatic  control valve  not working","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Crew adjusted already. Service on board when call SIN 27-Nov also.","2020-12-16","ANTW205033","Completed","2020-11-29","No","No","No","Internal","Automatic control feed valve function  tried out during boiler health check by  service technicians."]
[null,null,null,null,14683,"107_Mon Nov 16 2020 11:26:38 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","A/E & M/E FO  back wash  filters are  leaking thru the gland","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Retighten the connecting flanges after dismantled the Viscosity units..","2020-12-31","","Completed","2020-12-05","No","No","No","Internal","Pls submit R.O. for necessary repair kits."]
[null,null,null,null,null,"107_Mon Nov 16 2020 11:22:28 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","Hypermist HP pump press gauge  is not working","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","The spare come on board,We intalled finish.Now is good.","2021-02-28","ANTW 205078","Completed","2021-01-29","No",null,null,"Internal"]
[null,null,null,null,null,"107_Mon Nov 16 2020 10:56:19 GMT+0000","2020-11-16","Observation","Ship Staff","Ship Staff Insp.","Main engine Alpha lub station pump no.1 pipe connection leaking","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Try one more to retighten again, no leaking now","2021-01-31",null,"Completed","2021-01-30","No",null,null,"Internal"]
[null,null,null,null,15233,"107_Wed Nov 25 2020 05:49:34 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","Exhaust Gas Economizer soot blower two sets valves  are seized, require to be made operational.","E/R - Boiler,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","Action taken","2020-12-15","","Completed","2020-12-01","No","No","No","Internal","Faulty soot blower (aft ) dismantled, overhauled and fitted back. by shore technicians at Singapore. Tried out found satisfactory."]
[null,null,null,null,15234,"107_Wed Nov 25 2020 05:52:02 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Oily Water Separator 15 ppm alarm and Three way valves functioning to be checked. OWS damage pipes to be renewed.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Action  taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","15 ppm OCM renewed and 3-way valve function tested along with the alarms. found satisfactory.  Damage pipes renewed."]
[null,null,null,null,15235,"107_Wed Nov 25 2020 05:53:40 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","HFO Purifier  No. 1 and  M/E L.O. purifier are not working","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","HFO purifier No.1 and ME L.O. purifier   health check carried out  and  tried out satisfactorily by shore technician at singapore."]
[null,null,null,null,15236,"107_Wed Nov 25 2020 05:55:41 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Aux boiler combustion control system health check required to be carried out","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Action  Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","Aux Boiler combustion control system health checks carried out at  Singapore this time by shore technicians."]
[null,null,null,null,15238,"107_Wed Nov 25 2020 05:59:27 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","Incinerator failed to fire with Waste oil","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","Trouble shooting carried out and Waste oil pump overhauled, tried out-found satisfactory."]
[null,null,null,null,15244,"107_Wed Nov 25 2020 06:13:48 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","VDR and Navigation equipment health check to be carried out.","Elect. Mach. & Equip.,Navigation - VDR / BNWAS","Communication","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","VDR and Navigation equipment's health check carried out  by Service technician  at  Singapore this time."]
[null,null,null,null,15245,"107_Wed Nov 25 2020 06:15:41 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","VSAT antenna upgrading to be carried out","Navigation - Others","Navigation","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","Service technician attended in Singapore and VSAT antenna upgraded."]
[null,null,null,null,15246,"107_Wed Nov 25 2020 06:18:02 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Elevator annual servicing to be carried out","Elect. Mach. & Equip.","Safety / LSA / FFA","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","Service technician attended in Singapore and annual servicing completed ."]
[null,null,null,null,15247,"107_Wed Nov 25 2020 06:20:42 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Life rafts  annual servicing to be carried out","LSA / FFA","Safety / LSA / FFA","Behaviour Based","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","All life rafts are renewed with new types  this time at Singapore."]
[null,null,null,null,15248,"107_Wed Nov 25 2020 06:22:49 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","VSAT & ECDIS cable laying to be carried out","Navigation - ECDIS","Navigation","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","Cable laid  up  during her stay in Singapore."]
[null,null,null,null,15249,"107_Wed Nov 25 2020 06:24:52 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","2nd ECDIS maker FURUNO to be installed  based on owner approval","Navigation - ECDIS","Navigation","Equipment Related","","","","","Action  Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","2nd ECDIS installed on board , Maker: FURUNO, tried out found satisfactory."]
[null,null,null,null,15250,"107_Wed Nov 25 2020 06:48:26 GMT+0000","2020-11-25","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","General inspection and cleaning  of Hull,  flat bottom, vertical side, sea chest, rudder & Propeller","Hull & Tanks","Structural Condn. / WT integrity ","External Factors","","","","","Action Taken","2020-11-30","","Completed","2020-11-29","No","No","No","Internal","Diving company from Big M Marine  Pte Ltd, Singapore  inspected and cleaned up Hull, flat bottom, vertical side, sea chest  , rudder and Propeller.  propeller polished."]
[null,null,null,null,15550,"107_Tue Dec 08 2020 05:52:01 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","New KVH antenna installation:\nNew antenna and pedestal is installed at Singapore.\nDistance piece and pedestal to be \tpainted soonest prior stars rusting. Apply primer and final coat.","Navigation - GMDSS & Communication","Navigation","External Factors","","","","","completed","2020-12-21","","Completed","2020-12-03","No","No","No","Internal","Distance piece and pedestal to be \tpainted soonest prior stars rusting. Apply primer and final coat."]
[null,null,null,null,15551,"107_Tue Dec 08 2020 05:55:15 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Low insulation alarm (Earthing) on Main switch board and  Emergency Switchboard.\n\nFor 110 volts feeder panel observed low insulation on main switch board and emergency switchboard.\nETO need to resolve and clear the low insulation alarm for 110 volts line. It \tshould be close to infinite.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","External Factors","","","","","Some galley equipments no good, repaired.","2020-12-21","","Completed","2020-12-08","No","No","No","Internal","Pls do check the source of low insulation and rectify."]
[null,null,null,null,15552,"107_Tue Dec 08 2020 05:57:41 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","VDR float free (EPIRB) capsule: VDR Float free capsule junction box which is located on aft side of the bridge, bracket is corroded and junction box is just hanging with two bolts.\nNew holding plate to be fitted, apply paint then fit float free EPIRB junction \tbox properly.","Deck - Pipe / Fittings","Navigation","External Factors","","","","","make new bracket and maintannace attention","2020-12-31","","Completed","2020-11-12","No","No","No","Internal","New holding plate to be fitted, apply paint then fit float free EPIRB junction \tbox properly."]
[null,null,null,null,15553,"107_Tue Dec 08 2020 06:00:21 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Old MF/HF ATU unit: Old MF/HF ATU (Antenna coupler) unit is still in place. This is not in use. Remove old ATU unit and dispose.","Elect. Mach. & Equip.","Navigation","External Factors","","","","","completed","2021-12-09","","Completed","2020-12-09","No","No","No","Internal","Pls Remove old ATU unit and dispose."]
[null,null,null,null,15554,"107_Tue Dec 08 2020 06:02:53 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Present MF/HF ATU Unit (On compass deck): New MF/HF ATU unit base plate is corroded and rusted. \nRemove the ATU unit, chip and paint the base plate and fit back the ATU \tunit. Also make sure grounding copper strip is properly fitted to hull and ATU.","Elect. Mach. & Equip.","Navigation","External Factors","","","","","completed","2020-12-31","","Completed","2020-12-05","No","No","No","Internal","Remove the ATU unit, chip and paint the base plate and fit back the ATU \tunit. Also make sure grounding copper strip is properly fitted to hull and ATU."]
[null,null,null,null,15555,"107_Tue Dec 08 2020 06:06:02 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","New Wartsila / Transas SSAS and Tracking system: Refer below photos. ETO has put the ON/OFF switch, this switch actually not \trequire as main battery charger has fuses inside. If it is connected with other equipment then need to secure this switch and DC power cable properly to avoid short circuit in future.","Elect. Mach. & Equip.","General Appearance","External Factors","","","","","completed","2020-12-31","","Completed","2020-12-05","No","No","No","Internal","If  ON/OFF switch  is  not connected with other \tequipment then need to secure this switch and DC power cable properly to \tavoid short circuit in future."]
[null,null,null,null,15556,"107_Tue Dec 08 2020 06:08:35 GMT+0000","2020-11-27","Observation","Ship Staff","Suptd. Insp.","Wi-Fi unit for officer’s recreation room: New LAN cable to be laid from CCR (Chief officer desk) ships network switch till Officer’s recreation room.\nOnce LAN cable is laid and RJ-45 sockets are fitted then shift the Wi-Fi unit \tpresently fitted on D-Deck to Officer’s re-creation room. \nAs per company policy Wi-Fi should be in the Crew and Officer’s re-creation rooms.","Elect. Mach. & Equip.","General Appearance","External Factors","","","","","completed","2020-12-31","","Completed","2020-12-08","No","No","No","Internal","Once LAN cable is laid and RJ-45 sockets are fitted then shift the Wi-Fi unit \tpresently fitted on D-Deck to Officer’s re-creation room."]
[null,null,null,null,15564,"107_Tue Dec 08 2020 08:17:57 GMT+0000","2020-11-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Domestic fridge compressor no. 1 sighted oil level too low and oil charged, same oil separator required to be checked and oil low level alarm to be tested for both the compressors.","E/R - Aux. Mach.","Eng. / Strg. Comp.","External Factors","","","","","Refri.oil top-up, & check, no found any leaking.","2020-12-31","","Completed","2020-12-05","No","No","No","Internal","Pls check the condition of the oil separator and and oil low level alarm to be tested for both the compressors."]
[null,null,null,null,null,"107_Tue Dec 08 2020 07:47:07 GMT+0000","2020-11-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine room supply fan suction nets heavily rusted, same to be de-rusted and painted.","Elect. Mach. & Equip.","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","Supply fan suction to be de-rusted and painted","2021-01-31",null,"Completed","2021-01-03","No",null,null,"Internal"]
[null,null,null,null,15563,"107_Tue Dec 08 2020 07:53:10 GMT+0000","2020-11-29","Defect","Ship Staff","Ship Staff Insp.","No #1  Boiler supply pump  dish press low, new spare pump will be required to supply","E/R - Pumps","Eng. / Strg. Comp.","External Factors","","","","","The completed new pump & motor refitted on position by workshop, test & found ok. Old pump for spare also.","2020-12-31","ANTW205058","Completed","2020-11-29","No","No","No","Internal","New pump sourcing in progress."]
[null,null,null,null,15570,"107_Tue Dec 08 2020 10:34:31 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Port & Stbd bunker station pipes drain lines sighted corroded, same to de-rusted and painted.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","MAINTENANCE PLAN IN PROGRESS","2021-01-31","","Completed","2020-12-13","No","No","No","Internal"]
[null,null,null,null,15572,"107_Tue Dec 08 2020 10:38:01 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Lifeboat davit (P&S) gearbox motor housing corroded, same to be de-rusted and painted.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","Completed de-rusted and painted @ 20201212.","2020-12-31","","Completed","2020-12-12","No","No","No","Internal"]
[null,null,null,null,15573,"107_Tue Dec 08 2020 10:39:34 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency generator room top deck all empty drums to be removed and deck to be painted.","Miscellaneous","General Appearance","External Factors","","","","","Action Required","2020-12-31","","Completed","2020-12-06","No","No","No","Internal"]
[null,null,null,null,15575,"107_Tue Dec 08 2020 10:43:34 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FWG production  too low- Evaporator and condenser to be cleaned","E/R - Aux. Mach.","Eng. / Strg. Comp.","External Factors,Equipment Related","","","","","Chemical cleaned the evaporator / condenser @ 20201222 Richards Bay anchor. Working @ 20201227, but found product little less than when ship ballast condition.","2020-12-31","","Completed","2020-12-22","No","No","No","Internal"]
[null,null,null,null,null,"107_Tue Dec 08 2020 07:49:14 GMT+0000","2020-11-29","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","M/E F.O. viscosity meter assy removed by UNIMARINE and off landed at Singapore for repair.","E/R - Pumps","Eng. / Strg. Comp.","External Factors",null,null,"Not Applicable","Not Applicable","M/E F.O viscosity controller intalled finish.Test not leaking, Now the viscosity controller working at visc control model already.","2021-01-31",null,"Completed","2021-02-23","No",null,null,"Internal"]
[null,null,null,null,15455,"107_7/12/2020 9:10:02 PM","2020-12-03","Defect","Ship Staff","Ship Staff Insp.","Steam pipe connected to EGE soot blowier damaged & broken","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Dec-08th - Pipe renewed.","2021-01-05","","Completed","2020-12-08","No","No","No","Internal"]
[null,null,null,null,14674,"107_Mon Nov 16 2020 11:12:57 GMT+0000","2020-12-07","Defect,Observation","Ship Staff","Ship Staff Insp.","Three (3) mooring winches brake linings are not good, required renewal","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","plan renewal by this month","2020-12-30","","Completed","2020-11-12","No","No","No","Internal"]
[null,null,null,null,15581,"107_12/13/2020 5:06:01 AM","2020-12-12","Observation","Ship Staff","Ship Staff Insp.","Digital books ENP just have software, due to ship signal poor, not able to download digital books and IMO digital books does not have books license and need books list","Navigation - Others","Navigation","Inappropriate Procedure","","","","","we need shore download books send to ship NAVBOX","2020-12-25","","Completed","2020-12-16","No","No","No","Internal"]
[null,null,null,null,15582,"107_12/13/2020 11:31:33 AM","2020-12-12","Observation","Ship Staff","Ship Staff Insp.","BNWAS: Bracket  of control devices which is located on starboard side of the bridge, bracket is corroded and damage New holding plate to be fitted, apply paint then fit box properly.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","External Factors","","","","","New holding plate to be fitted, apply paint then fit box properly.","2020-12-25","","Completed","2020-12-17","No","No","No","Internal"]
[null,null,null,null,null,"107_31/12/2020 4:13:02 AM","2020-12-12","Observation","Ship Staff","Ship Staff Insp.","Digital books ENP just have software, due to ship signal poor, not can be download digital books and IMO digital books no have books license and need books list)","Navigation - Others","Navigation","Equipment Related",null,null,"Not Applicable","Not Applicable","COMPLETED DOWNLOAD","2021-01-31",null,"Completed","2021-01-01","No",null,null,"Internal"]
[null,null,null,null,null,"107_31/12/2020 4:18:21 AM","2020-12-12","Observation","Ship Staff","Ship Staff Insp.","BNWAS: Bracket of control devices which is located on starboard side of the bridge, bracket is corroded and damage New holding plate to be fitted, apply paint then fit box properly.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","External Factors",null,null,"Not Applicable","Not Applicable","Will fabricated newly bracket etc.","2021-01-31",null,"Completed","2021-03-01","No",null,null,"Internal"]
[null,null,null,null,null,"107_2/2/2021 11:00:20 PM","2021-02-01","Observation","Ship Staff","Ship Staff Insp.","No6 hatch cover can't opened by fixing hyd.pump.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","Raised spare requisition ANTW215029. Try to adjust the safety valve of pump. Can operate No6 hatch cover. Renewed the pump when receipt.","2021-03-31","Waiting spare requisition ANTW215029.","Completed","2021-03-20","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["107","ANTWERP (31-12-2020)","107_1610604945956.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]