{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":5,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":48,"n_cols":28,"rows_kept":48,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","09-Mar-2022",null,null,"Ship Name","ANTWERP (09-03-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,14667,"107_Mon Nov 16 2020 10:58:32 GMT+0000","2021-01-11","Defect","Ship Staff","Ship Staff Insp.","Main engine RHRS counter and REV counter are Not working. Total ME RHRS on 9th Sept'21 is 98251 which recorded manually. Recorded Date changed as spares not rec'd . Actual date 9th Sept'21","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","T/C Rev counter renewed with a spare rec'd. ME Rev counter as well as RHRS counter to be renewed after receiving the spares","2022-03-31","ANTW215012","Waiting spare",null,"No","No","No","Internal","will supply in convenient port, please update spare receiving status"]
[null,null,null,null,14671,"107_Mon Nov 16 2020 11:06:02 GMT+0000","2021-01-11","Defect","Ship Staff","Ship Staff Insp.","No.1 HFO purifier temp control valve malfunctioning. No.2 HFO Purifier Temp. controller complete device found missing. Recorded Date changed as spares not rec'd . Actual date 9th Sept'21","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","#1 FO PFR control valve mechanism not moving freely . Planning to overhaul at the earliest. New Controller to be fitted for #2 HFO controller as per office Instruction. IMA worked in DD on #1 HFO temp cont. valve. But Problem not solved","2022-03-31","ANTW210188","Waiting spare",null,"No","No","No","Internal","Please  do check and  advise  in details what is the problem. on the temp control valve."]
[null,null,null,null,21887,"107_15/10/2021 23:40:25","2021-01-11","Defect","Ship Staff","Ship Staff Insp.","ME and DG Viscosity controller.malfunction. Recorded Date changed as spares not rec'd . Actual date 22 Sept' Sept'21","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Service requisition has been made.\n\nIMA staffs attended in DD. But not working. Presently temp. is being controlled manually. Office has been informed with the details.","2022-03-31","ANTW210178","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,21891,"107_15/10/2021 23:16:05","2021-01-11","Non Conformity","Ship Staff","Ship Staff Insp.","Commutator in Galley found missing. Recorded Date changed as spares not rec'd . Actual date 29th Sept'21","Accommodation","MARPOL Related","Equipment Related","","","","","Waiting for spare.","2022-03-31","ANTW210166","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,23825,"107_2/1/2022 5:09:54 PM","2021-01-12","Observation","Ship Staff","Ship Staff Insp.","ME Liner Measuring tool Missing","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Searched in all Spare / Store and other locations in ER. Office was notified. Requition made as per office advise.","2022-03-31","ANTW220030","Waiting spare",null,"No","No","No","Internal","will process RO and supply in convenient port"]
[null,null,null,null,23827,"107_2/1/2022 5:34:01 PM","2021-01-12","Defect","Ship Staff","Ship Staff Insp.","#2 DG , #4 unit Fuel Pump connecting pipe Arm seat surface worn down / leaking","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Tried lapping the surface. But unable to get proper sealing. Requisition raised for new spare. Still we are tyrying to lap and rectify.","2022-03-31","ANTW220004","Waiting spare",null,"No","No","No","Internal","will supply spare in next convenient port"]
[null,null,null,null,15569,"107_Tue Dec 08 2020 10:33:21 GMT+0000","2021-08-15","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Main deck, cross decks, poop decks and forecastle deck sighted scattered spot rust, same to be hydro blasted and painted.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","Work in progress, as given priority to hold cleaning/washing","2022-03-30","","In progress",null,"No","No","No","Internal","Vsl to keep office updated with weekly reporting for maintenance progress."]
[null,null,null,null,15559,"107_Tue Dec 08 2020 07:45:26 GMT+0000","2021-08-31","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Deck air lines sighted corroded in various places, all corroded pipes to be renewed.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","Work is in progress","2022-03-30","ANTW210015.","In progress",null,"Yes","No","No","Internal","please update status"]
[null,null,null,null,23119,"107_14/12/2021 14:57:23","2021-09-12","Defect","Ship Staff","Ship Staff Insp.","FO Bunker Tank STBD filling valve is too tight to operate","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","Removed the valve and noticed gear ass'y broken. No spare on-board. requisition made. ","2022-03-31","ANTW220012","Waiting spare",null,"No","No","No","Internal","please carry out and update."]
[null,null,null,null,20169,"107_7/14/2021 8:31:57 PM","2021-10-08","Observation","Ship Staff","Ship Staff Insp.","NO.2-5 hatch coaming scattered spot rust should be hydro blasted and painted","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","Work in progress","2022-03-30","","In progress",null,"No","No","No","Internal","please carry out as plan and keep update"]
[null,null,null,null,23120,"107_14/12/2021 15:43:12","2021-10-12","Critical Equipment","Ship Staff","Ship Staff Insp.","Auto STBY Pump starting not happening for ME LO Pump, Cam Shaft LO Pump and MCSW Pump.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Few Pumps control devices repaired and made operational. Requisition will be raised for faulty pumps control PCB.","2022-03-31","ANTW220001","Waiting spare",null,"No","No","No","Internal","please check and confirm. raise RO if required"]
[null,null,null,null,22774,"107_11/30/2021 10:49:21 PM","2021-11-11","Defect","Ship Staff","Ship Staff Insp.","ME JACKET COOLING WATER TEMPERATURE CONTROLER NOT WORKING","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","REQUISITION MADE . WILL BE RENEWED AFTER SPARE SUPPLY","2022-03-31","ANTW210189","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,22776,"107_11/30/2021 10:53:59 PM","2021-11-14","Defect","Ship Staff","Ship Staff Insp.","ME FO SERV. TANK TEMP. CONTROLLER FOR STEAM VALVE NOT WORKING","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","PRESENTLY TEMPERATURE CONTROL MANUALLY","2022-03-31","ANTW210190","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,20606,"107_8/15/2021 12:55:44","2021-11-15","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","BRIDGE WINDOW WIPER 2 OF 3 OUT OF ORDER","Navigation - Others","Navigation","Equipment Related","","","","","Rec'd only spare Motors (Reqn. partially). Need rail and V-Belt. Details were sent to the office during Dry Dock along with the Pictures and Drawing. Waiting for spares","2022-03-31","ANTW210119","Waiting spare",null,"Yes","No","No","Internal","spare will supply in convenient port"]
[null,null,null,null,22777,"107_11/30/2021 11:26:54 PM","2021-11-19","Defect","Ship Staff","Ship Staff Insp.","HFO SETT. & SERV. TANK LEVEL GAUGE NOT WORKING","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","GAUGES WILL BE RENEWED AFTER SUPPLY","2022-03-31","ANTW210201","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,22778,"107_11/30/2021 11:30:50 PM","2021-11-21","Defect","Ship Staff","Ship Staff Insp.","EMERGENCY GENERATOR HYDRAULIC STARTER SYSTEM MALFUNCTION","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","REQUISITION MADE FOR SPARE KIT AND STARTER","2022-03-31","ANTW210198","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,23122,"107_12/15/2021 7:39:49 PM","2021-12-12","Defect","Ship Staff","Ship Staff Insp.","Port Steering Gear Pump Oil Seal leaking. (Pls. note this issue is there since Dry Dock Sept'21)","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Requisition made for Seal and other consumable for rectification. Presently made an arrangement to collect the leaky Oil","2022-03-31","ANTW210200","Waiting spare",null,"No","No","No","Internal","will supply spare in convenient port"]
[null,null,null,null,23125,"107_14/12/2021 15:18:54","2021-12-13","Defect","Ship Staff","Ship Staff Insp.","Sewage Holding Tank level Gauge is not working","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Planning to open and check the internal mechanism, then will do rectification as required. If not possible to repair, will raise requisition for new gauge.","2022-03-31","ANTW220003","Waiting spare",null,"No","No","No","Internal","spare will supply in convenient port"]
[null,null,null,null,23130,"107_14/12/2021 17:01:36","2021-12-14","Observation","Ship Staff","Ship Staff Insp.","AE1 RPM Indicator at the Engine side shows lesser (700) than rated RPM (900)","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Tried with new Tacho meter and cable. still it is showing the error. Requisition made for driving gear","2022-03-31","ANTW220004","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,23348,"107_1/1/2022 5:14:21 PM","2022-01-01","Defect","Ship Staff","Ship Staff Insp.","DG D.O. Pump mechanical seal leaking","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","As there is no spare seal onboard requisition has been sent","2022-03-31","ANTW220004","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,23349,"107_1/1/2022 7:42:18 PM","2022-01-01","Defect","Ship Staff","Ship Staff Insp.","Gang way Motor (S) not holding in its position","Deck - Machinery","General Appearance","Equipment Related","","","","","Replaced with an overhauled spare Motor. Spare requisition has been sent to overhaul the faulty Motor.","2022-03-31","ANTW220010","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,23350,"107_1/1/2022 7:46:48 PM","2022-01-01","Defect","Ship Staff","Ship Staff Insp.","Hydro Blaster triggering pressure fluctuate","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","Already overhauled. Triggering control valve is very sensitive. Still some time misoperate and the pressure rises more than 1000 Bar. Requisition made for trigger gun.","2022-03-31","ANTW220009","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,23478,"107_1/14/2022 4:07:30 PM","2022-01-01","Defect","Ship Staff","Ship Staff Insp.","Boiler FO low Pr. Change over Pr. Switch faulty","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","spare not available, made requisition.","2022-03-31","ANTW220029","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,23479,"107_1/14/2022 4:15:01 PM","2022-01-01","Defect","Ship Staff","Ship Staff Insp.","Foam Nozzle leak due to damaged valves in SG room","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Requisition sent","2022-02-28","ANTW220057","Waiting spare",null,"No","No","No","Internal","job still pending? if completed please fill up complete date and close the defect"]
[null,null,null,null,23828,"107_2/1/2022 5:13:21 PM","2022-01-17","Defect","Ship Staff","Ship Staff Insp.","Boiler Chemical Dosing Pump inoperational","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Opened, checked and tried to overhaul. But not successful. Requisition raised as the Drew insist to dosing through pump only.","2022-03-31","ANTW200029","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,23829,"107_2/1/2022 4:53:26 PM","2022-01-19","Defect","Ship Staff","Ship Staff Insp.","Accom. AC control system, compressor and Motor Performance is abnormal","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Fitted toggle switch for 75 %. Still AC behaves quite abnormal after 50%. Raised requisition for Complete Motor and Compressor. Also making req. for consumables.","2022-03-31","ANTW220006, ANTW220008","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,23831,"107_2/1/2022 5:25:13 PM","2022-01-22","Defect","Ship Staff","Ship Staff Insp.","#2 Boiler circulating Pump Seal leaking","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","No spare onboard. Requisition made","2022-03-31","ANTW200029","Waiting spare",null,"No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,23832,"107_2/1/2022 5:42:41 PM","2022-01-23","Defect","Ship Staff","Ship Staff Insp.","ME and DG auto Back wash Filter operating mechanism not functioning on Auto","E/R - Aux. Engine,E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Operartion checked and confirmed. Gear arrangements found to be worn out. Requisition made.","2022-03-31","ANTW220045","Waiting spare",null,"No","No","No","Internal","will supply in next convenient port"]
[null,null,null,null,23957,"107_2/16/2022 3:22:30 PM","2022-02-14","Defect","Ship Staff","Ship Staff Insp.","#2 Cyl. L.O. Pump Oil Seal Leak","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Already located spare. Will be done at 1st oppertunity.","2022-03-29","","In progress",null,"No","No","No","Internal","please carry out and update"]
[null,null,null,null,23961,"107_2/16/2022 3:28:42 PM","2022-02-15","Observation","Ship Staff","Ship Staff Insp.","Waste oil Sounding and DO settling tank Sounding Pipes are chocked. Improper quantity measurement.","Hull & Tanks","Eng. / Strg. Comp.","Equipment Related","","","","","Checked Waste oil tank. There is a huge rock sought of sludge all around sounding pipe. Need to plan and do complete cleaning of the tank. D.O. settling tank sounding pipe cleared. ","2022-03-30","","In progress",null,"No","No","No","Internal","please carry out and update"]
[null,null,null,null,23959,"107_2/16/2022 2:55:52 PM","2022-03-02","Defect","Ship Staff","Suptd. Insp.","UMS Mode Inoperational","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","This defect is mentioned by DPA. Various defects on automation such as STBY pump not changing over, various temp. controller non-operational and few more automation not workings to be solved before making ER UMS.","2022-05-30","ANTW220001, ANTW220045, ANTW220014","In progress",null,"No","No","No","Internal","will supply spare as raised RO in next convenient port"]

{"sheet":"Completed","index":1,"n_rows":142,"n_cols":28,"rows_kept":142,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","09-Mar-2022",null,null,"Ship Name","ANTWERP (09-03-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,14664,"107_Mon Nov 16 2020 10:52:14 GMT+0000","2020-01-12","Observation","Ship Staff","Ship Staff Insp.","VDR display shows radar alert alarm sometimes.","Navigation - VDR / BNWAS","Communication","Equipment Related","","","","","already completed ","2020-12-15","","Completed","2020-01-12","No","No","No","Internal","Pls do check and find out the cause of alarms on the VDR display  monitor"]
[null,null,null,null,14673,"107_Mon Nov 16 2020 11:11:18 GMT+0000","2020-01-12","Observation","Ship Staff","Ship Staff Insp.","Port side windlass brake lining  required renewal","Deck - Mooring Machinery","General Appearance","Equipment Related","","","","","REPLACE BY DD","2021-06-04","ANTW200013","Completed","2021-09-05","Yes","No","No","Internal","please update status due to docking under extend to Sep 2021"]
[null,null,null,null,15571,"107_Tue Dec 08 2020 10:36:12 GMT+0000","2020-03-03","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel painting faded, same to be painted with designated LOGO.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","Completed forward, portside & stbdside painting jobs.behind side will be complete when D-Docking.","2021-06-01","","Completed","2021-06-23","No","No","No","Internal","will do it during docking under extend to Sep 2021"]
[null,null,null,null,15566,"107_Tue Dec 08 2020 08:23:49 GMT+0000","2020-03-17","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port Windlass: Outer drum bush is badly worn – requires to be renewed soonest to avoid shaft damage. Main shaft bearing is badly worn out which causing excessive shaft movement.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","oVERHAULED IN DRY DOCK","2021-06-09","","Completed","2021-09-09","Yes","No","No","Internal","Pls  check spare R.O.B  and submit R.O. for the spare parts if require."]
[null,null,null,null,14666,"107_Mon Nov 16 2020 10:56:19 GMT+0000","2020-11-16","Observation","Ship Staff","Ship Staff Insp.","Main engine Alpha lub station pump no.1 pipe connection leaking","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Try one more to retighten again, no leaking now","2021-01-31","","Completed","2021-01-30","No","No","No","Internal","Pls  do rectify as soon as possible."]
[null,null,null,null,14670,"107_Mon Nov 16 2020 11:04:36 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","Steering gear no. 1& 2 hyd pump oil seal  found leaking excessively","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Shore service engineers on board for repair @ Sgp 2020-11-27~30. Now new problem are leaking from shaft seal of rudder angle. So suugest to close this & writen new.","2020-12-31","ANTW205043","Completed","2020-11-30","No","No","No","Internal","Pls submit requisition for spare parts"]
[null,null,null,null,14675,"107_Mon Nov 16 2020 11:14:20 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","Hatch covers hydraulic pipes corroded and leaking in various locations, required renewal and press test","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Some pipe renewed by crew already.","2020-12-30","","Completed","2020-12-03","No","No","No","Internal","Leaky pipes renewed. Pls  submit RO of the  required pipes & fittings ."]
[null,null,null,null,14676,"107_Mon Nov 16 2020 11:15:46 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","ME Lub oil purifier supply pump  are  not working","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Electrical power supply issue was solved and made operational. ","2021-09-04","ANTW-007-2021","Completed","2021-09-09","No","No","No","Internal","Pls do check and plan to overhaul pump if required."]
[null,null,null,null,14677,"107_Mon Nov 16 2020 11:18:05 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","M/E lube oil stand by  pump  found starting auto but no alert alarm activated in ECR panel","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","\"cyclect\" engineers on board for check, test, later supplied 3+7pcs contactor & renewed by crew. Test & found normal, but found some problem after sail again. So closed this & writen other later.","2021-01-15","ANWT205042, 205054.","Completed","2020-11-29","No","No","No","Internal","Pls advise which pump contactor are having problem now."]
[null,null,null,null,14678,"107_Mon Nov 16 2020 11:19:28 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","M/E JCFW  stand by  pump  found starting auto but no alert alarm activated in ECR panel","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Same than ME LO pump","2021-01-15","ANWT205042, 205054","Completed","2020-11-29","No","No","No","Internal","Pls  renew contactor after receiving spare."]
[null,null,null,null,14679,"107_Mon Nov 16 2020 11:20:54 GMT+0000","2020-11-16","Defect,Observation","Ship Staff","Ship Staff Insp.","Provision crane hydraulic piping  condition not good, required renewal","Deck - Machinery","Eng. / Strg. Comp.","Equipment Related","","","","","Renewed many soft hose by workshop personal & some can't renewed due to old connector welding by previous crew. these hose stay on board for spare.","2021-06-04","ANTW205043","Completed","2021-09-07","No","No","No","Internal","Pls renew if spare pipe available or submit requisition."]
[null,null,null,null,14680,"107_Mon Nov 16 2020 11:22:28 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","Hypermist HP pump press gauge  is not working","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","The spare come on board,We intalled finish.Now is good.","2021-02-28","ANTW 205078","Completed","2021-01-29","No","No","No","Internal","Pls order new press gauge if not available onboard."]
[null,null,null,null,14681,"107_Mon Nov 16 2020 11:24:05 GMT+0000","2020-11-16","Other","Ship Staff","Ship Staff Insp.","There was no ODS & Suphur content record book found on board","Documentation","Cert. & Docu.","Equipment Related","","","","","SI bring 2books - Bunker sample & SECA FCO record book on board 20-Nov-2020 ( Incluclinding S%). Re ODS office have standard \"word\" file.","2020-12-16","","Completed","2020-11-30","No","No","No","Internal",""]
[null,null,null,null,14682,"107_Mon Nov 16 2020 11:25:29 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","Aux boiler feed water automatic  control valve  not working","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Crew adjusted already. Service on board when call SIN 27-Nov also.","2020-12-16","ANTW205033","Completed","2020-11-29","No","No","No","Internal","Automatic control feed valve function  tried out during boiler health check by  service technicians."]
[null,null,null,null,14683,"107_Mon Nov 16 2020 11:26:38 GMT+0000","2020-11-16","Defect","Ship Staff","Ship Staff Insp.","A/E & M/E FO  back wash  filters are  leaking thru the gland","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Retighten the connecting flanges after dismantled the Viscosity units..","2020-12-31","","Completed","2020-12-05","No","No","No","Internal","Pls submit R.O. for necessary repair kits."]
[null,null,null,null,15233,"107_Wed Nov 25 2020 05:49:34 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","Exhaust Gas Economizer soot blower two sets valves  are seized, require to be made operational.","E/R - Boiler,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","Action taken","2020-12-15","","Completed","2020-12-01","No","No","No","Internal","Faulty soot blower (aft ) dismantled, overhauled and fitted back. by shore technicians at Singapore. Tried out found satisfactory."]
[null,null,null,null,15234,"107_Wed Nov 25 2020 05:52:02 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Oily Water Separator 15 ppm alarm and Three way valves functioning to be checked. OWS damage pipes to be renewed.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Action  taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","15 ppm OCM renewed and 3-way valve function tested along with the alarms. found satisfactory.  Damage pipes renewed."]
[null,null,null,null,15235,"107_Wed Nov 25 2020 05:53:40 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","HFO Purifier  No. 1 and  M/E L.O. purifier are not working","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","HFO purifier No.1 and ME L.O. purifier   health check carried out  and  tried out satisfactorily by shore technician at singapore."]
[null,null,null,null,15236,"107_Wed Nov 25 2020 05:55:41 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Aux boiler combustion control system health check required to be carried out","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Action  Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","Aux Boiler combustion control system health checks carried out at  Singapore this time by shore technicians."]
[null,null,null,null,15238,"107_Wed Nov 25 2020 05:59:27 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","Incinerator failed to fire with Waste oil","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","Trouble shooting carried out and Waste oil pump overhauled, tried out-found satisfactory."]
[null,null,null,null,15239,"107_Wed Nov 25 2020 06:01:46 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","Accommodation A/C compressor required to be overhaul as no record from previous owners","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Job attended by Breeze in DD, problem was with one expansion valve, same replaced, compressor is in order","2021-04-06","ANTW 205045 rcvd on board @ 20201129SIN.","Completed","2021-04-09","Yes","No","No","Internal","To overhaul the compressor during DD."]
[null,null,null,null,15240,"107_Wed Nov 25 2020 06:04:23 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","Aux engine no. 1 &  2 running hours counter not working","Elect. Mach. & Equip.","Eng. / Strg. Comp.","External Factors","","","","","Rectified in Dry Dock","2021-06-04","ANTW 205079","Completed","2021-09-09","No","No","No","Internal","will supply in next convenient port"]
[null,null,null,null,15243,"107_Wed Nov 25 2020 06:11:18 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Ballast control  system   04 nos valves are show error from cargo control room","Deck - Pipe / Fittings","Eng. / Strg. Comp.","Equipment Related","","","","","The spare was  supply on S.G.P .Ballast control system 2 sets valve renewed.Now all valve show( indictor) is normal.","2021-05-31","Exchanged by ANTW215053.","Completed","2021-05-18","No","No","No","Internal","Service technicians attended at Singapore. Pls test the valves operation and advise."]
[null,null,null,null,15244,"107_Wed Nov 25 2020 06:13:48 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","VDR and Navigation equipment health check to be carried out.","Elect. Mach. & Equip.,Navigation - VDR / BNWAS","Communication","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","VDR and Navigation equipment's health check carried out  by Service technician  at  Singapore this time."]
[null,null,null,null,15245,"107_Wed Nov 25 2020 06:15:41 GMT+0000","2020-11-25","Defect","Ship Staff","Ship Staff Insp.","VSAT antenna upgrading to be carried out","Navigation - Others","Navigation","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","Service technician attended in Singapore and VSAT antenna upgraded."]
[null,null,null,null,15246,"107_Wed Nov 25 2020 06:18:02 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Elevator annual servicing to be carried out","Elect. Mach. & Equip.","Safety / LSA / FFA","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","Service technician attended in Singapore and annual servicing completed ."]
[null,null,null,null,15247,"107_Wed Nov 25 2020 06:20:42 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","Life rafts  annual servicing to be carried out","LSA / FFA","Safety / LSA / FFA","Behaviour Based","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","All life rafts are renewed with new types  this time at Singapore."]
[null,null,null,null,15248,"107_Wed Nov 25 2020 06:22:49 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","VSAT & ECDIS cable laying to be carried out","Navigation - ECDIS","Navigation","Equipment Related","","","","","Action Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","Cable laid  up  during her stay in Singapore."]
[null,null,null,null,15249,"107_Wed Nov 25 2020 06:24:52 GMT+0000","2020-11-25","Observation","Ship Staff","Ship Staff Insp.","2nd ECDIS maker FURUNO to be installed  based on owner approval","Navigation - ECDIS","Navigation","Equipment Related","","","","","Action  Taken","2020-12-10","","Completed","2020-11-30","No","No","No","Internal","2nd ECDIS installed on board , Maker: FURUNO, tried out found satisfactory."]
[null,null,null,null,15250,"107_Wed Nov 25 2020 06:48:26 GMT+0000","2020-11-25","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","General inspection and cleaning  of Hull,  flat bottom, vertical side, sea chest, rudder & Propeller","Hull & Tanks","Structural Condn. / WT integrity ","External Factors","","","","","Action Taken","2020-11-30","","Completed","2020-11-29","No","No","No","Internal","Diving company from Big M Marine  Pte Ltd, Singapore  inspected and cleaned up Hull, flat bottom, vertical side, sea chest  , rudder and Propeller.  propeller polished."]
[null,null,null,null,15550,"107_Tue Dec 08 2020 05:52:01 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","New KVH antenna installation:\nNew antenna and pedestal is installed at Singapore.\nDistance piece and pedestal to be \tpainted soonest prior stars rusting. Apply primer and final coat.","Navigation - GMDSS & Communication","Navigation","External Factors","","","","","completed","2020-12-21","","Completed","2020-12-03","No","No","No","Internal","Distance piece and pedestal to be \tpainted soonest prior stars rusting. Apply primer and final coat."]
[null,null,null,null,15551,"107_Tue Dec 08 2020 05:55:15 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Low insulation alarm (Earthing) on Main switch board and  Emergency Switchboard.\n\nFor 110 volts feeder panel observed low insulation on main switch board and emergency switchboard.\nETO need to resolve and clear the low insulation alarm for 110 volts line. It \tshould be close to infinite.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","External Factors","","","","","Some galley equipments no good, repaired.","2020-12-21","","Completed","2020-12-08","No","No","No","Internal","Pls do check the source of low insulation and rectify."]
[null,null,null,null,15552,"107_Tue Dec 08 2020 05:57:41 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","VDR float free (EPIRB) capsule: VDR Float free capsule junction box which is located on aft side of the bridge, bracket is corroded and junction box is just hanging with two bolts.\nNew holding plate to be fitted, apply paint then fit float free EPIRB junction \tbox properly.","Deck - Pipe / Fittings","Navigation","External Factors","","","","","make new bracket and maintannace attention","2020-12-31","","Completed","2020-11-12","No","No","No","Internal","New holding plate to be fitted, apply paint then fit float free EPIRB junction \tbox properly."]
[null,null,null,null,15553,"107_Tue Dec 08 2020 06:00:21 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Old MF/HF ATU unit: Old MF/HF ATU (Antenna coupler) unit is still in place. This is not in use. Remove old ATU unit and dispose.","Elect. Mach. & Equip.","Navigation","External Factors","","","","","completed","2021-12-09","","Completed","2020-12-09","No","No","No","Internal","Pls Remove old ATU unit and dispose."]
[null,null,null,null,15554,"107_Tue Dec 08 2020 06:02:53 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Present MF/HF ATU Unit (On compass deck): New MF/HF ATU unit base plate is corroded and rusted. \nRemove the ATU unit, chip and paint the base plate and fit back the ATU \tunit. Also make sure grounding copper strip is properly fitted to hull and ATU.","Elect. Mach. & Equip.","Navigation","External Factors","","","","","completed","2020-12-31","","Completed","2020-12-05","No","No","No","Internal","Remove the ATU unit, chip and paint the base plate and fit back the ATU \tunit. Also make sure grounding copper strip is properly fitted to hull and ATU."]
[null,null,null,null,15555,"107_Tue Dec 08 2020 06:06:02 GMT+0000","2020-11-27","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","New Wartsila / Transas SSAS and Tracking system: Refer below photos. ETO has put the ON/OFF switch, this switch actually not \trequire as main battery charger has fuses inside. If it is connected with other equipment then need to secure this switch and DC power cable properly to avoid short circuit in future.","Elect. Mach. & Equip.","General Appearance","External Factors","","","","","completed","2020-12-31","","Completed","2020-12-05","No","No","No","Internal","If  ON/OFF switch  is  not connected with other \tequipment then need to secure this switch and DC power cable properly to \tavoid short circuit in future."]
[null,null,null,null,15556,"107_Tue Dec 08 2020 06:08:35 GMT+0000","2020-11-27","Observation","Ship Staff","Suptd. Insp.","Wi-Fi unit for officer’s recreation room: New LAN cable to be laid from CCR (Chief officer desk) ships network switch till Officer’s recreation room.\nOnce LAN cable is laid and RJ-45 sockets are fitted then shift the Wi-Fi unit \tpresently fitted on D-Deck to Officer’s re-creation room. \nAs per company policy Wi-Fi should be in the Crew and Officer’s re-creation rooms.","Elect. Mach. & Equip.","General Appearance","External Factors","","","","","completed","2020-12-31","","Completed","2020-12-08","No","No","No","Internal","Once LAN cable is laid and RJ-45 sockets are fitted then shift the Wi-Fi unit \tpresently fitted on D-Deck to Officer’s re-creation room."]
[null,null,null,null,15558,"107_Tue Dec 08 2020 07:43:47 GMT+0000","2020-11-28","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Deck hydraulic pipes for hatch cover corroded in various places, all pipes to be press tested and leaky pipes to be renewed.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","All wasted/corroded Hydraulic line on deck replaced with new pipes in DD","2021-05-30","ANWT210015.","Completed","2021-03-09","Yes","No","No","Internal","keep upgrading to bring up vessel performance"]
[null,null,null,null,15560,"107_Tue Dec 08 2020 07:47:07 GMT+0000","2020-11-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine room supply fan suction nets heavily rusted, same to be de-rusted and painted.","Elect. Mach. & Equip.","General Appearance","External Factors","","","","","Supply fan suction to be de-rusted and painted","2021-01-31","","Completed","2021-01-03","No","No","No","Internal"]
[null,null,null,null,15564,"107_Tue Dec 08 2020 08:17:57 GMT+0000","2020-11-28","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Domestic fridge compressor no. 1 sighted oil level too low and oil charged, same oil separator required to be checked and oil low level alarm to be tested for both the compressors.","E/R - Aux. Mach.","Eng. / Strg. Comp.","External Factors","","","","","Refri.oil top-up, & check, no found any leaking.","2020-12-31","","Completed","2020-12-05","No","No","No","Internal","Pls check the condition of the oil separator and and oil low level alarm to be tested for both the compressors."]
[null,null,null,null,15561,"107_Tue Dec 08 2020 07:49:14 GMT+0000","2020-11-29","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","M/E F.O. viscosity meter assy removed by UNIMARINE and off landed at Singapore for repair.","E/R - Pumps","Eng. / Strg. Comp.","External Factors","","","","","M/E F.O viscosity controller intalled finish.Test not leaking, Now the viscosity controller working at visc control model already.","2021-01-31","","Completed","2021-02-23","No","No","No","Internal","Viscosity controller pump unit overhauled  at Singapore and  received  vessel At Fujairah on 28 Jan 2021. Pls fit back & try out."]
[null,null,null,null,15563,"107_Tue Dec 08 2020 07:53:10 GMT+0000","2020-11-29","Defect","Ship Staff","Ship Staff Insp.","No #1  Boiler supply pump  dish press low, new spare pump will be required to supply","E/R - Pumps","Eng. / Strg. Comp.","External Factors","","","","","The completed new pump & motor refitted on position by workshop, test & found ok. Old pump for spare also.","2020-12-31","ANTW205058","Completed","2020-11-29","No","No","No","Internal","New pump sourcing in progress."]
[null,null,null,null,15570,"107_Tue Dec 08 2020 10:34:31 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Port & Stbd bunker station pipes drain lines sighted corroded, same to de-rusted and painted.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","MAINTENANCE PLAN IN PROGRESS","2021-01-31","","Completed","2020-12-13","No","No","No","Internal"]
[null,null,null,null,15572,"107_Tue Dec 08 2020 10:38:01 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Lifeboat davit (P&S) gearbox motor housing corroded, same to be de-rusted and painted.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","Completed de-rusted and painted @ 20201212.","2020-12-31","","Completed","2020-12-12","No","No","No","Internal"]
[null,null,null,null,15573,"107_Tue Dec 08 2020 10:39:34 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency generator room top deck all empty drums to be removed and deck to be painted.","Miscellaneous","General Appearance","External Factors","","","","","Action Required","2020-12-31","","Completed","2020-12-06","No","No","No","Internal"]
[null,null,null,null,15575,"107_Tue Dec 08 2020 10:43:34 GMT+0000","2020-11-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FWG production  too low- Evaporator and condenser to be cleaned","E/R - Aux. Mach.","Eng. / Strg. Comp.","External Factors,Equipment Related","","","","","Chemical cleaned the evaporator / condenser @ 20201222 Richards Bay anchor. Working @ 20201227, but found product little less than when ship ballast condition.","2020-12-31","","Completed","2020-12-22","No","No","No","Internal"]
[null,null,null,null,15455,"107_7/12/2020 9:10:02 PM","2020-12-03","Defect","Ship Staff","Ship Staff Insp.","Steam pipe connected to EGE soot blowier damaged & broken","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Dec-08th - Pipe renewed.","2021-01-05","","Completed","2020-12-08","No","No","No","Internal"]
[null,null,null,null,14674,"107_Mon Nov 16 2020 11:12:57 GMT+0000","2020-12-07","Defect,Observation","Ship Staff","Ship Staff Insp.","Three (3) mooring winches brake linings are not good, required renewal","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","plan renewal by this month","2020-12-30","","Completed","2020-11-12","No","No","No","Internal"]
[null,null,null,null,16300,"107_31/12/2020 4:13:02 AM","2020-12-12","Observation","Ship Staff","Ship Staff Insp.","Digital books ENP just have software, due to ship signal poor, not can be download digital books and IMO digital books no have books license and need books list)","Navigation - Others","Navigation","Equipment Related","","","","","COMPLETED DOWNLOAD","2021-01-31","","Completed","2021-01-01","No","No","No","Internal"]
[null,null,null,null,16302,"107_31/12/2020 4:18:21 AM","2020-12-12","Observation","Ship Staff","Ship Staff Insp.","BNWAS: Bracket of control devices which is located on starboard side of the bridge, bracket is corroded and damage New holding plate to be fitted, apply paint then fit box properly.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","External Factors","","","","","Will fabricated newly bracket etc.","2021-01-31","","Completed","2021-03-01","No","No","No","Internal"]
[null,null,null,null,15581,"107_12/13/2020 5:06:01 AM","2020-12-12","Observation","Ship Staff","Ship Staff Insp.","Digital books ENP just have software, due to ship signal poor, not able to download digital books and IMO digital books does not have books license and need books list","Navigation - Others","Navigation","Inappropriate Procedure","","","","","we need shore download books send to ship NAVBOX","2020-12-25","","Completed","2020-12-16","No","No","No","Internal"]
[null,null,null,null,15582,"107_12/13/2020 11:31:33 AM","2020-12-12","Observation","Ship Staff","Ship Staff Insp.","BNWAS: Bracket  of control devices which is located on starboard side of the bridge, bracket is corroded and damage New holding plate to be fitted, apply paint then fit box properly.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","External Factors","","","","","New holding plate to be fitted, apply paint then fit box properly.","2020-12-25","","Completed","2020-12-17","No","No","No","Internal"]
[null,null,null,null,14684,"107_Mon Nov 16 2020 11:28:17 GMT+0000","2021-01-11","Observation","Ship Staff","Ship Staff Insp.","Port Windlass unable to heave up Anchor cable at 4 shackles on Deck. Recorded Date changed as spares not rec'd . Actual date 27th Sept'21","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Hyd Motor renewed. Working Better. one New Block found in Midship Store. Same replaced and noticed working well. Non similar one landed in ingapore for replacement.","2022-01-31","ANTW210144","Completed","2022-12-01","No","No","No","Internal","Pls update spare receiving status and get the job done ASAP"]
[null,null,null,null,23962,"107_2/16/2022 3:43:49 PM","2021-01-12","Defect","Ship Staff","Ship Staff Insp.","SLUDEG PUMP SAFETY VALVE INOPERATIONAL","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Overhauled","2022-03-30","","Completed","2021-05-12","No","No","No","Internal"]
[null,null,null,null,18325,"107_2/2/2021 11:00:20 PM","2021-02-01","Observation","Ship Staff","Ship Staff Insp.","No6 hatch cover can't opened by fixing hyd.pump.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Raised spare requisition ANTW215029. Try to adjust the safety valve of pump. Can operate No6 hatch cover. Renewed the pump when receipt.","2021-03-31","Waiting spare requisition ANTW215029.","Completed","2021-03-20","No","No","No","Internal"]
[null,null,null,null,15562,"107_Tue Dec 08 2020 07:50:58 GMT+0000","2021-03-02","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","A/E F.O. viscosity meter assy removed by UNIMARINE and off landed at Singapore for repair.","E/R - Pumps","Eng. / Strg. Comp.","External Factors,Equipment Related","","","","","AT Singapore shore engineer come on board.Checked and test Running is normal at that time.l","2021-05-08","","Completed","2021-05-08","Yes","No","No","Internal","Visco meter overhauled and supplied to vsl.  Still it is malfunctioning. It will be dealt with during docking in June'21"]
[null,null,null,null,15237,"107_Wed Nov 25 2020 05:57:32 GMT+0000","2021-03-04","Observation","Ship Staff","Ship Staff Insp.","Topping up air compressor required to be overhauled due to poor performance","E/R - Air Comp.","Eng. / Strg. Comp.","External Factors","","","","","Complet overhauling done by ship staff and put in use. ","2021-06-04","ANTW 205077","Completed","2021-09-20","No","No","No","Internal","spare supplied, please update"]
[null,null,null,null,15557,"107_Tue Dec 08 2020 07:38:04 GMT+0000","2021-03-05","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel deck  light holder  3 nos supports corroded and wasted, same to be renewed.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","The spare  re-supplied on S.G.P . The light renewed completed.The light holder 3 nos supports re-rust and paint.","2021-06-05","","Completed","2021-05-17","Yes","No","No","Internal","Requisition will be supplied at next convenient port."]
[null,null,null,null,15242,"107_Wed Nov 25 2020 06:08:16 GMT+0000","2021-03-10","Observation","Ship Staff","Ship Staff Insp.","A/E No.3 fuel injectors to be renewed as it is overdue.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","All renewed during Decarb of the DG3 in DD.","2021-06-09","ANTW205073, 215034","Completed","2021-09-09","No","No","No","Internal","Please prepare one sets of fuel injector and replace  all six  units fuel injectors."]
[null,null,null,null,15580,"107_12/13/2020 4:53:59 AM","2021-03-18","Defect","Ship Staff","Ship Staff Insp.","VDR sometimes will display rudder error?timeout on SI17 rudder indicator","Navigation - VDR / BNWAS","Navigation","Equipment Related","","","","","Rectified in Dry Dock","2021-06-15","","Completed","2021-09-09","No","No","No","Internal","please keep monitor and will solve it during dry dock"]
[null,null,null,null,16301,"107_31/12/2020 4:22:32 AM","2021-03-22","Observation","Ship Staff","Ship Staff Insp.","No2 FO supply pump for HFO purifier: mech.seal leaking.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Waiting spares antw215016. Anyway, exchanged by old mech.seal & no leaking now.","2021-06-17","ANTW 027-2020 send to office @ 20201228.","Completed","2021-03-09","No","No","No","Internal","Spares will be supplied at next convenient port. owner will supply"]
[null,null,null,null,15567,"107_Tue Dec 08 2020 08:26:47 GMT+0000","2021-04-05","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Provision Crane (S): Found hoist and slewing limit not working, not able to carry out further trouble shooting due to no platform for the winch limit. Jib slewing limit is badly corroded and jammed, needs to be replace with new. Limit switch cam corroded and need change. Manual control lever not able to return to center upon release, and externally badly corroded. All hoses need to be renewal.  Cylinder Load holding valve requires to be renewed. Internal slewing bearing gear dry and need greasing. Winch standing platform is badly corroded. Spares will be sourced to rectify above mentioned faults.","Deck - Machinery","General Appearance","Equipment Related","","","","","The renewed hoses when D-docking.\n\n\n\n\n\n\n\nRectified in DD.","2021-06-10","ANTW 205083","Completed","2021-09-09","Yes","No","No","Internal","Pls do check and advise  Job will be carried out during docking"]
[null,null,null,null,19636,"107_6/10/2021 10:35:55 PM","2021-05-31","Defect","Owner / Marine / Tech. Suptd.","Engineering Audit","Dump condenser/drain cooler in poor condition,both sidecovers temporary re-conditioned,7 pcs of tube blocked","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","New Dump Condenser Installed","2021-08-10","","Completed","2021-08-26","Yes","No","No","Internal","will carry out in DD."]
[null,null,null,null,19733,"107_6/17/2021 8:37:00 PM","2021-06-15","Defect,Observation","Class Surveyor","Others (Eg. Insurance etc.)","No.1 cargo hatch cover operating station leakage excessive due to poor condition of valve plate","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Job attended in DD","2021-07-15","","Completed","2021-03-09","No","No","No","External","will supply spare parts in convenient port to replace damage one"]
[null,null,null,null,20168,"107_7/14/2021 3:52:31 AM","2021-07-14","Observation","Ship Staff","Ship Staff Insp.","ECR air condition plant in poor condition both compressor and condenser,gas leakage in several places","Elect. Mach. & Equip.,Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","raise spare parts,replace the compressor and condenser when dry docking","2021-08-15","ANTW210075","Completed","2021-03-09","No","No","No","Internal","will carry out in DD"]
[null,null,null,null,15565,"107_Tue Dec 08 2020 08:21:34 GMT+0000","2021-07-27","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Stbd Windlass: Main shaft bearing is badly worn out which causing excessive shaft movement.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Inspected in DD and found in stasfactory condition.","2021-09-30","","Completed","2021-09-05","Yes","No","No","Internal","Pls submit R.O. for the spare parts. Job to be carried out during docking."]
[null,null,null,null,19527,"107_12-05-2021 08:28:32","2021-08-10","Defect","Ship Staff","Engineering Audit","G/E fuel oil visocity controller steam adjust valve cann't move.Adjust set valve but The Control air cann't move .","Deck - Pipe / Fittings,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Job attended in Dry Dock by IMA, controllers under observations","2021-10-31","","Completed","2021-09-08","No","No","No","Internal","please update status after service attending in Singapore"]
[null,null,null,null,20603,"107_8/15/2021 07:37:51","2021-08-15","Observation","Ship Staff","Ship Staff Insp.","S/S UPPER NAV.LIGHT IS DAMAGE","Navigation - Others","Navigation","External Factors","","","","","RAISED RO ANTW210104","2021-08-31","","Completed","2021-09-05","No","No","No","Internal","please get it done in ship yard"]
[null,null,null,null,20604,"107_8/15/2021 12:34:11","2021-08-15","Defect","Ship Staff","Ship Staff Insp.","ELECTRICAL HORN PANEL OUT OF ORDER","Navigation - Others","Navigation","Inappropriate Procedure","","","","","RAISED RO ANTW210045","2021-08-31","ANTW210045","Completed","2021-08-23","No","No","No","Internal","will supplied spare in yard. otherwise please make sure to rectify prior to leave from yard"]
[null,null,null,null,20605,"107_8/15/2021 12:49:27","2021-08-15","Observation,Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","S-BAND / X-BAND RADAR POOR DETECTION FAIL ","Navigation - RADAR","Navigation","Equipment Related","","","","","INFORMED TECH.SUPT. PRAVEEN GANDHI AND FOR SERVICE IN DD DATED 15 AUG.2021","2021-08-31","","Completed","2021-08-31","Yes","No","No","Internal","please get the job done in shipyard"]
[null,null,null,null,20607,"107_8/15/2021 13:05:27","2021-08-15","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ECDIS NO.2  TO CHECK NAVTEX SENSOR & FUN FOR MONITOR FOR COOLING SHOWING ERROR","Navigation - ECDIS","Navigation","Equipment Related","","","","","INFORMED TECH.SUPT. PRAVEEN GANDHI & BY OBSERVATION INTERNAL AUDIT OF CAPT. KHOSA DATED 8 AUG.2021","2021-08-31","","Completed","2021-09-07","Yes","No","No","Internal","please get the job done in shipyard"]
[null,null,null,null,15568,"107_Tue Dec 08 2020 08:30:11 GMT+0000","2021-08-15","Defect","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","AE LO purifier temperature controller require spare for repairs, same being sourced. Two nos of automatic steam control valve overhauled for HFO purifier as same found erratic.","E/R - Purifier,Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Job attended by IMA, controller under observations","2021-10-31","","Completed","2021-09-08","Yes","No","No","Internal","please update status"]
[null,null,null,null,15574,"107_Tue Dec 08 2020 10:41:28 GMT+0000","2021-08-27","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Crew laundry room upper deck common toilets floor tiles rust stained and same required to be renewed.","Accommodation","General Appearance","External Factors","","","","","Material rec'd, work is in progress","2021-12-30","","Completed","2022-01-02","Yes","No","No","Internal","please get the job done ASAP"]
[null,null,null,null,22784,"107_17-Nov-21 19:21:50","2021-08-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","TO BE CLEAN EXHAUST VENTILATION IN GALLEY. TO RENEW VARIOUS RUBBER PACKING ON CREW’S MAIN DOOR.","Accommodation","MLC Related","Human Error","","","","","Exhaut ventilation cleaned and rubber packing renewed","2021-11-29","","Completed","2021-10-06","No","No","No","Internal"]
[null,null,null,null,22785,"107_17-Nov-21 19:24:02","2021-08-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FUNNEL PAINTING TO BE COMPLETED.","Miscellaneous","General Appearance","Human Error","","","","","Funnel painted","2021-11-29","","Completed","2021-10-14","No","No","No","Internal"]
[null,null,null,null,22786,"107_17-Nov-21 19:57:28","2021-08-29","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Topping up compressor not working","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Overhauled and now in good working condition","2021-11-29","","Completed","2021-10-05","No","No","No","Internal"]
[null,null,null,null,22787,"107_17-Nov-21 19:59:56","2021-08-29","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AE 2 ACB OCR to replace with spare ocr received in yard","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","OCR replaced","2021-11-29","","Completed","2021-10-05","No","No","No","Internal"]
[null,null,null,null,22788,"107_17-Nov-21 20:03:54","2021-08-29","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FO sludge tank HL alarm inoperational","Critical Equip.,Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Alarm reactified","2021-10-30","","Completed","2021-10-02","No","No","No","Internal"]
[null,null,null,null,22789,"107_17-Nov-21 20:24:37","2021-08-29","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main Air compressor to overhaul, as takes long time to press up","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Overhauled and working in good condition","2021-11-29","","Completed","2021-10-10","No","No","No","Internal"]
[null,null,null,null,22790,"107_17-Nov-21 20:26:39","2021-08-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sea chest MGPS anodes to replace by vessel staff","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Anodes replaced","2021-11-29","","Completed","2021-10-13","No","No","No","Internal"]
[null,null,null,null,22791,"107_17-Nov-21 20:29:22","2021-08-29","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main Air compressor intermittently trips on High air temp, required overhauling of compressor, major spares located, consumables to check ","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Overhauled and working in good order","2021-11-29","","Completed","2021-10-05","No","No","No","Internal"]
[null,null,null,null,22792,"107_17-Nov-21 20:31:43","2021-08-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME maouvering area to be clean and neat","Miscellaneous","General Appearance","Human Error","","","","","Cleaned and painted","2021-11-29","","Completed","2021-10-04","No","No","No","Internal"]
[null,null,null,null,22779,"107_17-Nov-21 18:55:39","2021-08-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","DANGER ZONE MARKING WITH TIGER STRIPE.","Miscellaneous","Navigation","Human Error","","","","","Danger zones marked with tiger strips","2021-11-29","","Completed","2021-10-14","No","No","No","Internal"]
[null,null,null,null,22780,"107_17-Nov-21 19:05:51","2021-08-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","EMERGENCY GENERATOR VENTILATION PACKING RUBBER TO BE REPLACED.","Miscellaneous","General Appearance","Human Error","","","","","Rubber packing changed","2021-11-29","","Completed","2021-10-10","No","No","No","Internal"]
[null,null,null,null,22781,"107_17-Nov-21 19:11:51","2021-08-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FUNNEL EXHAUST PIPES TO BE DE-RUSTED(SCRIPPED ONLY) AND PAINTED.","Miscellaneous","General Appearance","Human Error","","","","","Funnel exhaust pipes scrapped and painted","2021-11-29","","Completed","2021-10-13","No","No","No","Internal"]
[null,null,null,null,22782,"107_17-Nov-21 19:16:09","2021-08-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","PROVISION CRANES P/S WASTED FLATFORMS TO BE RENEW, DE-RUSTED/PAINTED.","Deck - Machinery","General Appearance","Human Error","","","","","Platforms renewed","2021-11-29","","Completed","2021-10-03","No","No","No","Internal"]
[null,null,null,null,22783,"107_17-Nov-21 19:18:56","2021-08-29","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","TO RECONDITIONED ALL CONTROL STANDS OF HYDRAULIC HATCH COVERS, TO BE DE-RUSTED/PAINTED.","Deck - Pipe / Fittings","General Appearance","Human Error","","","","","Control stands reconditioned","2021-11-29","","Completed","2021-10-20","No","No","No","Internal"]
[null,null,null,null,21889,"107_15/10/2021 23:01:42","2021-09-09","Observation","Ship Staff","Ship Staff Insp.","Boiler Feed Water Pump #1 and #2 Seals are not in place.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Both Pumps overhauled with Mechanical seal ","2021-11-15","ANTW215131","Completed","2021-11-15","No","No","No","Internal","please update status"]
[null,null,null,null,21890,"107_15/10/2021 23:27:29","2021-10-10","Defect","Ship Staff","Ship Staff Insp.","Port Side Bunker Davit Pnuematic Motor non operational","Deck - Machinery","Eng. / Strg. Comp.","Equipment Related","","","","","Overhauled and made operational","2021-11-20","","Completed","2021-02-11","No","No","No","Internal","please keep update status"]
[null,null,null,null,21892,"107_15/10/2021 23:19:47","2021-10-13","Breakdown","Ship Staff","Ship Staff Insp.","#2 Main Cooling SW Pump Motor Burnt","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Motor renewed with a new spare rec'd","2021-10-11","ANTW210165","Completed","2021-05-11","No","No","No","Internal","noted, will supply in convenient port"]
[null,null,null,null,null,"107_15/10/2021 23:09:56","2021-11-01","Defect","Ship Staff","Ship Staff Insp.","Boiler FO Flow meter completely damaged. ME and DG FO flowmeter not showing correct quantity.Recorded Date changed as spares not rec'd . Actual date 22nd Sept'21","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Checking all Bunker tank quantity manually at every noon and showing appropriate consumption based on the ME speed and DG load and Boiler RHRS. Requisition will be done as per office instruction.","2022-03-31","ANTW210179","Completed","2022-07-03","No",null,null,"Internal"]
[null,null,null,null,19637,"107_11/6/2021 8:19:59 AM","2021-11-06","Defect","Ship Staff","Ship Staff Insp.","Part of WBT manholes?14pcs? and HFO manholes?2pcs? serious corrosion become weak .It mus be renewwed","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","Bunker Tanks manholes renewed and WBT manhole gaskets renewed in DD","2021-11-06","","Completed","2021-08-30","Yes","No","No","Internal","please de-rust and paint first. will carry out renew in DD, please including it in the DD spec"]
[null,null,null,null,22775,"107_11/30/2021 10:42:28 PM","2021-11-11","Defect","Ship Staff","Ship Staff Insp.","OVER CURRENT RELAY FOR DG #3 ACB MALFUNCTION","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Renewed with a spare one.","2022-02-28","ANTW210187","Completed","2022-09-02","No","No","No","Internal","will process and supply in convenient port"]
[null,null,null,null,null,"107_2/1/2022 5:17:52 PM","2021-12-01","Defect","Ship Staff","Ship Staff Insp.","Wiper Cabin Vaccum Toilet system inoperational","Accommodation","MLC Related","Equipment Related",null,null,"Not Applicable","Not Applicable","Control system and water suppy unit checked. Found Ok. Sewage outlet branch pipe is chocked. Planning to renew after Singapore","2022-02-28",null,"Completed","2022-12-03","No",null,null,"Internal"]
[null,null,null,null,23121,"107_14/12/2021 14:53:23","2021-12-11","Defect","Ship Staff","Ship Staff Insp.","While carrying out yearly pressure test of HFO bunker line, found section of pipe holed at 3 Bar air pressure","Deck - Pipe / Fittings","MARPOL Related","Equipment Related","","","","","Fabrication of 2 section of line completed. Other weaker section to identify and renew","2021-12-17","","Completed","2021-12-17","No","No","No","Internal","please update status for the job."]
[null,null,null,null,23123,"107_14/12/2021 15:04:20","2021-12-12","Non Conformity","Ship Staff","Ship Staff Insp.","Port FW tank Sight Glass Bottom Valve is ship's made one which is always in open position","Hull & Tanks","Safety / LSA / FFA","Equipment Related","","","","","Emptied out the tank and overhauled  the valve. ","2022-01-31","","Completed","2021-12-29","No","No","No","Internal","please check if spare not available raise RO"]
[null,null,null,null,23124,"107_14/12/2021 15:48:07","2021-12-12","Defect","Ship Staff","Ship Staff Insp.","Both Provision Cranes Safety limit switches are not working","Deck - Machinery","Safety / LSA / FFA","Equipment Related","","","","","Port side crane switch renewed and STBD side Switcheased up","2022-01-31","","Completed","2022-01-06","No","No","No","Internal","please carry out ASAP and update"]
[null,null,null,null,23126,"107_14/12/2021 15:27:34","2021-12-13","Defect","Ship Staff","Ship Staff Insp.","#8 Hatch cover operation is very slow.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","Found no issues with Flow control valve. Tried out with Emergency pump found working normal. Old block will be landed for repair as per Master's decision.","2021-12-18","ANTW215150","Completed","2021-12-29","No","No","No","Internal","please update status."]
[null,null,null,null,23127,"107_14/12/2021 16:37:07","2021-12-14","Defect","Ship Staff","Ship Staff Insp.","ER Toilet Vaccum system operating mechanism altered and fabricated with ordinary valve. Vaccum getting released and alarm on the panel","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Replaced the control system, water controller and repair the Push button switch. Working normal. ","2021-12-31","ANTW210228","Completed","2021-12-20","No","No","No","Internal","will supply spares in convenient port"]
[null,null,null,null,23128,"107_14/12/2021 16:42:57","2021-12-14","Defect","Ship Staff","Ship Staff Insp.","EGE soot Blower not functioning / Rotating","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Removed and overhaul done during Suez anchorage.","2021-12-31","","Completed","2021-12-15","No","No","No","Internal","please carry out and update"]
[null,null,null,null,23129,"107_14/12/2021 16:54:31","2021-12-14","Observation","Ship Staff","Ship Staff Insp.","Boiler Mountings such as air vent valve, gauge valve found not installed.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Instaledl the required valves at Port Said in Suez after depressurising the boiler.","2021-12-20","","Completed","2021-12-19","No","No","No","Internal","please carry out and update. item will due soon"]
[null,null,null,null,23482,"107_1/14/2022 4:24:18 PM","2022-01-01","Defect","Ship Staff","Ship Staff Insp.","Galley AC Non operational due to Cooling water line issue.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","New line fabricated for condensor. Cond. cleaned. System checked, Gas charged, safet tested, started and put in use. Leak test done. All OK","2022-03-31","","Completed","2022-02-21","No","No","No","Internal","please carry out before due date"]
[null,null,null,null,null,"107_1/14/2022 4:20:14 PM","2022-01-01","Defect","Ship Staff","Ship Staff Insp.","STBD Windlass Flushing valve jammed","Deck - Mooring Machinery","Mooring","Equipment Related",null,null,"Not Applicable","Not Applicable","Easing up is in progress","2022-02-28",null,"Completed","2022-12-03","No",null,null,"Internal"]
[null,null,null,null,null,"107_1/14/2022 4:40:30 PM","2022-01-01","Defect","Ship Staff","Ship Staff Insp.","Sludge Pump Relief valve malfunction","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Inside parts damaged. Raised a requisition.","2022-03-31","ANTW220021","Completed","2022-06-03","No",null,null,"Internal"]
[null,null,null,null,null,"107_2/16/2022 12:25:07 PM","2022-01-02","Guarantee Claim","Ship Staff","Ship Staff Insp.","Gym Equipment parts missing, delivered in DD.","Miscellaneous","MLC Related","Equipment Related",null,null,"Not Applicable","Not Applicable","Message sent to 26th Dec'21. Weight System Exerciser, Maker WEIDERPRO 6900, Model no. 831.14922.2, supplied in Dubai DD, in Sept’21 does not contain all the parts","2022-05-31","Procure Dept. knows the RO number","Completed","2022-03-13","No",null,null,"Internal"]
[null,null,null,null,23695,"107_17-Jan-22 21:44:01","2022-01-06","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck pipe mechanical vent mushroom head damper wheel seized","Deck - Pipe / Fittings","General Appearance","Human Error","","","","","Repaired","2022-03-09","","Completed","2022-01-15","No","No","No","Internal"]
[null,null,null,null,23696,"107_17-Jan-22 21:47:48","2022-01-06","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency generator MGO tank save all oily observed","Miscellaneous","General Appearance","Human Error","","","","","to be cleaned","2022-03-06","","Completed","2022-01-07","No","No","No","Internal"]
[null,null,null,null,23830,"107_2/1/2022 5:22:19 PM","2022-01-21","Defect","Ship Staff","Ship Staff Insp.","Aux. Cooling SW pump seal leaks. Trying to isolate for overhaul, noticed inlet valve connected to the sea chest line not holding.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Pump overhauled with the available spares.","2022-02-07","","Completed","2022-09-02","No","No","No","Internal","if the valve malfunction please order and make plan to renew. please update the pump overhaul status"]
[null,null,null,null,23833,"107_2/1/2022 5:39:17 PM","2022-01-28","Observation","Ship Staff","Ship Staff Insp.","#3 DG Turbocharger Gas leaking from casing Joint","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Casing Bolts and nut tighten and noticed no any leakage even at 420 kw load","2022-02-04","","Completed","2022-07-02","No","No","No","Internal","to carry out the job at anchorage and update"]
[null,null,null,null,null,"107_2/16/2022 2:36:33 PM","2022-02-01","Guarantee Claim","Ship Staff","Ship Staff Insp.","#8 Hatch cover new block rec'd is leaking","Deck - Machinery","Cargo / Ballast Systems","Equipment Related",null,null,"Not Applicable","Not Applicable","#8 Hatch cover problem solved as there was an issue with a non return valve which was installed wrongly in DD. w.r.t. New block oil flow configration to be confirmed with office assistance. If it is not matching, then we need to land this new block for replacement. One more spare block is found in the forward Bosun store, need to check and confirm its function","2022-03-31","ANTW215132","Completed","2022-12-03","No",null,null,"Internal"]
[null,null,null,null,null,"107_2/16/2022 12:15:29 PM","2022-02-02","Defect","Ship Staff","Ship Staff Insp.","ECR COMPUTER CPU DEFECTIVE","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Computer used for Paper works in ECR is Defective. Showing Error code: 0x80070002 which is normally due to file corruption / registry issues. As there are Huge Paper works are being done daily & at Month end in ER, unable to manage with one computer.","2022-02-28","ANTW220043","Completed","2022-12-03","No",null,null,"Internal"]
[null,null,null,null,null,"107_2/16/2022 3:07:07 PM","2022-02-02","Defect","Ship Staff","Ship Staff Insp.","Steam traps in ER are not operational","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Most of the important steam trap in ER are not operational. F.O heaters of Main & Aux engine, Purifier heaters are among them. Due to this issue we are unable to maintain required temperature.","2022-03-31","ANTW220052","Completed","2022-10-03","No",null,null,"Internal"]
[null,null,null,null,null,"107_2/16/2022 1:21:51 PM","2022-02-14","Defect","Ship Staff","Ship Staff Insp.","Intermediate Shaft Bearing has slight leakage from the Aft side O-ring","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Requisition sent on 23rd Feb","2022-03-31","ANTW220061","Completed","2022-02-24","No",null,null,"Internal"]
[null,null,null,null,null,"107_2/16/2022 3:32:54 PM","2022-02-15","Observation","Ship Staff","Ship Staff Insp.","#2 Prov. Ref Compr. Motor making Noise","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","Vsl. has only one bearing. hence we already send requisition for Motor overhauling.","2022-03-30","ANTW220049","Completed","2022-02-28","No",null,null,"Internal"]
[null,null,null,null,23687,"107_17-Jan-22 21:38:47","2022-06-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port bunker manifold oil spill tray drain with wood plug","Deck - Pipe / Fittings","General Appearance","Human Error","","","","","proper plug to be fabricated","2022-01-30","","Completed","2022-10-01","No","No","No","Internal"]
[null,null,null,null,23688,"107_17-Jan-22 21:40:30","2022-06-01","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Compress airline on deck leaking beside HC7 and HC4","Deck - Pipe / Fittings","General Appearance","Human Error","","","","","New line fabricated","2022-01-30","","Completed","2022-10-01","No","No","No","Internal"]
[null,null,null,null,23689,"107_17-Jan-22 21:49:31","2022-06-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME LO oil cooler cooling water leakage sign observed on top flange","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Reactified","2022-06-03","","Completed","2022-10-01","No","No","No","Internal"]
[null,null,null,null,23690,"107_17-Jan-22 21:51:09","2022-06-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME shaft grounding device to carry out maintenance. Slip ring to clean","E/R - Main Engine","Eng. / Strg. Comp.","Human Error","","","","","Reactified","2022-06-03","","Completed","2022-07-01","No","No","No","Internal"]
[null,null,null,null,23691,"107_17-Jan-22 21:52:43","2022-06-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Economizer soot blower steam drain valve leakage. Lagging to wrap properly","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Human Error","","","","","Rectified","2022-06-03","","Completed","2022-07-01","No","No","No","Internal"]
[null,null,null,null,23692,"107_17-Jan-22 21:54:45","2022-06-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency generator both ventilator and air duct wire mesh damaged","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Human Error","","","","","changed","2022-06-03","","Completed","2022-07-01","No","No","No","Internal"]
[null,null,null,null,23693,"107_17-Jan-22 21:45:46","2022-06-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both anchor chain pipe security plate excessive gap observed","Deck - Pipe / Fittings","General Appearance","Human Error","","","","","fabricated","2022-06-03","","Completed","2022-08-01","No","No","No","Internal"]
[null,null,null,null,23694,"107_17-Jan-22 21:42:33","2022-06-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck store top rusty and spot to chip and paint","Miscellaneous","General Appearance","Human Error","","","","","De rusting and painting  done","2022-01-29","","Completed","2022-08-01","No","No","No","Internal"]
[null,null,null,null,23480,"107_1/14/2022 3:41:18 PM","2022-06-01","Defect","Ship Staff","Ship Staff Insp.","EGE Steam inlet pipe holed","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","The whole section of pipe is been renewed","2022-01-30","","Completed","2022-06-01","No","No","No","Internal","please update on 30 Jan 2022"]
[null,null,null,null,23481,"107_1/14/2022 3:31:56 PM","2022-08-01","Defect","Ship Staff","Ship Staff Insp.","MDO (P) level gauge is faulty","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Overhauled and fitted. ","2022-02-28","","Completed","2022-01-20","No","No","No","Internal","please keep update status"]
[null,null,null,null,23484,"107_1/15/2022 12:40:06 PM","2022-08-01","Defect","Ship Staff","Ship Staff Insp.","Port cylinder LO manifold filling pipe is weakend and rusted","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","New Pipe line Fabricated and fitted in place. ","2022-01-30","","Completed","2022-09-01","No","No","No","Internal","please update status and close out within the windows"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["107","ANTWERP (09-03-2022)","107_1646789649028.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]