{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":6,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":114,"n_cols":28,"rows_kept":114,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","04-Apr-2022",null,null,"Ship Name","ONISILOS"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,null,"131_6/4/2022 2:53:01 PM","2022-02-18","Defect","Ship Staff","Ship Staff Insp.","IG main isolation line platform support legs wasted","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",11.5,"Medium","Not Applicable","Not Applicable","To be repaired in dry dock","2022-07-07",null,"Deferred to D D",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:08:57 PM","2022-02-18","Defect","Ship Staff","Ship Staff Insp.","6 S Heating Pipes (near Supply and Return valves) Support frame wasted.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",11.5,"Medium","Not Applicable","Not Applicable","To be repaired in dry dock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 2:35:06 PM","2022-02-19","Defect","Ship Staff","Ship Staff Insp.","Emergency stop box for COP port side midship manifold renewal of broken supports and frames.","Cargo Mach.,Miscellaneous","General Appearance","Equipment Related",8.1,"Very High","Not Applicable","Not Applicable","TO BE REPAIRED IN DRY DOCK","2022-07-31",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 2:50:05 PM","2022-02-19","Defect","Ship Staff","Ship Staff Insp.","Rain deflectors main entrance for Midship Rain deflectors main entrance for Midship Rain deflectors main entrance for Midship store Stbd,Boiler Platform, and Battery Room wasted.\r\n\r\n\r\n\r\n","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related",11.6,"Medium","Not Applicable","Not Applicable","To be repaired in drydock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:01:13 PM","2022-02-19","Defect","Ship Staff","Ship Staff Insp.","SLOP P Heating Pipes (Supply and Return) Support frame wasted","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",11.5,"Medium","Not Applicable","Not Applicable","To be repaired in drydock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:02:47 PM","2022-02-19","Defect","Ship Staff","Ship Staff Insp.","SLOP S Heating Pipes (near Supply and Return valves) Support frame wasted.\r\n\r\n\r\n\r\n","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",11.5,"Medium","Not Applicable","Not Applicable","To be repaired in dry dock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:07:21 PM","2022-02-19","Defect,Observation","Ship Staff","Ship Staff Insp.","Conduit line guard frame fwd of break of accommodation  port side.","Deck - Pipe / Fittings","General Appearance","Equipment Related",11.1,"High","Not Applicable","Not Applicable","To be repaired in dry dock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_9/4/2022 10:55:42 AM","2022-02-20","Defect,Observation","Ship Staff","Ship Staff Insp.","STEERING GEAR GREASE PUMP PCB NOT WORKING/ DEFECTIVE.\t","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","NEED RENEWAL, RO RAISED- ONIS22050","2022-05-31",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 2:59:27 PM","2022-02-21","Defect,Observation","Ship Staff","Ship Staff Insp.","Pilot ladder rest rail port side stanchion hole  wasted.","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related",11.5,"Medium","Not Applicable","Not Applicable","To be repaired in drydock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 2:39:52 PM","2022-02-22","Defect,Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FWG O/B VALVE STUCK IN OPEN POSITION.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","JOB DETAILS ADDED IN DD SPECS.","2022-07-31",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:51:43 PM","2022-02-24","Defect,Observation","Ship Staff","Ship Staff Insp.","O2 sensor for VECS system malfunction","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.26,"High","Not Applicable","Not Applicable","Requisition has been raised.","2022-06-06","ONIS220023","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:48:11 PM","2022-02-25","Critical Equipment","Ship Staff","Ship Staff Insp.","Leak from port and stbd windlass relief valves","Deck - Mooring Machinery","Mooring","Equipment Related",9.1999999999999993,"Very High","Not Applicable","Not Applicable","Requisition has been raised for spare parts.No spares available on board.High pressure Orings are changed after every leak takes place","2022-06-06","ONIS220030","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:24:22 PM","2022-03-02","Defect","Ship Staff","Ship Staff Insp.","Dent in 1 S WBT\r\n","Hull & Tanks","Structural Condn. / WT integrity ","External Factors",11.1,"High","Not Applicable","Not Applicable","To be repaired in dry dock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 2:41:43 PM","2022-03-03","Defect","Ship Staff","Ship Staff Insp.","FPK WBT 2 nd stringer ladder port badly corroded and wasted","Hull & Tanks","Cargo / Ballast Systems","Equipment Related",11.7,"High","Not Applicable","Not Applicable","To be repaired in drydock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:28:42 PM","2022-03-03","Defect","Ship Staff","Ship Staff Insp.","Dent in 6P WBT","Hull & Tanks","Structural Condn. / WT integrity ","External Factors",11.1,"High","Not Applicable","Not Applicable","To be repaired in dry dock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 5:33:07 PM","2022-03-03","Defect,Observation","Ship Staff","Nav Audit / Verification","BRIDGE WINDOW WIPERS NOT OPERATIONAL.","Navigation - Others","Navigation","Equipment Related",4.3,"Medium","Not Applicable","Not Applicable","REQUISITION- ONIS220009 FOR CONTROLLER UNIT, AWAITING SPARES","2022-06-03","ONIS220009","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 9:36:04 AM","2022-03-03","Defect,Observation","Ship Staff","Ship Staff Insp.","ME VISCOTHERM SEONSOR NOT WORKING/DEFECTIVE ALSO SENSOE CABLE DAMAGED.","E/R - Aux. Mach.,E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","NEED RENEWAL OF SENSOR. RO RAISED - ONIS220018","2022-06-03",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:26:05 PM","2022-03-04","Defect","Ship Staff","Ship Staff Insp.","Dent in 2S WBT","Hull & Tanks","Structural Condn. / WT integrity ","External Factors",11.1,null,"Not Applicable","Not Applicable","To be repaired in Dry dock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 2:47:22 PM","2022-03-05","Defect","Ship Staff","Ship Staff Insp.","3S WBT entrance ladder wasted ","Hull & Tanks","Cargo / Ballast Systems","Equipment Related",11.7,"High","Not Applicable","Not Applicable","To be repaired in dry dock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_9/4/2022 10:20:00 AM","2022-03-07","Defect","Ship Staff","Ship Staff Insp.","IG SCRUBBER TOWER DEMISTER PILLED OUT AT SOME PLACES AND DAMAGED REQUIRE RENEWAL.","Inert Gas","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","DAMAGED DEMISTER TO BE RENEWED IN DD. ADDED IN DD SPECS.","2022-07-31",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 2:43:44 PM","2022-03-10","Defect","Ship Staff","Ship Staff Insp.","4S WBT entrance ladder wasted ","Hull & Tanks","Cargo / Ballast Systems","Equipment Related",11.7,"High","Not Applicable","Not Applicable","To be repaired in drydock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:31:32 PM","2022-03-10","Defect,Observation","Ship Staff","Ship Staff Insp.","Gangway Port Side shifting channel bended, rusted and wasted ","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related",5.47,"Medium","Not Applicable","Not Applicable","To be repaired in dry dock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:33:24 PM","2022-03-10","Defect,Observation","Ship Staff","Ship Staff Insp.","Gangway Stbd Side shifting channel bended, rusted and wasted ","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related",5.47,"Medium","Not Applicable","Not Applicable","To be repaired in dry dock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 11:22:06 AM","2022-03-15","Defect,Observation","Ship Staff","Ship Staff Insp.","NO.2 AC COMPRESSOR HAVING ISSUE WHILE STARTING, FAILS TO START. CONTROLLER PCB DEFECTIVE.","Accommodation,E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","NEED TO RENEW CONTROLLER PCB. RO RAISED-ONIS220028","2022-06-15",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 1:47:44 PM","2022-03-15","Defect,Observation","Ship Staff","Ship Staff Insp.","20.\tALL COPT AND WBPT TURBINE COMMON DRAIN LINE WASTED, CONNECTED WITH FLEXIBLE HOSES AT SOME POINT NEED TO RENEWED COMPLETELY","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","PIPE MATERIAL RECIEVED LAST SINGAPORE CALL, JOB WILL BE PLANNED ACCORDINGLY.","2022-05-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:11:22 PM","2022-03-18","Defect","Ship Staff","Ship Staff Insp.","SLOP S Heating Pipes Support frame wasted","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",11.5,"Medium","Not Applicable","Not Applicable","To be repaired in drydock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:15:27 PM","2022-03-18","Defect","Ship Staff","Ship Staff Insp.","SLOP S Heating Pipes Support frame wasted.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related",11.5,"Medium","Not Applicable","Not Applicable","To be repaired in Dry Dock","2022-07-07",null,"Deferred to D D",null,"Yes",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:39:20 PM","2022-03-22","Observation","Ship Staff","Ship Staff Insp.","Pressure sensor for Slop P COT  not working","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.1300000000000008,"Medium","Not Applicable","Not Applicable","Pressure sensor has been order . Awaiting spares ","2022-06-06","ONIS220044","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 2:51:26 PM","2022-03-25","Defect,Observation","Ship Staff","Ship Staff Insp.","CONTROL AIR DRYER FAN MOTOR DAMAGED.","E/R - Aux. Mach.,Miscellaneous","Eng. / Strg. Comp.","External Factors",10.32,"Very High","Not Applicable","Not Applicable","REQUIRE TO CHANGE WITH NEW. RO RAISED FOR NEW FAN MOTOR, ONIS220046","2022-05-31",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 3:07:38 PM","2022-03-31","Defect,Observation","Ship Staff","Ship Staff Insp.","ME AUTOBACK WASH FILTER DP PRESSURE SWTCH DIAPHRAGM DAMAGED. CURRENTLY SET ON 2 HR TIMELY BACKFLUSHING.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","NEED TO RENEW DP PRESSURE SWITCH RO RAISED- ONIS220051","2022-05-31",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:06:26 PM","2022-04-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","HEATING LINE INCLUDING VALVES FWD OF P/ROOM TILL 6 WINGS TO BE SUNDERED AND THERMAL COATING","Cargo Mach.","Cargo / Ballast Systems","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:05:02 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","GROOVING FOUND ON FWD MOORING CHOCKS STBD SIDE BOW X2 PCS-TO BE RECTIFIED DURING GAS FREE BFR OR AFTER DRYDOCK","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:07:47 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","SPOT SUNDER-PRIMER-COATING VENT OF BOSUN STORE","Critical Equip.,Miscellaneous","General Appearance","External Factors",11.7,"High","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:29:34 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","SUNDER-PRIMER-COATING MOORING WINCH MOTOR FORECASTLE ","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:32:42 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE TO CONDUIT LINE OF FWD LIFERAFT –SUNDER-PRIMER-COATING","Deck - Pipe / Fittings","General Appearance","External Factors",11.1,"Medium","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:37:37 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","INSTALLATION OF TALLOW TO BE MADE TO ALL EXPANSIONS CARGO/COW/FIRE/BUNKER ETC.  GREASE WITH GREEN COAT PREFERABLY","Miscellaneous","General Appearance","External Factors",11.4,"Very High","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:40:58 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FULL COATING FWD DECK MOORING AREA OF FWD BREAST","Hull & Tanks","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:44:46 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE TO BE MADE TO ALL P.V. VALVES REPLACEMENT OF SCREEN –SUNDER/PRIMER/FULL COATING","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.2100000000000009,"High","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:48:44 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE OF MAST RISER VALVE/CHIPPING-SUNDER-PRIMER-FULL COATING TO BE MADE","Inert Gas","Cargo / Ballast Systems","Equipment Related",11.4,"Very High","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:51:48 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","REPLACEMENT OF LOCK IN MAST RISER STAY WIRE SUPPORTS","Miscellaneous","General Appearance","External Factors",11.5,"Medium","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:54:14 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","SPOT MAINTENANCE FIRE WIRES WINCH-SUNDER/PRIMER/COATING","Deck - Mooring Machinery","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:56:33 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE SUNDER-PRIMER-FULL COATING CONDUIT OF NO 2S SAAB TANK RADAR-REPLACEMENT IF NEEDED.","Deck - Pipe / Fittings","General Appearance","External Factors",11.1,"Medium","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:01:23 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE TO BE CARRIED OUT IN CARGO LINES DRESSER COUPLINGS FM MIDHIP TILL AFT AREA 4 WINGS TO SLOPP/S","Deck - Mooring Machinery","General Appearance","Equipment Related",8.25,"Very High","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:03:50 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE TO BE MADE TO P.V. BREAKER SUNDER/PRIMER/COATING INCLUDING PLATFORM","Inert Gas","Cargo / Ballast Systems","Equipment Related",11.1,"High","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:07:05 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE ON U BOLTS OF STEAM LINE FM FWD TILL AFT SUNDER -COATING","Deck - Pipe / Fittings","General Appearance","External Factors",11.5,"Medium","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:10:32 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE –SUNDER/PRIMER/COATING MIDSHIP STORES STBD SIDE","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:27:00 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE REDUCERS P&S MANIFOLD AREA","Miscellaneous","Cargo / Ballast Systems","External Factors",8.59,"High","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:32:12 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE OF SAAB TANK RADAR’S SUNDER/PRIMER/FULL COATING","Miscellaneous","Cargo / Ballast Systems","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:35:16 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE OF ALL CABLE BOX LINES SUNDER/PRIMER/FULL COATING","Miscellaneous","General Appearance","External Factors",11.1,"Medium","Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:42:37 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp."," \tMAINTENANCE OF PILOT LADDER SHIFTING CHANNEL  TO BE MADE\r\nP&S SUNDER/PRIMER/FULL COATING\r\n","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:45:14 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENACE OF THE SUPPORTS OR REST RAILS TO BE DONE CHIPPING/SUNDER/PRIMER/COATING","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:47:03 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FIRE LINE IN THE AREA OF 6WINGS RUSTED TO BE MAINTENANCED SUNDER/PRIMER/COATING-SLIGHTLY NOT TO DAMAGED ","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-10",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:50:02 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CONDUIT LINE OF 5P –FM MIDSHIP MOVING TO PORT SIDE CORRODED TO BE REPLACED","Miscellaneous","General Appearance","External Factors",11.4,"Very High","Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-06",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:51:54 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","IG ISOLATION VALVES MAINTENANCE TO BE CARRIED OUT SUNDER/PRIMER COATING","Miscellaneous","General Appearance","External Factors",8.23,"Medium","Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:54:18 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CONDUIT OF 6S MAINTENANCE TO BE CARRIED OUT SUNDER/PRIMER/FULL COATING","Miscellaneous","General Appearance","External Factors",11.4,"Very High","Not Applicable","Not Applicable","PLANNED AS PE MAINTENANCE SCHEDULE","2022-07-06",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 11:56:34 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","DECK SEAL MAINTENANCE TO BE CARRIED OUT –CHIPPING/SUNDER/PRIMER/COATING","Cargo Mach.","Cargo / Ballast Systems","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-05",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:02:32 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","P/ROOM FANS MAINTENANCE TO BE CARRIED OUT SUNDER /PRIMER/COATING-ALSO IN THE TOP THE WHITE RUSTED AREA ","Cargo Mach.","Cargo / Ballast Systems","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:08:07 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NAVIGATION LIGHTS P&S DECK AREA TO BE DERUSTED SPOT SUNDER/PRIMER/COATING","Navigation - Others","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE","2022-07-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:10:12 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FISH PLATES P&S NEXT TO DUMP VALVE TO BE MAINTENANCED SUNDER/CHIPPING/PRIMER/FULL COATING INCLUDING DUMP VALVES ","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-13",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:11:45 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","PLATFORM OF BOTH LIFEBOTAS TO BE MAINTENANCED –SUNDER/PRIMER/COATING","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-15",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:13:38 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LIFEBOATS HOOKS DAVIT INCLUDING ROLLERS TO BE MAINTENANCED CHIPPING/SUNDER/PRIMER/FULL COATING","LSA / FFA","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-30",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:15:25 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","BRACKET OF LIFEBOATS TO BE MAINTENANCED SUNDER/PRIMER/COATING\r\nP&S\r\n","LSA / FFA","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:16:48 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","REFRESHMENT & MAINTENANCE OF BRAKE LIFEBOATS –RED MARKING P&S","LSA / FFA","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:18:43 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AFT AREA MUSTER STATION PORT SIDE&STBD SIDE TO BE PAINTED DECK SURFACE FULL","Miscellaneous","General Appearance","External Factors",11.1,"High","Not Applicable","Not Applicable","DE-RUSTING AND PAINTING IN PROGRESS","2022-07-06",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:20:47 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","EMCY STOP BOX VACUUM TOILETS ETC. AFT AREA PORT SIDE TO BE MAINTENANCED CHIPPING/SUNDER/FULL COATING + MARKING","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","DR-RUSTING AND PAINTING IN PROGRESS","2022-07-06",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:22:21 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CHINA PASSAGE AFT AREA FWD GARBAGE ROOM TO BE PAINTED FULL DECK SURFACE INCLUDING SAFETY WAY","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-08",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:29:17 PM","2022-04-02","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","DERUSTING TO BE MADE WITH METAL BRIGHT/RUST REMOVER AFT PROVISION CRANES\r\n\r\n\r\n-SHORT LEAKAGE OBSERVED BY LEVERS P&S PROV.CRANES –SUBJECT TO CHECK O RINGS REPLACEMENT\r\n","Deck - Machinery","Safety / LSA / FFA","Equipment Related",8.5,null,"Not Applicable","Not Applicable","SPARES NEEDS TO BE ORDERED","2022-07-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:31:08 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","PA BOX &EMCY ALARM TO BE MAINTENANCED SUNDER/PRIMER/FULL COATING IN THE AREA OF LIFEBOATS PLATFORM P&S","LSA / FFA","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-17",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:32:33 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LIFERAFTS PLATFORM /LIFERAFT DAVIT TO BE DERUSTING P&S SIDE","LSA / FFA","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-14",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:34:32 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AFT MANIFOLD CYL OIL ETC. TO BE MAINTENANCED SUNDER/CHIPPING/FULL COATING +STENCILS NAMES INDICATION","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-08",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:41:47 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","OXYG&ACETYLENE ROOM ENTRANCE TO BE PAINTED FULL AREA","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-08",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:43:28 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AIR INTAKE OF EMCY GENERATOR TO BE DERUSTED AND FULL COATING","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-11",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:45:02 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NATURAL VENT OF P/ROOM TO BE MAINTENANCED FROM INSIDE SUNDER-FULL COATING","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:49:50 PM","2022-04-02","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","REPLACEMENT OF GRATING MIDSHIP HOSE HANDLING CRANE","Deck - Machinery","Structural Condn. / WT integrity ","External Factors",8.5,"Medium","Not Applicable","Not Applicable","SPARES NEEDS TO BE ORDERED.SPARES RECEIVED WITH WRONG SUPPLY","2022-07-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:52:55 PM","2022-04-02","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","REPAIR OF WBT VENT SIDE FLAP FRAMES TO BE MADE BY FITTER","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related,External Factors",11.7,"High","Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-31",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:57:12 PM","2022-04-02","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CRACKED LIGHTS P/ROOM TOTAL 6 NO'S ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related",8.48,"Medium","Not Applicable","Not Applicable","HAVE SPARES ON BOARD 2 PCS .REQ HAS BEEN RAISED FOR ADDITIONAL 4 PCS","2022-07-31","ONIS220049","Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 1:00:23 PM","2022-04-02","Defect,Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","OIL LEAKAGE NOTICED IN THE ENTRANCE OF PUMP ROOM TOP HYDRAULIC LINES GOING DOWN TO VALVES INSIDE  PUMPROOM DECKS.HYDRAULIC LINES ARE PLASTIC COATED AND IN ADDITION HAS AN EXTRA RUBBER COVERINGS ON TOP","Cargo Mach.","Cargo / Ballast Systems","Equipment Related",8.44,"High","Not Applicable","Not Applicable","LEAK TRRACING IN PROGRESS","2022-07-31",null,"In progress",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 4:43:10 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","HYDRAULIC LINES MAIN DECK FROM THE AREA OF 5WINGS MOVING AFT TILL FWD OF PUMPROOM TO BE SUNDERED IN THE U BOLTS AREA AND PRIMER-COATING.SPOT","Deck - Pipe / Fittings","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 4:46:28 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","RUSTED MANIFOLDS VALVES OF VAPOUR.CARGO LINES\r\n-TO BE MAINTENANCED CHIPPING/SUNDER/PRIMER/COATING\r\n","Cargo Mach.","General Appearance","External Factors",8.41,"Medium","Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 4:55:39 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LIFEBUOYS ON MAIN DECK SOLAS TAPE TO BE REPLACED –FURTHER INSPECTION TO BE CARRIED OUT IF ANY DAMAGED/CRACKED","LSA / FFA","Safety / LSA / FFA","External Factors",5.31,"High","Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 4:58:44 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","REDUCERS BASE ON MAIN DECK TO BE SUNDERED AND PRIMER/COATING \r\nALSO DOWN OF THE SUPPORT –RUSTED AREA-INSPECTION \r\nMAINTENANCE TO SPARE REDUCERS TO BE MADE\r\n","Miscellaneous","Cargo / Ballast Systems","External Factors",8.41,"Medium","Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:00:51 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","DERUSTING OF FWD MAST TO BE MADE-SPOT SUNDER WHERE NEEDED-COATING","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:03:25 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","DROP LINES MIDSHIP TO BE MAINTENANCE-CHIPPING-SUNDER/PRIMER/FULL COATING","Cargo Mach.,Miscellaneous","Cargo / Ballast Systems","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:07:24 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","GANGWAY SUPPORTS TO BE MAINTENANCED PORT&STBD SIDE CHIPPING/SUNDER/PRIMER/FULL COATING","Miscellaneous","General Appearance","Equipment Related",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:09:06 PM","2022-04-02","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","COATING DECK SURFACE ON HEATING COILS SQUARE WITH BLACK","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:11:14 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FIRE DAMPERS PORT SIDE A DECK OUTER ACCOMODATION TO BE MAINTENANCED SUNDER/PRIMER/FULL COATING","Accommodation","General Appearance","External Factors",5.14,"Very High","Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:15:15 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MONKEY ISLAND DERUSTING TO BE MADE OVERFILL ALARM HOR BASE","Accommodation","General Appearance","External Factors",11.8,"Low","Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:17:05 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE SUNDER/PRIMER/FULL COATING ELEVATOR TRUNK ESCAPE HATCH COVER-PORT SIDE BRIDGE WING\r\nREFRESH OF STENCILS AND APPLY PLASTIC SEALS\r\n","Accommodation","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:20:40 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","COW BRANCH OF SLOP P TO BE MAINTENANCED MIDSHIP DOWN FM THE PLATFORM OF THE SAFET WAY-\r\nSLIGHT SUNDER/PRIMER/COATING\r\n","Deck - Pipe / Fittings","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:23:19 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","C.O.W LOCAL VALVES TO BE MAINTENANCED – CHIPPING/SUNDER/PRIMER/FULL COATING","Miscellaneous","Cargo / Ballast Systems","External Factors",8.34,"High","Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:25:00 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","HYDRAULIC LINES SUPPORTS ON MAIN DECK P&S NEXT TO PLATFORMS TO BE MAINTENANCED-SUNDER/PRIMER/FULL COATING","Deck - Pipe / Fittings","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED FOR MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:26:39 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","DERUSTING TO BE MADE SHIFTING DAVIT ACCOMM LADDER P&S","Deck - Machinery","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:31:06 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FULL COATING OF PAINT STORE TO BE MADE ","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:33:48 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE OF HOSE SUPPORT RAILS MANIFOLDS AREA P&S CHIPPING/SUNDER/PRIMER/FULL COATING","Miscellaneous","General Appearance","External Factors",8.41,"Medium","Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:35:39 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE MANIFOLDS AREA MARPOL LINE DRAINS P&S","Miscellaneous","General Appearance","External Factors",11.1,null,"Not Applicable","Not Applicable","PLANNED AS PER MAINTENANCE SCHEDULE","2022-07-02",null,"Not Started",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 2:47:44 PM","2022-04-02","Critical Equipment,Defect,Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","EMG FIRE PUMP Q VAC VACUUM UNIT NOT FUNCTIONING PROPERLY/ NOT GENERATING  ENOUGH VACUUM.","Critical Equip.,E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","NEED TO OVERHAUL VANE PUMP. RO RAISED- ONIS220036","2022-05-31",null,"Waiting spare",null,"No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 2:58:57 PM","2022-04-02","Defect,Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AUX COOLING SW AND EJECTOR PUMP SW SUCTION PIPE LINE TO RENEW","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","JOB DETAILS ADDED IN DD SPEC.","2022-07-31",null,"Deferred to D D",null,"No",null,null,"Internal"]

{"sheet":"Completed","index":1,"n_rows":51,"n_cols":28,"rows_kept":51,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","04-Apr-2022",null,null,"Ship Name","ONISILOS"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,null,"ID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,null,"131_8/4/2022 5:22:18 PM","2022-02-19","Defect","Ship Staff","Ship Staff Insp.","Atmospheric cond. opened up for cleaning and inspection, found end cover partition pate wasted. Causing inadequate flow through cooler.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","End cover partition plate fabricated and welded. Coated with epoxy paint.","2022-03-19",null,"Completed","2022-02-19","No",null,null,"Internal"]
[null,null,null,null,null,"131_9/4/2022 3:00:48 PM","2022-02-13","Defect,Observation","Ship Staff","Ship Staff Insp.","NO.1 BOILER FO BURNING PUMP MOTOR HAVING SOME NOISE AND VIBRATION DURING OPERATION.","E/R - Aux. Mach.,E/R - Boiler","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","NO.1 BOILER FO BURNING PUMP MOTOR OVERHAULED WITH NEW BEARINGS AND ALIGNED WITH PUMP TRIED OUT, FOUND SATISFACTORY.","2022-03-31",null,"Completed","2022-02-26","No",null,null,"Internal"]
[null,null,null,null,null,"131_8/4/2022 9:05:42 PM","2022-02-15","Defect","Ship Staff","Ship Staff Insp.","NO.1 LT COOLER STRAINER FOUND DAMAGED WHILE INSPECTION.\t","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",null,null,"Not Applicable","Not Applicable","FABRICATED NEW STRAINER WITH AVAILABLE MATERIAL ONBOARD, PUT BACK","2022-03-07",null,"Completed","2022-02-15","No",null,null,"Internal"]
[null,null,null,null,null,"131_9/4/2022 10:24:44 AM","2022-02-15","Defect,Observation","Ship Staff","Ship Staff Insp.","ME UNIT 6 JW LEAKING FROM PIPE CONNECTING CYLINDER HEAD AND JACKET.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","UNIT 6 DRAINED. ORING FOR CONNECTION TUBE AND GASKET RENEWED.","2022-03-15",null,"Completed","2022-03-18","No",null,null,"Internal"]
[null,null,null,null,null,"131_9/4/2022 11:53:08 AM","2022-02-16","Defect,Observation","Ship Staff","Ship Staff Insp.","NO.1 AUX BOILER FO CONTROLLER KEYPAD NOT WORKING, PLC ERROR FOR BOTH BOILER, BOTH BOILER GIVING SMOKE DURING START.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","BOILER TECHNICIAN VISITED AT SINGAPORE, changed no-1 boiler F.O flow controller key pad, changed plc battery for both boilers,air flow controller parameter checked and adjusted for both boiler.  ","2022-03-20",null,"Completed","2022-02-22","No",null,null,"Internal"]
[null,null,null,null,null,"131_8/4/2022 10:14:28 PM","2022-02-18","Defect","Ship Staff","Ship Staff Insp.","O2 ANALYSER SHOWING IRRATIC READING EVEN AFTER CALIBRATION, SUPECTING O2 SENSOR MALFUNCTIONING. ","Inert Gas","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","CHANGED WITH AVAILABLE ONBOARD SPARE SENSOR AND CALIBRATION DONE. FOUND SATISFACTORY.","2022-03-15",null,"Completed","2022-02-20","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 12:53:25 PM","2022-02-18","Defect,Observation","Ship Staff","Ship Staff Insp.","NO.2 BOILER SUPPLY PUMP LEAKING FROM MECH. SEAL. REQUIRED TO RENEW MECH SEAL.","E/R - Aux. Mach.,E/R - Boiler","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","NO.2 BOILER SUPPLY PUMP OVERHAULED WITH NEW MECHANICAL SEAL AND BEARING.","2022-04-18",null,"Completed","2022-03-19","No",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 2:26:49 PM","2022-02-19","Defect","Ship Staff","Ship Staff Insp.","DAMAGED AND WASTED GOOSENECK VENT ON FUNNEL DECK","Miscellaneous","General Appearance","Equipment Related",11.7,"High","Not Applicable","Not Applicable","Cropped and Fabricated.","2022-07-07","NA","Completed","2022-04-14","No",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:18:58 PM","2022-02-19","Defect","Ship Staff","Ship Staff Insp.","Funnel deck fish plate Port Side wasted and broken","Miscellaneous","General Appearance","Equipment Related",11.8,"Low","Not Applicable","Not Applicable","Cropped and Fabricated.","2022-07-07",null,"Completed","2022-04-14","No",null,null,"Internal"]
[null,null,null,null,null,"131_6/4/2022 3:20:50 PM","2022-02-19","Defect","Ship Staff","Ship Staff Insp.","Funnel deck fish plate Stbd Side wasted and broken.","Miscellaneous","General Appearance","Equipment Related",11.8,"Low","Not Applicable","Not Applicable","Cropped and Fabricated.","2022-07-07",null,"Completed","2022-04-14","No",null,null,"Internal"]
[null,null,null,null,null,"131_9/4/2022 2:44:39 PM","2022-02-22","Defect,Observation","Ship Staff","Ship Staff Insp.","COPT WARM UP VALVES NOT HOLDING","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","REPLACED WITH AVAILABLE SPARE ONBOARD.","2022-05-01",null,"Completed","2022-04-04","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 1:38:43 PM","2022-02-22","Defect,Observation","Ship Staff","Ship Staff Insp.","GALLEY O/B PIPE GOT HOLED AND LEAKING. NEED RENEWAL 2 PPIPE SECTIONS.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","GALLY O/B 2 PIPE SECTIONS TAKEN OUT, AND FABRICATED IN WORKSHOP WITH INSIDE PRIMER COATING AND REPLACED IT.","2022-04-08",null,"Completed","2022-04-06","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 1:21:02 PM","2022-02-24","Defect,Observation","Ship Staff","Ship Staff Insp.","NO.1 ECONOMISER FEED PUMP MOTOR HAVING NOISE AND VIBRATION ISSUE WHILE IN OOPERATION.","E/R - Aux. Mach.,E/R - Boiler","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","NO.1 ECO. FEED PUMP MOTOR OVERHAULED WITH NEW BEARINGS, APPLIED WARNISH TO ROTOR AND STATOR. ASSEMBLED AND ALIGNED WITH PUMP, TRIED OUT FOUND SATISFACTORY.","2022-04-30",null,"Completed","2022-03-30","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 12:43:03 PM","2022-02-25","Defect,Observation","Ship Staff","Ship Staff Insp.","AFT HYD. COOLER SW COOLING LINE RUSTED/THINNED DOWN AND HOLED MANY PLACES.","E/R - Aux. Mach.,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","ENTIRE SW COOLING LINE HAVING 8 PIPE SECTION GABRICATED IN WORKSHOP AND PUT BACK.","2022-04-30",null,"Completed","2022-03-19","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 1:27:02 PM","2022-03-05","Defect,Observation","Ship Staff","Ship Staff Insp.","SEWAGE  VENT PIPE NEAR BOILER PLATFORM RUSTED AND HOLED. NEED RENEWAL","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","3 PIPE SECTIONS OF SEWAGE VENT PIPE TAKEN OUT, FABRICATED IN WORKSHOP AND REPLACED.","2022-04-08",null,"Completed","2022-04-04","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 9:45:57 AM","2022-03-06","Defect,Observation","Ship Staff","Ship Staff Insp.","SIGNAL LIGHT COLUMN PCB FAULTY.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","REPLACED WITH SPARE PCB ONBOARD.","2022-06-06",null,"Completed","2022-04-05","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 1:43:13 PM","2022-03-08","Defect,Observation","Ship Staff","Ship Staff Insp.","ACCESS PLATFORM FROM C DECK TO ER VENT FAN DECK  SECURING BOLT MISSING.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","ACCESS PLATFORM FROM C DECK TO ER VENT FAN DECK  FASTENED WITH PLATE AND SECURING BOLT.","2022-05-08",null,"Completed","2022-03-21","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 3:13:46 PM","2022-03-12","Defect,Observation","Ship Staff","Ship Staff Insp.","ME UNIT 2 PUNCTURE VALVE LEAKING","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","ME UNIT 2 PUNCTURE VALVE REPLACED WITH OVERHAULED SPARE ONBOARD.","2022-03-31",null,"Completed","2022-03-30","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 3:18:23 PM","2022-03-15","Defect,Observation","Ship Staff","Ship Staff Insp.","STBD SIDE PROV. CRANE RUNNER LIMIT SWITCH STUCK IN ACTIVATED POSITION DUE TO WHICH CRANE CAN NOT HEAV UP LOAD.","Deck - Machinery","Safety / LSA / FFA","Equipment Related",null,null,"Not Applicable","Not Applicable","STUCKED LIMIT SWITCH REPLACED WITH AVAILABLE ONBOARD SPARE, CRANE OPERATION TRIED OUT FOUND TO BE SATISFACTORY.","2022-04-10",null,"Completed","2022-03-25","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 1:02:12 PM","2022-03-26","Defect,Observation","Ship Staff","Ship Staff Insp.","DECK SEAL PUMP COMMON SUCTION LINE GOT HOLED, LEAKING.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","TAKEN OUT THE PIPESECTION, FABRICATED IN WORKSHOP. AND REPLACED IT.","2022-04-05",null,"Completed","2022-03-26","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 1:33:34 PM","2022-04-01","Defect,Observation","Ship Staff","Ship Staff Insp.","NO.2 ME CIRCULATING PUMP HAVING NOISE AND VIBRATION WHILE IN OPERATION.","E/R - Aux. Mach.,E/R - Pumps","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","NO.2 ME CIRC PUMP OVERHAULED WITH NEW BEARINGS AND IDLE ROTORS. TRIED OUT FOUND SATISFACTORY.","2022-05-08",null,"Completed","2022-04-04","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:03:55 PM","2022-04-01","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE OF P/ROOM DAVIT/SUNDER-PRIMER-FULL COATING","Miscellaneous","General Appearance","External Factors",11.1,"High","Not Applicable","Not Applicable","DE - RUSTING AND PAINTING COMPLETED","2022-07-06",null,"Completed","2022-04-20","No",null,null,"Internal"]
[null,null,null,null,null,"131_10/4/2022 3:03:05 PM","2022-04-02","Defect,Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FWG EVAPORATING SHELL CORRODED AND THINNED DOWN FROM INSIDE, HAVING ONE INCH HOLE WHICH TEMPORARALY FILLED WITH CEMENT BOX.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related",10.32,"Very High","Not Applicable","Not Applicable","FWG CONDENSER TOP COVER OPENED, ENTIRE AREA CHIPPED FROM INSIDE, DOUBLER WELDED ON DAMAGED/HOLED AREA. COATED WITH EPOXY PAINT 3 COATS. DEMISTER WASHED AND CLEANED. ","2022-07-31",null,"Completed","2022-04-15","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:37:33 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AFT MOORING AREA DECK SURFACE SPOT SUNDER/CHIPPING/PRIMER\r\nFULL COATING OF AFT DECK SURFACE\r\n","Miscellaneous","General Appearance","External Factors",null,null,"Not Applicable","Not Applicable","DE-RUSTING AND PAINTING COMPLETED","2022-07-01",null,"Completed","2022-04-14","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:00:02 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE-CHIPPING SUNDER-PRIMER/FULL COATING/MARKING BLOCK DAVIT FORECASTLE - CLIPPER RECTIFICATION","Miscellaneous","General Appearance","External Factors",11.1,"High","Not Applicable","Not Applicable","DE - RUSTING AND PAINTING COMPLETED","2022-07-02",null,"Completed","2022-04-20","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:27:57 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ARRANGEMENTS TO BE MADE TO FORECASTLE IN THE GRATINGS/SPARE RUBBERS ETC. REMOVE OBJECTS / GENERAL CLEANINGS  – HOUSEKEEPING OF FORECASTLE","Miscellaneous","General Appearance","External Factors",11.12,"Low","Not Applicable","Not Applicable","GENERAL HOUSEKEEPING AND CLEANING COMPLETED","2022-07-02",null,"Completed","2022-04-20","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:30:56 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","DERUSTING OF RAILS FM BOW TILL NO1WINGS PORT&STBD-REFRESH COATING","Miscellaneous","General Appearance","External Factors",11.1,"High","Not Applicable","Not Applicable","DE - RUSTING AND PAINTING COMPLETED","2022-07-02",null,"Completed","2022-04-19","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:24:23 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AFT ENTRANCE OF BOILER PLATFORM TO BE MAINTENANCED WEATHERTIGHT DOOR FULL COATING+ MARKING","Miscellaneous","General Appearance","External Factors",11.1,"High","Not Applicable","Not Applicable","DE - RUSTING AND PAINTING COMPLETED","2022-07-02",null,"Completed","2022-04-20","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:46:24 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ISOLATION VALVES FOAM FIRE LINE UP FROM THE P/ROOM ENTRANCE TO BE MAINTENANCED-CHIPPING/SUNDER/FULL COATING","LSA / FFA","General Appearance","External Factors",11.1,"High","Not Applicable","Not Applicable","DE - RUSTING AND PAINTING COMPLETED","2022-07-31",null,"Completed","2022-04-20","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 5:29:10 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","PROPER ARRANGEMENTS TO BE MADE ON HELICOPTER EQUIP.BOX PORT MIDSHIP STORE","LSA / FFA","Safety / LSA / FFA","External Factors",5.13,"High","Not Applicable","Not Applicable","ALL HELICOPTER EQUIPMENTS ARE ARRANGED.","2022-07-02",null,"Completed","2022-04-20","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:36:13 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE OF PLATFORM EMCY GENERATOR ENTRANCE DERUSTING /SUNDER/PRIMER/FULL COATING","Miscellaneous","General Appearance","External Factors",11.1,"High","Not Applicable","Not Applicable","DE - RUSTING AND PAINTING COMPLETED","2022-07-15",null,"Completed","2022-04-20","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 12:39:24 PM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","PUMPMAN’S STORE WEATHERTIGHT DOOR TO BE DERUSTING FULL COATING +MARKING STENCILS","Miscellaneous","General Appearance","External Factors",11.1,"High","Not Applicable","Not Applicable","DE - RUSTING AND PAINTING COMPLETED","2022-07-08",null,"Completed","2022-04-20","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:35:00 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAINTENANCE-SUNDER-CHIPPING-FULL COATING FWD LIFEJACKET BOX NEXT TO FWD LIFERAFT","Miscellaneous","General Appearance","External Factors",11.1,"High","Not Applicable","Not Applicable","DE - RUSTING AND PAINTING COMPLETED","2022-07-02",null,"Completed","2022-04-20","No",null,null,"Internal"]
[null,null,null,null,null,"131_7/4/2022 10:26:24 AM","2022-04-02","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FWD WIRE SUPPORT SUNDER-PRIMER-FULL COATING","Miscellaneous","General Appearance","External Factors",11.1,"High","Not Applicable","Not Applicable","DE - RUSTING AND PAINTING COMPLETED","2022-07-02",null,"Completed","2022-04-20","No",null,null,"Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":427,"n_cols":3,"rows_kept":427,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",8243]
["1.10","Low",8252]
["1.11","Low",8253]
["1.12","Low",8254]
["1.13","Low",8255]
["1.14","Low",8256]
["1.15","Low",8257]
["1.16","Low",8259]
["1.17","Low",8260]
["1.18","Low",8261]
["1.19","Low",8262]
["1.2","Low",8244]
["1.20","Low",8263]
["1.21","Low",8265]
["1.22","Low",8266]
["1.23","Low",8267]
["1.24","Low",8268]
["1.25","Low",8269]
["1.26","Low",8270]
["1.3","Low",8245]
["1.4","Low",8246]
["1.5","Low",8247]
["1.6","Low",8248]
["1.7","Low",8249]
["1.8","Low",8250]
["1.9","Low",8251]
["1.99","High",11258]
["10.1","Medium",8461]
["10.10","High",8470]
["10.11","Medium",8471]
["10.12","Very High",8472]
["10.13","Very High",8473]
["10.14","Medium",8474]
["10.15","Low",8475]
["10.16","Very High",8476]
["10.17","Very High",8477]
["10.18","High",8478]
["10.19","Very High",8479]
["10.2","Low",8462]
["10.20","High",8480]
["10.21","Medium",8481]
["10.22","Low",8482]
["10.23","Medium",8483]
["10.24","Low",8484]
["10.25","Very High",8485]
["10.26","High",8486]
["10.27","Medium",8487]
["10.28","Low",8488]
["10.29","Medium",8489]
["10.3","Medium",8463]
["10.30","High",8490]
["10.31","Very High",8491]
["10.32","Very High",8492]
["10.33","High",8493]
["10.34","High",8494]
["10.35","Very High",8495]
["10.36","Very High",8496]
["10.37","Medium",8497]
["10.38","Medium",8498]
["10.39","High",8499]
["10.4","High",8464]
["10.40","Medium",8500]
["10.41","Medium",8501]
["10.42","Medium",8502]
["10.43","Medium",8503]
["10.44","Medium",8504]
["10.45","Very High",8505]
["10.46","High",8506]
["10.47","Medium",8507]
["10.48","High",8508]
["10.49","Medium",8509]
["10.5","Low",8465]
["10.50","High",8510]
["10.51","Low",8511]
["10.52","Medium",8512]
["10.53","Medium",8513]
["10.54","High",8514]
["10.55","Low",8515]
["10.6","Very High",8466]
["10.7","Medium",8467]
["10.8","Medium",8468]
["10.9","Medium",8469]
["10.99","High",8516]
["11.1","High",8420]
["11.10","Medium",8429]
["11.11","Very High",8430]
["11.12","Low",8431]
["11.13","Low",8432]
["11.14","Medium",8433]
["11.15","Low",8434]
["11.16","Low",8435]
["11.17","Low",8436]
["11.2","Medium",8421]
["11.3","Medium",8422]
["11.4","Very High",8423]
["11.5","Medium",8424]
["11.6","Medium",8425]
["11.7","High",8426]
["11.8","Low",8427]
["11.9","Low",8428]
["11.99","High",8437]
["12.1","High",8438]
["12.10","High",8448]
["12.11","High",8449]
["12.12","High",8450]
["12.13","High",8451]
["12.14","High",8452]
["12.15","High",8453]
["12.16","High",8454]
["12.17","High",8455]
["12.18","High",8456]
["12.19","High",8457]
["12.2","High",8439]
["12.20","High",8458]
["12.21","High",8459]
["12.3","High",8441]
["12.4","High",8442]
["12.5","High",8443]
["12.6","High",8444]
["12.7","High",8445]
["12.8","High",8446]
["12.9","High",8447]
["12.99","High",8460]
["2.1","Very High",8296]
["2.1.9","Very High",11259]
["2.10","Medium",8304]
["2.11","Medium",8305]
["2.12","Low",8306]
["2.13","Low",8307]
["2.14","Low",8308]
["2.15","Low",8309]
["2.16","Medium",8310]
["2.2","Medium",8297]
["2.3","High",8295]
["2.4","Medium",8298]
["2.5","Medium",8299]
["2.6","Low",8300]
["2.7","High",8301]
["2.8","High",8302]
["2.9","Medium",8303]
["2.99","High",8311]
["3.1","High",8312]
["3.2","Very High",8313]
["3.3","High",8314]
["3.4","Low",8294]
["3.5","Medium",8315]
["3.6","High",8316]
["3.7","Very High",8317]
["3.8","Very High",8318]
["3.99","High",8319]
["4.1","High",8320]
["4.10","High",8329]
["4.11","Medium",8330]
["4.12","Very High",8331]
["4.13","Very High",8332]
["4.14","Very High",8333]
["4.15","Very High",8334]
["4.16","Very High",8335]
["4.17","Very High",8336]
["4.18","Very High",8337]
["4.19","Low",8338]
["4.2","Medium",8321]
["4.20","Very High",8339]
["4.21","High",8340]
["4.22","Low",8341]
["4.23","High",8342]
["4.24","High",8343]
["4.25","Low",8344]
["4.26","Low",8345]
["4.27","High",8346]
["4.3","Medium",8322]
["4.4","High",8323]
["4.5","Very High",8324]
["4.6","Medium",8325]
["4.7","High",8326]
["4.8","Medium",8327]
["4.9","Medium",8328]
["4.99","High",8347]
["5.1","Very High",8517]
["5.10","High",8526]
["5.11","Low",8527]
["5.12","Medium",8528]
["5.13","High",8529]
["5.14","Very High",8530]
["5.15","Medium",8531]
["5.16","Very High",8532]
["5.17","Very High",8533]
["5.18","High",8534]
["5.19","Medium",8535]
["5.2","Very High",8518]
["5.20","Medium",8536]
["5.21","Medium",8537]
["5.22","High",8539]
["5.23","Very High",8540]
["5.24","Very High",8541]
["5.25","Medium",8542]
["5.26","Medium",8543]
["5.27","Medium",8544]
["5.28","Very High",8545]
["5.29","High",8546]
["5.3","Low",8519]
["5.30","High",8547]
["5.31","High",8548]
["5.32","High",8549]
["5.33","High",8550]
["5.34","Low",8551]
["5.35","Medium",8552]
["5.36","Low",8553]
["5.37","Low",8554]
["5.38","High",8555]
["5.39","Very High",8556]
["5.4","High",8520]
["5.40","Very High",8557]
["5.41","Very High",8558]
["5.42","Medium",8559]
["5.43","High",8560]
["5.44","High",8561]
["5.45","Medium",8564]
["5.46","Medium",8565]
["5.47","Medium",8566]
["5.48","Medium",8567]
["5.5","Low",8521]
["5.6","Low",8522]
["5.7","Medium",8523]
["5.8","Medium",8524]
["5.9","Very High",8525]
["5.99","High",8568]
["6.1","Medium",8348]
["6.10","Low",8357]
["6.11","High",8358]
["6.12","Medium",8359]
["6.13","Low",8360]
["6.14","High",8361]
["6.15","High",8362]
["6.16","Very High",8363]
["6.17","Very High",8364]
["6.18","Medium",8365]
["6.19","Low",8366]
["6.2","High",8349]
["6.20","Medium",8367]
["6.21","High",8368]
["6.22","Medium",8369]
["6.3","Low",8350]
["6.4","High",8351]
["6.5","Medium",8352]
["6.6","Medium",8353]
["6.7","High",8354]
["6.8","High",8355]
["6.9","Low",8356]
["6.99","High",8370]
["7.1","High",8371]
["7.10","High",8380]
["7.11","High",8381]
["7.12","High",8382]
["7.13","Medium",8383]
["7.14","Medium",8384]
["7.15","High",8385]
["7.16","High",8386]
["7.17","High",8387]
["7.2","High",8372]
["7.3","Low",8373]
["7.4","Low",8374]
["7.5","Low",8375]
["7.6","Medium",8376]
["7.7","Low",8377]
["7.8","High",8378]
["7.9","High",8379]
["7.99","High",8388]
["8.1","Very High",8569]
["8.10","Very High",8578]
["8.100","Low",11227]
["8.101","Medium",11228]
["8.102","Low",11229]
["8.103","Low",11230]
["8.104","Low",11231]
["8.105","Medium",11232]
["8.106","Medium",11233]
["8.107","Low",11234]
["8.108","High",11235]
["8.109","Very High",11236]
["8.11","Medium",8579]
["8.110","High",11237]
["8.111","Medium",11238]
["8.112","High",11239]
["8.113","Medium",11240]
["8.114","Low",11241]
["8.115","High",11242]
["8.116","Medium",11243]
["8.117","Medium",11244]
["8.118","Medium",11245]
["8.119","High",11246]
["8.12","Medium",8580]
["8.120","High",11247]
["8.121","Medium",11248]
["8.122","High",11249]
["8.123","High",11250]
["8.124","Low",11251]
["8.125","High",11252]
["8.126","Medium",11253]
["8.127","Medium",11254]
["8.13","Medium",8581]
["8.14","Very High",8582]
["8.15","High",8583]
["8.16","Very High",8584]
["8.17","Low",8585]
["8.18","High",8586]
["8.19","High",8587]
["8.199","High",11255]
["8.2","Medium",8570]
["8.20","Medium",8588]
["8.21","High",8589]
["8.22","Very High",8590]
["8.23","Medium",8591]
["8.24","Medium",8592]
["8.25","Very High",8593]
["8.26","High",8594]
["8.27","Medium",8595]
["8.28","Medium",8596]
["8.29","High",8598]
["8.3","Very High",8571]
["8.30","High",8599]
["8.31","High",8600]
["8.32","Low",8601]
["8.33","Medium",8602]
["8.34","High",8603]
["8.35","Medium",8604]
["8.36","Medium",8605]
["8.37","High",8607]
["8.38","Medium",8608]
["8.39","Medium",8609]
["8.4","Medium",8572]
["8.40","High",8610]
["8.41","Medium",8611]
["8.42","Medium",8612]
["8.43","Very High",8613]
["8.44","High",8615]
["8.45","High",8616]
["8.46","Very High",8617]
["8.47","Very High",8618]
["8.48","Medium",8619]
["8.49","High",8620]
["8.5","Very High",8573]
["8.50","Medium",8621]
["8.51","Low",8622]
["8.52","Low",8623]
["8.53","Low",8624]
["8.54","High",8625]
["8.55","Low",11182]
["8.56","Medium",11183]
["8.57","Medium",11184]
["8.58","High",11185]
["8.59","High",11186]
["8.6","Medium",8574]
["8.60","High",11187]
["8.61","Medium",11188]
["8.62","Very High",11189]
["8.63","High",11190]
["8.64","Medium",11191]
["8.65","Low",11192]
["8.66","High",11193]
["8.67","High",11194]
["8.68","High",11195]
["8.69","Medium",11196]
["8.7","High",8575]
["8.70","Medium",11197]
["8.71","Very High",11198]
["8.72","Medium",11199]
["8.73","Medium",11200]
["8.74","High",11201]
["8.75","Medium",11202]
["8.76","Medium",11203]
["8.77","Medium",11204]
["8.78","Medium",11205]
["8.79","Medium",11206]
["8.8","Medium",8576]
["8.80","Medium",11207]
["8.81","Low",11208]
["8.82","Medium",11209]
["8.83","Low",11210]
["8.84","Low",11211]
["8.85","Medium",11212]
["8.86","Medium",11213]
["8.87","Medium",11214]
["8.88","Low",11215]
["8.89","High",11216]
["8.9","High",8577]
["8.90","High",11217]
["8.91","High",11218]
["8.92","Medium",11219]
["8.93","Low",11220]
["8.94","Low",11221]
["8.95","Medium",11222]
["8.96","Medium",11223]
["8.97","Low",11224]
["8.98","High",11225]
["8.99","Medium",11226]
["9.1","Low",8390]
["9.10","Medium",8399]
["9.11","Medium",8400]
["9.12","Medium",8401]
["9.13","Low",8402]
["9.14","Medium",8403]
["9.15","Medium",8404]
["9.16","High",8405]
["9.17","High",8406]
["9.18","Low",8407]
["9.19","Low",8408]
["9.2","Very High",8391]
["9.20","Medium",8409]
["9.21","Medium",8410]
["9.22","Low",8411]
["9.23","Low",8412]
["9.24","Medium",8413]
["9.25","Low",8414]
["9.26","Low",8415]
["9.27","Low",8416]
["9.28","Medium",8417]
["9.29","Low",8418]
["9.3","Very High",8392]
["9.4","High",8393]
["9.5","High",8394]
["9.6","Low",8395]
["9.7","Medium",8396]
["9.8","Medium",8397]
["9.9","Medium",8398]
["9.99","High",8419]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["131","ONISILOS","131_1649044447968.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]