## Report
SR.NO. | Record Date | Vessel Name | Observer code | Type of Inspection | Column1 | Equipment Categories | Area of Observation | Deficiency Cause | ACTION /STATUS
1 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Hatch cover hydraulic pipe corroded , leaky at various location. | PIPING | DECK | EQUIPMENT RELATED | RECTIFICATION IN PROGRESS (RAISED RO-NATT220091 )
2 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Main air compressor was reported that cylinder head gasket burst out frequently due to no original spares onboard , communication already going on this , aeration issue also exists | ER MC -MAC | E/R | EXTERNAL FACTORS | LOT OF MAINTENANCE ALREADY DONE ON MAC , RECORDED IN DWD , RAISED RO-NATT220006 & NATT220088
3 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Stbd side anchor windlass was reported heavy vibration | MOORING EQMT | DECK | EQUIPMENT RELATED | TRIED OT STBD WINDLASS , FOUN NO VIBRATION IN GEAR CASE AND HYD MOTOR , CHAIN STOPPER ROLLER HAS WOBBLING EFFECT IN P-S DIRECTION , OFFICE COMMUNICATION GOING ON THIS
5 |  | M V NATTY | SUPERINTENDENT | INTERNAL | New evaporator for AHU was received onboard, CE is working on replacement. |  | AHU ROOM |  | JOB IN PROGRESS
4 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Emergency fire pump discharge pressure was at 7.0 bar, but no water discharge from forecastle fire hose. | PUMPS | E/R | EQUIPMENT RELATED | RAISED RO -NATT220033
5 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | No.2 ballast pump damaged, spare parts procurement was in progress. | PUMPS | E/R | EQUIPMENT RELATED | RAISED RO-NATT225003 ( NATT210038 ) / NATT220026 , RECONDITIONED PUMP BEING CONNECTED AT SINGAPORE
6 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Life raft service and HRU will be expired in Jun 2022. same has been instructed CO to inform office to arrange. | SAFETY , LSA | DECK | EXTERNAL FACTORS | TO SEND ASHORE FOR SERVICING
7 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Windlass and mooring winch body and their hydraulic pipe rust developing. | MOORING EQMT | DECK | HUMAN RELATED | DERUSTING AND PAINTING JOB IN PROGRESS.
8 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Forecastle anchor washing sea water pressure gauge damaged. | GAUGES | DECK | HUMAN RELATED | NEED TO RECTIFY
9 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Draft gauge pneumatic pipe on deck was corroded and supporting bracket was wasted. | GAUGES | DECK | BEHAVIOUR BASED | NEED FITTER ASSISTANCE.
10 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Mono rail crane was not operational fully, travelling gear and pinion not meshing , issue is with the traversing plate | CRANE | DECK | EQUIPMENT RELATED | DETAILED REPORT & JOB SCOPE ALREADY SENT TO OFFICE , AWAITING FOR WORK SHOP
11 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | ER Ventilation fan cosmetic upgradation need to be attended. | BLOWERS | DECK | HUMAN RELATED | COMPLETED
12 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Valve position indication for Water ballast valve 3s,4s was not working properly. | VALVES | CCR | EQUIPMENT RELATED | NEED FURTHER INVISTIGATION
13 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Both ECDIS was reported response slowly, recommended to upgrade to new version. | NAVIGATION | BRIDGE | EQUIPMENT RELATED | WAITING FOR OFFICE INSTRUCTIONS
14 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Rust development on main deck, cross deck and superstructure, cosmetic upgradation in progress. | DECK COSMETICS | DECK | HUMAN RELATED | DERUSTING AND PAINTING JOB IN PROGRESS.
15 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Cosmetic upgradation for cargo hold hatch cover was in progress, No.1, No.2 and No.3 was completed. | DK COSMETICS | DECK | HUMAN RELATED | COMPLETED
16 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Rust developing on hatch cover hydraulic motor, hydraulic jack and their hydraulic hose connection, de-rusting and coating need to be prioritized. | DECK COSMETICS | DECK | HUMAN RELATED | DERUSTING AND PAINTING JOB IN PROGRESS.
17 | 2021-12-08 | M V NATTY | SUPERINTENDENT | INTERNAL | Chain block in forecastle bosun store to be arranged properly. | HOUSEKEEPING | DECK | HUMAN RELATED | COMPLETED
18 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | GARBAGE COMPACTOR TO BE INSTALLED | MACHINE | ER | EQUIPMENT RELATED | ALREADY INSTALLED , RO RAISED NATTY 220093 FOR CONTACTOR
19 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | HATCH COVER HYD RAM LEAKING 2 AFT/FWD RAM, No. 7 FWD RAM. | LEAKS | DECK | EQUIPMENT RELATED | SPARE RAM RECEIVED RECENTLY , NEED TO RECTIFY
20 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | HATCH SOCKET LIGHT BOX RUSTED | ELEC. MACH & EQUIP. | DECK | EQUIPMENT RELATED | SPARES RECEIVED WORK IN PROGRESS
21 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | HATCH COVER HYD DRIVING MOTOR LEAKING (No. 2 & 4 PORT/STBD, No. 6 STBD) | DECK -PIPE/FITTINGS | DECK | EQUIPMENT RELATED | RAISED RO-NATT225009
22 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | VARIOUS VENTS FLAME ARRESTORS CHECKING ALREADY STARTED , SAME TO BE STENCILED & CHECKED | DECK -PIPE/FITTINGS | DECK | HUMAN RELATED | COMPLETED
23 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | RESCUE BOAT GASOLINE OIL IN FRWD PAINT LOCKER TO BE SHIFTED IN STEERING GEAR ROOM | HOUSEKEEPING | E/R | HUMAN RELATED | COMPLETED
24 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | SCBA COMPRESSOR FONDATION TO BE MADE | DECK- MACHINERY | EMERG GEN ROOM | HUMAN RELATED | TO START
25 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | ARRANGE CHEMICAL STORAGE AREA | HOUSEKEEPING | STEERING ROOM | HUMAN RELATED | COMPLETED, SEPERATED AS PER ACIDIC ALKALINE
26 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | EMERGENCY GENERATOR ROOM FLAP VENT MESH BROKEN SAME TO RECTIFIED | MACHINERY | EM DG | EQUIPMENT RELATED | ALREADY REPAIRED THE DAMPERS , OUTSIDE MESH TO REPAIR
27 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | EMERGENCY FIRE PUMP BILGES TO BE DE- RUSTED | HOUSEKEEPING | ER | EXTERNAL FACTORS | COMPLETED
28 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | AC ROOM FRESH AIR INLET FINS DAMAGED | POOR METAL | ER | EXTERNAL FACTORS | WORK IN PROGRESS
29 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | ICCP FORE PEAK STORE DISPLAY NOT WORKING | ELEC. MACH & EQUIP. | DECK | EQUIPMENT RELATED | RO RAISED NATTY 220077
30 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | CANVAS COVER TO BE MADE FOR PRESSURE GAUGE AND THERMOMEATER IN BUNKER MANIFOLD | DECK -PIPE/FITTINGS | DECK | HUMAN RELATED | COMPLETED
31 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | PAINT ROOM AND MID SHIP BOSUN STORE EXHAUST FAN STARTING PANEL RUSTED | ELEC. MACH & EQUIP. | DECK | HUMAN RELATED | DE RUSTED AND PAINTED
32 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | BILGE HOLDING TANK NEEDS TO BE CLEANED AND IT IS IN THIS CONDITION SINCE TAKEOVER, HENCE WE DO NOT GO BELOW 10 M3 WHEN RUNNING OWS TO AVOID OIL , SAME TO BE CLEANED | HOUSEKEEPING | ER | INAPPROPRIATE PROCEDURES | ALREADY CLEANED AND PUT IN USE
33 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | ARROWS LEADUP TO EMERGENCY ESCAPE ON E/R 2ND DECK TO BE PASTED | SAFETY , LSA | ER | HUMAN RELATED | COMPLETED
34 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | EMERGENCY ESCAPE PULLEY IS MISSING , SAME ALSO REPORTED IN THIS MONTHS HSQEEN PLUS IN LPSQ NCN . PULLEY TO BE FITTED FOR RESCUE PURPOSE ETC | SAFETY , LSA | ER | INAPPROPRIATE PROCEDURES | COMPLETED
35 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | CHINA PASSAGE TO BE SQUARED UP | MISCELLANEOUS | DECK | EXTERNAL FACTORS | GARBAGE NEED TO BE LANDED IN FIRST OPPORTUNITY
36 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | DATE OF FLASHBACK ARRESTOR TO PUT | SAFETY | ER | EXTERNAL FACTORS | RAISING FRESH RO AS 2021 RO CANCELLED
37 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | BUNKER TANKS VENT HEAD NOT CLEANED | HOUSEKEEPING | ER | HUMAN RELATED | COMPLETED
38 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | DRAIN PLUG NOT HOLDING PROPERLY | DECK COSMETICS | ER | EQUIPMENT RELATED | COMPLETED
39 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | DUCT KEEL ENTRANCE MARK TO BE PLACED | ER COSMETICS | ER | INAPPROPRIATE PROCEDURES | COMPLETED
40 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | EMERGENCY FIRE PUMP MINIMUM DRAFT MISSING | PUMPS | ER | INAPPROPRIATE PROCEDURES | COMPLETED
41 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | PURIFIER ROOM HOUSEKEEPING TO BE DONE | HOUSEKEEPING | ER | BEHAVIOUR BASED | COMPLETED
42 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | MOTORS NOT SECURED PROPERLY | MACHINE | ER | INAPPROPRIATE PROCEDURES | SECURED IN PLACE WITH ANGLE BARS
43 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | OPEN AND CLOSE STENCILS NEED TO BE RE DONE | DECK-MACHINERY | DECK | HUMAN RELATED | COMPLETED
44 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | VARIOUS PHOTOGRAPHIC PROCEDURES ARE MADE BUT NEED TO MAKE MORE | OPERATIONS | ER | EQUIPMENT RELATED | MANY MADE , JOB IN PROGRESS
45 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Level gauge for sewage holding tank completely broken | MACHINE | ER | EQUIPMENT RELATED | REPLACED WITH NEW, SATISFACTORY.
46 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Sight glass for f.w hydrophore water level not visible | MACHINE | ER | EQUIPMENT RELATED | CLEANED , NOW OK
47 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Three way change over valve actuator of fuel oil inlet and return line for all three generator engine and main engine are not connected | MACHINE | ER | EQUIPMENT RELATED | NEED FURTHER INVISTIGATION AND RAISE RO FOR THE SAME
48 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Engine room Service Air Compressor not operational | ER MC -MAC | ER | EQUIPMENT RELATED | NEED FURTHER INVISTIGATION AND RAISE RO FOR THE SAME , PARTS MISSING COMPLETELY , CRAMKSHAFT BAD
49 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Both AHU cabinet flaps having too much corrosion and mechanical damages. | MACHINE | ER | EQUIPMENT RELATED | NEED FURTHER INVISTIGATION AND RAISE RO FOR THE SAME
50 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | F.W. generator not creating enough vacuum with ejector p/p in loaded condition. | MACHINE | ER | EQUIPMENT RELATED | NEED FURTHER INVISTIGATION AND RAISE RO FOR THE SAME
51 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Rescue boat limit defective. | SAFETY , LSA | DECK | EQUIPMENT RELATED | REPLACED WITH NEW LIMIT SWITCH , TESTED WORKING SATISFACTORY.
52 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Bunker davit (port side) limit switch defective. | DECK-MACHINERY | DECK | EQUIPMENT RELATED | REPLACED WITH NEW LIMIT SWITCH , TESTED WORKING SATISFACTORY.
53 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Bilge pump starter contactor found defective. | MACHINE | ER | EQUIPMENT RELATED | REPLACED WITH NEW LIMIT SWITCH , TESTED WORKING SATISFACTORY.
54 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | 440 V and 220 V found with low insulation during takeover. | ELEC. MACH & EQUIP. | DECK | EQUIPMENT RELATED | RECTIFIED NOW INSULATION IS INFINITY.
55 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Main air compressor No. 1 liner and piston found scored. | ER MC -MAC | ER | EQUIPMENT RELATED | COMPLETED, RENEWED WITH NEW SPARES
56 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Need to replace flouresent lamp with led lights in engine room and accomodation | MACHINE | ACCOMODATION / ER | EQUIPMENT RELATED | WORK IN PROGRESS.
57 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | No spare magnetic contactors, relays and ACB's not available onboard. | ELEC. MACH & EQUIP. | ER | EQUIPMENT RELATED | RO S RAISED
58 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | E Room tanktop rusty and too much dirty with oil traces. | HOUSEKEEPING | ER | EXTERNAL FACTORS | DERUSTING AND PAINTING JOB IN PROGRESS.
59 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Bunker manifolds valves are hard to operate. | MACHINE | ER | EXTERNAL FACTORS | STBD SIDE VALVE ALREADY RENEWED , PORT SIDE NEED TO BE RENEWED.
60 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Spare parts room and Engine room store area, require housekeeping. | HOUSEKEEPING | ER | HUMAN RELATED | JOB IN PROGRESS
61 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Anti splashing tapes missing on ME, D.G. and tanks | SAFETY | ER | EQUIPMENT RELATED | COMPLETED
62 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | IMO symbols missing and escape route not marked in engine room. | SAFETY , LSA | ER | HUMAN RELATED | COMPLETED
63 | 2022-01-15 | M V NATTY | SHIP STAFF | INTERNAL | Electrical panels lamps missing not working. | SAFETY | ER | EQUIPMENT RELATED | RECTIFIED NOW ALL WORKING CONDITION.
64 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | E/R blower flaps not operational from remote location (fire control station). When operating locally, the lever needs to be eased up at least three times to close flaps | SAFETY , LSA | ER | EQUIPMENT RELATED | EASED UP , WORKING SATISFACTORY
65 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | Observed Aux engine #3 crank case relief doors (three in number) are continuously dripping lub oil when generator is running | HOUSEKEEPING | ER | EQUIPMENT RELATED | LEAKAGE ARRESTED
66 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | No. 2 H.F.O purifier not operational. | MACHINE | ER | EQUIPMENT RELATED | MADE OPERATIONAL AFTER TAKE OVER, PURIFIER IN USE
67 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | Aux. Engine Tank top oil leakage job pending | MACHINE | ER | EQUIPMENT RELATED | ARRESTED VARIOUS LEAKAGE AFTER TAKE OVER FROM ALL THREE AE'S
68 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | Aux. Engine fuel oil module, no #1 booster pump seal leaking. | MACHINE | ER | EQUIPMENT RELATED | BOOSTER PUMP MECHANICAL SEAL RENEWED AND PUMP O'HAULED AFTER TAKE OVER
69 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | Aux. Engine fuel oil module, no #2 booster pump seal leaking. | MACHINE | ER | EQUIPMENT RELATED | BOOSTER PUMP MECHANICAL SEAL RENEWED AND PUMP O'HAULED AFTER TAKE OVER
70 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | Standby air starting v/v's for M.E. not overhauled. | MACHINE | ER | EQUIPMENT RELATED | O'HAULED 2 NO SPARE VALVES AND KEPT STBY AFTER TAKE OVER
71 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | Standby F.O. injectors not overhauled and pressure tested. | MACHINE | ER | EQUIPMENT RELATED | O'HAULED 6.NO SPARE FUEL VALVES AFTER TAKE OVER.
72 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | Standby Fuel pump Puncture valve and suction valve, not overhauled. Spares for o'hauling old valves not available on-board. | MACHINE | ER | EQUIPMENT RELATED | O'HAULED 4.NO SPARE PUNCTURE VALVE AFTER TAKE OVER.
73 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | No new spare exhaust v/v seat on-board. a) three old exhaust valve seat which has to be send for reconditioning" | MACHINE | ER | EQUIPMENT RELATED | ALL READY RECEIVED SPARES AFTER TAKE OVER
74 | 2021-11-25 | M V NATTY | OBSERVER | INTERNAL | Cargo Hold ladders damaged at various locations. | CARGO HOLDS | DECK | EXTERNAL FACTORS | NEED FITTER ASSISTANCE.
75 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Stbd gangway head platform wasted | DECK-MACHINERY | DECK | EXTERNAL FACTORS | CHIPPING AND PAINTING CARRIED OUT.
76 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | As per master Stbd windless bushes worn( for the last 3 months Stbd anchor not used). | DECK-MACHINERY | DECK | EXTERNAL FACTORS | REPAIRS UNDER PLANING
77 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | ECDIS no back up memory ( only for 2 hours) | NAVIGATION-ECDIS | BRIDGE | EQUIPMENT RELATED | MANUFACTURING DEFECT
78 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | No3 A/E not operational waiting spare parts | MACHINE | E/R | EQUIPMENT RELATED | RECIVED NEW AIR STARTING MAOTOR AND FLYWHEEL RIM , FITTED AND AE#3 MADE OPERATIONAL
79 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Mooring ropes in poor condition No spare ropes on board | DECK- MOORING | DECK | EXTERNAL FACTORS | COMPLETED.
80 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Rendering points missed at winches (not available testing kit) | DECK- MOORING | DECK | HUMAN RELATED | COMPLETED.
81 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Snap back zones/dangerous zones not inscribed on deck | DECK- MOORING | DECK | HUMAN RELATED | COMPLETED.
82 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Markings and stencils around accommodation superstructures and deck found in poor condition, generally stencils not marked / inscribed. | ACCOMMODATION | DECK | HUMAN RELATED | COMPLETED.
83 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Weathertight doors poor condition/ frozen | ACCOMMODATION | DECK | HUMAN RELATED | COMPLETED.
84 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | bilges / water ingress alarm out of order | CARGO HOLDS | DUCT KEEL | EXTERNAL FACTORS | RECTIFIED, WORKING SATISFACTORY.
85 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Dewatering system alarm out of order | DECK-PIPE & FITTINGS | DECK | EQUIPMENT RELATED | RECTIFIED, WORKING SATISFACTORY.
86 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Dead man alarm out of order | SAFETY | ER | EQUIPMENT RELATED | RECTIFIED, WORKING SATISFACTORY.
87 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Gangways combination ladders foundations for rigging/secure the ladder on deck not existing ( ladder secured on railings) , ladder ropes passed over the fish plate ( Friction of ropes with the risk of being cut.) | DECK-MACHINERY | DECK | EXTERNAL FACTORS | COMPLETED.
88 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Hatch covers packing rubber painted | CARGO HOLDS | DECK | HUMAN RELATED | JOB UNDERWAY.
89 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Deck rusted | DECK | DECK | HUMAN RELATED | JOB UNDERWAY.
90 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Booby hatches heavily rusted | CARGO HOLDS | DECK | HUMAN RELATED | JOB UNDERWAY.
91 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Hatch coamings rusted | CARGO HOLDS | DECK | HUMAN RELATED | JOB UNDERWAY.
92 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Accommodation superstructures spot rusted. | ACCOMMODATION | DECK | HUMAN RELATED | COMPLETED
93 | 2021-12-08 | M V NATTY | OWNER | INTERNAL | Engine room found in a good cosmetic appearance, according C/E we have machinery and piping leakages |  | ER |  | OBESERVATION BY OWNER
94 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | CAPACITY OF PERSONS MISSING ON RESCUE BOAT | SAFETY , LSA | DECK | HUMAN RELATED | COMPLETED
95 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | REFELCTIVE TAPES TO CHANGE ON LIFEBOAT, RESCUE BOAT | SAFETY , LSA | DECK | HUMAN RELATED | COMPLETED
96 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | STENCILING MISSING ON E/R BLOWERS | E/R-MACHINERY | DECK | HUMAN RELATED | COMPLETED
97 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | LIFERAFT LOCATION OF POSTER TO CHANGE , TO PUT NEAR EMEREGNCY LIGHT | SAFETY , LSA | DECK | HUMAN RELATED | COMPLETED
98 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | STENCILING FADED ON MONKEY ISLAND | NAVIGATION | DECK | HUMAN RELATED | COMPLETED
99 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | DIRECTION SHOWING TOWARDS LIFEBOAT STATION MISSING | SAFETY, LSA | DECK | HUMAN RELATED | COMPLETED
100 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | LIFEBOAT TALK BACK SYSTEM STENCILL PLATE TO CLEAN. | SAFETY , LSA | DECK | EXTERNAL FACTORS | COMPLETED
101 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | WHEEL SPANNER TO PUT NEAR HYDRANT IN ACC. | SAFETY , LSA | DECK | KNOWLEDGE BASED | COMPLETED
102 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | WRONG LIFEBOAT PROCEDURE IN PLACE | SAFETY , LSA | DECK | HUMAN RELATED | REPLACED WITH CORRECT ONE, COMPLETED
103 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | GREASING NOT DONE FOR LIFEBOAT RELEASE HOOK | SAFETY , LSA | DECK | KNOWLEDGE BASED | COMPLETED
104 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | CLEANING OF THE ACRYLIC HATCHES TO DO FOR LIFEBOAT | SAFETY , LSA | DECK | HUMAN RELATED | COMPLETED
105 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | LAUNCHING PROCEDURE MISSING INSIDE LIFEBOAT , PROCEDURES ARE FOR WRONG TYPE BOAT | SAFETY , LSA | DECK | HUMAN RELATED | SAME RECTIFIED, COMPLETED
106 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | GRATINGS MISSING FOR ACC.DRAINS | ACCOMMODATION | DECK | EXTERNAL FACTORS | NEED FITTER ASSISTANCE.
107 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | REPAIRS TO DO ON PIPE FOR ACC.DRAINS | ACCOMMODATION | DECK | EXTERNAL FACTORS | NEED FITTER ASSISTANCE.
108 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | NOT SECURED TRASH CANS INSIDE ACC. | ACCOMMODATION | DECK | HUMAN RELATED | PENDING, NEED TO RECTIFY
109 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | TO CHANGE CANVAS FOR LIFERAFT LADDERS | LSA/FFA | DECK | EXTERNAL FACTORS | COMPLETED
110 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | STENCILING MISSING ON ISLOATION VALVE | SAFETY , LSA | DECK | HUMAN RELATED | COMPLETED
111 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | WRONG TOOLS IN PLACE , TO PUT CORRECT SPANNER FOR ISC | SAFETY , LSA | DECK | HUMAN RELATED | COMPLETED
112 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | CHANGE CANVAS FOR RESCUE BOAT ENGINE | SAFETY , LSA | DECK | HUMAN RELATED | JOB UNDERWAY.
113 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | BUTTERFLY NUT TO PUT ON LIFERAFT LIGHTS | SAFETY , LSA | DECK | EXTERNAL FACTORS | COMPLETED
114 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | POSTERS HOUSEKEEPING INSIDE ACC. TO IMPORVE | ACCOMMODATION | DECK | BEHAVIOUR BASED | COMPLETED
115 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | OLD MANAGEMENT NAME TO ERASE FROM BASKETBALL RING | ACCOMMODATION | DECK | EXTERNAL FACTORS | PAINTED
116 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | No smoking , no naked lights to stencil on both sides acc.entry | ACCOMMODATION | DECK | KNOWLEDGE BASED | COMPLETED
117 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Portholes rusted and rust stains near port holes on full acc. | ACCOMMODATION | DECK | EXTERNAL FACTORS | COMPLETED
118 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Suez room toilet bottom half bulkhead rusted. | ACCOMMODATION | DECK | EXTERNAL FACTORS | COMPLETED
119 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Funnel deck mushroom vent electrical junction box broken | E/R-MACHINERY | DECK | HUMAN RELATED | RECTIFIED.
120 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Stbd side a deck weathertight door dog legs rusted. | ACCOMMODATION | DECK | HUMAN RELATED | PENDING, NEED TO RECTIFY
121 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Pipe ducts filled with electrical items. Need to be cleared. |  | ACCOMODATION |  | WAITING FOR BOXES
122 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Crew laundry tiles broken. | ACCOMMODATION | ACCOMODATION | EXTERNAL FACTORS | COMPLETED
123 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Crew laundry dryer not operational. | ACCOMMODATION | ACCOMODATION | EXTERNAL FACTORS | RAISED RO NATT220025
124 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Change room floor tiles broken | ACCOMMODATION | ACCOMODATION | EXTERNAL FACTORS | COMPLETED
125 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Tools need to be removed from changing locker. | ACCOMMODATION | ACCOMODATION | BEHAVIOUR BASED | COMPLETED
126 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Stbd side acc door sill badly rusted. | ACCOMMODATION | ACCOMODATION | EXTERNAL FACTORS | COMPLETED
127 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Port side acc door sill badly rusted. | ACCOMMODATION | ACCOMODATION | EXTERNAL FACTORS | COMPLETED
128 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | No markings of restricted area on stbd side acc enterance. | ACCOMMODATION | ACCOMODATION | KNOWLEDGE BASED | COMPLETED
129 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | No markings of restricted area on suez room. | ACCOMMODATION | ACCOMODATION |  | COMPLETED
130 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Galley/pantry tiles broken. | ACCOMMODATION | ACCOMODATION | EXTERNAL FACTORS | COMPLETED
131 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Provision store cold chamber lock loose. |  | ACCOMODATION | EQUIPMENT RELATED | RECTIFIED
132 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Alleyways/cabin illumination not bright | ACCOMMODATION | ACCOMMODATION | EXTERNAL FACTORS | WORK IN PROGRESS.
133 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | A deck cable duct light broken. | ACCOMMODATION | ACCOMODATION | KNOWLEDGE BASED | RECTIFIED
134 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Imo symbol need to be renewed for restricted area. | LSA/FFA | DECK | EXTERNAL FACTORS | COMPLETED
135 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Cabin toilet flush system non operational for some cabins | ACCOMMODATION | ACCOMODATION | EXTERNAL FACTORS | AWAITING SPARES
136 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Ballast control console on bridge non operational | MISCELLANEOUS | BRIDGE | EQUIPMENT RELATED | INFORMED TO OFFICE
137 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | All manhole cover handles need to be freed. | HULL & TANKS | DECK | HUMAN RELATED | PENDING, NEED TO RECTIFY
138 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Cleats frozen and rubber washer painted | CARGO HOLDS | DECK | HUMAN RELATED | JOB UNDERWAY.
139 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Hatch cleats clearence need to be adjusted | CARGO HOLDS | DECK | HUMAN RELATED | JOB UNDERWAY.
140 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Hatch cover piston locking pin not secured with chain | CARGO HOLDS | DECK | HUMAN RELATED | COMPLETED
141 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Cargo hold gas sampling point stencill need to be done. | CARGO HOLDS | DECK | HUMAN RELATED | COMPLETED
142 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Fire hydrant cap not secured with chain | SAFETY , LSA | DECK | HUMAN RELATED | COMPLETED
143 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Hatch cover #6stbd motor leaking | CARGO MACH. | DECK | EQUIPMENT RELATED | PENDING, NEED TO RECTIFY
144 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Remote guage pipes on deck not secured and protection damaged | DECK- PIPE/FITTINGS | DECK | EXTERNAL FACTORS | PIPE SECURED, NEED FITTER ASSISTANCE FOR REPAIRING PROTECTION.
145 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Midship gangway port side bottom platform & last step damaged. | DECK-MACHINERY | DECK | EQUIPMENT RELATED | NEED FITTER ASSISTANCE.
146 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Midship gangway port side bottom platform bolts missing for eye pad . | DECK-MACHINERY | DECK | HUMAN RELATED | COMPLETED
147 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Midship gangway port side rubber cushion for parking missing. | DECK-MACHINERY | DECK | HUMAN RELATED | COMPLETED
148 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Securing chain missing for drip trays. | DECK-MACHINERY | DECK | HUMAN RELATED | COMPLETED
149 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Drain valve for hatch cover, cap missing. | CARGO HOLDS | DECK | HUMAN RELATED | CAP RCVD BUT WRONG SIZE. WILL ASK FOR CORRECT SIZE.
150 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Mushroom vent wheel for opening closing stuck. | DECK-PIPE & FITTINGS | DECK | HUMAN RELATED | COMPLETED
151 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Booby hatches on main deck heavily rusted. | HULL & TANKS | DECK | EXTERNAL FACTORS | JOB UNDERWAY.
152 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Markings need to be refreshed on main deck. | MISCELLANEOUS | DECK | HUMAN RELATED | COMPLETED
153 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Stbd side midship gangway upper platform slightly bent. | DECK-MACHINERY | DECK | EXTERNAL FACTORS | PENDING, NEED TO RECTIFY
154 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Scupper not snug fit on main deck. | MISCELLANEOUS | DECK | EXTERNAL FACTORS | AWAITING CORRECT SIZE SUPPLY.
155 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Bolts for ballast tank vent cover broken and stuck in the body. | DECK-PIPE & FITTINGS | DECK | HUMAN RELATED | NEED FITTER ASSISTANCE.
156 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Stencill for sounding pipes missing. | HULL & TANKS | DECK | HUMAN RELATED | COMPLETED
157 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Sounding caps not sitting properly (pipe thread gone) | HULL & TANKS | DECK | EXTERNAL FACTORS | JOB UNDERWAY.
158 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Co2 line in paint locker needs to be painted red. | SAFETY , LSA | DECK | HUMAN RELATED | COMPLETED
159 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Sopep drums need to be stencilled. | MISCELLANEOUS | DECK | HUMAN RELATED | COMPLETED
160 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Sopep locker and helicopter equipments need to be segregated and arranged. | MISCELLANEOUS | DECK | KNOWLEDGE BASED | COMPLETED
161 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Air pipe line on main deck corroded at various locations | DECK-PIPE & FITTINGS | DECK | HUMAN RELATED | NEED FITTER ASSISTANCE.
162 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Fwd breast winches heavily corroded. | DECK-PIPE & FITTINGS | DECK | HUMAN RELATED | JOB UNDERWAY.
163 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Hatch cover #3 fwd jack leaking. | CARGO MACH. | DECK | EQUIPMENT RELATED | PENDING, NEED TO RECTIFY
164 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Hacth cover control lever union leaking for hatch no.2 | CARGO MACH. | DECK | EQUIPMENT RELATED | PENDING, NEED TO RECTIFY
165 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Hatch cover #1 aft jack leaking | CARGO MACH. | DECK | EQUIPMENT RELATED | PENDING, NEED TO RECTIFY
166 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | No.2 hatch cover port & stbd side motor leaking. | CARGO MACH. | DECK | EQUIPMENT RELATED | PENDING, NEED TO RECTIFY
167 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Securing clamp for pipes on deck heavily corroded. | DECK-PIPE & FITTINGS | DECK | HUMAN RELATED | RECTIFICATION IN PROGRESS (RAISED RO-NATT220091
168 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Booby hatches packing retaining channel rusted on main deck. | HULL & TANKS | DECK | HUMAN RELATED | PENDING, NEED TO RECTIFY
169 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Securing pin for booby hatches not secured with chains. | HULL & TANKS | DECK | HUMAN RELATED | RECTIFICATION IN PROGRESS (RAISED RO-NATT220091
170 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | No.1 hatch stbd side hydraulic pipes angle bar wasted. | DECK-PIPE & FITTINGS | DECK | HUMAN RELATED | NEED FITTER ASSISTANCE.
171 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Fpk store bilge well cover missing. | DECK-PIPE & FITTINGS | DECK | HUMAN RELATED | NEED FITTER ASSISTANCE.
172 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Co2 bottles for paint locker, base getting corroded. | SAFETY , LSA | DECK | KNOWLEDGE BASED | BASE FOITETD WITH WOODEN PLANKS / MATTINGS , COMPLETED
173 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Light switch on main deck covered with plastic bottle and tape. | ELEC. MACH & EQUIP. | DECK | BEHAVIOUR BASED | CAPE OPEN AND CHECK FOUND GOOD BUT CAP IS FOR PROTECTION AGAINS HEAVY WEATHER ON DECK ONLY
174 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Suez davit fwd need to be eased. | MISCELLANEOUS | DECK | HUMAN RELATED | PENDING, NEED TO RECTIFY
175 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Air vents stencill missing. | DECK COSMETICS | DECK/ENGINE | EXTERNAL FACTORS | JOB UNDERWAY.
176 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Port side acc upper deck fire hose box hinge loose | LSA/FFA | DECK | HUMAN RELATED | COMPLETED
177 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Ac intake louvers badly dented.
178 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Goose neck vent for e/r rubber packing damaged. | MISCELLANEOUS | DECK | HUMAN RELATED | NEED TO RECTIFY
179 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Co2 room door upper sil badly rusted. | MISCELLANEOUS | DECK | HUMAN RELATED | PENDING, NEED TO RECTIFY
180 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Co2 release valve handle loose. | MISCELLANEOUS |  | HUMAN RELATED | NEED TO RECTIFY
181 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Warning plates on deck needs to be cleaned for rust stains. | MISCELLANEOUS | DECK | HUMAN RELATED | COMPLETED
182 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Steering flat vent handle frozen. | DECK-MACHINERY | DECK | EXTERNAL FACTORS | COMPLETED
183 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Ap tk. Air vent inside rust accumulated. | DECK-PIPE & FITTINGS | DECK | HUMAN RELATED | COMPLETED
184 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Imo symbol need to be renewed once damaged. | SAFETY , LSA | DECK | HUMAN RELATED | COMPLETED, CONTINUOS PROCESS.
185 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Fpk store air vent handle broken. | DECK-PIPE & FITTINGS | DECK | EQUIPMENT RELATED | COMPLETED
186 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | No spare wires onboard, no certificate for the wires in use. Almost all wires due for change. | MISCELLANEOUS | DECK | EXTERNAL FACTORS | AWAITING SUPPLY. RCVD ONLY LIFEBOAT,RESCUE BOAT AND GANGWAY WIRE.
187 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Pumps guages not operational in ships office (except for no.1ballast pump). |  | CCR |  | NO 1 AND 2 BALLAST PUMP GUAGES TRANSMITTER RENEWED AND TESTED FOUND WORKING SATISFACTORY.
188 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Tank valves operation non reliable. Shows open but actually close. | CARGO MACH. | CCR | EQUIPMENT RELATED | PENDING, NEED TO RECTIFY
189 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Duct keel trolley non operational | MISCELLANEOUS | DECK | HUMAN RELATED | PENDING, NEED TO RECTIFY
190 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Bilge pump starter contactor found defective. | MACHINE | ER | EQUIPMENT RELATED | COMPLETED
191 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | No spare magnetic contactors, relays available onboard. | MACHINE | ER | EQUIPMENT RELATED | ALREADY RECEIVED.
192 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | GMDSS , Emergency batteries need replacement | SAFETY | ER | EQUIPMENT RELATED | COMPLETED
193 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | DG 2 LO Pump leaking very badly under pressure | MACHINE | ER | EQUIPMENT RELATED | COMPLETED
194 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | DG 2 LO Pump attached overspeed device to check | MACHINE | ER | EQUIPMENT RELATED | COMPLETED
195 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Aux boiler burner basic spares not available | MACHINE | ER | EQUIPMENT RELATED | ALREADY RECEIVED.
196 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | DG spare cartridge for Turbocharger not available | MACHINE | ER | EQUIPMENT RELATED | ALREADY RECEIVED.
197 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | LO purifier spares not available | MACHINE | ER | EQUIPMENT RELATED | ALREADY RECEIVED.
198 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Flashback arrestors need to be changed | MACHINE | ER | EQUIPMENT RELATED | NEED TO RAISE RO
199 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Incinerator burner basic spares not available | MACHINE | ER | EQUIPMENT RELATED | ALREADY RECEIVED.
200 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Deck lights spares not available | MACHINE | ER | EQUIPMENT RELATED | ALREADY RECEIVED.
201 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Belts not available | MACHINE | ER | EQUIPMENT RELATED | ALREADY RECEIVED.
202 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | Motor bearings not available | MACHINE | ER | EQUIPMENT RELATED | ALREADY RECEIVED.
203 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | BALLAST P/P # 1 & # 2 DISCHARGE GUAGE PR.TRANSMITTER FAULTY | PUMPS | ER | EQUIPMENT RELATED | SAME RENEWED AND CHECKED WORKING SATISFACTORY
204 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | BALLAST P/P # 2 CURRENT TRANSMITTER FOR AMPIER MEATER FAULTY | PUMPS | ER | EQUIPMENT RELATED | SAME RENEWED
205 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | SEWAGE BLOWER NOT OPERATIONAL. | MACHINE | ER | EQUIPMENT RELATED | BLOWER RECIVED , AWAITING FOR CONTACTER RO RAISED RO-NATT220079
206 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | ELEVATOR RETIRING CAM NEED TO CHANGE | MACHINE | ER | EQUIPMENT RELATED | AWAITING FOR SERVICE TECHNICIAN RO -NATT220095
207 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | AHU #1 EVOPRATOR NOT OPERATIONAL | MACHINE | ER | EQUIPMENT RELATED | AWAITING FOR WORKSHOP AT SINGAPORE
208 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | FOOT SWITCH FOR WORKSHOP MACHINERY NOT FITTED | MACHINE | ER | EQUIPMENT RELATED | RO RAISED AWAITING FOR SPARES NATT220090
209 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | UPS FOR BNWAS NOT OPERATIONAL | SAFETY , LSA | ER | EQUIPMENT RELATED | RO RAISED AWAITING FOR SPARES NATT220087
210 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | SPARES NOT IN STEEL BOX | HOUSEKEEPING | ER | INAPPROPRIATE PROCEDURES | RO RAISED AWAITING FOR SPARES
211 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | MAIN AIR COMP #2 STBD SIDE TRIPPED ON LOW LUBOIL PRESSURE , DISMANTLLED AND INSPECTED AFT CRANK PIN BEARING SEACED , SAME RENEWED WITH NEW SHELL BEARING , PIN HAVING SLIGHT OVALITY | ER MC -MAC | ER | EQUIPMENT RELATED | SAME HASE BEEN TEMPRORARLY RECTIIED AND ON OBSERVATION
212 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | ELEVATOR LIGHT AND TELEPHONE TO BE CHANGE. | SAFETY | ER | EQUIPMENT RELATED | COMPLETED.
213 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | BALLAST LINE IN DUCT KEEL NEAR FOREPEAK AND 1 CENTER TANK FILLING LINE LEAKING | DECK-PIPE & FITTINGS | DECK | EXTERNAL FACTORS | SAME HASE BEEN TEMPRORARLY ARRESTED , INCERT NEED TO BE PUT IN BALLAST PASAGE
214 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | WHILE RUNNING MAIN AIR COMPRESSOR #2 AREATION PROBLOM OBSERVED IN L.T SYSTEM DUE TO AIR SEEPAGE | ER MC -MAC | ER | EQUIPMENT RELATED | RO. RAISED FOR ORIGINAL SPARES AND GASKETS. RO ,NO -NATT220006
215 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | DUCT KEEL EDUCTOR VALVE COMPLETELY CHOCKED NAD NOT TAKING SUCTION | VALVES | ER | EQUIPMENT RELATED | SAME RECTIFIED , NEED TO RENEW COMPLEATE VALVE
216 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | BIO FOULING PLAN MISSING | FILING | CE OFFICE | NEW MGT | SAME PRINTED AND FILED
217 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | CALIBRATION CERTIFICATE FOR FLOW MEATER MISSING | MACHINE | ER | HUMAN RELATED | OLD RECORDS AVAILABLE , NEED TO DISCUSS
218 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | AIR CONDITION COOLING EFFECT IS LOW | MACHINE | ER | EQUIPMENT RELATED | JOB IN PROGRESS , NEW EVOPRATOR INSTALLED IN #1 AHU UNIT , BRAZING NEED TO BE DONE , OTHER EVOPRATOR ALREADY CLEANED , OVERALL PERFORMANCE HAS BEEN IMPROVED.
219 | 2022-02-16 | M V NATTY | SHIP STAFF | INTERNAL | LED MIGRATION NOT COMPLETED . | MACHINE | ER | HUMAN RELATED | WORK IN PROGRESS.