## Sheet 1
ZENO - POST DD DEFECT LIST |  |  |  | 2022-06-26
S.NO | DEFECT | REQN | Corrective Action | STATUS | Office Remarks | Vessel remarks
1 | Aux. boiler -2 feed water controller sipart defective . | ZENO220016 | Controller not working, checked with service engineer and tested other units, all defective. RO raised | Completed | Noted on PO | Completed. Received and renewed.
2 | Fwd ICCP inopertional |  | Fwd ICCP anodes replaced by yard, as per yard report both PCB are defective & need to be changed. To be followed. 31/1/2022 : in consulation with makers, to put on after 4 weeks after DD. Makers requested details, same forwarded | Switched ON, Amp still "0". | check after four weeks, then we will decide how to proceed | As per advise interchanged Fwd ICCP PCB with AFT, AFT working with both FWD AMP reading "-0" with both PCB's. As per advise from Correstech , kept ON.
3 | Graviner MK-6 Oil mist detector panel both PCB maulfunctioning | ZENO225004 | Giving error RO raised | Spare recd | Noted on PO | 3 PCB's rced and renewed. Status display PCB on RO, system working satisfactory. Technician visit being planned.
4 | Vapor emmission control system o2 analyzer complete sensor defective. | ZENO225002 | As per service engineer sensor to be replaced same ordered | Completed. | Noted on PO | Renewed. Working satisfactory.
5 | Emergency switch board 220 v panel insulation meter defective | ZENO220015 | showing "0" reading, meter faulty requistion raised. Approved and being supplied at Singapore | Completed. | Noted on PO | Renewed.
6 | Two light fittings not working on bridge deck |  | Light fitting steel pipes were renewed by yard, after fitting two fittings power not coming. Same to be traced | Completed, lighting checked and broken wires rectified |  | Replace
7 | No.2 Boiler smoke density meter not working |  | Potentiometer on order for No 1 , will be checked with same for no 2. | Awaiting spare | Please update on the fault finding, Is the PCB defective? | is erratic, potentiometer on order for no 1, will be checked for no 2 also when recd.same fault in both,
8 | One MCP not working for fire detection | ZENO220001 | Spare rec'd same to be attended. 31/1/2022 : New changed but not recognizing same being checked with office and makers | Completed | we can see - the communciation is on with Consilium Greece. Please continue to follow - Maker advse | Received spare, and renewed.
9 | Economiser feed pump No.2 seal leaking |  | Pump seal leaking, same to be attended | Completed, pump overhauled and tested. |  | Completed mechaincal seal change
10 | Lagging on steam valves damaged or missing |  | After steam valve overhaul, various laggings were torn or are in bad condition. Same to be replaced. Vessel received laggings for few, others to be made and fitted | Completed. Photos attcahed in weekly work done. | Do vessel has sufficient lagging for the steam? | Install nw lagging
11 | Aux. boilers air trunking flexible bellow to change |  | Flexible bellow was replaced by yard but with canvas same not strong and same to be changed. Requistion raised | Received | Noted on PO | As per owners to observe and To be renewed if required.
12 | Ballast tank 3 Port and 6 Port sounding not showing constant in SAAB monitor PC. |  | Suspect leakage in the air line, due to that sounding not showing constant. | Will be chkd in loaded passage again | Update on the trouble-shooting done till now | FOUND NO PNEUMATIC LEAKS IN TANKS. PROPER FUNCTIONING TO BE CHECKED DURING BALLAST PASSAGE.
13 | 3 Port ballast tank main valve 3PBM indicator in CCR Showing 10 % open & 3 STBD ballast tank Main Valve 3SBM indicator not working IN CCR. | ZENO220042 | Valve opening and fully closing . In ship yard with the hydel service technician valve status visually verified In Bosun store local manual solenod valve indicator & in 3P port ballast tank valve indicator, both local valve opening and closing fully . 3S Main valve fully opening and closing but indicator in CCR and Bosun store not working. | Awaiting spares | Update on the trouble-shooting done till now | Valves and controls chkd, valve operating satisfactory. Problem was rectified, but after loading operation again showing 10 % Open.Found potentiometer defective, RO raised for potentiometers.
14 | 4 stbd ballast tank main valve 4SBM indicator showing 0 % open in CCR when valve is fully open. |  | hydel technician suspected electrical issue & suggested to change the valve indicator in CCR panel. | Completed
15 | No.2 WBP Discharge valve B122 not opening from CCR. |  | Discharge valve fully opening from Hydraulic room & local in pumproom. Same attended by Hydel and aisan marine technician. hydel technician suspected electrical issue & suggested to change the valve indicator in CCR panel. 31/1/2022, no fault designed to operate slowly | Completed
16 | Fire hoses boxes supports to be renewed. |  | All damage supports will be replaced prior vessel to change over in inert condition. 31/1/2022 : support welded | Completed
17 | Various save all tray comings wasted from top section |  | Hotwork to be carried out, same requested | Completed
18 | Foam line drain valve pipe leaking ( fwd of pump room) on main deck |  | Pipe will be renewed. 31/1/2022 Pipe renewed | Completed
19 | Forward Breast line inlet hydraulic pipe line section ( below the platform ) need to renew. |  | Pipe will be removed and New pipe to be fabricated in E/R . | Completed
20 | Stbd side gangway air line pipe last section to be renewed. |  | Pipe will be removed and New pipe to be fabricated in E/R Workshop. | Completed
21 | 3S WBT valve indicator not showing valve position in CCR . | ZENO220042 | Valve opening and fully closing from CCR and Local forepeak store. Required to check and identify the problem. | Awaiting spares |  | Found Potentiometer defective . RO ZENO220042 Raised.
22 | Catwalk near 4S COT having hole. |  | Catwalk will be removed and transferred to E/R Work shop for fabrication. | Completed
23 | Stbd side bridge wing fire line penetration area having hole( between fire hydrant and deck level penetration part). |  | Completed | Hot work completed.
24 | Mooring winch AFT breast line, both stern line and Fwd breast line hydraulic oil leaking from control lever block. | ZENO220061 | Minor leakage from damge 'O' ring / seal due to pitting / scratch marks inside the control lever block, require to renew full block set. Same was chkd by HYDEL technicians and owners supt in DD and after renewing O ring/oil seal the leakage starts as soon as the control lever is moved 2-3 times.Will raise new requisition for new full sets of control lever block. | Awaiting spares |  | One block and lever removed , polished and o rings renewed. No lekage after overhaul, 3 others repaired after last loadport leaking after one operation in Disport. Spares awaited.
25 | No.2 COP seperator level gauge not working after discharging. | ZENO220060 | As per service engineer in DD to be renewed as bellows inside have lost tension. | Awaiting spares |  | Not working , is erratic and gets stuck either on Full or Empty.
26 | IGS system paper recorder for IG pressure and O2 % not recording in CCR. |  | Troble shooting as per office advise in progress. | Awaiting spares |  | Both IGS O2 and pressure readings are wrong, recorder working is faulty. Technician visit/spare planned for next convenient port.
27 | 1S & 3S COT PV valve leaking from vaccum side Gasket packing. |  | Renewal of gasket carried out. | Completed.
28 | Main deck Steam Line leaking from Dresser copling near 6W's COT on deck. |  | Inspection and renewal of packing to be carried out in upcoming week. | Completed. |  | Gland packing renewed.
29 | Foam branch line pipe near 3W's COT having leakage |  | Temporary repair carried out, will remove pipe from the location and replace with new pipe in upcoming week. | Completed.
30 | PA System - not working for Bridge wings and port side boat deck outside accomodation | ZENO220019 | Was checked by tech in DD. Stbd side outside accomodation was repaired for full operation. One PCB needs to be renewed. Awaiting spares | Spare recd |  | New PCB replaced, however the problem persists. To be rectified with consltation from technical
31 | 4 nos Foam line isolation valves found leaking |  | No.1, No. 2, No. 4 and No 6 Foam line isolation valves overhauled | Completed.
32 | 4 nos Fire line isolation valves found leaking |  | No.4 and No.3 Fire line isolation valves overhauled | Completed.
33 | 3 Port LSMGO bunker vent drain pipe found corroded and damaged |  | Same fabricated and renewed | Completed.
34 | 1 Port HFO bunker vent found corroded and damaged |  | Same fabricated and renewed | Completed.
35 | 1 no Fire line isolation valves found leaking |  | No.5 Fire line isolation valve to be overhauled | In progress