{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":27,"n_cols":28,"rows_kept":27,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","27-Aug-2022",null,null,"Ship Name","NN TENACITY (19-04-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,21100,null,"125_21/9/2021 3:10:06 pm","2022-02-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Draft gauges are showing erratic reading.","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","Air blown and checked piping for air leakages found no leakage , air pressure checked found satisfactory supply available at control panel,Gauges need to be re-calibrated.Awaiting spares.","2022-05-15T08:00:00","NTEN220006","In progress",null,"No","No","No","Internal","spare part to be connected to vessel at next convenient port."]
[null,null,null,23198,null,"125_18/12/2021 6:12:57 pm","2022-02-18T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Steering gear room exhast fan MCCB breaker is defective.","Elect. Mach. & Equip.,Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Steering gear room exhaust fan MCCB is defective.Kept off .Awaiting spares.","2022-05-18T08:00:00","NTEN210112","Not Started",null,"No","No","No","Internal","spare part was ready,  will connect to vessel at next convenient port."]
[null,null,null,22173,null,"125_30/10/2021 11:12:31 am","2022-02-24T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Ship fitted with non LED lights need to be replaced with LED lights","Accommodation,Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","45% modificaition completed,E/R area work in progress.","2022-05-24T23:59:35","NTEN210078","In progress",null,"No","No","No","Internal","Please expedite"]
[null,null,null,null,26261,"125_Thu Jun 02 2022 04:42:58 GMT+0800","2022-04-04T08:00:00","Defect","Ship Staff","Ship Staff Insp.","During routine inspection it was observed hatch cover drain channel -drain pipes & valves are either missing or wasted heavily at various hatch coamings.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","New pipes & valves to be fixed/welded in position","2022-07-03T08:00:00","REQ No. NTEN220072","In progress",null,"No","No","No","Internal"]
[null,null,null,null,15254,"125_Fri Jul 01 2022 23:27:09 GMT+0800","2022-06-26T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Hospital Exhaust  fan found not working.  Fan & casing  found frozen and heavily deteriorated. ","Accommodation","MLC Related","Equipment Related","","","","","Fan/motor assembly  needs to be renewed/replaced.","2022-09-25T08:00:00","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,14889,"125_Mon Aug 01 2022 16:42:39 GMT+0800","2022-07-26T08:00:00","Observation","FSC Inspector","Flag State Insp.","Moderate rust patches observed on the ship's side railing","Hull & Tanks","General Appearance","External Factors","","","","","Maintenance required on ship side railings.","2022-10-26T08:00:00","","In progress",null,"No","No","No","External"]
[null,null,null,null,86358,"125_Mon Aug 01 2022 16:57:45 GMT+0800","2022-07-26T08:00:00","Observation","FSC Inspector","Flag State Insp.","Tripod base of all gangways turntable platform found frozen & rusted","Miscellaneous","General Appearance","Human Error","","","","","Tripod base of all gangways turntable platform need to be derusted & eased up.","2022-10-26T08:00:00","","Not Started",null,"No","No","No","External"]
[null,null,null,null,49924,"125_Mon Aug 01 2022 17:03:59 GMT+0800","2022-07-26T08:00:00","Observation","FSC Inspector","Flag State Insp.","Companion ways on the accommodation to be derusted & painted as required.","Accommodation","General Appearance","External Factors","","","","","Companion ways on the accommodation to be derusted & painted as required.","2022-10-26T08:00:00","","In progress",null,"No","No","No","External"]
[null,null,null,null,73967,"125_Mon Aug 01 2022 17:07:02 GMT+0800","2022-07-26T08:00:00","Observation","FSC Inspector","Flag State Insp.","Lifeboat release hook - To remove paint from the release hook.","LSA / FFA","Safety / LSA / FFA","External Factors","","","","","Paint to be removed when boat is lowered for maneuvering during next quarterly scheduled drill.","2022-10-26T08:00:00","","Not Started",null,"No","No","No","External"]
[null,null,null,null,89100,"125_Fri Aug 26 2022 17:28:26 GMT+0800","2022-08-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","220 V Insulation monitor , Reading needle is broken ","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Insulation monitor to be renewed","2022-11-15T08:00:00","NTEN220146 ECR MSBD PANEL INSULATION MONITOR AND AMMETER","Waiting spare",null,"No","No","No","Internal"]

{"sheet":"Completed","index":1,"n_rows":99,"n_cols":28,"rows_kept":99,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","27-Aug-2022",null,null,"Ship Name","NN TENACITY (19-04-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,21092,null,"125_21/9/2021 2:01:00 pm","2021-08-14T23:59:35","Non Conformity","FSC Inspector","Flag State Insp.","Emcy generator panel is showing low resistance of 0.1 onms","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","","","","","Low insulation source identified and same rectified. ","2021-09-15T23:59:35","","Completed","2021-08-20T23:59:35","No","No","No","External"]
[null,null,null,21093,null,"125_21/9/2021 2:10:56 pm","2021-08-14T23:59:35","Non Conformity","FSC Inspector","Flag State Insp.","Hatch cover cleats of all holds frozen, required to be free & greased.","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","All cargo holds auto cleats made free moving and greased and covered with denso tape to protect nut/thread.","2021-09-15T23:59:35","","Completed","2021-08-20T23:59:35","No","No","No","External"]
[null,null,null,21094,null,"125_21/9/2021 2:23:08 pm","2021-08-14T23:59:35","Observation","FSC Inspector","Flag State Insp.","Generators insulation around exhaust not in good condition","E/R - Aux. Engine","Eng. / Strg. Comp.","Human Error","","","","","Insulation lagging around generator exhaust renewed with new one.","2021-09-15T23:59:35","","Completed","2021-08-14T23:59:35","No","No","No","External"]
[null,null,null,21095,null,"125_21/9/2021 2:32:10 pm","2021-08-14T23:59:35","Observation","FSC Inspector","Flag State Insp.","Publication AHP 20 not updated","Navigation - Others","Navigation","Human Error,Inappropriate Procedure","","","","","Vessel downloaded latest AHP 20 from www.hydro.gov.au/prodserv/publications/ash.htm","2021-09-15T23:59:35","","Completed","2021-08-20T23:59:35","No","No","No","External"]
[null,null,null,21096,null,"125_21/9/2021 2:40:07 pm","2021-08-14T23:59:35","Observation","FSC Inspector","Flag State Insp.","MSDS sheet for some e/room chemicals not available","Documentation","Cert. & Docu.","External Factors","","","","","MSDS for chemical requested and same  recvd from office.","2021-09-15T23:59:35","","Completed","2021-08-22T23:59:35","No","No","No","External"]
[null,null,null,21097,null,"125_21/9/2021 2:59:59 pm","2021-08-14T23:59:35","Observation","FSC Inspector","Flag State Insp.","AS PER CIC NO. 3 PART 1 , VESSEL SMS DOES NOT HAVE ADDED REQUIREMENTS TO SUBMIT PSC REPORTS TO ADMINISTRATION.","Miscellaneous","ISM Related","External Factors","","","","","Reference to Liberian Marine Notice PSC-001, Rev 01/21 has been added to Company Management System on 19th Aug 2021. Additionally, the Marine Notice has been included under HSQEEn Misc Docs.","2021-09-14T23:59:35","","Completed","2021-08-19T23:59:35","No","No","No","External"]
[null,null,null,21099,null,"125_21/9/2021 13:26:03","2021-08-14T23:59:35","Non Conformity","FSC Inspector","Flag State Insp.","Rescue boat search light not in working condition","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Damaged wire renewed and hole covered with silicon.","2021-09-15T23:59:35","","Completed","2021-08-14T23:59:35","No","No","No","External"]
[null,null,null,21285,null,"125_29/9/2021 14:01:16","2021-09-06T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","Safety Management System was not ensured proper implementation as following evidence: Gasket on outlet piping line situated between no. 2 cylinder head & exhaust v/v misaligned  (due to insufficient  maintenance) result in M/E out of order ( Jacket cooling water going high due to insufficient water flow through outlet piping line)    ","E/R - Main Engine","ISM Related","Equipment Related,Inappropriate Procedure","","","Propulsion and auxiliary machinery","","Maintenance procedure modified as per makers manual and included in Chief Engineer's standing orders.","2021-12-05T23:59:35","","Completed","2021-09-25T23:59:35","No","No","No","External"]
[null,null,null,21098,null,"125_21/9/2021 3:39:29 pm","2021-09-06T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","Responsible crew not familiar with immersion suit wearing operation","LSA / FFA","Safety / LSA / FFA","Knowledge Based","","","Other","","Crew mustered and training was given in proper doning of immersion suit within 2 mintues.","2021-09-06T23:59:35","","Completed","2021-09-06T23:59:35","No","No","No","External"]
[null,null,null,21286,null,"125_30/9/2021 10:19:04 pm","2021-09-17T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME & AE FUEL OIL CIRCULATING PUMP LIP SEAL LEAKING.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","LIP SEAL REPLACED WITH SPARE SUPPLIED FROM LOCAL WORKSHOP FABIRCATED. RO RAISED","2021-12-30T23:59:35","NTEN215035","Completed","2021-09-20T23:59:35","No","No","No","Internal"]
[null,null,null,21613,null,"125_16/10/2021 19:08:31","2021-09-20T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","S - band radar stopped transmitting and painting radar target echoes.","Navigation - RADAR","Navigation","Equipment Related","","","","","Office informed and shore service engineer arranged for repair","2021-11-30T23:59:35","NTEN215037","Completed","2021-11-05T23:59:35","No","No","No","Internal","Already arranged service attendance at this call Korea, waiting for vessel berthing."]
[null,null,null,21284,null,"125_1/10/2021 11:35:25","2021-09-25T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Ballast tank valve indicatornot showing proper indications.","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","Valve indicators adjusted to show proper indication cross checked from local and remote indication found satisfactory.","2021-11-30T23:59:35","","Completed","2021-10-07T23:59:35","No","No","No","Internal","Kindly complete this job at this anchorage."]
[null,null,null,21614,null,"125_16/10/2021 5:20:29 pm","2021-10-03T23:59:35","Critical Equipment,Observation","Ship Staff","Ship Staff Insp.","OWS BOTH CHAMBERS PRESSURE WAS SHOWING HIGHER THAN NORMAL AND PPM WAS SHOWING MORE THAN 15PPM.","Critical Equip.","MARPOL Related","Behaviour Based","","","","","BOTH FIRST AND SECOND STAGE FILTERS REMOVED AND CLEANING OF BOTH FILTERS CARRIED OUT, FIRST AND SECOND STAGE CHAMBERS INTERNALLY CLEANED AND INSPECTED,OIL SENSOR CLEANED AND TRIED OUT.","2021-10-05T23:59:35","","Completed","2021-10-04T23:59:35","No","No","No","Internal"]
[null,null,null,21615,null,"125_16/10/2021 5:31:01 pm","2021-10-06T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Fore peak tank valve BA-01 not operating from local station at forepeak and remote station in CCR.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","Forepeak tank valve BA-01 hard to operate, same freed by removing actuator,tested from local as well remote operation found satisfactory working.","2021-10-15T23:59:35","","Completed","2021-10-07T23:59:35","No","No","No","Internal"]
[null,null,null,21612,null,"125_16/10/2021 5:42:55 pm","2021-10-08T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Main cooling sea water pump no. 1 tripped, Electrical motor burnt.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Electrical motor to be replaced with new spare motor,no spare motor onboard, RO raised.Awaiting spares","2021-11-30T23:59:35","NTEN210064","Completed","2021-11-07T23:59:35","No","No","No","Internal","Spare motor will be connected at Hadong, Korea. Kindly renew upon receipt."]
[null,null,null,21616,null,"125_16/10/2021 6:35:07 pm","2021-10-10T23:59:35","Defect","Ship Staff","Ship Staff Insp.","MAIN ENGINE LUB OIL PP NO. 1 FOUND DRAWING HIGH CURRENT THAN NORMAL.\t","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","MAIN ENGINE LUB OIL PUMP NO. 1 OVERHAULING CARRIED OUT, PUMP CASING RING OF SECOND STAGE BOTTOM SIDE REPLACED, BEARINGS REPLACED WITH SPARE ONES.","2021-10-30T23:59:35","NTEN210065","Completed","2021-10-11T23:59:35","No","No","No","Internal"]
[null,null,null,22180,null,"125_30/10/2021 8:40:47 am","2021-10-24T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Incinerator sluice door operating air hoses leaking. (2 no’s) to be renewed","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Incinerator sluice door both operating air hoses renewed with spare ones. No air leakage working satisfatory.","2021-11-05T23:59:35","","Completed","2021-10-28T23:59:35","No","No","No","Internal"]
[null,null,null,22181,null,"125_30/10/2021 11:19:45 am","2021-10-24T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AE-2 starting air line air reducer leaking from tell-tale hole to be rectified.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","AE-2 starting air line air reducer leakage from tale hole rectified.Working satisfactory.","2021-11-15T23:59:35","","Completed","2021-10-25T23:59:35","No","No","No","Internal"]
[null,null,null,22182,null,"125_31/10/2021 10:58:54","2021-10-24T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fire hydrant port side accommodation entrance leaking, same to be lapped and fixed.","Deck - Pipe / Fittings","Safety / LSA / FFA","Equipment Related","","","","","Fire hydrant lapped and leakage rectified.","2021-11-05T23:59:35","","Completed","2021-10-25T23:59:35","No","No","No","Internal"]
[null,null,null,22175,null,"125_30/10/2021 12:47:07 pm","2021-10-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Flame proof light near Oxy-Acetylene room fitting to be renewed","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Flame proof Light replaced with new spare supplied.working satisfactory.","2022-12-31T23:59:35","NTEN210066","Completed","2021-12-23T23:59:35","No","No","No","Internal","connected to vessel on 16th Dec."]
[null,null,null,22176,null,"125_31/10/2021 12:23:42","2021-10-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Manhole cover lifting handle broken at 3 places.","Miscellaneous","General Appearance","Equipment Related","","","","","Fabricate new handle and fit.","2021-11-30T23:59:35","","Completed","2021-11-19T23:59:35","No","No","No","Internal","Manhole cover to remove from place & carry out hot work in engine room workshop"]
[null,null,null,22177,null,"125_31/10/2021 12:28:30","2021-10-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Checker plate step wasted near the Stbdside PILOT assist ladder. to cropped and renew","Miscellaneous","General Appearance","Equipment Related","","","","","Same to cropped and renew.","2021-11-25T23:59:35","","Completed","2021-11-18T23:59:35","No","No","No","Internal","Hot work permit to request. Ship staff to check for combustible materials in the vicinity of hot work."]
[null,null,null,22178,null,"125_31/10/2021 12:36:56","2021-10-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Accommodation/ Pilot assist ladder stowing davit hook/ lock found frozen.","Deck - Machinery","ISM Related","Equipment Related","","","","","Same to be made free and operational.","2021-11-15T23:59:35","","Completed","2021-11-14T23:59:35","No","No","No","Internal","This job to be completed on priority & report to office"]
[null,null,null,22179,null,"125_31/10/2021 12:47:52","2021-10-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Suez davit found rusted and frozen.","Deck - Machinery","General Appearance","Equipment Related","","","","","Suez davit to be de-rusted, greased, free moving and upgrade cosmetic appearance.","2021-11-15T23:59:35","","Completed","2021-11-14T23:59:35","No","No","No","Internal","Noted, once done please report to office."]
[null,null,null,22601,null,"125_15/11/2021 8:23:58 pm","2021-11-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME & AE FO CIRCULATING PUMP NO. 2 SEAL LEAKAGE ","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","SPARES RECEIVED AT LANSHAN CHINA LIP SEAL RENEWED.","2021-12-15T23:59:35","NTEN210043/2","Completed","2021-12-20T23:59:35","No","No","No","Internal"]
[null,null,null,22602,null,"125_15/11/2021 8:34:05 pm","2021-11-03T23:59:35","Observation","Ship Staff","Ship Staff Insp.","ENGINE ROOM OVERHEAD CRANE REMOTE CONTROL CABLE CONDITION  NOT GOOD DUE AGEING","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","ENGINE ROOM OVERHEAD CRANE REMOTE CONTROL CABLE RENEWED,WORKING SATISFACTORY.","2022-01-15T23:59:35","NTEN210073","Completed","2021-12-19T23:59:35","No","No","No","Internal","Spare parts to be connected to vessel at Next convenient port."]
[null,null,null,23036,null,"125_30/11/2021 12:01:45 am","2021-11-07T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Refrigeration compressor no. 2 connecting rod & piston along with mechanical seal damaged.\t","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","complete ref. compressor NO.2 REPLACED with spare received at china Lanshan.","2021-12-15T23:59:35","NTEN210089","Completed","2021-12-20T23:59:35","No","No","No","Internal"]
[null,null,null,22600,null,"125_15/11/2021 16:32:57","2021-11-10T23:59:35","Other","Ship Staff","ISM Audit","SCBA sets to be mounted on hooks - internal audit recommadation","Miscellaneous","Safety / LSA / FFA","External Factors","","","","","New hooks to be fabricated.","2021-11-20T23:59:35","","Completed","2021-11-20T23:59:35","No","No","No","Internal"]
[null,null,null,23035,null,"125_24/11/2021 11:46:02 pm","2021-11-20T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Emergency generator battery start method in operational due to defective Aux magnet Switch (AMS).\t","Critical Equip.","Emgcy. Systems","Equipment Related","","","","","Defective Aux Magnet Switch (AMS)  replaced with new spare ones, Emergency generator engine tried out with battery starting mode, found working satisfactory.","2021-12-20T23:59:35","NTEN210095 ","Completed","2021-12-18T23:59:35","No","No","No","Internal"]
[null,null,null,22172,null,"125_31/10/2021 12:42:03","2021-11-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hatch cover 1,2,4,8, & 9 to de-rust and paint full coat, Hatch cover 3,5,6,7 to  spot de-rust and upgrade the cosmetic appearance.","Deck - Machinery","General Appearance","Equipment Related","","","","","Derust and paint the hatch covers and assosiated fitting.","2022-01-31T23:59:35","","Completed","2022-01-31T23:59:35","No","No","No","Internal","work progress to be updated."]
[null,null,null,23039,null,"125_30/11/2021 12:05:59 am","2021-11-27T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Aux engine no.3 lub oil priming pump making abnormal noise due to defective bearing.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Aux engine no.3 bearing renewed with spare ones, flexible coupling repaired and fitted back, lub oil priming pump working satisfatory.","2021-12-05T23:59:35","","Completed","2021-11-29T23:59:35","No","No","No","Internal"]
[null,null,null,23199,null,"125_18/12/2021 4:26:50 pm","2021-12-04T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Aft mooringwinch stbd side control lever oil seal is slightly leaking and lever is hard to operate.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","leaky oil seal to renewed,no leakage.","2022-02-28T23:59:35","NTEN220002","Completed","2022-02-26T23:59:35","No","No","No","Internal","spare parts supplied on 13th Feb at Singapore. please confirm and update."]
[null,null,null,23201,null,"125_18/12/2021 4:12:16 pm","2021-12-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Aft LT cooler end plate having crack and sea water leaking at end plate.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Temporary repair to restrict the leak from the crack carried using rubber gaskets and rubber glue.rubber out at all 4 corners of the end plate and plates tigtened, system tried out and found leak is restricted.","2021-12-20T23:59:35","","Completed","2021-12-15T23:59:35","No","No","No","Internal"]
[null,null,null,23202,null,"125_19/12/2021 11:25:14 am","2021-12-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Reefer compressor-1 discharge pressure gauge is defective and showing wrong discharge pressure","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","discharge pressure gauge replaced with newly supplied pressure gauge at Lanshan- China. gauge fitted and leak test carried. found working satisfactory.","2021-12-31T23:59:35","NTEN210089","Completed","2021-12-19T23:59:35","No","No","No","Internal"]
[null,null,null,23200,null,"125_18/12/2021 4:20:20 pm","2021-12-15T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Aux. boiler pilot burner pump  body leaking due to cracked cover.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Spares received and fitted, pump tried out and found leak is restricted.","2022-03-14T23:59:35","NTEN220007","Completed","2022-02-14T23:59:35","No","No","No","Internal","RO is under processing."]
[null,null,null,23203,null,"125_18/12/2021 4:32:20 pm","2021-12-17T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Main cooling sea water pump-1 mechanical seal cooling water line is leaking due to ruptured copper pipe.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Main cooling sea water pump-1 mechanical seal cooling water line removed and replaced with new copper piping. fitted in place and valves opened, satisfactory with no leaks.","2021-12-18T23:59:35","","Completed","2021-12-17T23:59:35","No","No","No","Internal"]
[null,null,null,23371,null,"125_2/1/2022 12:55:34 pm","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fire and GS pump suction valve gland packing leakage.","E/R - Pumps","General Appearance","Equipment Related","","","","","Fire and GS pump suction valve gland packing renewed.","2022-01-15T23:59:35","","Completed","2022-01-03T23:59:35","No","No","No","Internal","pls update status of rectification."]
[null,null,null,23372,null,"125_2/1/2022 12:50:22 pm","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency generator engine fuel oil tank air vent head rusted,oily stain in saveing all","Critical Equip.","Emgcy. Systems","Equipment Related","","","","","Oily stain cleaned ,air vent head overhauling carried out & painted.","2022-01-15T23:59:35","","Completed","2022-01-09T23:59:35","No","No","No","Internal","pls update status of rectification."]
[null,null,null,23373,null,"125_2/1/2022 12:58:36 pm","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Air duct mesh in Purifier room observed dirty.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Air duct mesh cleaned.","2022-01-30T23:59:35","","Completed","2022-01-04T23:59:35","No","No","No","Internal","pls update status of rectification."]
[null,null,null,23374,null,"125_2/1/2022 1:01:44 pm","2021-12-26T23:59:35","Critical Equipment","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency generator engine starting battery side cover to be fabricated.","Critical Equip.,Miscellaneous","Emgcy. Systems","Equipment Related","","","","","Emergency generator engine starting battery side cover fabricated and fitted.","2022-01-31T23:59:35","","Completed","2022-01-02T23:59:35","No","No","No","Internal","pls schedule and update rectification status."]
[null,null,null,23375,null,"125_2/1/2022 1:05:16 pm","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hot well steam pipe lagging found damaged.","Miscellaneous","Safety / LSA / FFA","Equipment Related","","","","","Hot well steam pipe defective lagging Replaced and painted.","2022-01-31T23:59:35","","Completed","2022-01-04T23:59:35","No","No","No","Internal","pls update rectification status."]
[null,null,null,23675,null,"125_18/1/2022 2:09:15 am","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Ventilation damper for emergency generator engine room rusted.","Deck - Pipe / Fittings,Miscellaneous","General Appearance","Equipment Related","","","","","Derusted and painted.","2022-02-20T23:59:35","","Completed","2022-02-06T23:59:35","No","No","No","Internal","Please make work plan , to commence ASAP."]
[null,null,null,23676,null,"125_18/1/2022 2:03:40 am","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Windlass and mooring winch shaft bearing/bush grease point was dry,no proper greasing observed.","Deck - Machinery,Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Windlass and mooring winch shaft bearing/bush grease point was properly greased.","2022-02-20T23:59:35","","Completed","2022-01-30T23:59:35","No","No","No","Internal","Please keep update."]
[null,null,null,23677,null,"125_18/1/2022 2:13:43 am","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Self closing device for foam room door not working.","Accommodation,Miscellaneous","Safety / LSA / FFA","Equipment Related","","","","","Rectified","2022-02-10T23:59:35","","Completed","2022-01-30T23:59:35","No","No","No","Internal","pls update"]
[null,null,null,23678,null,"125_17/1/2022 9:34:18 pm","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Officer mess room air vent duct heavily rusted.","Accommodation","General Appearance","Equipment Related","","","","","Officer mess room air vent duct heavily rusted removed and de-rusted,freed and fixed back.","2022-01-10T23:59:35","","Completed","2022-01-09T23:59:35","No","No","No","Internal"]
[null,null,null,23679,null,"125_17/1/2022 9:43:32 pm","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Embarkation ladder - stbd side lighting switch box heavily rusted.\t","Deck - Machinery","Safety / LSA / FFA","Equipment Related","","","","","stbd side lighting switch box de- rusted and painted.","2022-01-10T23:59:35","","Completed","2022-01-10T23:59:35","No","No","No","Internal"]
[null,null,null,23680,null,"125_17/1/2022 9:47:15 pm","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","GS pump sea water suction valve gland leakage.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Gland packing renewed, piping painted.","2022-01-05T23:59:35","","Completed","2022-01-03T23:59:35","No","No","No","Internal"]
[null,null,null,23681,null,"125_17/1/2022 9:52:09 pm","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Elevator room watertight door upper rain shield corroded and wasted to renew.","Deck - Machinery,Elect. Mach. & Equip.,Miscellaneous","Structural Condn. / WT integrity ","Equipment Related","","","","","Elevator room watertight door upper rain shield cropped and renewed.","2022-01-15T23:59:35","","Completed","2022-01-15T23:59:35","No","No","No","Internal"]
[null,null,null,23682,null,"125_18/1/2022 1:48:48 am","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Insulation lagging on piping in purifier room dirty.","E/R - Pipes/ valves & fittings,Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Damamged Insulation lagging on piping repaired & painted in purifier room.","2022-01-10T23:59:35","","Completed","2022-01-06T23:59:35","No","No","No","Internal"]
[null,null,null,23683,null,"125_18/1/2022 1:53:43 am","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Door lock upper deck port side entrance not working properly,door frame need to reinforce.","Accommodation","General Appearance","Equipment Related","","","","","Door lock upper deck port side entrance repaired, door frame reinforced.","2022-01-14T23:59:35","","Completed","2022-01-11T23:59:35","No","No","No","Internal"]
[null,null,null,23684,null,"125_18/1/2022 1:56:36 am","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Windlass and mooring winch foundation, structure , brake band and hydraulic piping connections rusted.","Deck - Mooring Machinery","General Appearance","Equipment Related","","","","","Windlass and mooring winch foundation, structure , brake band and hydraulic piping connections derusted and painted.","2022-01-15T23:59:35","","Completed","2022-01-14T23:59:35","No","No","No","Internal"]
[null,null,null,23685,null,"125_18/1/2022 2:21:32 am","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency fire pump compartment floor plate rusted.\t","E/R - Pumps,Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Emergency fire pump compartment floor loose rust chipped off and painted.","2022-01-15T23:59:35","","Completed","2022-01-14T23:59:35","No","No","No","Internal"]
[null,null,null,23686,null,"125_18/1/2022 2:00:43 am","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","International shore connection and spanner not maintained properly, box damaged.","Miscellaneous","MARPOL Related","Equipment Related","","","","","International shore connection and spanner maintained properly, box repaired.","2022-01-10T23:59:35","","Completed","2022-01-09T23:59:35","No","No","No","Internal"]
[null,null,null,22174,null,"125_30/10/2021 11:34:49 am","2021-12-26T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","E/R bottom platform - Local signal light column alarm rotatory lamp not working. To be investigated and rectified.","Elect. Mach. & Equip.,Miscellaneous","Emgcy. Systems","Equipment Related","","","","","SPARES received and fitted , working satisfactory.","2022-02-15T23:59:35","NTEN210067","Completed","2022-02-14T23:59:35","No","No","No","Internal","spare parts to be connected to vessel at Next convenient port."]
[null,null,null,23552,null,"125_8/1/2022 9:49:53 pm","2022-01-05T23:59:35","Observation","Ship Staff","Ship Staff Insp.","AE-1 attached HT cooling water pump leaking observed at Tell tale hole ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","AE-1 attached HT pump removed and inspected, mechanical seal and O-rings renewed. fitted back in place and checked, satisfactory with no leaks.","2022-01-10T23:59:35","","Completed","2022-01-07T23:59:35","No","No","No","Internal"]
[null,null,null,23796,null,"125_1/2/2022 7:28:51 pm","2022-01-17T23:59:35","Observation","Ship Staff","Ship Staff Insp.","EGE - boiler water circulating pump no-1 leaking due to damaged mechanical seal","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","pump opened mechanical seal renewed with spare seal onboard.","2022-03-15T23:59:35","NTEN220013","Completed","2022-02-25T23:59:35","No","No","No","Internal","RO is under processing."]
[null,null,null,23795,null,"125_1/2/2022 7:33:02 pm","2022-01-18T23:59:35","Defect,Observation","Ship Staff","Ship Staff Insp.","ME and GE FO circulating pump no-1 leaking.","E/R - Aux. Engine,E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","ME and GE FO circulating pump no-1 opened mechanical seal replaced with supplied spares working satisfactory.","2022-03-15T23:59:35","NTEN220014","Completed","2022-02-25T23:59:35","No","No","No","Internal","RO is under processing."]
[null,null,null,23797,null,"125_1/2/2022 7:36:58 pm","2022-01-24T23:59:35","Observation","Ship Staff","Ship Staff Insp.","ER bilge well port and stbd- suction valves hard to operate.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","defective valves removed, cleaned a, greased and freed.","2022-02-07T23:59:35","","Completed","2022-01-31T23:59:35","No","No","No","Internal"]
[null,null,null,23920,null,"125_13/2/2022 5:57:47 pm","2022-02-05T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Main mast air horn found not working properly","Navigation - Others","Navigation","Equipment Related","","","","","Air horn solenoid valves overhauled, air horn diaphragm and o ring renewed, working satisfactory.","2022-02-12T23:59:35","","Completed","2022-02-08T23:59:35","No","No","No","Internal"]
[null,null,null,23918,null,"125_15/2/2022 10:49:26 am","2022-02-12T23:59:35","Observation","Ship Staff","Ship Staff Insp.","insulation matting at Cargo control panel is in detoriated condition, and is chaffed at various locations.","Elect. Mach. & Equip.,Miscellaneous","Cargo / Ballast Systems","External Factors","","","","","Mat replaced with new supplied one.","2022-04-15T23:59:35","NTEN220046","Completed","2022-02-27T23:59:35","No","No","No","Internal","RO is under processing."]
[null,null,null,23919,null,"125_15/2/2022 5:23:33 pm","2022-02-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","exhaust gas economiser tray drain is chocked and drain pipe observed to be wasted out at pipe seam","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","pipe to removed and entire section renewed with new fabricated piping. ","2022-02-28T23:59:35","","Completed","2022-02-17T23:59:35","No","No","No","Internal","pls update work progress."]
[null,null,null,23921,null,"125_15/2/2022 10:52:13 am","2022-02-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","MAC-2 second stage air side thermometer leaking due to ruptured thimble.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","MAC-2 second stage air side thermometer replaced with new spare . MAC-2 tried out.","2022-02-20T23:59:35","","Completed","2022-02-15T23:59:35","No","No","No","Internal"]
[null,null,null,24930,null,"125_15/3/2022 2:49:30 am","2022-03-06T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Line for ME T/C grit wash found chocked","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Human Error","","","","","Remove the Line and container and clear the line","2022-03-10T23:59:35","","Completed","2022-03-07T23:59:35","No","No","No","Internal"]
[null,null,null,24931,null,"125_15/3/2022 6:04:10 pm","2022-03-06T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","LO leakage from No.2  ME LO Pump ","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Oil seal to be renewed","2022-03-30T23:59:35","","Completed","2022-03-14T23:59:35","No","No","No","Internal"]
[null,null,null,24933,null,"125_31/3/2022 10:20:23 pm","2022-03-08T23:59:35","Defect","Ship Staff","Ship Staff Insp.","BOILER FEED WATER PUMP NOT STARTING ON AUTO","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","CLEANED WATER LEVEL INDICATOR TRANSDUCER AND TRIED OUT, PUMP CUT-IN AND CUT-OUT SATISFACTORY","2022-04-30T23:59:35","","Completed","2022-03-30T23:59:35","No","No","No","Internal"]
[null,null,null,24932,null,"125_17/3/2022 1:20:26 pm","2022-03-15T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Fwd mooring winches break band joints found frozen.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Break band joints needs to be freed and adjusted so as avoid excessive/ uneven wear on the break liners.","2022-06-14T23:59:35","","Completed","2022-03-19T23:59:35","No","No","No","Internal"]
[null,null,null,null,76245,"125_Wed Apr 27 2022 21:03:04 GMT+0800","2022-04-05T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Aft mooring winches (8nos) brake band hinges found frozen.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Needs to be opened, heated/de-rusted & fixed back with grease","2022-07-04T08:00:00","","Completed","2022-04-19T08:00:00","No","No","No","Internal"]
[null,null,null,24928,null,"125_17/3/2022 1:11:41 pm","2022-03-12T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Lower platform of vertical ladder in hold no. 9 (on aft bulkhead) found damaged.","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","Need to repair platform and safety railing  for safe access to hold no. 9 from aft end","2022-06-11T08:00:00","","Completed","2022-05-02T08:00:00","No","No","No","Internal","as per email instruction, pls check drawing and advise work plan."]
[null,null,null,null,23537,"125_Thu Jun 02 2022 04:23:37 GMT+0800","2022-05-05T08:00:00","Observation","Ship Staff","Ship Staff Insp.","During routine maintenance on deck it was observed that safety chains at Port & Stbd Provision crane platforms & at Lifeboat wire drum inspection platform are heavily corroded and wasted.","LSA / FFA,Deck - Machinery","Safety / LSA / FFA","Equipment Related","","","","","Safety chains at  provision crane platforms & lifeboat wire drum inspection platform needs to be renewed.","2022-08-04T08:00:00","","Completed","2022-05-14T08:00:00","No","No","No","Internal"]
[null,null,null,null,74257,"125_Thu Jun 02 2022 04:32:19 GMT+0800","2022-05-26T08:00:00","Observation","Ship Staff","Ship Staff Insp.","During routine inspection on deck it was observed that Brake rendering markers were not adjusted on mooring winch brake shafts after annual brake rendering test. ","Deck - Mooring Machinery","Mooring","Human Error","","","","","New or adjusted brake rendering pointers as per brake test to be welded on mooring winch brake shafts","2022-08-25T08:00:00","","Completed","2022-05-28T08:00:00","No","No","No","Internal"]
[null,null,null,null,59982,"125_Thu Jun 02 2022 09:23:12 GMT+0800","2022-05-22T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","AMS NO.2 STOPPED AND NOT STARTING","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","TROUBLE SHOOTING DONE BY SERVICE ENGINEER AND RECTIFIED THE FAULT.","2022-08-30T08:00:00","","Completed","2022-06-13T08:00:00","No","No","No","Internal"]
[null,null,null,23037,null,"125_30/11/2021 12:15:34 am","2022-02-16T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Low sea chest copper anode of MGPS system observed 80% consumed,need replaceme","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Copper anode  replaced with new spare one. .","2022-05-16T08:00:00","NTEN210093","Completed","2022-04-11T08:00:00","No","No","No","Internal","Spare parts to be connected to vessel at next convenient port."]
[null,null,null,null,33811,"125_Fri Jul 01 2022 17:34:25 GMT+0800","2022-06-27T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Warm up valve on the hatch cover hydraulic line system aft of no. 9 hold portside found frozen.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Warm up valve derusted & using WD40 freed.  Valve lubricated after freeing.","2022-09-26T08:00:00","","Completed","2022-07-02T08:00:00","No","No","No","Internal"]
[null,null,null,24929,null,"125_2/4/2022 06:48:13","2022-03-30T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Ballast tank vent Float guide found missing/ damaged at no. 3 S ballast tank.","Cargo Mach.,Critical Equip.,Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","New float guide needs to be fabricated and welded during loaded passage as at present tanks are full with ballast water & water comes out from vent as vessel rolls.","2022-06-29T08:00:00","","Completed","2022-07-02T08:00:00","No","No","No","Internal","please get it done at earliest opportunity."]
[null,null,null,null,98936,"125_Fri Jul 15 2022 13:52:06 GMT+0800","2022-06-28T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Ladder handrail at A deck stbd - found heavily corroded & bottom surface found opened with sharp edges which could cause very severe hand injury to personnel using ladder and handrail.","Accommodation","General Appearance","External Factors","","","","","Handrail needs to cropped and renewed at the earliest opportunity","2022-09-27T08:00:00","","Completed","2022-07-07T08:00:00","No","No","No","Internal"]
[null,null,null,null,85985,"125_Tue Aug 02 2022 10:35:10 GMT+0800","2022-07-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Hatch Cover no. 8 Stbd motor return line - minor leakage overserved in hydraulic return line.  ","Cargo Mach.","Cargo / Ballast Systems","External Factors,Equipment Related","","","","","Hydraulic line needs to be repaired / replaced to arrest the leakage. ","2022-10-27T08:00:00","","Completed","2022-08-01T08:00:00","No","No","No","Internal"]
[null,null,null,null,29009,"125_Thu Jun 02 2022 09:29:33 GMT+0800","2022-05-31T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","PARTITION PLATE BETWEEN INLET AND OUTLET WATER OF ATMOSPHERIC CONDESOR ERODED RESULTING IN SHORT CYCLING OG COOLING WATER HENCE REDUCING EFFICIENCY OF THE COOLER","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","New Atmospheric condenser installed","2022-08-31T08:00:00","NTEN220073 :  ATMOSPHERIC CONDENSER ","Completed","2022-08-08T08:00:00","No","No","No","Internal"]
[null,null,null,null,74203,"125_Fri Jul 01 2022 22:29:16 GMT+0800","2022-06-13T08:00:00","Condn of Class / Memo","Class Surveyor","Others (Eg. Insurance etc.)","Limit switches of both port and stbd provision cranes not operational","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related","","","","","All limit switches overhauled. Now working satisfactory","2022-09-13T08:00:00","","Completed","2022-07-26T08:00:00","No","No","No","External"]
[null,null,null,null,63629,"125_Fri Jul 01 2022 22:33:49 GMT+0800","2022-06-20T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","Aft cooler FW outlet valve stuck in closed condition","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Rectified","2022-09-18T08:00:00","","Completed","2022-07-18T08:00:00","No","No","No","Internal"]
[null,null,null,null,11249,"125_Mon Aug 01 2022 17:00:05 GMT+0800","2022-07-26T08:00:00","Observation","FSC Inspector","Flag State Insp.","Booby hatch lid internal securing arrangement found to be not securing properly.","Miscellaneous","Cargo / Ballast Systems","Human Error","","","","","Booby hatch lid internal securing arrangement to be checked/repaired/fabricated & maintained.","2022-10-26T08:00:00","","Completed","2022-08-20T08:00:00","No","No","No","External"]
[null,null,null,null,36295,"125_Fri Aug 26 2022 19:30:28 GMT+0800","2022-08-16T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Minor leak observed at Hatch cover hydraulic return line for no. 9 Stbd side.","Cargo Mach.,Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","Leaking Hydraulic pipe section to be renewed","2022-11-15T08:00:00","","Completed","2022-08-16T08:00:00","No","No","No","Internal"]
[null,null,null,null,80707,"125_Fri Aug 26 2022 17:31:18 GMT+0800","2022-07-26T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","BWTS Communication panel and No.1 TRO unit malfunction","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","Service engineer attended the fault and rectified","2022-09-10T08:00:00","","Completed","2022-08-27T08:00:00","No","No","No","Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["125","NN TENACITY (19-04-2022)","125_1650598090700.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]