## Mainsheet
Defect - Damage Monitoring Sheet
|  |  |  | Date of Report | 2022-10-10 |  |  | Ship Name | SCARLETT (04-08-2022)
VERSION : 2.0
ID | SHIPSIDE UNIQUEID | UNIQUE ID | Date Recorded | Type of Deficiency | Observer code | Type of Inspection | Description of Deficiency | Equipment Categories | Area of Observation | Deficiency Cause | VIQ Ref Number | Risk Value of Obs | PSC Ref Number | PSC MOU ID | Action Taken or Required | Target Date | PO Ref No. | Status Code | Date Completed | Drydock | Info Sharing | Critical Item | Audit Type | Superintendent Remarks
23133 |  | 112_15/11/2021 7:09:14 PM | 2021-11-04 | Defect | Ship Staff | Ship Staff Insp. | Tank level gauges for the following tanks show erroneous readings. a. WBT #1C b. WBT #4P c. WBT #6P d. WBT #7S | Hull & Tanks | Cargo / Ballast Systems | Equipment Related |  |  |  |  | Calibration done by service engineer, awaiting final testing & correction after control air is available | 2022-02-01 |  | Deferred to D D |  | Yes | No | No | Internal | please check and confirm. Raise RO as required
23134 |  | 112_15/11/2021 7:13:04 PM | 2021-11-04 | Defect | Ship Staff | Ship Staff Insp. | Valve indication for the following shows erroneous positions a. WBV 01 b. WBV 21 c. 2WV 50 d. 2WV 51 e. 2WV 52 f. 2 WV 53 g. 2 WV 56 h. 1 WV 17 a. BGV 02 b. BGV 12 | Miscellaneous | Cargo / Ballast Systems | Equipment Related |  |  |  |  | Calibration done by service engineer, calibration done & awaiting final testing & correction after VRCS is available | 2022-02-01 |  | Deferred to D D |  | Yes | No | No | Internal | vessel electrician to check and investigation. update final condition. Raise Ro as required
19532 |  | 112_6/5/2021 8:39:29 AM | 2021-11-07 | Observation | Ship Staff | Ship Staff Insp. | G/E F.O. flowmeter is not working | E/R - Aux. Mach. | Eng. / Strg. Comp. | Equipment Related |  |  |  |  | Flowmeter sent to shore for calibration. Based on the shore report same need to be replaced. Awaiting owner approval for new supply | 2022-02-05 | SCAR215078 | In progress |  | No | No | No | Internal | spare will supply in convenient port
18364 |  | 112_20/3/2021 4:14:10 PM | 2021-11-20 | Observation | Owner / Marine / Tech. Suptd. | Suptd. Insp. | All generators performance not satisfactory With no.2 DG Lo consumption on higher side around 60 Ltr per day, Need to carry out overhauling of DGs & supply spare parts accordingly. | E/R - Aux. Engine | Eng. / Strg. Comp. | Equipment Related |  |  |  |  | All 3 DG's overhauling in progress. | 2022-02-15 | SCAR215105 | Waiting spare |  | No | No | No | Internal | spare will supply in convenient port
18383 |  | 112_20/3/2021 3:59:13 PM | 2021-11-20 | Observation | Owner / Marine / Tech. Suptd. | Suptd. Insp. | GE & ME Viscotherm sensor to be procured & replaced | Elect. Mach. & Equip. | Eng. / Strg. Comp. | Equipment Related |  |  |  |  | Sensors and control valve have been renewed, awaiting final testing once the fuel system is put in operation. | 2022-02-15 | SCAR215076 215077 | In progress |  | No | No | No | Internal | spare will supply in convenient port
23140 |  | 112_5/12/2021 4:36:29 AM | 2021-11-22 | Defect | Ship Staff | Ship Staff Insp. | Corroded FL light fittings at various locations near accomodation area | Elect. Mach. & Equip. | Safety / LSA / FFA | Equipment Related |  |  |  |  | Replacement of light fixtures in progress | 2022-02-20 | SCAR210134 | In progress |  | No | No | No | Internal | spare will supply in next port
23147 |  | 112_15/12/2021 5:49:17 PM | 2021-12-12 | Defect | Ship Staff | Ship Staff Insp. | Remote display of the aft draught in the cargo control room giving a false reading. | Miscellaneous | Cargo / Ballast Systems | Equipment Related |  |  |  |  | Calibration done by service engineer, awaiting final testing & correction after control air is available | 2022-02-12 |  | Not Started |  | No | No | No | Internal | please check and confirm the draft gauge working condition and update
26404 | 90521 | 112_Wed Aug 03 2022 12:25:03 GMT+0800 | 2022-07-15 | Observation | Ship Staff | Ship Staff Insp. | The VDR software is available onboard but same is not configured | Navigation - VDR / BNWAS | Navigation | Inappropriate Procedure |  |  |  |  | Awaiting supply of data cable locally being purchased as per telcon with Mr. Kamlesh and test data backup. VDR software has been installed in the NAV PC. | 2022-11-14 |  | Not Started |  | No | No | No | Internal | to liaise with IT department and get update