{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":28,"n_cols":28,"rows_kept":28,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","11-Nov-2022",null,null,"Ship Name","DHT CHINA (11-11-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,26031,30832,"121_Fri Jul 01 2022 18:00:29 GMT+0800","2022-06-22T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Refrigeration system, meat room door handle found defective.","Miscellaneous","MLC Related","Equipment Related","10.32","Very High","","","Temporary repair work carried out. Require new handle to renew it.","2022-11-27T23:59:35","DCHI220139","Waiting spare",null,"No","No","No","Internal","Raise requisition."]
[null,null,null,26178,11010,"121_Thu Jul 07 2022 16:45:19 GMT+0800","2022-07-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Impingement plate to be fitted by tag welding, for the atmospheric condenser 6k drain line and the steam dump  return inlet opening.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Hot work to be carried out to fix the plate - awaiting vessel stoppage and possible opportunity to execute the job ","2022-11-27T23:59:35","","Not Started",null,"No","No","No","Internal","Noted."]
[null,null,null,26179,55109,"121_Thu Jul 07 2022 16:55:58 GMT+0800","2022-07-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME Aux Blower no #1 motor seat has to be replaced with new plate which has a telltale hole  drain arrangement  which serves as  a indicator for leaking gas lock seals to prevent damage to motor drive end bearing.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Awaiting first available opportunity for vessel stoppage to execute the job. ","2022-11-27T23:59:35","DCHI220116","Not Started",null,"No","No","No","Internal","PO issued, awaiting readiness."]
[null,null,null,26662,43880,"121_Thu Sep 01 2022 15:45:25 GMT+0800","2022-08-27T23:59:35","Defect","Ship Staff","Engineering Audit","The NO #1 LT cooler inlet strainer found damaged. The filter weld seam was found broken,","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Spot welding done  as complete run was not possible due to the thickness, and then cold repair was done applying devcon  putty to seal the gaps.Requisition raised for the same","2022-11-29T23:59:35","DCHI 220149","Waiting spare",null,"No","No","No","Internal","Noted, will process this requisition."]
[null,null,null,26663,42289,"121_Thu Sep 01 2022 20:09:01 GMT+0800","2022-08-27T23:59:35","Observation","Ship Staff","Engineering Audit","No.1 Boiler water circulating pump Gland found bent","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Replaced with new Gland packing but further tightening not possible, needs replacement. Req raised","2022-11-26T23:59:35","DCHI220150","Waiting spare",null,"No","No","No","Internal","Noted, will process this requisition."]
[null,null,null,27550,98377,"121_Thu Sep 29 2022 14:17:58 GMT+0800","2022-09-25T23:59:35","Observation","Ship Staff","Engineering Audit","AE viscotherm electronic viscosity controller is not giving the 220 Volts output required for operation of the Electric Actuator in open/close direction  Also on varying the set point of the viscosity at the controller.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Suspect problem with the  viscosity controller, have sent report to our office Auto support to advise us on further troubleshooting.","2022-11-29T23:59:35","","In progress",null,"No","No","No","Internal","Noted. Raise RO for required spare after troubleshootng."]
[null,null,null,27549,72034,"121_Tue Oct 04 2022 10:30:12 GMT+0800","2022-10-03T23:59:35","Other","Ship Staff","Suptd. Insp.","Paint inside of NO:2 BWTS filter with Sigma CSF-650 to avoid internal rusting,","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.8","Medium","","","Requires to paint internally during next scheduled inspection.","2022-11-29T23:59:35","","Not Started",null,"No","No","No","Internal"]
[null,null,null,27548,54395,"121_Tue Oct 18 2022 12:27:43 GMT+0800","2022-10-08T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No:1 DG Exhaust pipe bellow in funnel deck has leakage marks. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","10.19","Very High","","","To be inspected and renewed if required.","2023-01-09T23:59:35","","Not Started",null,"No","No","No","Internal"]
[null,null,null,27551,61721,"121_Tue Oct 18 2022 12:17:47 GMT+0800","2022-10-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","IGG display touch screen faded ","Cargo Mach.","Eng. / Strg. Comp.","Equipment Related","8.25","Very High","","","IGG display touch screen to renew ","2023-01-09T23:59:35","DCHI220183","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,27552,41935,"121_Tue Oct 18 2022 12:09:14 GMT+0800","2022-10-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Forward hydraulic power pack, no:3 hydraulic pump pressure gauge defective.","Deck - Mooring Machinery","Mooring","Equipment Related","10.32","Very High","","","DCHI220156- Awaiting Spares","2022-11-09T23:59:35","DCHI220156","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,27553,29947,"121_Tue Oct 18 2022 13:39:12 GMT+0800","2022-10-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Steering room fire fighter’s walkie-talkie batteries and spare batteries not charging. To be renewed.","LSA / FFA","Safety / LSA / FFA","Equipment Related","5.43","High","","","Requisition for spare batteries raised","2022-12-09T23:59:35","DCHI220179","Waiting spare",null,"No","No","No","Internal"]

{"sheet":"Completed","index":1,"n_rows":173,"n_cols":28,"rows_kept":173,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","11-Nov-2022",null,null,"Ship Name","DHT CHINA (11-11-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,20022,null,"121_14-Jul-21 4:13:05 PM","2021-01-02T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Engine room ventilation duct material corroded wasted in various places","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Few of the of the corroded sections cropped and new plate inserted and few of the sections repaired in place . This job was carried out in the dry dock.","2021-01-05T23:59:35","","Completed","2021-09-25T23:59:35","No","No","No","Internal","Raise refman defect to carry out job in DD."]
[null,null,null,20418,null,"121_16-Jul-21 11:10:57 AM","2021-02-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Bridge Port side window wiper not working","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Inspected and found that motor is running howerver roller and belt is not. Same need to removed from its place and overhauled","2021-12-26T23:59:35","","Completed","2021-11-14T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,20416,null,"121_16-Jul-21 11:41:31 AM","2021-03-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Order printer unit paper take up device is malfunctioning","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Spare received and renewed.","2021-08-26T23:59:35","","Completed","2021-08-23T23:59:35","No","No","No","Internal"]
[null,null,null,20023,null,"121_14-Jul-21 2:09:56 PM","2021-05-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Aux Engine fuel oil flow meter malfunctioning.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","The flow meter was calibrated at shore by the shore techinician at the dry dock and is now working satisfactory.","2021-05-05T23:59:35","DCHI210015","Completed","2021-09-23T23:59:35","No","No","No","Internal","PO issued. Awaiting rediness."]
[null,null,null,20024,null,"121_14-Jul-21 2:13:54 PM","2021-06-02T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Scrubber gas outlet section material wasted.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","The corroded section cropped and new plate inserted ,carried out in the dry dock.","2021-06-05T23:59:35","","Completed","2021-09-23T23:59:35","No","No","No","Internal","Raise refman defect for job to be carried out in DD."]
[null,null,null,20019,null,"121_28-Jun-21 11:44:56 PM","2021-06-16T23:59:35","Defect","Ship Staff","Ship Staff Insp.","COPT NO 1 PUMP SIDE LOWER BEARING TEMPERATURE SENSOR FALUTY","Cargo Mach.","Eng. / Strg. Comp.","Equipment Related","8.8","Medium","","","Spare new temperature sensor received.","2021-09-16T23:59:35","","Completed","2021-09-04T23:59:35","No","No","No","Internal","Raise requisition ASAP."]
[null,null,null,20029,null,"121_28-Jun-21 11:48:27 PM","2021-06-16T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NO 1 AUX BOILER SMOKE DENSITY SENSOR FAULTY","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Renewed with new spare at dry dock, tried out and is found working satifctory.","2021-09-16T23:59:35","","Completed","2021-09-11T23:59:35","No","No","No","Internal","Raise requisition ASAP."]
[null,null,null,24865,null,"121_05-Mar-22 1:35:38 PM","2021-06-17T23:59:35","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Light hoods at the following locations were observed with either one or multiple cracks: 1) one light hood at extreme starboard side on cargo and ballast pump turbine platform. 2) two light hoods to the forward end and slightly to port side on the engine side maneuvering platform. 3) two light hoods in the purifier room.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","Defective light hoods replaced during the inspection","2021-07-17T23:59:35","","Completed","2021-06-17T23:59:35","No","No","No","External"]
[null,null,null,20031,null,"121_7/12/2021 3:51:12 PM","2021-06-18T23:59:35","Observation","Ship Staff","Ship Staff Insp.","PV breaker gauge glass found opaque and marking blurred.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.28","Medium","","","Water from PV breaker drained and gauge glass  cleaned. Marking on the plate highlighted. Calibration carried out.","2021-06-25T23:59:35","","Completed","2021-06-24T23:59:35","No","No","No","Internal"]
[null,null,null,20032,null,"121_7/12/2021 3:46:02 PM","2021-06-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Flame screen of PV valves found damaged and rusted.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.41","Medium","","","Flame screens of all PV valves renewed.","2021-06-25T23:59:35","","Completed","2021-06-25T23:59:35","No","No","No","Internal"]
[null,null,null,20030,null,"121_28-Jun-21 11:53:58 PM","2021-06-20T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","The change over cock for the main engine autobackwash filter found leaking","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","The O ring of the change over cock renewed , the leak rectified.","2021-06-22T23:59:35","","Completed","2021-06-20T23:59:35","No","No","No","Internal"]
[null,null,null,20020,null,"121_7/12/2021 4:02:19 PM","2021-06-21T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Wires of both provision cranes, engine room crane and elevator due for renewal.","Deck - Machinery","Safety / LSA / FFA","Equipment Related","8.63","High","","","Requisition raised for spare wires. Wire of both provision cranes has been changed. Vessel is awaiting spare wires for E/Room crane and elevator.","2021-07-25T23:59:35","DCHI210034","Completed","2021-07-17T23:59:35","No","No","No","Internal","Raise requisition for new spare wires."]
[null,null,null,20021,null,"121_14-Jul-21 2:01:05 PM","2021-06-21T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Incinerator combustion air pressure switch malfuctioning","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","The pressure switch renewed with new spare received, tried out and is found working satisfactory.","2021-09-21T23:59:35","","Completed","2021-12-04T23:59:35","No","No","No","Internal","Raise requisition ASAP."]
[null,null,null,20417,null,"121_7/27/2021 11:29:45 AM","2021-06-21T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Telegraph light indicator (Kongsberg) for dead slow astern not working.","Critical Equip.,Navigation - Others","Navigation","Equipment Related","4.7","High","","","Spares received and telegraph light indicator repaired.","2021-10-26T23:59:35","","Completed","2021-10-12T23:59:35","No","No","No","Internal"]
[null,null,null,20419,null,"121_16-Jul-21 11:38:09 AM","2021-06-21T23:59:35","Defect","Ship Staff","Ship Staff Insp.","\"Duty engineer on duty\" indicator light not working on bridge UMS panel.","Miscellaneous","General Appearance","Equipment Related","4.7","High","","","The bridge UMS Panel renewed with new spare","2021-09-25T23:59:35","","Completed","2021-09-10T23:59:35","No","No","No","Internal"]
[null,null,null,20025,null,"121_7/12/2021 3:56:15 PM","2021-06-24T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Flame screen of Ballast tank vent heads found damaged and rusted.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","11.7","High","","","Flame screen of ballast tank vent heads renewed.","2021-08-10T23:59:35","","Completed","2021-07-15T23:59:35","No","No","No","Internal","Believe vessel has spare mesh in hand."]
[null,null,null,20026,null,"121_7/5/2021 8:13:18 AM","2021-06-24T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Sound reception system's forward mic found non operational.","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Received new type/model  complete set. After changing with new spare. All in good order.","2022-04-23T23:59:35","DCHI220002","Completed","2022-03-31T23:59:35","No","No","No","Internal"]
[null,null,null,20420,null,"121_16-Jul-21 11:05:13 AM","2021-06-29T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Stbd Bridge Wing rudder angle indicator light is not functional","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Stbd bridge wing rudder angle indicator made functional by replacing potentiometer.","2021-08-26T23:59:35","","Completed","2021-08-25T23:59:35","No","No","No","Internal"]
[null,null,null,20033,null,"121_14-Jul-21 2:04:47 PM","2021-06-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","No 1 camshaft lub booster pump leaking from mechanical seal.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Pump overhauled, mechanical seal renewed.","2021-09-30T23:59:35","","Completed","2021-06-30T23:59:35","No","No","No","Internal"]
[null,null,null,20018,null,"121_7/12/2021 3:40:27 PM","2021-07-02T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Fire hydrant under foam monitor no. 6 found frozen.","LSA / FFA","Safety / LSA / FFA","Equipment Related","5.35","Medium","","","Fire hydrant overhauled and tested atfter installation, no leaks found.","2021-08-10T23:59:35","","Completed","2021-07-11T23:59:35","No","No","No","Internal","Noted. Update progress in weekly deck maintenance report."]
[null,null,null,20027,null,"121_7/12/2021 2:18:51 PM","2021-07-02T23:59:35","Observation","Ship Staff","Ship Staff Insp.","2S WBT Stripper Valve BA009 found non operational from CCR.","Cargo Mach.,Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","Solenoid of valve BA009 checked and purged by HKT technician. Valve operation tried out from CCR and by hydraulic hand pump.","2021-08-10T23:59:35","","Completed","2021-09-11T23:59:35","No","No","No","Internal","Update progress in weekly deck maintenance report."]
[null,null,null,20028,null,"121_7/12/2021 4:06:38 PM","2021-07-02T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Stbd. side SOPEP wilden pump found non operational.","Miscellaneous","MARPOL Related","Equipment Related","6.3","Low","","","Wilden pump overhauled and tested, found working satisfactory.","2021-08-10T23:59:35","","Completed","2021-07-06T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,20034,null,"121_14-Jul-21 2:17:35 PM","2021-07-04T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Main Engine Fuel oil circulating pump no 2 having noise and vibration","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Main Engine Fuel oil circulating pump no 2 overhauled and motor overhauled.","2021-10-04T23:59:35","","Completed","2021-07-04T23:59:35","No","No","No","Internal"]
[null,null,null,20421,null,"121_16-Jul-21 11:48:38 AM","2021-07-05T23:59:35","Defect","Ship Staff","Ship Staff Insp.","IG deck pressure I/O fault on HMI screen and showing false readings","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.22","Very High","","","Faulty electrical cable renewed during dry dock and IG alarm rectified by HKT marine technician.","2021-07-25T23:59:35","","Completed","2021-09-13T23:59:35","No","No","No","Internal"]
[null,null,null,20431,null,"121_28-Jul-21 10:13:12 PM","2021-07-11T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Forward life raft light stand found rusted and frozen.","LSA / FFA","Safety / LSA / FFA","Equipment Related","5.22","High","","","Life raft light stand de-rusted and made free.","2021-07-26T23:59:35","","Completed","2021-07-19T23:59:35","No","No","No","Internal"]
[null,null,null,20422,null,"121_28-Jul-21 10:17:18 PM","2021-07-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Port lifeboat self lowering wire found rusted and damaged.","LSA / FFA","Safety / LSA / FFA","Equipment Related","5.27","Medium","","","Self lowering wire replaced.","2021-08-02T23:59:35","","Completed","2021-07-30T23:59:35","No","No","No","Internal"]
[null,null,null,20423,null,"121_28-Jul-21 10:27:26 PM","2021-07-22T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Air filter for aft ETA air motor found wasted.","Deck - Mooring Machinery","Mooring","Equipment Related","9.28","Medium","","","Aft ETA air filter replaced.","2021-08-05T23:59:35","","Completed","2021-07-23T23:59:35","No","No","No","Internal"]
[null,null,null,20433,null,"121_7/28/2021 5:39:47 AM","2021-07-22T23:59:35","Critical Equipment,Observation","Ship Staff","Ship Staff Insp.","Magnetic compass illumination bulb holder defective.","Navigation - Others","Navigation","Equipment Related","4.9","Medium","","","Magnetic compass illumination bulb holder renewed during dry dock.","2021-09-25T23:59:35","","Completed","2021-09-09T23:59:35","No","No","No","Internal"]
[null,null,null,20449,null,"121_16-Aug-21 3:57:57 PM","2021-07-27T23:59:35","Defect","Ship Staff","Ship Staff Insp.","The change over cock of the Generator autoback wash filter leaking","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","O ring renewed , leak rectified","2021-10-27T23:59:35","","Completed","2021-08-01T23:59:35","No","No","No","Internal"]
[null,null,null,20446,null,"121_16-Aug-21 9:06:25 AM","2021-07-28T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Main Air Control Line Pressure Gauge defective","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","The defective  pressure gauge renewed with new spare pressure guage","2021-10-28T23:59:35","","Completed","2021-07-31T23:59:35","No","No","No","Internal"]
[null,null,null,20447,null,"121_16-Aug-21 9:08:57 AM","2021-07-28T23:59:35","Defect","Ship Staff","Ship Staff Insp.","HFO Transfer Pump Suction/Discharge Pressure Gauge defective","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","HFO Transfer Pump Suction/Discharge Pressure Gauge renewed with new spare pressure gauge.","2021-10-28T23:59:35","","Completed","2021-07-31T23:59:35","No","No","No","Internal"]
[null,null,null,20448,null,"121_16-Aug-21 9:11:07 AM","2021-07-28T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Stern Tube Pump No.2 Suction /Discharge Pressure Gauges Defective","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","stern Tube Pump No.2 Suction/Discharge Pressure Gauges renewed with new spare pressure gauges","2021-10-28T23:59:35","","Completed","2021-07-31T23:59:35","No","No","No","Internal"]
[null,null,null,20424,null,"121_8/1/2021 7:36:35 PM","2021-08-03T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Doppler log distance counter not operational","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Doppler log distance counter renewed, working satisfactory","2021-12-26T23:59:35","DCHI210123","Completed","2021-12-15T23:59:35","No","No","No","Internal","Raise requisition ASAP."]
[null,null,null,20425,null,"121_8/2/2021 7:47:21 AM","2021-08-03T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Navtex not receiving message on 518Kz","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Aerial replaced and navtex working properly.","2021-09-25T23:59:35","","Completed","2021-09-10T23:59:35","No","No","No","Internal"]
[null,null,null,20426,null,"121_16-Aug-21 9:18:10 AM","2021-08-06T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CO2 Room Gas Monitor alarm 1 on; noted O2 17.5%","LSA / FFA","Safety / LSA / FFA","Equipment Related","10.32","Very High","","","Span calibration of oxygen sensor in CO2 room carried out, found working satisfactory.","2021-11-06T23:59:35","","Completed","2021-08-14T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,20427,null,"121_16-Aug-21 9:23:53 AM","2021-08-06T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME LO Storage tank gauge glass lower flange leaking","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related","10.32","Very High","","","Leak from the gauge glass  spring loaded valve rectified. ","2022-11-27T23:59:35","","Completed","2022-09-16T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,20428,null,"121_16-Aug-21 9:29:05 AM","2021-08-06T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Provision Refrigerant Compressor#1 Shaft Seal suspected leaking","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","The leak observed and measured , the oil leak rate from shaft seal is within the tolearance at normal condiiton ie 0.05cm3/hr","2021-11-06T23:59:35","","Completed","2021-08-10T23:59:35","No","No","No","Internal","Raise requisition if spare required."]
[null,null,null,20429,null,"121_16-Aug-21 9:31:26 AM","2021-08-06T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Accomodation air conditioning Compressor#1 discharge pressure gauge defective","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","The discharge pressure gauge observed for zero reading and is found correct and is functioning satisfactory.","2021-11-06T23:59:35","","Completed","2021-08-10T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,20435,null,"121_16-Aug-21 9:49:15 AM","2021-08-06T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main Engine air Cooler aft Condensate drain line signal glass dirty ","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","The drain line signal glass cleaned.","2021-11-06T23:59:35","","Completed","2021-09-01T23:59:35","No","No","No","Internal"]
[null,null,null,20436,null,"121_16-Aug-21 10:36:13 AM","2021-08-06T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck Pipelines to de-rust mainly around pipe support and paint","Deck - Pipe / Fittings","General Appearance","Equipment Related","8.3","Very High","","","De-rusting and painting of deck pipelines and supports carried out as required.","2022-09-25T23:59:35","","Completed","2022-09-12T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,20437,null,"121_16-Aug-21 10:39:46 AM","2021-08-06T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","COW Line noted with several spot rust - to derust and paint","Deck - Pipe / Fittings","General Appearance","Equipment Related","8.3","Very High","","","De-rusting and painting of COW line completed.","2021-12-26T23:59:35","","Completed","2021-12-22T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,20438,null,"121_16-Aug-21 10:44:10 AM","2021-08-06T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","COW Line branch pipes support brackets rusted and U clamps wasted, teflon packing iwo U Clamps missing","Deck - Pipe / Fittings","General Appearance","Equipment Related","8.3","Very High","","","De-rusting and painting of COW lines completed.  Teflon packing under U-clamp renewed.","2021-12-26T23:59:35","","Completed","2021-12-22T23:59:35","No","No","No","Internal"]
[null,null,null,20439,null,"121_16-Aug-21 10:47:24 AM","2021-08-06T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mooring Winch No.3 and No.5 gear case LO sight glass to replace","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Sight glass of mooring winches replaced.","2021-11-16T23:59:35","","Completed","2021-09-15T23:59:35","No","No","No","Internal"]
[null,null,null,20440,null,"121_16-Aug-21 10:50:19 AM","2021-08-06T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mooring Winch No.2 and No.6 gear case LO sight glass opaque , Check LO quality and renew if required ,clean sight glass","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Lube oil renewed and sight glass cleaned.","2021-11-16T23:59:35","","Completed","2021-09-15T23:59:35","No","No","No","Internal"]
[null,null,null,20441,null,"121_16-Aug-21 10:55:45 AM","2021-08-06T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bosun Store floor plate alongside aft bulkhead to derust and paint","Miscellaneous","General Appearance","Equipment Related","11.12","Low","","","De-rusting, painting and cleaning of bosun store carried out.","2021-11-16T23:59:35","","Completed","2021-10-10T23:59:35","No","No","No","Internal"]
[null,null,null,20442,null,"121_15-Aug-21 2:34:45 PM","2021-08-10T23:59:35","Defect","Ship Staff","Ship Staff Insp.","GPS printer not printing legibly.Printer head defctive","Navigation - DGPS / EPFS / AIS","Navigation","Equipment Related","4.2","Medium","","","Printer head replaced during dry dock.","2021-09-26T23:59:35","","Completed","2021-09-10T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,20443,null,"121_15-Aug-21 2:50:18 PM","2021-08-10T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Port side bridge wing manoevering station.Control not being transfered for ME telepgraph.","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Issue rectified and ME telegraph control change over tested, found satisfactory.","2021-10-27T23:59:35","","Completed","2021-09-25T23:59:35","No","No","No","Internal","AC4 maintenance will be done after docking at Singapore."]
[null,null,null,20445,null,"121_15-Aug-21 2:59:06 PM","2021-08-10T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Magnetic Compass Adjustment not done for over 2 years","Navigation - Others","Navigation","Equipment Related","4.9","Medium","","","Magnetic compass adjusted and Deviation card prepared during dry dock.","2021-11-10T23:59:35","","Completed","2021-09-13T23:59:35","No","No","No","Internal","Service will be done while docking."]
[null,null,null,23058,null,"121_06-Dec-21 7:12:33 AM","2021-10-12T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No 1 sewage Plant blower to renew","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","No 1 sewage plant blower renwed with new blower received. Tried out working satisfactory.","2022-01-12T23:59:35","DCHI210113","Completed","2021-12-17T23:59:35","No","No","No","Internal","PO issued, awaiting readiness."]
[null,null,null,23059,null,"121_06-Dec-21 6:31:10 AM","2021-10-12T23:59:35","Defect,Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CCTV Installation","Miscellaneous","Communication","Equipment Related","7.6","Medium","","","CCTV installation and commitioning completed. Working satisfactory.","2022-02-11T23:59:35","","Completed","2021-12-11T23:59:35","No","No","No","Internal","Commissioning guidelines sent to vessel."]
[null,null,null,23060,null,"121_06-Dec-21 7:08:12 AM","2021-10-12T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","100 % LT Cooler FW inlet Temp gauge defective","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.25","Very High","","","FW inlet temp gauge renewed.","2021-12-12T23:59:35","","Completed","2021-12-01T23:59:35","No","No","No","Internal","Raise requisition."]
[null,null,null,23061,null,"121_06-Dec-21 6:35:14 AM","2021-10-12T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No 2 Boiler Local operating panel defective","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","No 2 Boiler Local operating panel screen renewed.","2021-12-12T23:59:35","","Completed","2021-12-03T23:59:35","No","No","No","Internal","Spare supplied to vessel."]
[null,null,null,23062,null,"121_06-Dec-21 6:39:49 AM","2021-10-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Panel cooling AC's to fit on various electrical panels","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.37","Medium","","","All 4 ac's (boiler panel, EGCS main panel and EGCS VFD pumps panel) fitted. Working satisfactory","2022-01-12T23:59:35","","Completed","2022-01-05T23:59:35","No","No","No","Internal","How many remaining?"]
[null,null,null,23064,null,"121_06-Dec-21 5:01:38 AM","2021-10-12T23:59:35","Observation","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","Port anchor Chain entangled and not coming out of spurling pipe","Deck - Machinery","Mooring","Equipment Related","9.2","Very High","","","Cleared in chain locker","2021-10-22T23:59:35","","Completed","2021-10-22T23:59:35","No","No","No","External"]
[null,null,null,23065,null,"121_06-Dec-21 5:06:53 AM","2021-10-12T23:59:35","Defect","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","Starboard anchor brake need adjustment","Deck - Machinery","Mooring","Equipment Related","9.2","Very High","","","The starboard anchor brake adjusted","2021-11-12T23:59:35","","Completed","2021-11-22T23:59:35","No","No","No","External"]
[null,null,null,23066,null,"121_06-Dec-21 5:12:10 AM","2021-10-12T23:59:35","Defect","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","Hose handlind crane hose couplings to be protected","Cargo Mach.","Structural Condn. / WT integrity ","Equipment Related","10.28","Low","","","The hose couplings applied with Denso tape","2021-10-27T23:59:35","","Completed","2021-10-27T23:59:35","No","No","No","External"]
[null,null,null,23067,null,"121_06-Dec-21 5:22:18 AM","2021-10-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Ballast water Sampling point to be stencilled.","Cargo Mach.","General Appearance","Equipment Related","8.14","Very High","","","The Ballast Water Sampling point Stenciled.","2021-11-12T23:59:35","","Completed","2021-11-12T23:59:35","No","No","No","Internal"]
[null,null,null,23068,null,"121_06-Dec-21 5:33:07 AM","2021-10-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pumproom bulkheads to be cleaned","Deck - Pipe / Fittings","General Appearance","Equipment Related","8.44","High","","","Bulkheads Cleaned.","2021-11-12T23:59:35","","Completed","2021-11-12T23:59:35","No","No","No","Internal"]
[null,null,null,23069,null,"121_06-Dec-21 6:47:28 AM","2021-10-12T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","IGG Local display unit defective","Cargo Mach.","Eng. / Strg. Comp.","Equipment Related","10.37","Medium","","","The IGG local display was found freezed, the same restarted and is found operational","2022-01-12T23:59:35","","Completed","2021-11-12T23:59:35","No","No","No","Internal"]
[null,null,null,23070,null,"121_06-Dec-21 6:43:48 AM","2021-10-12T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No 1 Boiler FD fan ammeter defective","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.37","Medium","","","The ammeter repaired and is funcitonal.","2022-01-12T23:59:35","","Completed","2021-11-12T23:59:35","No","No","No","Internal"]
[null,null,null,23071,null,"121_06-Dec-21 6:51:28 AM","2021-10-12T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No 1 & 2 Boiler main steam pressure gauges to fit properly","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.25","Very High","","","The Boiler Main Steam pressure gauges fitted and secured properly.","2021-11-12T23:59:35","","Completed","2021-12-01T23:59:35","No","No","No","Internal"]
[null,null,null,23090,null,"121_Tue Dec 07 2021 05:33:18 GMT+0000","2021-10-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Spare parts inventory to be completed and all spare parts to be added to PAL. Operational spare parts to be identified as per SMS and marked in PAL.","Documentation","ISM Related","Inappropriate Procedure","10.12","Very High","","","Operational spare parts checked and other spare parts updated.","2022-01-26T23:59:35","","Completed","2022-01-05T23:59:35","No","No","No","Internal","What is progress on same?"]
[null,null,null,22435,null,"121_31-Oct-21 3:58:20 PM","2021-10-12T23:59:35","Other","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Anemometer junction box broken. Anemometer is working erratically.","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Anemometer junction box renewed.","2021-12-12T23:59:35","DCHI210091","Completed","2021-12-11T23:59:35","No","No","No","Internal","Spare junction box supplied to vessel."]
[null,null,null,22440,null,"121_28-Oct-21 7:17:24 PM","2021-10-18T23:59:35","Defect","Ship Staff","Ship Staff Insp.","The Inert Gas Oxygen Analyser was showing erratic readings.","Cargo Mach.,Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","5.23","Very High","","","The oxygen sensor for  Analyser  renewed with new spare","2021-10-25T23:59:35","","Completed","2021-10-20T23:59:35","No","No","No","Internal"]
[null,null,null,22436,null,"121_10/31/2021 5:09:40 PM","2021-10-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Mechanical Seal of Deck Seal Pump leaking","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","The Mechanical Seal  renewed with new spare. Pump tried out working satisfactory.","2022-01-18T23:59:35","DCHI210098","Completed","2021-12-15T23:59:35","No","No","No","Internal","PO issued. Awaiting readiness."]
[null,null,null,22437,null,"121_10/31/2021 5:12:48 PM","2021-10-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Motor of the Deck Seal Pump found burnt and reading zero Insulation","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Motor of the Pump renewed with new motor received.","2022-01-18T23:59:35","DCHI210099","Completed","2021-12-15T23:59:35","No","No","No","Internal","Spare motor supplied to vessel."]
[null,null,null,22441,null,"121_28-Oct-21 7:23:17 PM","2021-10-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","The Electric heater in the dryer room of the laundry found defective ","Elect. Mach. & Equip.","MLC Related","Equipment Related","11.15","Low","","","On Inspection all the wirings were found in burnt condition,the same renewed and tested, found working satisfactory.","2021-10-26T23:59:35","","Completed","2021-10-23T23:59:35","No","No","No","Internal"]
[null,null,null,22438,null,"121_31-Oct-21 4:03:28 PM","2021-10-26T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Emergency generator vent flap rbber packing channel corroded","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","11.6","Medium","","","Channel croped and rubber packing renewed","2021-12-25T23:59:35","","Completed","2021-11-25T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,22439,null,"121_31-Oct-21 4:31:52 PM","2021-10-26T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Self sealing couplings of 3 actuators of ballast system valves found damaged and leaking.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.8","Medium","","","REPLACED THE COUPLING FOR THE ACTUATORS. LEAK RECTIFIED.","2022-11-27T23:59:35","DCHI210100","Completed","2022-09-14T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,22442,null,"121_31-Oct-21 3:40:37 PM","2021-10-26T23:59:35","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Vessel had installed in last shipyard EGCS, maintenance for this equipment was not reflected\n\non the vessel planned maintenance system.","Documentation","Eng. / Strg. Comp.","External Factors","10.12","Very High","","","After EGC is operatonal the Jobs were triggered in PAL PMS.","2021-10-26T23:59:35","","Completed","2021-10-26T23:59:35","No","No","No","External"]
[null,null,null,22443,null,"121_31-Oct-21 3:32:30 PM","2021-10-26T23:59:35","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Vessel was capable of transfer of engine room residues to Stbd. Slop tank using non\n\npermanent connection. This was not reflected under Section 3 of the IOPP form B.","Miscellaneous","Cert. & Docu.","Human Error","2.11","Medium","","","Corect the IOPP Cert form B","2021-10-26T23:59:35","","Completed","2021-10-26T23:59:35","No","No","No","External"]
[null,null,null,20430,null,"121_16-Aug-21 9:34:42 AM","2021-11-03T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ECR one window glass shattered","Miscellaneous","Eng. / Strg. Comp.","Industry Issue","10.29","Medium","","","The ECR glass renewed with new spare and the defect rectified.","2021-11-16T23:59:35","","Completed","2021-11-15T23:59:35","No","No","No","Internal","To be renewed at China."]
[null,null,null,20432,null,"121_16-Aug-21 9:37:29 AM","2021-11-03T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LT Cooler No.1 and No.2 SW Outlet flange leaking","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.29","Medium","","","The sacrificial flanges renewed with new gaskets, leak rectified. ","2021-11-16T23:59:35","","Completed","2021-11-05T23:59:35","No","No","No","Internal"]
[null,null,null,20434,null,"121_16-Aug-21 9:42:40 AM","2021-11-03T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main Engine Lubricator Pipe Connections Leaking","E/R - Main Engine,Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","The main engine lubricators overhauled in dry dock and all the lubricator pipe connections leaks rectified.","2021-11-06T23:59:35","","Completed","2021-07-05T23:59:35","No","No","No","Internal"]
[null,null,null,20444,null,"121_16-Aug-21 9:44:54 AM","2021-11-03T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Stern tube Oil tank to mark for normal oil level to be maintained","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","The stern tube oil tank marked for normal oil level to be maintained.","2021-11-06T23:59:35","","Completed","2021-11-09T23:59:35","No","No","No","Internal"]
[null,null,null,22702,null,"121_17-Nov-21 5:27:58 PM","2021-11-08T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Incinerator secondary burner motor found burnt and reading zero insulation","Miscellaneous","MARPOL Related","Equipment Related","10.32","Very High","","","Incinerator secondary burner motor renewed, Incinerator tried out working satisfactory.","2022-02-07T23:59:35","DCHI210111 :WO INCINERATOR UNIT","Completed","2021-12-16T23:59:35","No","No","No","Internal","Such defect should be intimated by email."]
[null,null,null,22703,null,"121_11/16/2021 11:22:26 AM","2021-11-10T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Midship port and forward draft gauge showing error","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.4","Medium","","","Leakage from  the overboard valve in tank rectified.","2022-03-26T23:59:35","","Completed","2022-01-14T23:59:35","No","No","No","Internal"]
[null,null,null,22704,null,"121_11/16/2021 11:25:38 AM","2021-11-10T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Leak from pumproom davit oil seal","Deck - Machinery","Safety / LSA / FFA","Equipment Related","8.5","Very High","","","Renewed oil seal and tried out, and was found working satisfactory","2022-11-27T23:59:35","DCHI 220015","Completed","2022-09-25T23:59:35","No","No","No","Internal","Noted. Target date revised"]
[null,null,null,22705,null,"121_11/16/2021 11:33:17 AM","2021-11-10T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Drain pipe of galley deck is choked with debris","Miscellaneous","General Appearance","Equipment Related","11.13","Low","","","The Pipe cleared of debris and now clear.","2021-12-25T23:59:35","","Completed","2021-11-14T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,23072,null,"121_06-Dec-21 5:27:27 AM","2021-11-12T23:59:35","Defect,Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","2P inner& outer bunker tank vent pipes rusted at bottom","Deck - Pipe / Fittings","General Appearance","Equipment Related","11.7","High","","","The Vent Pipes derusted and coated with primer","2021-11-12T23:59:35","","Completed","2021-11-12T23:59:35","No","No","No","Internal"]
[null,null,null,23073,null,"121_06-Dec-21 1:50:00 PM","2021-11-12T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Scrubber Cooling Sea Water Pump no.2 mechanical seal leaking , the shaft seized and unable to turn","Cargo Mach.,E/R - Pumps","Cargo / Ballast Systems","Equipment Related","10.32","Very High","","","The Scrubber Pump opened up , the  mechanical seal renewed, the mouth ring and the casing ring eased up, the line bearing renewed and boxed back. The Pump tried out and is found running satisfactory.","2022-02-11T23:59:35","","Completed","2021-11-15T23:59:35","No","No","No","Internal"]
[null,null,null,23074,null,"121_06-Dec-21 2:09:07 PM","2021-11-12T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Galley AC filter frame found corroded","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","New Galley AC Frame fabricated and fitted back ","2022-02-11T23:59:35","","Completed","2021-11-16T23:59:35","No","No","No","Internal"]
[null,null,null,23063,null,"121_30-Nov-21 11:23:05 PM","2021-11-25T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Christmas tree light shade cover clamp securing bolts broken.","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Broken studs to be drilled out and new stud bolts to be fitted.  Awaiting Anchorage to rig Scafolding to access the area for safe opereation.","2022-01-25T23:59:35","","Completed","2022-01-23T23:59:35","No","No","No","Internal","Target date revised. When the job is planned for?"]
[null,null,null,24866,null,"121_05-Mar-22 1:30:34 PM","2021-11-30T23:59:35","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","The dimmer controller of the gyrocompass repeater fitted at the emergency steering position in the steering gear found defective","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.41","Medium","","","Fault rectified during inspection","2021-12-31T23:59:35","","Completed","2021-11-30T23:59:35","No","No","No","External"]
[null,null,null,23286,null,"121_29-Dec-21 8:06:04 PM","2021-12-11T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Water boiler  on bridge needs to be replaced     as buttons are damaged.","Miscellaneous","MLC Related","Equipment Related","11.16","Low","","","Vessel rcvd a new water boiler @ Singapore and replaced the faulty one.","2022-03-26T23:59:35","DCHI 220011","Completed","2022-04-09T23:59:35","No","No","No","Internal"]
[null,null,null,23287,null,"121_29-Dec-21 7:59:49 PM","2021-12-11T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fore Peak Store bulkhead covered with dust all around.  To be cleaned.","Miscellaneous","General Appearance","External Factors","11.1","High","","","Full bulkhead to be cleaned at suitable oppurtunity.","2022-01-11T23:59:35","","Completed","2022-01-11T23:59:35","No","No","No","Internal"]
[null,null,null,23288,null,"121_12/28/2021 5:51:09 PM","2021-12-11T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","VRCS hydraulic pump start /stop setting found irratic ","Deck - Machinery","Eng. / Strg. Comp.","Equipment Related","8.14","Very High","","","Hydraulic pump start/stop  setting to adjusted. Working satisfactory.","2021-12-26T23:59:35","","Completed","2021-12-17T23:59:35","No","No","No","Internal"]
[null,null,null,23289,null,"121_12/28/2021 5:44:20 PM","2021-12-11T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fire pump overboard valve has leakage mark from the gland","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.31","Very High","","","Minor leakages rectified by nipping gland , old marked cleared.","2021-12-18T23:59:35","","Completed","2021-12-13T23:59:35","No","No","No","Internal"]
[null,null,null,23290,null,"121_12/28/2021 5:39:08 PM","2021-12-11T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","QMI Oil mist detector in engine room found switched off","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.22","Low","","","E/R QMI oil mist detector put in use after rectifying faults by cleaning and renewal of sensor heads..","2021-12-18T23:59:35","","Completed","2021-12-18T23:59:35","No","No","No","Internal"]
[null,null,null,23291,null,"121_29-Dec-21 8:12:02 PM","2021-12-11T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Crew Mess room damaged chair to be repaired.","Accommodation","General Appearance","Equipment Related","11.13","Low","","","Torn Canvas cover renewed with new canvas covered.  Chair repaired.","2021-12-21T23:59:35","","Completed","2021-12-21T23:59:35","No","No","No","Internal"]
[null,null,null,23292,null,"121_29-Dec-21 7:42:58 PM","2021-12-11T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Found Port Crane Working platform grating with fibre grating. To be replaced","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","8.5","Very High","","","Renewed with full length galvanised steel gratings","2021-12-21T23:59:35","","Completed","2021-12-21T23:59:35","No","No","No","Internal"]
[null,null,null,23536,null,"121_13-Jan-22 10:05:17 AM","2021-12-22T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","AE #3 governor bevel gear damaged. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Inappropriate Procedure","10.32","Very High","","","AE#3 governor renewed with spare overhauled governor, bevel gear replaced with new spares received, AE#3 tried out on full load working satisfactory.","2022-01-10T23:59:35","","Completed","2022-01-06T23:59:35","No","No","No","Internal"]
[null,null,null,24957,null,"121_4/19/2022 4:19:46 PM","2021-12-30T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","IG blower no:-1 (100%) was tripping on overload, after the trouble shooting found that terminal connection lug was broken.","Elect. Mach. & Equip.","Cargo / Ballast Systems","Equipment Related","10.32","Very High","","","IG blower no:-1 (100%) terminal connection renewed with new connections. Ather the maintenance IG blower tried out. All in good order.","2022-04-25T23:59:35","","Completed","2022-04-07T23:59:35","No","No","No","Internal"]
[null,null,null,23535,null,"121_14-Jan-22 3:46:00 PM","2021-12-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME jacket water controller leaking from the gland o-ring","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Additional o-ring and gasket used to rectify leakage, Presently no leakage observed.","2022-02-10T23:59:35","DCHI220014","Completed","2022-02-09T23:59:35","No","No","No","Internal","Noted, will process requisition."]
[null,null,null,23537,null,"121_16-Jan-22 9:09:36 AM","2021-12-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","AC compressor #1 motor low insulation detected.One winding internal grounding.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Motor replaced with spare reconditioned motor. AC compressor #1 tried out, working satisfactory.","2022-01-10T23:59:35","","Completed","2021-12-30T23:59:35","No","No","No","Internal"]
[null,null,null,23538,null,"121_16-Jan-22 8:59:54 AM","2022-01-08T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Aux boiler #1 safety valve gasket leaking","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Boiler isolated and depressurised, Safety valve gasket renewed.","2022-01-15T23:59:35","","Completed","2022-01-09T23:59:35","No","No","No","Internal"]
[null,null,null,23762,null,"121_29-Jan-22 2:06:50 PM","2022-01-12T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Observation tank salinity sensor faulty.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Salinity sensor holder modified as per new design and sensor installed in place. Presently working in fine.","2022-06-25T23:59:35","DCHI220023","Completed","2022-05-09T23:59:35","No","No","No","Internal","Noted, will process requisition."]
[null,null,null,23764,null,"121_31-Jan-22 7:19:06 AM","2022-01-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Observation tank oil in water sensor faulty","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Oil in water sensor renewed, working satisfactory","2022-01-13T23:59:35","","Completed","2022-01-13T23:59:35","No","No","No","Internal"]
[null,null,null,23761,null,"121_29-Jan-22 2:15:57 PM","2022-01-15T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Inert gas blower 60% discharge valve IP converter faulty","Inert Gas","Eng. / Strg. Comp.","Equipment Related","8.33","Medium","","","IP converter renewed with new spare and tested, all in good order.","2022-05-26T23:59:35","DCHI220020","Completed","2022-05-19T23:59:35","No","No","No","Internal","Noted. Will process requisition."]
[null,null,null,23763,null,"121_27-Jan-22 10:54:19 AM","2022-01-17T23:59:35","Defect","Ship Staff","Ship Staff Insp.","I.G Printer head not marking on Printer Paper","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.25","Very High","","","New Printer Head received, and Replaced and tested. ","2022-03-23T23:59:35","DCHI 220005","Completed","2022-03-10T23:59:35","No","No","No","Internal"]
[null,null,null,24958,null,"121_4/19/2022 4:10:43 PM","2022-01-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Fresh water generator no:-2 eductor is leaking from threaded connections.","E/R - Pipes/ valves & fittings,Miscellaneous","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Renewed with new spare. Fresh water generator tried out. All in good order.","2022-05-25T23:59:35","","Completed","2022-04-13T23:59:35","No","No","No","Internal"]
[null,null,null,24959,null,"121_4/19/2022 4:24:33 PM","2022-01-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Crew elevator door limit switch in 2nd deck is not functional.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","New spare received and changed the door limit switch. Presently working satisfactorily.","2022-04-25T23:59:35","","Completed","2022-04-11T23:59:35","No","No","No","Internal"]
[null,null,null,23875,null,"121_15-Feb-22 4:59:08 PM","2022-01-31T23:59:35","Defect,Guarantee Claim","Ship Staff","Ship Staff Insp.","EGCS SW feed pump #2 mechanical seal leaking.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","EGCS SW feed pump #2 mechanical seal renewed. Pump tried out, working satisfactory.","2022-03-10T23:59:35","","Completed","2022-02-07T23:59:35","No","No","No","Internal"]
[null,null,null,24160,null,"121_28-Feb-22 11:02:06 PM","2022-02-17T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Slght Seepage of Hydraulic oil found near M1, hydraulic winch main line.","Deck - Mooring Machinery,Deck - Pipe / Fittings","Mooring","Equipment Related","11.4","Very High","","","Section of Pipe to be removed, and wasted portion to  renewed.","2022-02-19T23:59:35","","Completed","2022-02-19T23:59:35","No","No","No","Internal"]
[null,null,null,24161,null,"121_27-Feb-22 9:45:17 AM","2022-02-19T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Water Ballast Tank Gas detection system alarming \"Analyse pump - Internal Leakage\" ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.46","Very High","","","Fault tracing carried out, Solenoid V6, V7 and Vacuum Switch VS1 replaced from ship spares. Solenoids V2 - 4, V101 & 2 cleaned. System restored. Analyse pump & Transport pump vibration dampers damaged need to order spares.","2022-03-19T23:59:35","","Completed","2022-02-21T23:59:35","No","No","No","Internal"]
[null,null,null,24159,null,"121_27-Feb-22 10:02:28 AM","2022-02-21T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Incinerator primary burner motor burnt and reading zero insulation","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","",""," Motor  replaced with new motor received.","2022-03-21T23:59:35","DCHI220051","Completed","2022-03-12T23:59:35","No","No","No","Internal"]
[null,null,null,24867,null,"121_19-Mar-22 10:47:31 AM","2022-03-06T23:59:35","Defect","Ship Staff","Ship Staff Insp.","HFO purifier #1 vibration sensor giving false alarm.","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","HFO purifier #1 vibration sensor renewed, Purifier tried out working satisfactory. ","2022-04-06T23:59:35","","Completed","2022-03-06T23:59:35","No","No","No","Internal"]
[null,null,null,24868,null,"121_19-Mar-22 12:38:32 PM","2022-03-12T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Provision compressor #2 magnetic contactor malfunctioning","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Provision compressor #2 magnetic contactor renewed. Compressor tried out working satisfactory.","2022-04-12T23:59:35","","Completed","2022-03-12T23:59:35","No","No","No","Internal"]
[null,null,null,24869,null,"121_03-Apr-22 9:41:41 AM","2022-03-23T23:59:35","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","The stopper of the slewing limit switch on the port side provision crane was noted to have bent from the base.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","8.5","Very High","","","Slewing limit switch operating rod removed and reapired. After the repair work operation of limit switch checked. Now working satisfactorily.","2022-04-03T23:59:35","","Completed","2022-03-24T23:59:35","No","No","No","External"]
[null,null,null,24870,null,"121_03-Apr-22 9:52:27 AM","2022-03-23T23:59:35","Defect","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","IG pressure trasnmitter for the no:-1 stbd cargo tank was not fucntional.","Inert Gas","Cargo / Ballast Systems","Equipment Related","8.13","Medium","","","IG pressure trasnmitter for the no:-1 stbd cargo tank renewed wtih new spare. Now working satisfactorily.","2022-04-05T23:59:35","","Completed","2022-03-28T23:59:35","No","No","No","External"]
[null,null,null,24960,null,"121_18-Apr-22 5:19:39 PM","2022-03-31T23:59:35","Defect","Ship Staff","Ship Staff Insp.","PV breaker drain cock leaking.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.36","Medium","","","The thread of the drain cock was cleaned and put back in place using thread seal. No leak observed.","2022-04-15T23:59:35","","Completed","2022-04-06T23:59:35","No","No","No","Internal"]
[null,null,null,24955,null,"121_18-Apr-22 5:11:18 PM","2022-04-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","The water level in the deck seal is below normal.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.22","Very High","","","Upon investigation it was found that the drain valve was leaking, same was cleaned and lapped. After boxing up the water level in the deck seal was maintaining.","2022-04-25T23:59:35","","Completed","2022-04-15T23:59:35","No","No","No","Internal","Update status after inspection."]
[null,null,null,24956,null,"121_18-Apr-22 5:15:44 PM","2022-04-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Two wheels of valves of steam lines on slop stbd are broken","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.27","Medium","","","Broken wheels replaced with the new ones.","2022-04-25T23:59:35","","Completed","2022-04-17T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,25263,63252,"121_Sun May 01 2022 17:27:01 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","M3, M4 and M5 winches to de-rust and paint","Deck - Mooring Machinery","Mooring","Equipment Related","11.4","Very High","","","De-rusting and painting of M4 and M5 completed.","2022-06-25T23:59:35","","Completed","2022-05-01T23:59:35","No","No","No","Internal","Target date revised."]
[null,null,null,25264,74589,"121_Tue Apr 26 2022 20:40:05 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Accommodation block spot rusts to de-rust and paint.","Accommodation","General Appearance","External Factors","11.8","Low","","","Accommodation block spot rusts de rusted and painted","2022-10-26T23:59:35","","Completed","2022-09-12T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25265,64173,"121_Sun May 01 2022 17:30:33 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","HFO/MGO bunker lines to de-rust and paint.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","11.14","Medium","","","De-rusting and painting of HFO/MGO bunker lines have been completed.","2022-06-07T23:59:35","","Completed","2022-05-26T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25266,64955,"121_Sun May 01 2022 17:33:01 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Minor hydraulic leak observed below 3B hydraulic box.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.8","Medium","","","Leak from the pipe was arrested.","2022-06-25T23:59:35","","Completed","2022-06-13T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25267,35652,"121_Sun May 01 2022 17:39:01 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Stbd windlass minor leak from control lever.","Deck - Mooring Machinery","Mooring","Equipment Related","9.14","Medium","","","Damaged O-ring was replaced with a new one.","2022-06-25T23:59:35","","Completed","2022-06-12T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25268,52337,"121_Sun May 01 2022 17:46:24 GMT+0800","2022-04-08T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Many safety hoops lying in bosun store. All of them to be installed on ladders.","Miscellaneous","Safety / LSA / FFA","Equipment Related","5.47","Medium","","","Safety hoops installed as required in all vertical ladders.","2022-10-26T23:59:35","","Completed","2022-09-10T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25269,95854,"121_Sun May 01 2022 17:48:49 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Minor leak from no:3 hydraulic pump.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","9.14","Medium","","","Leak rectified.","2022-06-25T23:59:35","","Completed","2022-07-07T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25270,38369,"121_Sun May 01 2022 17:51:12 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","1S tank dome to de-rust and paint.","Miscellaneous","Cargo / Ballast Systems","Equipment Related","11.4","Very High","","","De-rusting and painting of 1S tank dome completed.","2022-06-25T23:59:35","","Completed","2022-05-06T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25271,90771,"121_Sun May 01 2022 17:52:26 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mast riser top platform to de-rust and paint.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","11.4","Very High","","","To be de-rusted and painted.","2022-09-25T23:59:35","","Completed","2022-08-26T23:59:35","No","No","No","Internal","Update progress in weekly deck maintenance report."]
[null,null,null,25272,27252,"121_Sun May 01 2022 17:53:37 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hydraulic box No:2 to de-rust and paint.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","11.4","Very High","","","De-rusting and painting of the box completed.","2022-06-07T23:59:35","","Completed","2022-05-07T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25273,56682,"0_Tue Apr 26 2022 20:43:23 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","HFO tanks 3P and 1 P save all to de-rust and paint. Rust spots observed abound tank vent base.","Deck - Pipe / Fittings","General Appearance","Equipment Related","11.4","Very High","","","HFO tanks 3P and 1 P save all de-rusted and painted.","2022-06-25T23:59:35","","Completed","2022-05-07T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25274,38271,"121_Sun May 01 2022 17:23:06 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck seal vent valve showing wrong indication. Showing closed position locally.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Indication corrected.","2022-06-25T23:59:35","","Completed","2022-05-05T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25275,73828,"121_Sun May 01 2022 17:55:28 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Oil leak found below FCV-1211 actuator","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.8","Medium","","","leak rectified and oil topped up.","2022-06-25T23:59:35","","Completed","2022-05-29T23:59:35","No","No","No","Internal","Report job progress in weekly deck maintenance report."]
[null,null,null,25276,49710,"121_Sun May 01 2022 17:56:58 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mechanical seal for steam ballast pump leaking","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","8.8","Medium","","","Mechanical seal renewed and pump tried out, no leakage observed.","2022-07-07T23:59:35","","Completed","2022-05-03T23:59:35","No","No","No","Internal"]
[null,null,null,25277,53676,"121_Wed Apr 27 2022 12:41:07 GMT+0800","2022-04-08T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sewage treatment plant sludge recirculation not seen.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Sewage treatment plant recirculation hose cleaned and boxed back. Presently flow is visible in both the hose. ","2022-05-19T23:59:35","","Completed","2022-04-09T23:59:35","No","No","No","Internal"]
[null,null,null,25278,83117,"121_Wed Apr 27 2022 12:56:13 GMT+0800","2022-04-08T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Installation of panel cooling ACs to complete. EGCS panel vent openings to blank, as AC will be ineffective with openings in the panel.","Elect. Mach. & Equip.,E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.37","Medium","","","EGCS panel vent openings blanked, Boiler panel vent openings blanked, effective ness of AC retained back.","2022-05-20T23:59:35","","Completed","2022-04-20T23:59:35","No","No","No","Internal"]
[null,null,null,25279,44383,"121_Wed Apr 27 2022 15:52:57 GMT+0800","2022-04-08T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency fire pump room drain aft of No:3 DG frozen. To be freed up. Also to be stencilled for easy identification.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Emergency fire pump room drain valve eased up and stenciled near the valve for clear identification.","2022-05-08T23:59:35","","Completed","2022-04-21T23:59:35","No","No","No","Internal"]
[null,null,null,25280,72345,"121_Sun May 01 2022 17:37:16 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port windlass brake indicator misaligned. To be adjusted.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Defect rectified.","2022-05-08T23:59:35","","Completed","2022-04-20T23:59:35","No","No","No","Internal"]
[null,null,null,25281,25851,"121_Sun May 01 2022 17:43:08 GMT+0800","2022-04-08T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pressure gauge defective for no:3 hydraulic pump.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Pressure gauge was replaced.  ","2022-05-08T23:59:35","","Completed","2022-04-17T23:59:35","No","No","No","Internal"]
[null,null,null,25451,45067,"121_Mon May 16 2022 16:26:36 GMT+0800","2022-04-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Oily water separator heater gasket is leaking, need to renew the gasket.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","OWS heater opened up, gasket renewed and steam outlet pipe connection changed due to crank in sealing surface. ","2022-05-26T23:59:35","","Completed","2022-05-09T23:59:35","No","No","No","Internal"]
[null,null,null,25452,80129,"121_Mon May 16 2022 16:29:12 GMT+0800","2022-05-04T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","HFO purifier no:-1 motor coupling hub clutch pad damaged.","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Clutch pad holding stud was broken from its base. same was repaired and clutch holding stud renewed. ","2022-05-26T23:59:35","","Completed","2022-05-08T23:59:35","No","No","No","Internal"]
[null,null,null,25907,96319,"121_Tue May 31 2022 17:15:56 GMT+0800","2022-05-17T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Atmospheric condenser 12 tubes are already plugged and remaining tubes are not in good condition. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","RENEWED CONDENSER WITH NEW SPARE.","2022-07-25T23:59:35","","Completed","2022-06-19T23:59:35","No","No","No","Internal"]
[null,null,null,25909,39596,"121_Tue May 31 2022 17:21:50 GMT+0800","2022-05-21T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Aux boiler feed water pump no:-3 return pipeline to cascade tank have pin holes in various locations.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Renewed the pipeline sections.","2022-07-25T23:59:35","","Completed","2022-06-05T23:59:35","No","No","No","Internal"]
[null,null,null,25908,41151,"121_Sat Jun 04 2022 14:16:12 GMT+0800","2022-05-26T23:59:35","Observation","Ship Staff","Ship Staff Insp.","small leak from the S.W O/L instrument piece of the 100 % LT cooler.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","SARIFICIAL FLANGE AND GASKETS REPLACED WITH NEW SPARE.","2022-06-10T23:59:35","","Completed","2022-05-29T23:59:35","No","No","No","Internal"]
[null,null,null,26032,52492,"121_Fri Jul 01 2022 17:56:39 GMT+0800","2022-06-17T23:59:35","Defect","Ship Staff","Ship Staff Insp.","FWG no:-1 and no:-2 solenoid valve diaphragm for salinity high water return to evaporator having cracks in it, so part amount of generated fresh water bypassing to evaporator.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Replaced with new spare and presently working  satisfactory.","2022-11-27T23:59:35","DCHI220106","Completed","2022-09-20T23:59:35","No","No","No","Internal",""]
[null,null,null,26180,99316,"121_Fri Jul 15 2022 19:13:39 GMT+0800","2022-07-10T23:59:35","Defect","Ship Staff","Engineering Audit","AUX BOILER NO #1 smoke density motor faulty, showing phase resistance imbalance, motor need replacement. Requisition raised DCHI220097.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","When boiler is in operation, then service air line is connected as a precautionary measure.","2022-09-25T23:59:35","DCHI220097","Completed","2022-09-09T23:59:35","No","No","No","Internal","Noted."]
[null,null,null,26472,11408,"121_Wed Aug 03 2022 09:47:09 GMT+0800","2022-07-24T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Ballast over board valve BA039 was observed to be leaking slightly from the shaft seal.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","8.11","Medium","","","Oil drained from the actuator cylinder chamber and  renewed O rings, now working without leak.","2022-11-27T23:59:35","","Completed","2022-09-22T23:59:35","No","No","No","Internal",""]
[null,null,null,26471,58387,"121_Wed Aug 03 2022 10:52:38 GMT+0800","2022-07-25T23:59:35","Observation","Ship Staff","Ship Staff Insp.","CO2 room oxygen  analyzer  showing false reading ie 18% ,cleaned the sensor and tried to re calibrate the span and zero but to no avail.","LSA / FFA","Safety / LSA / FFA","Equipment Related","10.32","Very High","","","SPARE RECEIVED AT FUJAIRAH ANCHORAGE, SAME WAS REPLACED.NOW SHOWING 20.9% O2","2022-09-10T23:59:35","DCHI220133 O2 sensor for CO2 room","Completed","2022-08-20T23:59:35","No","No","No","Internal",""]
[null,null,null,27554,35041,"121_Thu Sep 29 2022 17:21:44 GMT+0800","2022-09-23T23:59:35","Defect","Ship Staff","Engineering Audit","Cascade tank salinity high alarm activated. Physically checked the chlorides and found it to be in normal limits. Suspect faulty salinity sensor.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","Salinometer replaced with new spare.","2022-10-10T23:59:35","DCHI 220166","Completed","2022-10-10T23:59:35","No","No","No","Internal","Noted, will process this requisition."]
[null,null,null,27561,41666,"121_Tue Oct 18 2022 13:10:53 GMT+0800","2022-10-07T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck seal Level Switch wire exposed in open deck. ","Deck - Machinery","Cargo / Ballast Systems","Inappropriate Procedure","10.37","Medium","","","Deck seal Level Switch wire properly secured inside cable gland.","2022-10-12T23:59:35","","Completed","2022-10-12T23:59:35","No","No","No","Internal"]
[null,null,null,27555,75422,"121_Tue Oct 18 2022 12:23:44 GMT+0800","2022-10-08T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LO purifier operating at 85 deg. ","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","10.32","Very High","","","ME LO Purifier heater cleaned and  temperature maintaining at 93 °C","2022-11-08T23:59:35","","Completed","2022-10-11T23:59:35","No","No","No","Internal"]
[null,null,null,27556,99156,"121_Tue Oct 18 2022 12:30:52 GMT+0800","2022-10-08T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sewage, Bilge/Sludge shore connection in port & stbd to be sealed with number seals and seal number to be entered in seal record book.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Inappropriate Procedure","6.15","High","","","Sewage, Bilge/Sludge shore connection in port & stbd  sealed with number seals and seal number entered in seal record book.","2022-10-19T23:59:35","","Completed","2022-10-12T23:59:35","No","No","No","Internal"]
[null,null,null,27557,22677,"121_Tue Oct 18 2022 12:12:36 GMT+0800","2022-10-08T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine room entrance from sunken deck fire door has air leaking through. ","Miscellaneous","Eng. / Strg. Comp.","Human Error","10.44","Medium","","","Packing renewed and air leak through fire door in engine room entrance rectified.","2022-10-23T23:59:35","","Completed","2022-10-14T23:59:35","No","No","No","Internal"]
[null,null,null,27558,73923,"121_Tue Oct 18 2022 13:34:57 GMT+0800","2022-10-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Expired old spare foam bottles kept in foam room. To be discarded.","LSA / FFA","Safety / LSA / FFA","Behaviour Based","5.35","Medium","","","Expired old spare foam bottles discarded","2022-10-20T23:59:35","","Completed","2022-10-14T23:59:35","No","No","No","Internal"]
[null,null,null,27559,13460,"121_Tue Oct 18 2022 13:40:52 GMT+0800","2022-10-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Lifebuoy aft of Stbd lifeboat to renew, as minor crack developed on it.","LSA / FFA","Safety / LSA / FFA","Equipment Related","5.31","High","","","Lifebuoy renewed with spare","2022-10-19T23:59:35","","Completed","2022-10-14T23:59:35","No","No","No","Internal"]
[null,null,null,27560,34013,"121_Tue Oct 18 2022 13:42:34 GMT+0800","2022-10-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port and stbd lifeboats have water ingress through split door. Packing to be renewed.","LSA / FFA","Safety / LSA / FFA","Equipment Related","5.30","High","","","Split door latches repaired and packing adjusted as required.","2022-11-09T23:59:35","","Completed","2022-10-16T23:59:35","No","No","No","Internal"]
[null,null,null,27562,73312,"121_Tue Oct 18 2022 13:36:49 GMT+0800","2022-10-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Spare DCP charges do not have expiry date on them. Requisition to be raised for new spare charges for DCP extinguishers.","LSA / FFA","Safety / LSA / FFA","Industry Issue","5.35","Medium","","","Requisition for spare DCP chargers raised","2022-12-09T23:59:35","DCHI220179","Completed","2022-10-26T23:59:35","No","No","No","Internal"]
[null,null,null,27563,87572,"121_Tue Oct 18 2022 13:31:20 GMT+0800","2022-10-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Spare CO2 cartridges for DCP/Foam extinguishers expired. Requisition to be raised for new cartridges.","LSA / FFA","Safety / LSA / FFA","Equipment Related","5.35","Medium","","","Requistion for new cartridges raised","2022-12-09T23:59:35","DCHI220179","Completed","2022-10-26T23:59:35","No","No","No","Internal"]
[null,null,null,27564,88526,"121_Tue Oct 18 2022 13:44:36 GMT+0800","2022-10-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port manifold drip tray grating bent. Need renewal of small section.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","6.6","Medium","","","Grating renewed with spare onboard","2022-10-19T23:59:35","","Completed","2022-10-14T23:59:35","No","No","No","Internal"]
[null,null,null,27565,22759,"121_Tue Oct 18 2022 13:50:18 GMT+0800","2022-10-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ER store and steward store in accommodation need to be arranged properly.","Miscellaneous","General Appearance","Behaviour Based","11.13","Low","","","Stores arranged and cleaned","2022-11-09T23:59:35","","Completed","2022-10-14T23:59:35","No","No","No","Internal"]
[null,null,null,27566,62069,"121_Wed Oct 19 2022 15:49:47 GMT+0800","2022-10-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","EGCS parameters not entered in ER Logbook. Vessel is supplied with scrubber stamp.","Documentation","Cert. & Docu.","Inappropriate Procedure","10.11","Medium","","","EGCS parameters entries made in ER logbook. All engineers appraised regarding the same.","2022-10-10T23:59:35","","Completed","2022-10-09T23:59:35","No","No","No","Internal"]
[null,null,null,27567,66385,"121_Wed Oct 19 2022 15:53:13 GMT+0800","2022-10-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","EGCS record book not updated. Entries to be made, fuel change over, trips, start/stop etc.","Documentation","Cert. & Docu.","Inappropriate Procedure","10.11","Medium","","","ECGS record book updated and all engine staff appraised regarding the correct procedure of record keeping. ","2022-10-19T23:59:35","","Completed","2022-10-11T23:59:35","No","No","No","Internal"]
[null,null,null,27568,85558,"121_Tue Oct 18 2022 13:47:48 GMT+0800","2022-10-09T23:59:35","Breakdown","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Navtex receiver display not functional.","Navigation - Others","Navigation","Equipment Related","4.7","High","","","Renewed the unit.","2022-12-09T23:59:35","DCHI225056","Completed","2022-10-26T23:59:35","No","No","No","Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":427,"n_cols":3,"rows_kept":427,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]
["1.1","Low",8243]
["1.10","Low",8252]
["1.11","Low",8253]
["1.12","Low",8254]
["1.13","Low",8255]
["1.14","Low",8256]
["1.15","Low",8257]
["1.16","Low",8259]
["1.17","Low",8260]
["1.18","Low",8261]
["1.19","Low",8262]
["1.2","Low",8244]
["1.20","Low",8263]
["1.21","Low",8265]
["1.22","Low",8266]
["1.23","Low",8267]
["1.24","Low",8268]
["1.25","Low",8269]
["1.26","Low",8270]
["1.3","Low",8245]
["1.4","Low",8246]
["1.5","Low",8247]
["1.6","Low",8248]
["1.7","Low",8249]
["1.8","Low",8250]
["1.9","Low",8251]
["1.99","High",11258]
["10.1","Medium",8461]
["10.10","High",8470]
["10.11","Medium",8471]
["10.12","Very High",8472]
["10.13","Very High",8473]
["10.14","Medium",8474]
["10.15","Low",8475]
["10.16","Very High",8476]
["10.17","Very High",8477]
["10.18","High",8478]
["10.19","Very High",8479]
["10.2","Low",8462]
["10.20","High",8480]
["10.21","Medium",8481]
["10.22","Low",8482]
["10.23","Medium",8483]
["10.24","Low",8484]
["10.25","Very High",8485]
["10.26","High",8486]
["10.27","Medium",8487]
["10.28","Low",8488]
["10.29","Medium",8489]
["10.3","Medium",8463]
["10.30","High",8490]
["10.31","Very High",8491]
["10.32","Very High",8492]
["10.33","High",8493]
["10.34","High",8494]
["10.35","Very High",8495]
["10.36","Very High",8496]
["10.37","Medium",8497]
["10.38","Medium",8498]
["10.39","High",8499]
["10.4","High",8464]
["10.40","Medium",8500]
["10.41","Medium",8501]
["10.42","Medium",8502]
["10.43","Medium",8503]
["10.44","Medium",8504]
["10.45","Very High",8505]
["10.46","High",8506]
["10.47","Medium",8507]
["10.48","High",8508]
["10.49","Medium",8509]
["10.5","Low",8465]
["10.50","High",8510]
["10.51","Low",8511]
["10.52","Medium",8512]
["10.53","Medium",8513]
["10.54","High",8514]
["10.55","Low",8515]
["10.6","Very High",8466]
["10.7","Medium",8467]
["10.8","Medium",8468]
["10.9","Medium",8469]
["10.99","High",8516]
["11.1","High",8420]
["11.10","Medium",8429]
["11.11","Very High",8430]
["11.12","Low",8431]
["11.13","Low",8432]
["11.14","Medium",8433]
["11.15","Low",8434]
["11.16","Low",8435]
["11.17","Low",8436]
["11.2","Medium",8421]
["11.3","Medium",8422]
["11.4","Very High",8423]
["11.5","Medium",8424]
["11.6","Medium",8425]
["11.7","High",8426]
["11.8","Low",8427]
["11.9","Low",8428]
["11.99","High",8437]
["12.1","High",8438]
["12.10","High",8448]
["12.11","High",8449]
["12.12","High",8450]
["12.13","High",8451]
["12.14","High",8452]
["12.15","High",8453]
["12.16","High",8454]
["12.17","High",8455]
["12.18","High",8456]
["12.19","High",8457]
["12.2","High",8439]
["12.20","High",8458]
["12.21","High",8459]
["12.3","High",8441]
["12.4","High",8442]
["12.5","High",8443]
["12.6","High",8444]
["12.7","High",8445]
["12.8","High",8446]
["12.9","High",8447]
["12.99","High",8460]
["2.1","Very High",8296]
["2.1.9","Very High",11259]
["2.10","Medium",8304]
["2.11","Medium",8305]
["2.12","Low",8306]
["2.13","Low",8307]
["2.14","Low",8308]
["2.15","Low",8309]
["2.16","Medium",8310]
["2.2","Medium",8297]
["2.3","High",8295]
["2.4","Medium",8298]
["2.5","Medium",8299]
["2.6","Low",8300]
["2.7","High",8301]
["2.8","High",8302]
["2.9","Medium",8303]
["2.99","High",8311]
["3.1","High",8312]
["3.2","Very High",8313]
["3.3","High",8314]
["3.4","Low",8294]
["3.5","Medium",8315]
["3.6","High",8316]
["3.7","Very High",8317]
["3.8","Very High",8318]
["3.99","High",8319]
["4.1","High",8320]
["4.10","High",8329]
["4.11","Medium",8330]
["4.12","Very High",8331]
["4.13","Very High",8332]
["4.14","Very High",8333]
["4.15","Very High",8334]
["4.16","Very High",8335]
["4.17","Very High",8336]
["4.18","Very High",8337]
["4.19","Low",8338]
["4.2","Medium",8321]
["4.20","Very High",8339]
["4.21","High",8340]
["4.22","Low",8341]
["4.23","High",8342]
["4.24","High",8343]
["4.25","Low",8344]
["4.26","Low",8345]
["4.27","High",8346]
["4.3","Medium",8322]
["4.4","High",8323]
["4.5","Very High",8324]
["4.6","Medium",8325]
["4.7","High",8326]
["4.8","Medium",8327]
["4.9","Medium",8328]
["4.99","High",8347]
["5.1","Very High",8517]
["5.10","High",8526]
["5.11","Low",8527]
["5.12","Medium",8528]
["5.13","High",8529]
["5.14","Very High",8530]
["5.15","Medium",8531]
["5.16","Very High",8532]
["5.17","Very High",8533]
["5.18","High",8534]
["5.19","Medium",8535]
["5.2","Very High",8518]
["5.20","Medium",8536]
["5.21","Medium",8537]
["5.22","High",8539]
["5.23","Very High",8540]
["5.24","Very High",8541]
["5.25","Medium",8542]
["5.26","Medium",8543]
["5.27","Medium",8544]
["5.28","Very High",8545]
["5.29","High",8546]
["5.3","Low",8519]
["5.30","High",8547]
["5.31","High",8548]
["5.32","High",8549]
["5.33","High",8550]
["5.34","Low",8551]
["5.35","Medium",8552]
["5.36","Low",8553]
["5.37","Low",8554]
["5.38","High",8555]
["5.39","Very High",8556]
["5.4","High",8520]
["5.40","Very High",8557]
["5.41","Very High",8558]
["5.42","Medium",8559]
["5.43","High",8560]
["5.44","High",8561]
["5.45","Medium",8564]
["5.46","Medium",8565]
["5.47","Medium",8566]
["5.48","Medium",8567]
["5.5","Low",8521]
["5.6","Low",8522]
["5.7","Medium",8523]
["5.8","Medium",8524]
["5.9","Very High",8525]
["5.99","High",8568]
["6.1","Medium",8348]
["6.10","Low",8357]
["6.11","High",8358]
["6.12","Medium",8359]
["6.13","Low",8360]
["6.14","High",8361]
["6.15","High",8362]
["6.16","Very High",8363]
["6.17","Very High",8364]
["6.18","Medium",8365]
["6.19","Low",8366]
["6.2","High",8349]
["6.20","Medium",8367]
["6.21","High",8368]
["6.22","Medium",8369]
["6.3","Low",8350]
["6.4","High",8351]
["6.5","Medium",8352]
["6.6","Medium",8353]
["6.7","High",8354]
["6.8","High",8355]
["6.9","Low",8356]
["6.99","High",8370]
["7.1","High",8371]
["7.10","High",8380]
["7.11","High",8381]
["7.12","High",8382]
["7.13","Medium",8383]
["7.14","Medium",8384]
["7.15","High",8385]
["7.16","High",8386]
["7.17","High",8387]
["7.2","High",8372]
["7.3","Low",8373]
["7.4","Low",8374]
["7.5","Low",8375]
["7.6","Medium",8376]
["7.7","Low",8377]
["7.8","High",8378]
["7.9","High",8379]
["7.99","High",8388]
["8.1","Very High",8569]
["8.10","Very High",8578]
["8.100","Low",11227]
["8.101","Medium",11228]
["8.102","Low",11229]
["8.103","Low",11230]
["8.104","Low",11231]
["8.105","Medium",11232]
["8.106","Medium",11233]
["8.107","Low",11234]
["8.108","High",11235]
["8.109","Very High",11236]
["8.11","Medium",8579]
["8.110","High",11237]
["8.111","Medium",11238]
["8.112","High",11239]
["8.113","Medium",11240]
["8.114","Low",11241]
["8.115","High",11242]
["8.116","Medium",11243]
["8.117","Medium",11244]
["8.118","Medium",11245]
["8.119","High",11246]
["8.12","Medium",8580]
["8.120","High",11247]
["8.121","Medium",11248]
["8.122","High",11249]
["8.123","High",11250]
["8.124","Low",11251]
["8.125","High",11252]
["8.126","Medium",11253]
["8.127","Medium",11254]
["8.13","Medium",8581]
["8.14","Very High",8582]
["8.15","High",8583]
["8.16","Very High",8584]
["8.17","Low",8585]
["8.18","High",8586]
["8.19","High",8587]
["8.199","High",11255]
["8.2","Medium",8570]
["8.20","Medium",8588]
["8.21","High",8589]
["8.22","Very High",8590]
["8.23","Medium",8591]
["8.24","Medium",8592]
["8.25","Very High",8593]
["8.26","High",8594]
["8.27","Medium",8595]
["8.28","Medium",8596]
["8.29","High",8598]
["8.3","Very High",8571]
["8.30","High",8599]
["8.31","High",8600]
["8.32","Low",8601]
["8.33","Medium",8602]
["8.34","High",8603]
["8.35","Medium",8604]
["8.36","Medium",8605]
["8.37","High",8607]
["8.38","Medium",8608]
["8.39","Medium",8609]
["8.4","Medium",8572]
["8.40","High",8610]
["8.41","Medium",8611]
["8.42","Medium",8612]
["8.43","Very High",8613]
["8.44","High",8615]
["8.45","High",8616]
["8.46","Very High",8617]
["8.47","Very High",8618]
["8.48","Medium",8619]
["8.49","High",8620]
["8.5","Very High",8573]
["8.50","Medium",8621]
["8.51","Low",8622]
["8.52","Low",8623]
["8.53","Low",8624]
["8.54","High",8625]
["8.55","Low",11182]
["8.56","Medium",11183]
["8.57","Medium",11184]
["8.58","High",11185]
["8.59","High",11186]
["8.6","Medium",8574]
["8.60","High",11187]
["8.61","Medium",11188]
["8.62","Very High",11189]
["8.63","High",11190]
["8.64","Medium",11191]
["8.65","Low",11192]
["8.66","High",11193]
["8.67","High",11194]
["8.68","High",11195]
["8.69","Medium",11196]
["8.7","High",8575]
["8.70","Medium",11197]
["8.71","Very High",11198]
["8.72","Medium",11199]
["8.73","Medium",11200]
["8.74","High",11201]
["8.75","Medium",11202]
["8.76","Medium",11203]
["8.77","Medium",11204]
["8.78","Medium",11205]
["8.79","Medium",11206]
["8.8","Medium",8576]
["8.80","Medium",11207]
["8.81","Low",11208]
["8.82","Medium",11209]
["8.83","Low",11210]
["8.84","Low",11211]
["8.85","Medium",11212]
["8.86","Medium",11213]
["8.87","Medium",11214]
["8.88","Low",11215]
["8.89","High",11216]
["8.9","High",8577]
["8.90","High",11217]
["8.91","High",11218]
["8.92","Medium",11219]
["8.93","Low",11220]
["8.94","Low",11221]
["8.95","Medium",11222]
["8.96","Medium",11223]
["8.97","Low",11224]
["8.98","High",11225]
["8.99","Medium",11226]
["9.1","Low",8390]
["9.10","Medium",8399]
["9.11","Medium",8400]
["9.12","Medium",8401]
["9.13","Low",8402]
["9.14","Medium",8403]
["9.15","Medium",8404]
["9.16","High",8405]
["9.17","High",8406]
["9.18","Low",8407]
["9.19","Low",8408]
["9.2","Very High",8391]
["9.20","Medium",8409]
["9.21","Medium",8410]
["9.22","Low",8411]
["9.23","Low",8412]
["9.24","Medium",8413]
["9.25","Low",8414]
["9.26","Low",8415]
["9.27","Low",8416]
["9.28","Medium",8417]
["9.29","Low",8418]
["9.3","Very High",8392]
["9.4","High",8393]
["9.5","High",8394]
["9.6","Low",8395]
["9.7","Medium",8396]
["9.8","Medium",8397]
["9.9","Medium",8398]
["9.99","High",8419]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["121","DHT CHINA (11-11-2022)","121_1668155780753.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]