{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":37,"n_cols":28,"rows_kept":37,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","01-Jan-2023",null,null,"Ship Name","PACIFIST (19-12-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,24706,null,"109_5/4/2022 11:58:25","2021-09-27T08:00:00","Defect","Ship Staff","Suptd. Insp.","hatch cover no.1, 2, 3, 4, 5 were in rust","Cargo Mach.","Structural Condn. / WT integrity ","Equipment Related","","","","","The tops of H/Covers 1-2-3-4-5 were chipped and painted. Chipping and painting of Hatch covers No 1; 2 including side panels and hatch coaming was completed. The job can be closed after completion chipping and painting the side panels of hatch covers Nos 3;4;5.","2023-01-31T08:00:00","","In progress",null,"No","No","No","Internal","if the defect completed please insert completion date to close the defect"]
[null,null,null,null,14224,"109_Sat Aug 20 2022 04:56:43 GMT+0800","2022-07-27T08:00:00","Defect","Ship Staff","Ship Staff Insp.","ALL CARGO HOLD ACCESS BOOBY HATCHES, RUBBER PACKING HARDENED.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","ALL CARGO HOLD BOOBY HATCH, REMOVE ALL HARDENED RUBBER PACKING, DERUSY AND UP GRADE RUBBER RETENTION CHANNEL AND RENEW RUBBER PACKING","2023-01-31T08:00:00","","In progress",null,"No","No","No","Internal","Please renew rubber packing , keep update work progress."]
[null,null,null,24709,null,"109_5/4/2022 18:56:59","2022-08-05T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Provision and bunker crane station rusty","Deck - Machinery","General Appearance","Equipment Related","","","","","The provision crane was chipped and painted 100 % at Mundra anchorage.  Chipping and painting  of bunker cranes should be carried out at first opportunity during good weather (no rolling) or at safety anchorage without cargo operations","2023-01-31T08:00:00","","In progress",null,"No","No","No","Internal","to complete , the item fall in overdue"]
[null,null,null,null,59479,"109_Tue Nov 15 2022 21:13:15 GMT+0800","2022-10-13T08:00:00","Defect","Ship Staff","Ship Staff Insp.","MANHOLE COVERS OF TST AND CARGO HOLD CAT WALK AREAS ARE THINNED DOWN AT THE EDGES. ALSO STUD HOLES ARE DAMAGED","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","",""," 7 MANHOLE COVERS HAVE BEEN RENEWED.","2023-01-31T08:00:00","","In progress","2022-11-22T08:00:00","No","No","No","Internal"]
[null,null,null,null,39742,"109_Tue Nov 15 2022 21:15:49 GMT+0800","2022-10-13T08:00:00","Observation","Ship Staff","Ship Staff Insp.","CONTROL BOX OF ALL HATCH COVERS NEED TO BE ATTENDED. MISSING WING NUTS, COVER PLATES TO BE PLACED","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","NEED TO CROP AND RENEW ","2023-01-31T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,68996,"109_Tue Nov 15 2022 20:58:44 GMT+0800","2022-10-27T08:00:00","Observation","Ship Staff","Ship Staff Insp.","SAVE ALL TRAYS OF FO/MGO VENTS HEAVILY CORRODE. NEED TO CROPPED AND RENEWED ","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","REQUIRED TO CROP AND RENEW SAVE ALL TRAY ","2023-01-31T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,86852,"109_Tue Nov 15 2022 21:17:23 GMT+0800","2022-10-30T08:00:00","Observation","Ship Staff","Ship Staff Insp.","PORT AND STBD ANCHOR SPURLING PIPE NEED TO BE COVERED WITH STEEL PLATE. SAME NEED TO FABRICATE","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","NEED TO FABRICATE NEW COVER AND PLACE IN POSITION","2023-01-31T08:00:00","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,65289,"0_Sat Dec 10 2022 04:22:56 GMT+0800","2022-12-05T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All loose heavy spares kept in boiler platform to  identify & secure by welding support / bracket. ","Miscellaneous","Eng. / Strg. Comp.","Inappropriate Procedure","","","","","Work in progress","2022-12-12T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,27882,40867,"0_Sat Dec 10 2022 04:25:17 GMT+0800","2022-12-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All metal scraps & garbage from engine room to off land ashore at next available opportunity. ","Miscellaneous","Eng. / Strg. Comp.","Behaviour Based","","","","","","2023-01-19T23:59:35","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,34085,"0_Sat Dec 10 2022 04:43:54 GMT+0800","2022-12-05T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Accommodation block main deck both sides cosmetic maintenances need to carry out immediately.  ","Accommodation","General Appearance","Behaviour Based","","","","","","2023-01-20T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,27888,79431,"0_Sat Dec 10 2022 04:27:38 GMT+0800","2022-12-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Liner jacket with old liner to remove & check, fit with one new liner with new o-ring for immediate usage.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","","2022-12-20T23:59:35","","Not Started",null,"No","No","No","Internal"]
[null,null,null,27889,77071,"0_Sat Dec 10 2022 04:33:47 GMT+0800","2022-12-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No dipstick with marking observed in Lifeboat fuel tank to measure the fuel quantity.   ","LSA / FFA","Safety / LSA / FFA","Knowledge Based","","","","","","2022-12-20T23:59:35","","Not Started",null,"No","No","No","Internal"]
[null,null,null,27890,68398,"0_Sat Dec 10 2022 04:45:30 GMT+0800","2022-12-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","De-rusting & touch up paint require for all the winches in forecastle deck. ","Deck - Machinery","Mooring","External Factors","","","","","","2023-01-04T23:59:35","","Not Started",null,"No","No","No","Internal"]
[null,null,null,27891,45327,"0_Sat Dec 10 2022 04:55:35 GMT+0800","2022-12-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Lots of  garbage, old scrap materials, paint drums etc lying all over main deck. Very poor housekeeping observed, need to take immediate action on garbage disposal & housekeeping. ","Deck - Machinery","General Appearance","Behaviour Based","","","","","will be landed ashore","2023-01-19T23:59:35","","In progress",null,"No","No","No","Internal"]
[null,null,null,27892,38078,"0_Sat Dec 10 2022 04:31:39 GMT+0800","2022-12-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Rescue boat fuel tank gauge showing incorrect quantity, same to investigate & rectify","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","","2022-12-20T23:59:35","","Not Started",null,"No","No","No","Internal"]
[null,null,null,27893,71120,"0_Sat Dec 10 2022 04:30:02 GMT+0800","2022-12-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine room spare parts Inventory to carry out","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","","2023-01-04T23:59:35","","Not Started",null,"No","No","No","Internal"]
[null,null,null,27894,29320,"0_Sat Dec 10 2022 04:52:01 GMT+0800","2022-12-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Most of the watertight door’s hinges, locking All the weathertight doors greasing points to be greased up.","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","","2023-01-19T23:59:35","","Not Started",null,"No","No","No","Internal"]
[null,null,null,27895,98694,"0_Sat Dec 10 2022 04:49:56 GMT+0800","2022-12-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cosmetic upgradation require on poop, main & accommodation block.","Accommodation","General Appearance","External Factors","","","","","","2023-03-04T23:59:35","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,77810,"109_Wed Dec 28 2022 11:07:18 GMT+0800","2022-12-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","ANCHOR LASHING WIRE FOR PORT AND STBD ANCHOR PARTED IN ROUGH WEATHER. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","REQUISITION RAISED WITH REQUISITION NO PACI220266 ","2023-01-31T08:00:00","REQUISITION NO PACI220266 ","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,83707,"109_Wed Dec 28 2022 17:26:36 GMT+0800","2022-12-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","AE 2 EXHAUST UPTAKE BELLOW FOUND BROKEN,RESULTING EXHAUST LEAKAGE IN ENGINE CASING","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Temporary repair carried out,waiting for spare    ","2023-01-31T08:00:00","PACI220267","Waiting spare",null,"No","No","No","Internal"]

{"sheet":"Completed","index":1,"n_rows":94,"n_cols":28,"rows_kept":94,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","01-Jan-2023",null,null,"Ship Name","PACIFIST (19-12-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,16261,null,"109_20/12/2020 2:45:45 PM","2020-12-08T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Main  SW Pump no.2 sea water discharge line pipe leakage","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Pipe renewed  by the shore workshop  and tried out found satisfactory.","2021-01-17T23:59:35","","Completed","2020-12-11T23:59:35","No","No","No","Internal",""]
[null,null,null,16262,null,"109_20/12/2020 2:52:28 PM","2020-12-08T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Sea water non return v/v to main cooling sea water pump and port cooling sea water pump no holding","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Change the valve at shipyard","2020-12-17T23:59:35","","Completed","2020-12-11T23:59:35","No","No","No","Internal","."]
[null,null,null,16263,null,"109_20/12/2020 2:58:11 PM","2020-12-08T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Sea water  pipe line to auxiliary engine put clip","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Damage pipe renewed by shore workshop and tried out, found satisfactory","2020-12-17T23:59:35","","Completed","2020-12-11T23:59:35","No","No","No","Internal",""]
[null,null,null,16264,null,"109_20/12/2020 3:02:29 PM","2020-12-08T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Sea water pipe to auxiliary boiler condenser suction line leakages","E/R - Pipes/ valves & fittings","General Appearance","Equipment Related","","","","","Leaky pipe renewed.","2020-12-17T23:59:35","","Completed","2020-12-11T23:59:35","No","No","No","Internal",""]
[null,null,null,16265,null,"109_20/12/2020 3:10:00 PM","2020-12-09T23:59:35","Defect","Ship Staff","Ship Staff Insp.","life boat battery charger no working","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Emergency spare  order no: 008-2020 and waiting the spare battery charger","2021-01-11T23:59:35","","Completed","2021-01-02T23:59:35","No","No","No","Internal","New battery charger installed and tried out, found satisfactory."]
[null,null,null,16266,null,"109_20/12/2020 3:14:34 PM","2020-12-09T23:59:35","Defect","Ship Staff","Ship Staff Insp.","F.W.G start and stop switch no working","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Start & stop switch  renewed from Engine Room Exhaust fan, tried out-found satisfactory","2020-12-28T23:59:35","","Completed","2020-12-20T23:59:35","No","No","No","Internal",""]
[null,null,null,16260,null,"109_21/12/2020 7:22:22 PM","2020-12-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NO.6 H/C CANT'T CLOSED AT LAST END DUE TO THE H/C CHAINS NOT  LENGTH NOT EQUAL AT F'&A' PARTY .","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related","","","","","ADJUST THE CHAIN LENGTH BY DECK HANDS","2020-12-28T23:59:35","","Completed","2021-01-28T23:59:35","No","No","No","Internal","Chain length adjusted  and tried out found satisfactory by shipstaffs."]
[null,null,null,16268,null,"109_21/12/2020 6:59:11 PM","2020-12-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","No.1-9 H/C HATCH COVER QUICKLY ACTING CLEATS  ALL SERIOUS RUST AND CAUSED ALL ADJUST SCREW NUTS  CAN'T MOVE FREELY.","Miscellaneous","Cargo / Ballast Systems","External Factors","","","","","ALL DISASSEMBLY , DERUST/PAINT/GREASE/RE-FIT .","2021-03-28T23:59:35","PACI210006","Completed","2021-05-05T23:59:35","No","No","No","Internal","Pls   update the progress of  de-rusting  and upgrading of HC cleats."]
[null,null,null,16269,null,"109_21/12/2020 7:09:19 PM","2020-12-13T23:59:35","Breakdown","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","ALL WATER LEVEL DETECT SENSORS OF BW TKS WERE OUT OF WORKING AND OR MISTAKE READ .","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","carried out inspection by shore service , waitting spare for renewal the malfunction sensors .","2021-04-27T23:59:35","","Completed","2021-06-25T23:59:35","Yes","No","No","Internal","please update status"]
[null,null,null,17623,null,"109_31/1/2021 7:29:58 PM","2020-12-31T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ALL HATCH COVER CHAINS WERE RUST","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","no. 1,6 hatch cover chains were renewal by shipyard in dd . ","2021-04-24T23:59:35","PACI210019","Completed","2021-05-17T23:59:35","Yes","No","No","Internal","please update status vessel already in dock"]
[null,null,null,17624,null,"109_31/1/2021 5:17:38 PM","2020-12-31T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NO.1-9 HATCH  H/C RUBBER PACKING CRACKS AND OLD","Cargo Mach.","Structural Condn. / WT integrity ","Equipment Related","","","","","Hold no.1-9 all hatch cover rubber packing are renewal by ship yard .","2021-04-27T23:59:35","PACI210004","Completed","2021-05-17T23:59:35","Yes","No","No","Internal","please update status vessel already in dock"]
[null,null,null,17625,null,"109_31/1/2021 6:56:16 PM","2020-12-31T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ALL WINDLASS & MOORING WINCHES BRAKE LINING WERE WEAR OUT OF LIMIT.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","all mooring winches & anchor windlass brake lining checked , and renewal both anchor windlass brake lining , both stern line winches' brake lining .","2021-04-24T23:59:35","PACI215059","Completed","2021-05-17T23:59:35","Yes","No","No","Internal","please update status vessel already in dock"]
[null,null,null,17627,null,"109_31/1/2021 7:11:04 PM","2020-12-31T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ALL THE MUSHROOM VENT HOUSING AND AIR INTAKE MESH WERE RUST STAIN .","Miscellaneous","General Appearance","Equipment Related","","","","","all mushroom vent housing carried out repair and mentenace and mesh  renewal  by shipyard in DD .","2021-02-25T23:59:35","","Completed","2021-05-28T23:59:35","No","No","No","Internal","please update status vessel already in dock"]
[null,null,null,17628,null,"109_31/1/2021 7:17:55 PM","2020-12-31T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ALL WEATHER TIGHT DOOR GREASE POINT NEED GREASE .","Accommodation,Miscellaneous","General Appearance","Behaviour Based,Equipment Related","","","","","CARRY OUT GREASE AND MATENANCE FOR ALL WEATHER TIGHT DOOR GREASE POINT .","2021-02-25T23:59:35","","Completed","2021-04-27T23:59:35","No","No","No","Internal","to expedite the job after docking"]
[null,null,null,17629,null,"109_31/1/2021 7:22:20 PM","2020-12-31T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ALL DECK AIR PIPE , ELECTRIC CONDUIT PIPE U-CLAMS CORRODED AND NEED RENEWAL .","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","ALL DECK PIPES' U-CLAMS ARE CARRIED OUT  INSPECTION AND RENEWAL BY SHIPYARD IN DD.","2021-04-24T23:59:35","","Completed","2021-05-28T23:59:35","Yes","No","No","Internal","please update status vessel already in dock"]
[null,null,null,17630,null,"109_31/1/2021 7:26:52 PM","2020-12-31T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ALL CARGO HOLD BULKHEAD WERE IN RUST CONDITION .","Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related","","","","","ALL CARGO HOLD CARRIED OUT SAND BLLAST AND MADE PAINT BY SHIP YARD IN DD.","2021-04-24T23:59:35","","Completed","2021-05-27T23:59:35","Yes","No","No","Internal","please update status vessel already in dock"]
[null,null,null,17631,null,"109_31/1/2021 7:34:35 PM","2020-12-31T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","RESCUE BOAT DAVIT WERE RUST","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","DE-RUST & MADE PAINT","2021-02-25T23:59:35","","Completed","2021-04-27T23:59:35","No","No","No","Internal","to expedite the job within due date"]
[null,null,null,17632,null,"109_31/1/2021 7:37:56 PM","2020-12-31T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LIFE BOAT DAVIT WERE RUST","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","CARRIED OUT DE-RUST AND MADE PAINT BY SHIP YARD IN DD .","2021-04-24T23:59:35","","Completed","2021-05-28T23:59:35","Yes","No","No","Internal","please update status"]
[null,null,null,17634,null,"109_31/1/2021 7:43:36 PM","2020-12-31T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","BOTH  PILOT GANGWAY LADDER LACK OF MAINTENANCE","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Pilot assisstant ladders derusted and painted, insert stencils, greasing wires .","2021-10-13T23:59:35","","Completed","2021-10-13T23:59:35","No","No","No","Internal","please update status vessel already in dock"]
[null,null,null,17636,null,"109_31/1/2021 7:50:13 PM","2020-12-31T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","F' BSN. STORE WERE DITY AND NEED TIDE UP .","Miscellaneous","General Appearance","Equipment Related","","","","","Cleaned, partly painted","2021-06-27T23:59:35","","Completed","2021-10-12T23:59:35","No","No","No","Internal","please update status"]
[null,null,null,21950,null,"109_15/10/2021 3:22:55 PM","2021-08-06T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Fish room evaporator coil thermostatic expansion valve found malfunctioning","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Fish room thermostatic expansion valve adjustment done, found working satisfactorily","2021-08-17T23:59:35","","Completed","2021-08-06T23:59:35","No","No","No","Internal"]
[null,null,null,21951,null,"109_15/10/2021 10:12:46 PM","2021-08-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Engine room Bilge pump unable to take suction","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Bilge pump overhauled with new spares and found working","2021-08-17T23:59:35","","Completed","2021-08-14T23:59:35","No","No","No","Internal"]
[null,null,null,26993,null,"109_Mon Sep 26 2022 03:05:37 GMT+0000","2021-10-31T23:59:35","Observation","PSC Insp.","PSC Inspection","the IMO symbol for the fire control plan not posted in the bridge","Documentation","Safety / LSA / FFA","","","","Fire safety","","","2021-10-31T23:59:35","","Completed","2021-10-31T23:59:35","No","No","No","External"]
[null,null,null,26994,null,"109_Mon Sep 26 2022 03:07:17 GMT+0000","2021-10-31T23:59:35","Observation","PSC Insp.","PSC Inspection","Bell book without signature of duty office after vessel berthed on 02.11.2021","Documentation","Cert. & Docu.","","","","Certificates & Documentation","","","2021-10-31T23:59:35","","Completed","2021-10-31T23:59:35","No","No","No","External"]
[null,null,null,26995,null,"109_Mon Sep 26 2022 03:10:49 GMT+0000","2021-11-22T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","Supply air low pressure alarm active on cargo hold water ingress alarm panel on bridge","Cargo Mach.","Cargo / Ballast Systems","","","","Emergency Systems","","","2021-11-22T23:59:35","","Completed","2021-11-22T23:59:35","No","No","No","External"]
[null,null,null,26996,null,"109_Mon Sep 26 2022 03:13:26 GMT+0000","2021-11-22T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","Main engine oil mist detector system failure alarm active in engine control room","E/R - Main Engine","Eng. / Strg. Comp.","","","","Propulsion and auxiliary machinery","","","2021-12-17T23:59:35","","Completed","2022-01-02T23:59:35","No","No","No","External"]
[null,null,null,26997,null,"109_Mon Sep 26 2022 03:15:11 GMT+0000","2021-11-22T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","All remote draft gauges defective","Cargo Mach.","Cargo / Ballast Systems","","","","Cargo operations including equipment","","","2021-12-06T23:59:35","","Completed","2022-01-02T23:59:35","No","No","No","External"]
[null,null,null,26998,null,"109_Mon Sep 26 2022 03:17:12 GMT+0000","2021-11-22T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","GDMSS Equipment batteries defective","Navigation - GMDSS & Communication","Navigation","","","","Radio communication","","","2021-11-27T23:59:35","","Completed","2021-11-22T23:59:35","No","No","No","External"]
[null,null,null,26999,null,"109_Mon Sep 26 2022 03:19:31 GMT+0000","2021-11-22T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","unable to demonstrate the operation of freefall lifeboat emergency steering","","Safety / LSA / FFA","","","","Life saving appliances","","","2021-11-27T23:59:35","","Completed","2021-11-23T23:59:35","No","No","No","External"]
[null,null,null,27000,null,"109_Mon Sep 26 2022 03:21:54 GMT+0000","2021-11-22T23:59:35","Observation","PSC Insp.","PSC Inspection","Ship deck cranes (PS&STBS) hook safety latched defective","Deck - Pipe / Fittings","Safety / LSA / FFA","","","","Other","","","2021-11-27T23:59:35","","Completed","2021-11-27T23:59:35","No","No","No","External"]
[null,null,null,27001,null,"109_Mon Sep 26 2022 03:24:02 GMT+0000","2021-11-22T23:59:35","Observation","PSC Insp.","PSC Inspection","The safety management system, as implemented on board, failsto ensure effective implementation of ISM Code element 8 and 10 as evidenced by deficiencies no 1 to 6","Documentation","ISM Related","","","","","","","2021-11-27T23:59:35","","Completed","2021-11-23T23:59:35","No","No","No","External"]
[null,null,null,17637,null,"109_28/1/2021 12:26:15 PM","2021-12-31T23:59:35","Defect","Ship Staff","Ship Staff Insp.","engine  room set tank level gauge no working","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","order the spare make sure the level gauge working","2022-04-22T23:59:35","PACI210023","Completed","2022-03-26T23:59:35","Yes","No","No","Internal"]
[null,null,null,17635,null,"109_31/1/2021 7:46:12 PM","2022-02-05T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","F' MAST WERE RUST","Miscellaneous","General Appearance","Equipment Related","","","","","The FWD Mast was chipped, primered and painted 100 %","2022-04-22T23:59:35","","Completed","2022-04-25T23:59:35","No","No","No","Internal","please update status, it should complete within due date"]
[null,null,null,24710,null,"109_5/4/2022 18:14:46","2022-02-17T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME & AE system LO filling line port side bunker manifold leakage","E/R - Pipes/ valves & fittings","General Appearance","Equipment Related","","","","","hot work carried out , pipe section renewed.","2022-04-27T23:59:35","","Completed","2022-04-06T23:59:35","No","No","No","Internal"]
[null,null,null,24711,null,"109_5/4/2022 18:53:18","2022-02-22T23:59:35","Defect","Ship Staff","Ship Staff Insp.","U-bolt and support for deck pipe rusty condition","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","to carry out maintenance","2022-05-09T23:59:35","","Completed","2022-04-06T23:59:35","No","No","No","Internal"]
[null,null,null,25924,51169,"109_Wed Jun 29 2022 17:05:13 GMT+0800","2022-04-23T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Control Air dryer membrane in bad condition, Need to renew the membrane.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Dryer membrane replaced with new spare, Dryer put in use. Working satisfactorily.","2022-07-27T23:59:35","PACI220110","Completed","2022-08-29T23:59:35","No","No","No","Internal","spare will supply, lead time end of July 2022"]
[null,null,null,25667,68606,"109_Wed Jun 15 2022 16:51:08 GMT+0800","2022-05-17T23:59:35","Defect","Ship Staff","Ship Staff Insp.","windlass port side emg. stop push button broken","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Emergency stop button renewed and system tried out.","2022-06-12T23:59:35","","Completed","2022-06-08T23:59:35","No","No","No","Internal"]
[null,null,null,25665,44529,"109_Wed Jun 15 2022 16:59:50 GMT+0800","2022-05-18T23:59:35","Defect,Guarantee Claim","Ship Staff","Ship Staff Insp.","BWTS ECU # 3 PRU # 1 & 2 taking zero current, EM defective.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Vessel has renewed the Defective EM","2022-07-12T23:59:35","Guarantee claim","Completed","2022-07-29T23:59:35","No","No","No","Internal","EM will supply next port. once receive please replace with Maker procedure and update"]
[null,null,null,25668,40388,"109_Wed Jun 15 2022 16:54:32 GMT+0800","2022-05-18T23:59:35","Defect","Ship Staff","Ship Staff Insp.","windlass port side bearing bush # 1 to renew ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Windlass Port side Top cover bearing bush renewed. Windlass tried out without load, No abnormal noise and vibration observed.","2022-06-12T23:59:35","","Completed","2022-06-10T23:59:35","No","No","No","Internal"]
[null,null,null,25666,95564,"109_Wed Jun 15 2022 17:02:54 GMT+0800","2022-05-23T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Drinking water sterilizer not operational as UV lamp and filter need replacement","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","UV lamp and filter replaced with new spare and working satisfactorily.","2022-07-12T23:59:35","PACI220108","Completed","2022-08-29T23:59:35","No","No","No","Internal","spare will supply next convenient port"]
[null,null,null,25926,33376,"109_Wed Jun 29 2022 17:08:44 GMT+0800","2022-06-15T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Water cooler fountain not operational.","Accommodation","MLC Related","Equipment Related","","","","","Vessel has replaced the spare parts for Water cooler fountain and now working satisfactorily.","2022-07-27T23:59:35","PACI220146","Completed","2022-09-18T23:59:35","No","No","No","Internal","spare will supply in next convenient port"]
[null,null,null,25925,18975,"109_Sat Jun 25 2022 12:05:57 GMT+0800","2022-06-19T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Temporary repair on fire line with sleeves of two halves.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","Sleeve  replaced with renewed pipe section and new sleeve.","2022-07-27T23:59:35","PACI220148","Completed","2022-07-11T23:59:35","No","No","No","Internal","please keep office update the status"]
[null,null,null,26157,16348,"109_Fri Jul 15 2022 21:35:15 GMT+0800","2022-07-12T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Replacement of the rubber gaskets of DBT manholes covers with signs of leakages in lower stools between cargo holds","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","In loading condition open the manhole covers of DBT tanks with traces of leakages in lower stools between cargo holds, remove the rust on the sealing face of the covers, chipping and grinding if required, renew the rubber gaskets. Due to high temperature this job could not be done with cargo coal loaded in Indonesia with temperature abt 45 deg.","2022-09-12T23:59:35","","Completed","2022-08-01T23:59:35","No","No","No","Internal","to find suitable time and complete ASAP"]
[null,null,null,27111,24367,"109_Sat Aug 20 2022 04:15:07 GMT+0800","2022-07-22T23:59:35","Defect","Ship Staff","Ship Staff Insp.","AFT STN SPRING ROPE PORT SIDE FAIRLEAD ROLLER AND FWD SPRING ROPE STBD SIDE ONE FAIRLEAD ROLLER JAMMED. NOT MIVING. NEED TO LUBRICATE AND FREE.","Deck - Pipe / Fittings","Mooring","Equipment Related","","","","","OPENED UP AND COMPLETE OVERHAULED. LUBRICATED AND FREED.","2022-08-12T23:59:35","","Completed","2022-08-12T23:59:35","No","No","No","Internal"]
[null,null,null,27117,53933,"109_Sat Aug 20 2022 04:22:32 GMT+0800","2022-07-23T23:59:35","Defect","Ship Staff","Ship Staff Insp.","HATCH COVER CLEATS OF ALL HATCH COVERS FOUND FROZEN. JAMMED. NEED TO FREE AND LUBRICATE THREADING.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","ALL HATCH COVER CLEATS TO BE REMOVED AND COMPLETE OVERHAULING TO BE DONE.","2022-08-28T23:59:35","","Completed","2022-08-12T23:59:35","No","No","No","Internal"]
[null,null,null,27112,25427,"109_Sat Aug 20 2022 04:44:00 GMT+0800","2022-07-25T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ACCOMMODATION INTERNAL DECKS INCL ALL ALLEYWAYS, CREW/OFFICER LAUNDRY/MESS ROOM/PANTRY,SMOKE ROOM. EXIT PASSAGES, LADDER AND PASSAGES ETC NEED TO BE COMPLETELY UP GRADED. ","Accommodation","General Appearance","Knowledge Based","","","","","SPOT DERUSTING TO BE CARRIED OUT AND NEED TO COMPLETE PAINT AND UP GRADE.","2022-08-20T23:59:35","","Completed","2022-08-06T23:59:35","No","No","No","Internal"]
[null,null,null,27118,29954,"109_Sat Aug 20 2022 04:49:54 GMT+0800","2022-07-26T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ALL LOWER STOOL SPACE ENTRANCE BOOBY HATCHES RUBBER PACKING FOUND HARDENED AND NO WATER TIGHT INTEGRITY. ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","ALL STOOL SPACE BOOBY HATCH NEED TO BE OPENED, REMOVE THE RUBBER PACKING, DERUST AND UPGRADE THE RUBER RETENTION CHANNEL, AND RENEW RUBBER PACKING. ALSO IF ANY WASTAGE OR HOLES TO ANY RUBBER RETENTION CHANNEL, SAME NEED TO BE CROPPED AND RENEWED.","2022-09-27T23:59:35","","Completed","2022-09-27T23:59:35","No","No","No","Internal"]
[null,null,null,27113,27491,"0_Sat Aug 20 2022 05:02:04 GMT+0800","2022-07-28T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ALL LIFE BUOYS ON SHIP FOUND SHIPS NAME AND PORT OF REGISTRY NOT VISIBLE DUE STENCILLING MISSING AND RUBBED OFF.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","ALL LIFE BUOYS TO BE RENEWED STENCILS","2022-08-17T23:59:35","","Completed","2022-08-07T23:59:35","No","No","No","Internal"]
[null,null,null,27106,51380,"0_Sat Aug 20 2022 07:20:25 GMT+0800","2022-07-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NO 2 HATCH COVER PORT/STBD SIDE FWD PART TO NO 3 HATCH COVER PORT/STBD SIDE AFTER PART MAIN DECK AREA FOUND HEAVILY CORRODED.","Hull & Tanks","General Appearance","Equipment Related","","","","","COMPLETE DERUSTING AND UP GRADATION REQUIRED. TO BE DERUSTED, APPLY 2 COATS OF PRIMER AND THEN FINISH COAT","2022-11-28T23:59:35","","Completed","2022-11-27T23:59:35","No","No","No","Internal","Please get it done asap."]
[null,null,null,27115,99449,"109_Sat Aug 20 2022 07:25:38 GMT+0800","2022-08-01T23:59:35","Defect","Ship Staff","Ship Staff Insp.","MUCKING WINCH SUPPORT BRACKET AT HATCH COAMING AREAS OF NO 2,5,6,7,8 AND 9 FOUND THINNED DOWN AND WASTED","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","NEED TO CROP AND RENEW PRIOR HOLD CLEANING STARTS AS SAME WILL BE USED FOR ATTACHED MUCKING WINCH SUPPRT.","2022-08-17T23:59:35","","Completed","2022-08-16T23:59:35","No","No","No","Internal"]
[null,null,null,27108,55570,"109_Sat Aug 20 2022 04:35:10 GMT+0800","2022-08-03T23:59:35","Defect","Ship Staff","Ship Staff Insp.","WHEN CARRYING OUT MAINTENANCE ON AIR VENTS OF BALLAST TANKS,FPT CENTRE VENT WHEN OPENED UP AND CARRYING OUT DERUSTING FOUND HOLED AND WASTED AT SEVERAL INTERNAL PLATINGS. ALSO NO 1 WBT PORT FWD VENT STEEL WASTED.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","RENEWED ALL BALLAST VENTS RECEIVED","2022-11-28T23:59:35","Requisition no PACI220231 for Ballast Tank Air Vent Heads","Completed","2022-11-22T23:59:35","No","No","No","Internal","Noted, please get it done asap."]
[null,null,null,27114,33119,"0_Sat Aug 20 2022 05:06:22 GMT+0800","2022-08-09T23:59:35","Defect","Ship Staff","Ship Staff Insp.","WHEN CARRYING OUT FIRE HOSE PRESSURE TEST FOR ALL DECK /ENGINE ROOM/ACCOMMODATION FIRE HOSES FOUND SEVERAL HOSES LEAKING.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","ALL FIRE HOISES TO BE RECTIFIED OF LEAKAGES AND RENEWED AS REQUIRED. ALL FIRE HOSES TO BE ARRANGED AS PER REQUIREMENT OF LENGTHS IN RESPECTIVE POSITIONS.","2022-08-17T23:59:35","","Completed","2022-08-15T23:59:35","No","No","No","Internal"]
[null,null,null,25927,92139,"109_Wed Jun 29 2022 17:10:44 GMT+0800","2022-08-12T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Waste oil tank Float level gauge not working.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Vessel has replaced the  new Float level gauge and working satisfactorily.","2022-10-27T23:59:35","PACI220145","Completed","2022-11-10T23:59:35","No","No","No","Internal","spare will supply in next convenient port"]
[null,null,null,27110,89542,"0_Sat Aug 20 2022 07:14:15 GMT+0800","2022-08-12T23:59:35","Defect","Ship Staff","Ship Staff Insp.","PORT GANGWAY TURNTABLE PLATFORM NUT FOUND FROZEN. NEED TO OPEN UP AND FREE. GREASING POINT FOUND CHOKED.","Deck - Pipe / Fittings","Safety / LSA / FFA","Equipment Related","","","","","PLANNED TO LASH THE PLATFORM WHEN AT SUITABLE ANCHORAGE AND OPEN UP NUT, FREE AND CLEAR CHOKE OF GREASING POINT AND COMPLETE GREASING TO BE DONE.","2022-10-28T23:59:35","","Completed","2022-10-16T23:59:35","No","No","No","Internal","noted, please perform safely, keep update work progress."]
[null,null,null,27116,30214,"109_Mon Aug 22 2022 19:27:55 GMT+0800","2022-08-19T23:59:35","Defect","Ship Staff","Ship Staff Insp.","FWT FILLING VALVES FOR PORT AND STBD AND SHORE CONNECTION FOUND JAMMED AND FROZEN. ","Deck - Pipe / Fittings","ISM Related","Equipment Related","","","","","NEED  TO COMPLETE OVERHAUL AND FREE","2022-08-28T23:59:35","","Completed","2022-08-28T23:59:35","No","No","No","Internal"]
[null,null,null,25664,99995,"109_Wed Jun 15 2022 16:47:45 GMT+0800","2022-09-01T23:59:35","Defect","Ship Staff","Ship Staff Insp.","WBT # 6 valve actuator not operational","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","WBT #6 valve actuator has been replaced and working satisfactorily.","2022-11-30T23:59:35","PACI220102","Completed","2022-10-14T23:59:35","No","No","No","Internal","to confirm offer one is suitable for vessel and place order"]
[null,null,null,27107,45636,"109_Mon Sep 19 2022 18:58:32 GMT+0800","2022-09-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Aft, Midship (P & S) and Fwd draft guage not operational.","Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related","","","","","All four draft gauges sensors renewed. Presently all are in working condition.","2022-10-28T23:59:35","","Completed","2022-10-09T23:59:35","No","No","No","Internal","Sensor will be connected to vessel at discharge port HUANGHUA, China."]
[null,null,null,27616,86509,"109_Mon Oct 03 2022 04:31:42 GMT+0800","2022-09-28T23:59:35","Defect","Ship Staff","Ship Staff Insp.","When all Ballast TST Tank manhole covers were opened, found covers thinned down and heavily corroded. Also frames on which manhole covers sit found badly corroded.","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","Complete derusting to be carried out of Manhole covers and frames and those wasted and thinned down need to be replaced and frames to be repaired as required","2022-11-28T23:59:35","Requisition no PACI220234 for manhole covers","Completed","2022-11-17T23:59:35","No","No","No","Internal"]
[null,null,null,27609,73163,"109_Tue Nov 15 2022 21:02:23 GMT+0800","2022-10-27T23:59:35","Observation","Ship Staff","Ship Staff Insp.","SUPPORT BRACKET FOR EPIRB NEED TO BE FABRICATED AND FITTED.","LSA / FFA","ISM Related","Equipment Related","","","","","cropped and renewed bracket","2022-12-13T23:59:35","","Completed","2022-11-30T23:59:35","No","No","No","Internal"]
[null,null,null,27617,10250,"109_Wed Nov 02 2022 18:25:51 GMT+0800","2022-10-27T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Wheelhouse port side door not closing properly. ","Navigation - Others","Mooring","Equipment Related","","","","","Repaired","2022-11-28T23:59:35","","Completed","2022-11-28T23:59:35","No","No","No","Internal"]
[null,null,null,27620,56834,"109_Wed Nov 02 2022 18:37:07 GMT+0800","2022-10-27T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Rescue boat limit switch hanging chain need to be reset as same getting cut off earlier before the boat is being lifted. clear from cradle","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Need to adjust chain length and then set limit.","2022-10-31T23:59:35","","Completed","2022-10-30T23:59:35","No","No","No","Internal"]
[null,null,null,27618,70933,"109_Tue Nov 15 2022 20:52:53 GMT+0800","2022-10-28T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ALL MOORING WINCH BRAKE BANDS NEED TO BE ATTENDED. BRAKE LININGS THINNED DOWN AND NEED REPLACEMENT. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","renewed 3 nos. remaining in progress","2022-12-13T23:59:35","","Completed","2022-11-07T23:59:35","No","No","No","Internal"]
[null,null,null,27613,42281,"109_Tue Nov 15 2022 20:48:28 GMT+0800","2022-11-08T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Forward Stn Fairlead rollers top plate wasted","Deck - Pipe / Fittings","Mooring","Equipment Related","","","","","Cropped and renewed","2022-12-13T23:59:35","","Completed","2022-11-27T23:59:35","No","No","No","Internal"]
[null,null,null,27896,41725,"0_Sat Dec 10 2022 04:40:44 GMT+0800","2022-12-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","4P TST new manhole cover lying on deck, same to fitted back immediately.","Deck - Pipe / Fittings","General Appearance","Behaviour Based","","","","","Renewed TST manhole cover","2022-12-10T23:59:35","","Completed","2022-12-09T23:59:35","No","No","No","Internal"]
[null,null,null,null,85812,"0_Sat Dec 10 2022 04:42:01 GMT+0800","2022-12-05T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All the Hatch cover opening / closing chain to adjust properly.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","Adjusted and tried out operation. All ok","2022-12-20T08:00:00","","Completed","2022-12-20T08:00:00","No","No","No","Internal"]
[null,null,null,null,65383,"109_Tue Nov 15 2022 20:55:39 GMT+0800","2022-10-29T08:00:00","Defect","Ship Staff","Ship Staff Insp.","MAIN DECK MANY AREAS FIRE LINE AND AIR LINE CORROED BADLY. NEED TO BE CROPPED AND RENEWED.","Deck - Pipe / Fittings","Safety / LSA / FFA","Equipment Related","","","","","RENEWED AS REQUIRED","2022-12-30T08:00:00","","Completed","2022-11-29T08:00:00","No","No","No","Internal"]
[null,null,null,null,64501,"109_Sat Dec 10 2022 04:18:16 GMT+0800","2022-12-05T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","L.O. drums in steering gear room kept on floor, all lube oil drums to keeo on wooden pallet. ","Miscellaneous","Eng. / Strg. Comp.","Knowledge Based","","","","","All L.O.drums re arranged on wooden pallets.","2022-12-12T08:00:00","","Completed","2022-12-14T08:00:00","No","No","No","Internal"]
[null,null,null,null,22019,"109_Tue Oct 18 2022 11:41:39 GMT+0800","2022-10-10T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Mooring Windlass (P) motor brake lining and Brake flange worn out because of heavy load of anchor chain. Motor is not holding in neutral position.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Repaired. Tried out after fitting new brakes. In Order.","2022-12-30T08:00:00","PACI220226","Completed","2022-12-26T08:00:00","No","No","No","Internal"]
[null,null,null,null,86924,"109_Wed Nov 02 2022 18:32:26 GMT+0800","2022-10-05T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Fire mens outfit on board 4 nos have helmet not covering the full face against fire for protection from heat and fire.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Received and placed in position.","2022-12-30T08:00:00","","Completed","2022-12-26T08:00:00","No","No","No","Internal"]
[null,null,null,24708,null,"109_5/4/2022 18:08:50","2022-08-04T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Deck Air Pipe rusty condition","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Renewal done as required.","2022-12-30T08:00:00","","Completed","2022-12-16T08:00:00","No","No","No","Internal","to update status. if completed please fill the complete date to close the defect"]
[null,null,null,null,87369,"0_Sat Dec 10 2022 04:20:29 GMT+0800","2022-12-05T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Refer cooling pump gland found leaking, same to rectify immediately.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Gland packing renewed","2022-12-12T08:00:00","","Completed",null,"No","No","No","Internal"]
[null,null,null,24707,null,"109_5/4/2022 18:20:21","2022-08-03T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Front bulkhead of superstructure","Miscellaneous","General Appearance","Equipment Related","","","","","derusted and painted","2022-12-30T08:00:00","","Completed","2022-12-16T08:00:00","No","No","No","Internal","to complete the job at first opportunity"]
[null,null,null,17633,null,"109_31/1/2021 7:40:53 PM","2022-08-25T08:00:00","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","HATCH COVER NO. 1,2,3 WERE IN RUST","Cargo Mach.","Structural Condn. / WT integrity ","Equipment Related","","","","","DERUSTED AND PAINTED.","2022-12-30T08:00:00","","Completed","2022-12-02T08:00:00","No","No","No","Internal","please let us know vessel intention for carrying out required maintenance. update status"]
[null,null,null,null,85217,"0_Sat Dec 10 2022 04:38:28 GMT+0800","2022-12-05T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Chemical drums found kept in engine room, same to shift immediately to chemical locker. ","E/R - Main Engine","General Appearance","Knowledge Based","","","","","All chemicals found in engine room shifted to chemical locker.","2022-12-12T08:00:00","","Completed","2022-12-08T08:00:00","No","No","No","Internal"]
[null,null,null,null,65561,"0_Sat Dec 10 2022 04:35:31 GMT+0800","2022-12-05T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Accommodation AC Room sighted poor condition, need to square up & upgrade accordingly. ","Accommodation","General Appearance","Equipment Related","","","","","AC room arranged,painted","2022-12-15T08:00:00","","Completed","2022-12-23T08:00:00","No","No","No","Internal"]
[null,null,null,null,78820,"109_Sat Dec 10 2022 04:11:30 GMT+0800","2022-12-05T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Engine room cleaning and housekeeping to be improved in Engine store, Engine Workshop, Engine control room.","Elect. Mach. & Equip.,Miscellaneous","Eng. / Strg. Comp.","Behaviour Based","","","","","Engine store,Engine workshop & Engine control room  re arranged and regularly being cleaned","2022-12-20T08:00:00","","Completed","2022-12-22T08:00:00","No","No","No","Internal"]
[null,null,null,null,50672,"109_Wed Dec 28 2022 17:36:10 GMT+0800","2022-12-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","A section of fresh air duct in AC room is completely corroded and holed,needs replacement at earliest","Accommodation","Structural Condn. / WT integrity ","Equipment Related","","","","","New frame fabricated and fitted.","2023-02-06T08:00:00","","Completed","2022-12-29T08:00:00","No","No","No","Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["109","PACIFIST (19-12-2022)","109_1671778107787.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]