{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":37,"n_cols":28,"rows_kept":37,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","06-Jan-2023",null,null,"Ship Name","NATTY (22-11-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,14091,"128_Wed Jun 15 2022 20:53:51 GMT+0800","2022-05-22T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Stbd side anchor windlass was reported heavy vibration","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","WILL INVESTIGATE FURTHER  , TRIED OUT STBD WINDLASS , FOUND NO VIBRATION IN GEAR CASE AND HYD MOTOR , CHAIN STOPPER ROLLER HAS WOBBLING EFFECT IN P-S DIRECTION . CHIAN ROLLER BUSH WORN DOWN.  \nRENEWED OIL OF GEAR CASES FOUND SIGNS OF WATER INGRESS. VENT HEADS CHECKED AND COVERED. GEAR CASE COVER GASKETS RENEWED AND SEALANTS USED. VESSEL GREASING ALL GREASING POINTS PROVIDED IN WINDLASS BEFORE EVERY OPERATION AND AT LEAST ONCE MONTHLY. NOISE ADN VIBRATION DURING OPERATION GREATLY REDUCED, BUT WOBBLE IS STILL THERE.","2023-02-28T08:00:00","","Deferred to D D",null,"No","No","No","Internal","Understand that noise / vibration of STBD windlass due to lack of greasing but chain roller has wobbling due to worn bush. Please confirm this anchor can be put into operation & bush renewal can be postponed till next docking."]
[null,null,null,null,82923,"128_Thu Jun 16 2022 05:11:37 GMT+0800","2022-07-28T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Three way change over valve actuator of fuel oil inlet and return line for all three generator engine and main engine are not connected","E/R - Main Engine,E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Will re check & revert with Requisition of items needed to rectify this ","2023-01-15T08:00:00","","In progress",null,"No","No","No","Internal","Investigation to be done on priority & follow up with office via separate message."]
[null,null,null,25897,99989,"0_Thu Jun 16 2022 21:07:26 GMT+0800","2022-08-05T23:59:35","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck rusted","Miscellaneous","Structural Condn. / WT integrity ","Human Error","","","","","upgradation in progress. Lot of areas de-rusted and painted after making hydro-blaster operational but Need to continue to the job.","2023-02-04T23:59:35","","In progress",null,"No","No","No","Internal","Need to make the Falch hydro blaster operational asap. Please check the require spares on board & raise requisition accordingly."]
[null,null,null,null,59058,"128_Thu Jun 16 2022 05:15:00 GMT+0800","2022-08-11T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Engine room Service Air Compressor not operational","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","As per discussion with office , plan has been sent for installation of screw type service air compressor in due course so as to reduce the running hours of Main compressors ","2023-01-30T08:00:00","","In progress",null,"No","No","No","Internal","Need to dismantle the complete compressor & revert which all parts require to renew to make the compressor operational."]
[null,null,null,null,25661,"128_Thu Jun 16 2022 08:58:34 GMT+0800","2022-08-25T08:00:00","Breakdown","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mono rail crane was not operational fully, travelling gear and pinion not meshing , issue is with the traversing plate","Miscellaneous","General Appearance","Equipment Related","","","","","DETAILED REPORT & JOB SCOPE ALREADY SENT TO OFFICE . JOB REQUIRES BOTH SHORE WORK SHOP AND CRANE TECHNICIAN ATTENDANCE. ","2023-01-30T08:00:00","","In progress",null,"No","No","No","Internal","Need to arrange W/S attendance during next call China, discharge port."]
[null,null,null,null,58124,"128_Thu Jun 16 2022 05:18:58 GMT+0800","2022-08-29T08:00:00","Defect","Ship Staff","Ship Staff Insp.","F.W. generator not creating enough vacuum  with ejector p/p in loaded condition.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","EJECTOR PUMP OVERHAULED WITH NEW IMPELLER AND MOUTH RINGS, EJECTOR PRESSURE NOW 3.5 BAR.  NEED TO REPLACE CASING OF EJECTOR PUMP AS WELL TO IMPROVE PRESSURE EVEN FURTHER, AS SAME IS BUILT UP / DAMAGED. ALSO NEED TO REPLACE NOZZLES AND INITIAL HOUSOING OF EJECTOR. REQUISTION RAISED NATT220254","2023-01-30T08:00:00","NATT220254","Waiting spare",null,"No","No","No","Internal","Kindly raise RO for the require spares & mention RO in DDRL for our follow up to supply spares."]
[null,null,null,null,45386,"0_Thu Jun 16 2022 21:53:40 GMT+0800","2022-08-31T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Ballast control console on bridge non operational","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","INFORMED OFFICE ON EMAIL , Preliminary investigation report has been sent already as per the checks that were advised from the office side but was no success , waiting for further advice","2023-01-30T08:00:00","","In progress",null,"No","No","No","Internal","Need to investigate & advise in separate mail."]
[null,null,null,null,39647,"128_Thu Jun 16 2022 05:33:47 GMT+0800","2022-09-30T08:00:00","Other","Ship Staff","Ship Staff Insp.","LED MIGRATION NOT COMPLETED .","Elect. Mach. & Equip.","Eng. / Strg. Comp.","External Factors","","","","","work in progress","2023-01-30T08:00:00","","In progress",null,"No","No","No","Internal","Please change all on board to LED asap."]
[null,null,null,null,92377,"128_Thu Jun 16 2022 05:21:37 GMT+0800","2022-10-10T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Need to replace flouresent lamp with led lights in engine room and accomodation","Accommodation,Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","WORK IN PROGRESS., already many areas in common spaces ,& ER changed to LED lights ","2023-01-30T08:00:00","","In progress",null,"No","No","No","Internal","Kindly get all the the lamp renewed in due course."]
[null,null,null,null,83100,"0_Thu Jun 16 2022 19:48:34 GMT+0800","2022-10-29T08:00:00","Critical Equipment","Owner / Marine / Tech. Suptd.","Suptd. Insp.","As per master Stbd windless bushes of chain roller worn out","Deck - Machinery","Mooring","Equipment Related","","","","","Not using stbd anchor .","2023-01-30T08:00:00","","Deferred to D D",null,"No","No","No","Internal","Please note this job only can be done at next DD, kindly transfer to DD & enter the job spec in REFMAN."]
[null,null,null,27585,82707,"128_Mon Nov 07 2022 19:22:26 GMT+0800","2022-11-01T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Aft peak  ballast tank vent head  float ball damaged.","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","PO raised and waiting for spare","2023-01-31T23:59:35","NATT220286 - APK  BALLAST  TANK VENT FLOAT BALL.","Waiting spare",null,"No","No","No","Internal","New float already supplied at Taranto, Italy & fitted in place. Kindly update accordingly."]
[null,null,null,null,27424,"128_Wed Nov 16 2022 16:04:49 GMT+0800","2022-11-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Performance of Ballast Pump No.2 is not optimal  & has leaks","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Pump has been tested , alignment done , ensured taht the seal cooling line & gauges lines are clean / clear , has been used 2 times since then . will further check on means to improve volumetric efficiency ","2023-01-30T08:00:00","","In progress",null,"No","No","No","Internal","Vessel has spare mech seal & line bush, please renew & update job in DDRL."]
[null,null,null,null,87505,"128_Wed Nov 16 2022 16:39:22 GMT+0800","2022-11-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","DG Backwash filter actuator is faulty","","Eng. / Strg. Comp.","Equipment Related","","","","","NATT220157 Requisition needed , Currently ensuring that all the candles are clean & also the Bypass filter is clean at all times along with the spare filters , attempt was also made to overhaul the actuator unit but the cam piece is slipping from the limit switch  , waiting spares","2023-01-15T08:00:00","NATT220157","Waiting spare",null,"No","No","No","Internal","Spares already connected to vessel, complete the job & update DDRL accordingly."]
[null,null,null,null,28500,"128_Wed Nov 16 2022 16:46:16 GMT+0800","2022-11-15T08:00:00","Other","Ship Staff","Ship Staff Insp.","ER Bilge areas are rusty & need cosmetic upgradation","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","Cleaning of Bilge areas has been started , also started to rectify various small leaks in that area","2023-01-15T08:00:00","","In progress",null,"No","No","No","Internal","Please complete the job asap & update."]
[null,null,null,null,50986,"128_Wed Nov 16 2022 17:15:09 GMT+0800","2022-11-15T08:00:00","Other","Ship Staff","Ship Staff Insp.","Found that the ER spare parts are not in proper steel boxes but in cardboard boxes , need to rectify this","E/R - Aux. Mach.","Eng. / Strg. Comp.","Inappropriate Procedure","","","","","Temporarily wooden boxes made for important and critical spares  ","2023-01-14T08:00:00","NATT225015","Waiting spare",null,"No","No","No","Internal","Spare boxes also connected to vessel, kindly keep all the spares in steel boxes & update."]
[null,null,null,null,66785,"128_Fri Dec 09 2022 15:05:37 GMT+0800","2022-12-07T08:00:00","Defect","Ship Staff","Ship Staff Insp.","JACKET WATER CONTROLLER FOR MAIN ENGINE NOT WORKING PROPERLY AND GIVING ERRATIC FEEDBACK DUE WICCH JACKET WATER FOR MAIN ENGINE NOT STABLE ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","SHIP STAFF INVESTOGATED THE CONTROLLER DISPLAY UNIT AND FOUND THAT ELECTRIC ACTUATOR IS FAULTY , ACTUATOR CARD SWAPPED WITH LT COOLER CONTROLLER , ITS WORKING RIGHT NOW BUT SOMETIME GOES TO NULL MODE , ","2023-01-15T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,63526,"128_Fri Jan 06 2023 16:47:21 GMT+0800","2023-01-06T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Main air compressor No.1 Forward Unit Piston needs to be replaced , also the NRV for this compressor not holding ","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Meantime as per discussion with office , the corrective / preventive steps being taken to be extra careful with use and operation of main compressors ","2023-01-15T08:00:00","-NATT220287-MAIN AIR COMPRESSOR SPARES \n -NATT220238-MAIN AIR COMPRESSOR SPARES TANABE ORIGINAL GENUINE SPARES  \n-NATT220326-MAIN AIR COMPRESSOR URGENT SPARES \n\n","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,18095,"128_Fri Jan 06 2023 16:50:31 GMT+0800","2023-01-06T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Leak noticed from the Falch Hydro Blaster Main Pump (  High Pressure Pump ) Body  ,( at the aft portion opposite side of the working pistons )","Deck - Machinery","General Appearance","Equipment Related","","","","","Meantime bearings / oil changed for the Denjet hydroblaster & cables prepared for the same . Will wait for maker s advice on Falch Hydroblaster ","2023-01-30T08:00:00","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,88747,"128_Fri Jan 06 2023 16:54:36 GMT+0800","2023-01-06T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Standby Boiler Feed Pump Contactors are erratic , standby start not available along with its alarms ","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Meantime ensuring motor & pump are running ok , as this ship has design of Boiler feed pumps such that they are cut cut out type & not level modulating type ,so the motor starts stops , hence have made ventilation requirements for the same ","2023-01-15T08:00:00","NATT220309-BOILER FEED WATER PUMP URGENT ELECTRICAL SPARES ","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,35221,"128_Fri Jan 06 2023 17:01:35 GMT+0800","2023-01-06T08:00:00","Defect","Ship Staff","Ship Staff Insp.","NO.3 DIESEL GENERATOR F.O LEAKAGE LEVEL SENSOR ERRATIC SOMETIMES ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Preliminary checks done on the mechanical side & electrical side , tried to rectify but still erratic hence have raised Requisition ","2023-01-15T08:00:00","NATT220327-FUEL OIL LEAKAGE LEVEL SENSOR FOR DIESEL GENERATOR ","Waiting spare",null,"No","No","No","Internal"]

{"sheet":"Completed","index":1,"n_rows":52,"n_cols":28,"rows_kept":52,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","06-Jan-2023",null,null,"Ship Name","NATTY (22-11-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,26946,null,"128_Thu Sep 22 2022 05:24:01 GMT+0000","2022-01-20T23:59:35","Observation","PSC Insp.","PSC Inspection","Gangway, accommodation- Iadder GANGWAY SAFETY NET-NOT PROPERLY INSTALLED","","","","","","Other","","","2022-03-29T23:59:35","","Completed","2022-02-23T23:59:35","No","No","No","External"]
[null,null,null,26947,null,"128_Thu Sep 22 2022 05:26:43 GMT+0000","2022-01-20T23:59:35","Observation","PSC Insp.","PSC Inspection","Fire fighting equipment and appliances1FIRE FIGHTING UHF MISSING IMO SYMBOL","","Safety / LSA / FFA","","","","Fire safety","","","2022-03-29T23:59:35","","Completed","2022-02-23T23:59:35","No","No","No","External"]
[null,null,null,26948,null,"128_Thu Sep 22 2022 05:29:07 GMT+0000","2022-01-20T23:59:35","Observation","PSC Insp.","PSC Inspection","Fire control plan FlRE CONTROL PLAN REQUIRED FOR\nCORRECTION.","","Safety / LSA / FFA","","","","Fire safety","","","2022-03-29T23:59:35","","Completed","2022-02-23T23:59:35","No","No","No","External"]
[null,null,null,26949,null,"128_Thu Sep 22 2022 05:33:48 GMT+0000","2022-01-20T23:59:35","Observation","PSC Insp.","PSC Inspection","Magnetic compass/DEVIATION TABLE FOR SHIP DS CHARME REQUIRED FOR RENEWAL.","","Navigation","","","","Safety of Navigation","","","2022-03-29T23:59:35","","Completed","2022-02-23T23:59:35","No","No","No","External"]
[null,null,null,26950,null,"128_Thu Sep 22 2022 05:35:27 GMT+0000","2022-01-20T23:59:35","Observation","PSC Insp.","PSC Inspection","Electronic charts (ECDIS) ABORT POINT, ANCHORAGE NOT MARKED IN APPROACH","Navigation - ECDIS","Navigation","","","","Safety of Navigation","","","2022-03-29T23:59:35","","Completed","2022-02-23T23:59:35","No","No","No","External"]
[null,null,null,26952,null,"128_Thu Sep 22 2022 05:41:51 GMT+0000","2022-01-20T23:59:35","Observation","PSC Insp.","PSC Inspection","Compass error Iog COMPASS OBSERVATION MADE NOT EVERY WATCH.","","","","","","Safety of Navigation","","","2022-01-31T23:59:35","","Completed","2022-01-23T23:59:35","No","No","No","External"]
[null,null,null,26953,null,"128_Thu Sep 22 2022 05:43:36 GMT+0000","2022-01-20T23:59:35","Observation","PSC Insp.","PSC Inspection","Lights, shapes, sound Signalsl BATTERY FOR ALDIS LAMP REQUIRED FOR CHARGING.","","","","","","Safety of Navigation","","","2022-03-29T23:59:35","","Completed","2022-02-23T23:59:35","No","No","No","External"]
[null,null,null,26951,null,"128_Thu Sep 22 2022 05:37:09 GMT+0000","2022-01-21T23:59:35","Observation","PSC Insp.","PSC Inspection","Compass error Iog COMPASS OBSERVATION MADE NOT EVERY WATCH.","Navigation - Others","Navigation","","","","Safety of Navigation","","","2022-03-30T23:59:35","","Completed","2022-02-24T23:59:35","No","No","No","External"]
[null,null,null,25906,96371,"128_Thu Jun 16 2022 06:09:25 GMT+0800","2022-04-12T23:59:35","Defect","Ship Staff","Ship Staff Insp.","MAIN ENGINE UNIT NO 6 EXHAUST TEMPERATURE SENSOR OUTPUT COMMUNICATION ERROR . EXHAUST DEVIATION SLOWDOWN CANCELLED.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","NO.6 UNIT EXHAUST TEMP INDICATION RECTIFIED BY REPLACING THE COMBINED SENSOR.","2022-08-16T23:59:35","","Completed","2022-05-22T23:59:35","No","No","No","Internal"]
[null,null,null,25892,26829,"128_Thu Jun 16 2022 06:00:15 GMT+0800","2022-05-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","A/E NO 1 NOT OPERATIONAL DUE TO DAMAGED FLYWHEEL RIM, AIR MOTOR & PINION . AIR START SOLENOOID VALVE ALSO NON-OPERATIONAL","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","SPARES RECEIVED AND AE NO 1 IN OPERATION.","2022-07-30T23:59:35","","Completed","2022-06-28T23:59:35","No","No","No","Internal"]
[null,null,null,25890,76798,"128_Thu Jun 16 2022 05:28:43 GMT+0800","2022-05-09T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Spare parts room and Engine room store area, require housekeeping.","Miscellaneous","Eng. / Strg. Comp.","Human Error","","","","","COMPLETED. BUT THE SPARE AND STORE AREA NEED TO BE MAINTAINED ON CONTINUOUS BASIS.","2022-08-06T23:59:35","","Completed","2022-08-01T23:59:35","No","No","No","Internal","Need photograph of stores / spare parts room on weekly basis."]
[null,null,null,25885,77249,"128_Thu Jun 16 2022 13:31:07 GMT+0800","2022-05-13T23:59:35","Other","Ship Staff","Ship Staff Insp.","HATCH COVER HYD RAM LEAKING 2 AFT","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","COMPLETED.","2022-08-13T23:59:35","","Completed","2022-08-08T23:59:35","No","No","No","Internal","Please renew the ram asap & report to office. This can be PSC detention deficiency."]
[null,null,null,25904,62087,"128_Thu Jun 16 2022 10:18:14 GMT+0800","2022-05-15T23:59:35","Defect","Ship Staff","Ship Staff Insp.","HATCH COVER HYD RAM LEAKING NO.2 FWD RAM,","Deck - Machinery","MARPOL Related","External Factors","","","","","NO.2 FWD RAM RENEWED.","2022-08-15T23:59:35","","Completed","2022-05-19T23:59:35","No","No","No","Internal"]
[null,null,null,25905,63360,"128_Tue Jun 21 2022 06:02:12 GMT+0800","2022-05-15T23:59:35","Defect","Ship Staff","Ship Staff Insp.","BOILER ALARM AND SIGNAL CONTROL PANEL  AND COMMUNICATION WITH ECR CONTROL PANEL FOUND FAULTY.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","boiler technician came and programmed the PLC after that all alarm working in ams and hmi panel.","2022-08-14T23:59:35","","Completed","2022-06-09T23:59:35","No","No","No","Internal"]
[null,null,null,25880,98548,"128_Thu Jun 16 2022 04:59:52 GMT+0800","2022-05-17T23:59:35","Critical Equipment","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency fire pump discharge pressure was at 7.0 bar, but no water discharge from forecastle fire hose.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","TRIED OUT WITH ANCHOR WASH CLOSED. GOT DISCHARGE AT FORECASTLE DECK. TESTED IN PRESENCE OF FSI AS WELL. AWAITING SPARES TO CARRY OUT COMPLETE OVERHAUL TO FURTHER IMPROVE PERFOMANCE.","2022-08-15T23:59:35"," RO -NATT220033","Completed","2022-08-05T23:59:35","No","No","No","Internal","Please investigate the reason no water will discharge when pump building up 7 bar pressure. Spares arranged by owner & we are pushing them to connect at Algeciras."]
[null,null,null,25901,71447,"128_Tue Jun 21 2022 05:53:26 GMT+0800","2022-05-31T23:59:35","Defect","Ship Staff","Ship Staff Insp.","mac 1 aft unit piston and liner seized found damaged piston scracthed liner, piston and piston rings damaged.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Aft unit of Mac 1  replaced with new liner and rings. Found fwd unit blowpast as well. MAC not building pressure . Require another liner block to make the compressor operational. MAC 1 FWD UNIT LINER REPLACED WITH SPARES RECEIVED. PISTON PIN O RING ALSO RENEWED. NO BLOWPAST NOW. COMPRESSOR WORKING ON AUTO.","2022-09-27T23:59:35","RO NO NATT220160.","Completed","2022-09-06T23:59:35","No","No","No","Internal","Trying to connect but long delivery time for the spares from Japan. Spares connected & vessel has completed the job. Please update in DDRL & close out."]
[null,null,null,25902,17015,"128_Fri Jun 24 2022 15:57:31 GMT+0800","2022-06-05T23:59:35","Defect","Ship Staff","Ship Staff Insp.","MAIN EGINE EXHAUST TEMPERATURE INDICATION FOR UNIT 1 NOT WORKING. HENCE EXHAUST DEVIATION SLOWDOWN CANCELLED.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","COMBINED SENSOR AND AMPLIFIER RECEICVED. BOTH RECEIVED WRONG SUPPLY. INFORMED OFFICE AND OWENRS' SUPPLY DEPT. AWAITING OWNER SIDE SUPPLY DEPT REVERT ON THIS. FOR NOW ADJUSTED TEMPERATURE RANGE OF AMPLIFIER TO GET SOME APPROXIMATED EXH VALUES ON ECR AMS.. STILL WOULD REQUIRE GENUINE SENSORS AND AMPLIFIER FOR A RELIABLE INDICATION.","2022-10-04T23:59:35","RO NO NATT220135.","Completed",null,"No","No","No","Internal","Correct spec of amplifier will be connected at next port of call"]
[null,null,null,25898,36558,"0_Thu Jun 16 2022 21:47:27 GMT+0800","2022-06-10T23:59:35","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Booby hatches heavily rusted","Deck - Pipe / Fittings","Cargo / Ballast Systems","Human Error","","","","","UPGRADATION IN PROGRESS. MANY AREAS FINISHED. NEED TO CONTINUE THE JOB.","2022-08-10T23:59:35","","Completed","2022-08-07T23:59:35","No","No","No","Internal","Vessel is in long voyage to Brazil, all booby hatches should be completed."]
[null,null,null,25893,50224,"0_Thu Jun 16 2022 15:03:58 GMT+0800","2022-06-29T23:59:35","Other","Ship Staff","Ship Staff Insp.","NO.7 hatch cover fwd  Hydraulic ram leakihg","Deck - Machinery","MARPOL Related","Equipment Related","","","","","RAM REPLACED","2022-09-28T23:59:35","","Completed","2022-08-30T23:59:35","No","No","No","Internal","Please raise RO for ram seal repair kit immediately."]
[null,null,null,25894,86053,"128_Thu Jun 16 2022 19:32:44 GMT+0800","2022-06-29T23:59:35","Other","Ship Staff","Ship Staff Insp.","HATCH COVER DRIVE MOTOR OF NO .2  PORT /STBD IS  LEAKING","Deck - Machinery","MARPOL Related","Equipment Related","","","","","2 STARBOARD MOTOR RENEWED AS BODY DAMAGED. \nSPARE MOTOR RECEIVED WILL PLAN RENEWAL AFTER DISCHARGE PORT.","2022-09-28T23:59:35","","Completed","2022-08-30T23:59:35","No","No","No","Internal","As informed vessel to raise RO for HC motor's gear box to make one complete hyd motor. Also the old one to off land for repair at Singapore."]
[null,null,null,25895,23663,"0_Thu Jun 16 2022 19:37:22 GMT+0800","2022-06-29T23:59:35","Other","Ship Staff","Ship Staff Insp.","HATCH COVER DRIVING MOTOR NO.4 PORT/STBD LEAKING","Deck - Pipe / Fittings","MARPOL Related","Equipment Related","","","","","Renewed with new motor","2022-09-28T23:59:35","","Completed","2022-08-30T23:59:35","No","No","No","Internal","Is there any RO raised by vessel? If not kindly raise RO with detail reason of asking the spares."]
[null,null,null,25900,17063,"0_Thu Jun 16 2022 22:08:55 GMT+0800","2022-06-29T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Hacth cover control lever union leaking for hatch no.2","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","",""," Renewed the bloc","2022-09-28T23:59:35","","Completed","2022-09-03T23:59:35","No","No","No","Internal","No reason this job kept under pending, kindly rectify & complete the job."]
[null,null,null,25881,88147,"128_Thu Jun 16 2022 05:08:14 GMT+0800","2022-07-12T23:59:35","Observation","Ship Staff","Ship Staff Insp.","SCBA COMPRESSOR FONDATION TO BE MADE.","Critical Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","COMPLETED.","2022-10-09T23:59:35","","Completed","2022-09-29T23:59:35","No","No","No","Internal","Noted this job already planned, please attend same at the earliest."]
[null,null,null,25903,86908,"128_Fri Jun 24 2022 16:01:33 GMT+0800","2022-07-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","AE 1 STARTING AIR LINE SPECIAL FLEXIBLE HOSE (MAKER SUPPY) BADLY DAMAGED.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","SPARE HOSE CONNECTED AT PORT CARTIER. SAME USED TO RENEW THE HOSE. PROBLEM RECTIFIED.","2022-10-28T23:59:35","NATT220172","Completed","2022-09-28T23:59:35","No","No","No","Internal","Spares to connect at Suez around 16th Oct 2022."]
[null,null,null,25888,27681,"128_Thu Jun 16 2022 06:07:50 GMT+0800","2022-09-09T23:59:35","Defect","Ship Staff","Ship Staff Insp.","MAIN AIR COMPRESSOR NO . 2  LUB OIL PRESSURE DROPPING DURING OPERATION.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","MAJOR OVERHAUL COMPLETED , NEW LO PUMP ALSO FIXED , NOW OK , HOWEVER WILL KEEP MONITORING ","2022-12-08T23:59:35","RO NO NATT220133","Completed","2022-10-09T23:59:35","No","No","No","Internal","Job already completed, kindly update DDRL & close out accordingly."]
[null,null,null,25887,89931,"128_Thu Jun 16 2022 06:11:25 GMT+0800","2022-09-27T23:59:35","Defect","Ship Staff","Ship Staff Insp.","WORKSHOP ELECTRIC BUFFING MOTOR FOUNDATION  LOOSE AND BROKEN.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","",""," FOUNDATION STAND REPAIRED ","2022-12-27T23:59:35","","Completed","2022-11-11T23:59:35","No","No","No","Internal","Noted, kindly update office once done."]
[null,null,null,27584,24815,"128_Sun Oct 16 2022 02:53:36 GMT+0800","2022-10-03T23:59:35","Defect","Ship Staff","Ship Staff Insp.","CARGO HOLD 5 P HATCH HYD MOTOR NOT OPERATIONAL. MOTOR BODY GETTING DAMAGED WHEN TRYING TO OPERATE HATCH COVER.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","1 HYD MOTOR AS PER RO NATT220296 RECIEVED IN SINGAPORE \nFIXED AND TESTED, FOUND SATISFACTORY. ","2022-11-29T23:59:35","NATT220247","Completed","2022-11-11T23:59:35","No","No","No","Internal"]
[null,null,null,27586,50271,"128_Mon Nov 07 2022 19:16:06 GMT+0800","2022-10-18T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Steering flat machinal mushroom vent mess plate found broken. ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Fabricated the mesh plate for mushroom vent of Steering flat  and boxed back.","2022-11-29T23:59:35","","Completed","2022-10-23T23:59:35","No","No","No","Internal"]
[null,null,null,27587,85156,"128_Mon Nov 07 2022 19:27:50 GMT+0800","2022-10-26T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NRV of cargo hold no 6 bilge line port side found chocked and not operational.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","NRV of cargo hold no 6 bilge line port side dismantle ,overhauled and boxed back.","2022-11-29T23:59:35","","Completed","2022-11-01T23:59:35","No","No","No","Internal"]
[null,null,null,null,80223,"128_Wed Nov 16 2022 15:04:05 GMT+0800","2022-11-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Found ME Jacket water pump has significant leakages & performance need to be improved also of the pump by overhaul","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","main engine jacket cooling water pump leak rectified and new mechanical sea installed \nmotor side DE and NDE bearing renewed with new one ","2022-11-29T08:00:00","","Completed","2022-11-22T08:00:00","No","No","No","Internal","Vessel has spare mech seal, need to renew asap & update."]
[null,null,null,null,58094,"128_Wed Nov 16 2022 16:43:16 GMT+0800","2022-11-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","FOUND THAT THE CALORIFIER UNIT COILS ARE GIVING 440 V INSULAITON ISSUE","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","",""," REQUISITION RECIEVED  : NATT220248 , INSTALLED THE SAME & WORKING GOOD NOW WITHOUT ANY 440 V INSULATION ","2022-12-29T08:00:00","NATT220248","Completed","2022-12-02T08:00:00","No","No","No","Internal","Spares already connected to vessel, please rectify & update."]
[null,null,null,null,75492,"128_Wed Nov 16 2022 15:06:13 GMT+0800","2022-11-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Found ME LO Temperature control valve has leaks from the seals","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Same attended , & rectified the leak , now ok ","2022-11-29T08:00:00","","Completed","2022-12-01T08:00:00","No","No","No","Internal","Need to attend this job at next call China. Once completed kindly update DDRL accordingly."]
[null,null,null,null,59845,"128_Wed Nov 16 2022 16:52:40 GMT+0800","2022-11-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Bunker Line Manifold valves are very tight , one of the valve handle is also not in good condition","Deck - Pipe / Fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Valve made free e ,new valve has been received in china  and same replaced ","2023-01-07T08:00:00","","Completed","2023-01-05T08:00:00","No","No","No","Internal","Kindly advise RO number for our process. : RO NATT220253 received at Lanshan / coafidian  "]
[null,null,null,null,82589,"128_Sat Dec 17 2022 07:03:48 GMT+0800","2022-12-08T08:00:00","Defect","Ship Staff","Ship Staff Insp.","The fresh water line busted outside accommodation at D deck due to sub zero temp. ","Deck - Pipe / Fittings","Ice Opns.","External Factors","","","","","The fresh water line isolated immediately and pipe renewal done ","2023-01-12T08:00:00","","Completed","2023-01-06T08:00:00","No","No","No","Internal"]
[null,null,null,null,13583,"128_Wed Nov 16 2022 16:54:42 GMT+0800","2022-11-15T08:00:00","Defect,Other","Ship Staff","Ship Staff Insp.","Hydrophore Sight glass need to clean & rectify so that correct level can be seen","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","New sight glasses fitted , now ok , also as a safety all told to keep the valves shut in UMS mode to avoid leaks ","2022-12-30T08:00:00","","Completed","2023-01-02T08:00:00","No","No","No","Internal","Need to complete in this port."]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["128","NATTY (22-11-2022)","128_1669107974900.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]