{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":31,"n_cols":28,"rows_kept":31,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","17-Mar-2023",null,null,"Ship Name","FANTASEA (13-08-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,93348,"0_Fri Jul 08 2022 02:08:18 GMT+0800","2022-05-28T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Galley AC non operational","Accommodation","MLC Related","Equipment Related","","","","","Requisition made for suitable complete Package AC.","2023-02-28T08:00:00","FANT220282","Waiting spare",null,"No","No","No","Internal","require complete detail of Galley Air cond including size, capacity. Need to ensure supplied complete air cond can pass through the door of air cond room."]
[null,null,null,null,26014,"0_Sun Jul 24 2022 19:23:35 GMT+0800","2022-07-14T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Bilge, sludge tank heating line penetrating tank top damaged.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","TEMPORARY WORK DONE . Tank required to be gass free prior welding work repairs can be carried out. ","2023-05-15T08:00:00","","Not Started",null,"No","No","No","Internal","Kindly get this job done after sludge discharge at China."]
[null,null,null,null,46707,"127_Mon Dec 19 2022 17:37:47 GMT+0800","2022-12-14T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME  Exhaust Pyrometer pockets plugged. To fit with local gauges","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Vessel raised PO . FANT 230004","2023-04-14T08:00:00","FANT 230004","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,78558,"127_Mon Dec 19 2022 17:47:04 GMT+0800","2022-12-07T08:00:00","Critical Equipment","Ship Staff","Ship Staff Insp.","Incinerator door limit switch is non operational ","Elect. Mach. & Equip.","MARPOL Related","Equipment Related","","","","","Inspected and found limit switch faulty.RO raised\nSpares awaited.","2023-04-30T08:00:00","FANT220377","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,20199,"127_Sun Jan 15 2023 19:26:04 GMT+0800","2022-12-12T08:00:00","Defect","Ship Staff","Ship Staff Insp.","The bush bearing of the forward starboard side, inboard drum is worn out.\nDrum wobbling. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","The bush bearing to be renewed.\nDeferred to DD.","2023-03-12T08:00:00","","Deferred to D D",null,"No","No","No","Internal"]
[null,null,null,null,13922,"127_Sun Jan 15 2023 19:30:05 GMT+0800","2022-12-26T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","Hatch cover jack motors are inoperational due to water logging post heavy weather.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Jack motors to be restored to operational working condition.","2023-04-28T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,62627,"127_Sun Jan 15 2023 19:33:43 GMT+0800","2022-12-26T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Wiring for the hatch cover jacks to be renewed due to frequent failures at all the hatch covers.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Renew the wiring.","2023-04-30T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,13788,"127_Sun Jan 15 2023 19:38:34 GMT+0800","2023-01-01T08:00:00","Defect","Ship Staff","Suptd. Insp.","Hatch cover chains have uneven tension/sagging at places.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related,Inappropriate Procedure","","","","","Chains to be measured, cropped and attuned, in accordance with the manual.","2023-03-31T08:00:00","","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,42142,"127_Sun Jan 15 2023 19:43:23 GMT+0800","2023-01-08T08:00:00","Other","Ship Staff","Ship Staff Insp.","Undersides of hatch covers have coating breakdown and thick rust formation.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","De-rusting and paint application of the undersides.","2023-04-08T08:00:00","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,96215,"127_Sun Jan 15 2023 19:50:51 GMT+0800","2023-01-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Pedestals and stools on deck thinned down/wasted.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","","","","","","Pedestals and stools to be cropped and renewed. ","2023-04-15T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,94736,"127_Sun Jan 15 2023 19:55:01 GMT+0800","2022-12-01T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Cable conduit on main deck, paint peeling off and has is severely rusted.","Deck - Pipe / Fittings","General Appearance","","","","","","To be de-rusted followed by application of compatible paint.","2023-04-12T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,90710,"127_Sun Jan 15 2023 19:58:48 GMT+0800","2022-11-28T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Accommodation flooring needs re-grouting.","Accommodation","General Appearance","","","","","","Floors to be re-grouted.","2023-04-28T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,62597,"127_Fri Mar 17 2023 21:53:06 GMT+0800","2023-03-05T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","The Engine Control Room Air Condition System is In-operational ","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Failure investigated and observed Compressor requires Renewal.","2023-04-30T08:00:00","FANT230134","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,68702,"127_Fri Mar 17 2023 21:57:46 GMT+0800","2023-02-28T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","The Ballast Pump No. 1  Impellor Damaged","E/R - Pumps","Cargo / Ballast Systems","Equipment Related","","","","","Pump Removed and Mount Made Ready for Replacement.","2023-04-30T08:00:00","FANT235032","Waiting spare",null,"No","No","No","Internal"]

{"sheet":"Completed","index":1,"n_rows":102,"n_cols":28,"rows_kept":102,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","17-Mar-2023",null,null,"Ship Name","FANTASEA (13-08-2022)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,21253,null,"127_9/28/2021 5:59:58 AM","2021-09-21T23:59:35","Defect","Ship Staff","Engineering Audit","Lost of starboard accommodation ladder during Suez Canal Transit due to equipment age.","Accommodation","Structural Condn. / WT integrity ","Equipment Related","","","","","GSM Office arranging very urgent replacement. new accommodation ladder recvd at ROtterdam and fitted by ship's staff on 23-Nov-2021. Load tested in presence of Class on 14-Dec-2021","2021-12-07T23:59:35","","Completed","2021-12-11T23:59:35","No","No","No","Internal","Will be connected at next port."]
[null,null,null,21251,null,"127_9/28/2021 5:20:23 AM","2021-09-23T23:59:35","Defect","Ship Staff","Engineering Audit","Port side Accommodation Ladder found some parts decomposing making it not suited for safe use.","Accommodation","Structural Condn. / WT integrity ","Equipment Related","","","",""," RO FANT210116 raised. GSM Office arranging very urgent replacement. New accommodation ladder recvd at ROtterdam and fitted by shore workshop at Yantai, China on 04-JAN-2022. Load tested in presence of Class on 06-JAN-2022 ","2021-12-23T23:59:35","FANT210116","Completed","2022-01-03T23:59:35","No","No","No","Internal","New ladder will be connected at next port of call."]
[null,null,null,21252,null,"127_9/28/2021 5:29:50 AM","2021-09-23T23:59:35","Defect","Ship Staff","Engineering Audit","Found starboard some parts Pilot Assisting Ladder decomposing. Also found angle bar doubler which is bulging underneath due to decomposing part of the ladder.","Accommodation","Structural Condn. / WT integrity ","Equipment Related","","","","","Raised an urgent RO for replacement.  RO FANT210116 raised. GSM Office arranging very urgent replacement. New Pilot  ladder recvd at Rotterdam and fitted by shore workshop at Yantai, China on 06-JAN-2022. Load tested in presence of Class on 06-JAN-2022. ","2021-12-07T23:59:35","FANT210117","Completed","2022-01-03T23:59:35","No","No","No","Internal","Already in order & to be connected to vessel at next port of call."]
[null,null,null,21250,null,"127_9/28/2021 5:49:44 AM","2021-09-24T23:59:35","Defect","Ship Staff","Engineering Audit","Echo Sounder alarm indicating sea bed not detected when making course alteration in narrow channel such as in Suez Canal, Dardanalles & Bosphorus Straits transits and when giving M/E astern propulsions during anchor operation.","Navigation - Echo Sounder / Speed Log","Navigation","Equipment Related","","","","","Noticed during transits in manuevering during channeling in Suez Canal Transit and while anchoring at Port Said. Found back into normal working condition in deep water. Observed another malfunction during transit inbound to Black Sea. Must be check by certified shore technician.","2021-11-27T23:59:35","","Completed","2021-12-27T23:59:35","No","No","No","Internal","resolved with remote troubleshooting"]
[null,null,null,26984,null,"127_Mon Sep 26 2022 02:16:39 GMT+0000","2021-10-17T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","No objective evidence could be provided that approved damage stability calculations were available onboard. Subsequently it could not be demonstrated that damage stability could be verified against the results of intact stability.","","","","","","Structural condition",1,"","2021-11-02T23:59:35","","Completed","2021-10-31T23:59:35","No","No","No","External"]
[null,null,null,26985,null,"127_Mon Sep 26 2022 02:19:34 GMT+0000","2021-10-17T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","Abandon ship drills - Lifeboat and Rescue Boat not maneuvered in the water at lease once every 3 months with their assigned crew onboard.","","Safety / LSA / FFA","","","","Emergency Systems",1,"","2021-11-02T23:59:35","","Completed","2021-10-17T23:59:35","No","No","No","External"]
[null,null,null,26986,null,"127_Mon Sep 26 2022 02:21:49 GMT+0000","2021-10-17T23:59:35","Observation","PSC Insp.","PSC Inspection","Cargo Operation- Although safety measurements were performed during the past voyage, they were not followed as per applicable legislation (eg. number of measurements  per day, all voyage and recording in the ship's log book.","Cargo Mach.","Communication","","","","Cargo operations including equipment",1,"","2021-10-02T23:59:35","","Completed","2021-11-01T23:59:35","No","No","No","External"]
[null,null,null,26987,null,"127_Mon Sep 26 2022 02:24:58 GMT+0000","2021-10-17T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","water, pipes, tanks - The by-pass valve of the sterilizing unit is open and the lamp is not functioning.","Deck - Pipe / Fittings","MLC Related","","","","MLC, 2006",1,"","2021-11-02T23:59:35","","Completed","2021-10-31T23:59:35","No","No","No","External"]
[null,null,null,26988,null,"127_Mon Sep 26 2022 02:27:20 GMT+0000","2021-10-17T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","ventilators, air pipes, casings - Found:\nDeck- Forecastle air pipe with gasket of air pipe fallen out.\nEngine Room- Several sounding pipes cannot be properly closed.","Deck - Pipe / Fittings","","","","","Water/Weathertight condition",1,"","2021-11-02T23:59:35","","Completed","2021-10-31T23:59:35","No","No","No","External"]
[null,null,null,26989,null,"127_Mon Sep 26 2022 02:30:08 GMT+0000","2021-10-17T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","manholes/flush scuttles - Found significant number of manhole covers on PS ballast top tanks (2, 3 fore and aft cover etc.) missing studs.","E/R - Main Engine","Cargo / Ballast Systems","","","","Water/Weathertight condition","","","2021-11-02T23:59:35","","Completed","2021-10-31T23:59:35","No","No","No","External"]
[null,null,null,26990,null,"127_Mon Sep 26 2022 02:32:43 GMT+0000","2021-10-17T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","Sewage treatment Plan - lower of sewage treatment plant is not providing enough air eg. gauge indicates 0.0 bar. And the APT manhole cover opened to fit hoses connected from grey water pipes and treated sewage. Same situation as described in the PSC Report from 2019. No solution provided yet. Class and/or Flag State to agree on a permanent solution.","Miscellaneous","","","","","Pollution Prevention",1,"","2021-11-02T23:59:35","","Completed","2021-10-31T23:59:35","No","No","No","External"]
[null,null,null,26992,null,"127_Mon Sep 26 2022 02:38:15 GMT+0000","2021-10-17T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","electrical - Found 110 VAC megh Ohm Meter in alarm at 0.01 in ECR.\nFound megh Ohm meter device in the EMDG room with a jumper installed in the instrument.","Elect. Mach. & Equip.","MLC Related","","","","MLC, 2006",1,"","2021-11-02T23:59:35","","Completed","2021-10-31T23:59:35","No","No","No","External"]
[null,null,null,22597,null,"127_11/16/2021 4:18:11 PM","2021-11-13T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Engineering Audit","Galley griller 440V low insulation","Elect. Mach. & Equip.","Safety / LSA / FFA","Equipment Related","","","","","to raised req","2021-11-22T23:59:35","","Completed","2021-11-27T23:59:35","No","No","No","Internal","replaced with onboard spare"]
[null,null,null,22598,null,"127_11/16/2021 4:11:56 PM","2021-11-13T23:59:35","Critical Equipment","Owner / Marine / Tech. Suptd.","Engineering Audit","Water mist solenoid valve for incinerator supply leaking","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","raised requisition","2021-11-22T23:59:35","FANT210040 water mist fire fighting system","Completed","2021-11-27T23:59:35","No","No","No","Internal","rectified with onboard spare"]
[null,null,null,26991,null,"127_Mon Sep 26 2022 02:36:15 GMT+0000","2021-11-17T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","covers(hatchway - portable - tarpaulins etc) Found:\n- Forecastle hatch missing two wing nuts and security pin\n- Engine Room hatch aft security pins missing","E/R - Main Engine","General Appearance","","","","Water/Weathertight condition",1,"","2021-11-02T23:59:35","","Completed","2021-10-31T23:59:35","No","No","No","External"]
[null,null,null,23556,null,"127_13-Jan-22 12:58:54","2021-12-06T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","BILGE PUMP IN-OPERATIONAL SCRATCHED AND OVERSIZED LINER AND DAMAGED PISTON RINGS.","Critical Equip.","MARPOL Related","Equipment Related","","","","","RO FANT210186 RAISED FOR NEW PUMP","2022-01-02T23:59:35","","Completed","2022-01-02T23:59:35","No","No","No","Internal"]
[null,null,null,23555,null,"127_13-Jan-22 13:08:17","2021-12-19T23:59:35","Defect","Ship Staff","Ship Staff Insp.","BOILER NOT WORKING IN AUTOMATIC MODE.  ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","REQUESTED SHORE SERVICE. PILOT CUT OFF VALVE AND NOZZLE REPAIRED. COMBUSTION SETTINGS ADJUSTED BY SHORE TECHNICIAN.","2022-01-19T23:59:35","","Completed","2021-12-28T23:59:35","No","No","No","Internal"]
[null,null,null,23557,null,"127_13-Jan-22 13:13:03","2021-12-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","DM1 ,DM2 AND DM3 MOTORS SHOWING ZERO INSULATION DUE TO WATER INGRESS DURING HEAVY WEATHER. DAMAGED PLANETARY GEAR FOR DM2.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","OVERHAULED , CLEANED, VARNISHED AND DRIED MOTORS FOR DM1 AND DM3 ON 30-DEC-2021. RENEWED PLANETARY GEAR FOR DM2 ON 05-JAN-2022 NEW MOTOR FITTED IN PACE AND TESTED FOR DM2 ON 10-JAN-2022.","2022-01-03T23:59:35","","Completed","2022-01-07T23:59:35","No","No","No","Internal"]
[null,null,null,23559,null,"127_13-Jan-22 13:16:31","2021-12-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","FOREPEAK TANK AIR VENT HEAD DAMAGED DURING HEAVY WEATHER.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Behaviour Based","","","","","RO FANT 210216 RAISED FOR NEW VENT HEAD. RENEWED BY SHIP STAFF.","2022-01-02T23:59:35","","Completed","2021-12-30T23:59:35","No","No","No","Internal"]
[null,null,null,23560,null,"127_13-Jan-22 13:20:19","2021-12-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","REMOVABLE RAILINGS ( P&S) FOR FORWARD LIFERAFT EMBARKATION WERE LOST DURING HEAVY WEATHER","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","RO FANT210219 RAISED FOR STEEL MATERIAL FOR FABRICATION. NEW RAILING FABRICATED AND FITTED BY SHIP STAFF.","2022-01-02T23:59:35","","Completed","2021-12-30T23:59:35","No","No","No","Internal"]
[null,null,null,23561,null,"127_13-Jan-22 13:23:12","2021-12-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","FORWARD LIFERAFT EMBARKATION LADDER DAMAGED DURING HEAVY WEATHER.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","RO FANT210206 RAISED FOR NEW LADDER. LADDER RECEIVED AND SECURED IN PLACE BY SHIP STAFF.","2022-01-02T23:59:35","","Completed","2022-01-02T23:59:35","No","No","No","Internal"]
[null,null,null,23562,null,"127_13-Jan-22 13:27:26","2021-12-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","PORT FWD NATURAL VENT COVER FOR NO1 HATCH COVER MISSING DURING HEAVY WEATHER","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","EXPOSED VENT WAS TEMPORARILTY SECURED BY SHIP STAFF ON 23-DEC-2021. NEW VENT COVER FABRICATED BY SHORE WORKSHOP AND FITTED IN PLACE BY SHIP STAFF ON 05-JAN-2022.","2022-01-02T23:59:35","","Completed","2022-01-02T23:59:35","No","No","No","Internal"]
[null,null,null,23563,null,"127_13-Jan-22 13:38:40","2021-12-19T23:59:35","Defect","Ship Staff","Ship Staff Insp.","FIRE LINE LEAKING ABREAST NO4 AND NO 6 HATCH COVER PORT SIDE AFTER PANTING AND POUNDING MOVEMENTS OF VESSEL DURING HEAVY WEATHER.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","LEAKS REPAIRED BY SHIP STAFF. OLD DAMAGED / WORN OUT SECTION OF FIRE LINE CROPPED AND RENEWED. ","2021-12-27T23:59:35","","Completed","2021-12-19T23:59:35","No","No","No","Internal"]
[null,null,null,23564,null,"127_13-Jan-22 13:45:14","2021-12-21T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","BALLAST PUMP NO.2 SIEZED. FOUND IMPELLOR AND CASING RINGS JAMMED. ","E/R - Pumps","Cargo / Ballast Systems","Equipment Related","","","","","REQUESTED FOR SHORE SERVICE. SAME ARRANGED BY OFFCIE AT YANTAI, CHINA. NEW CASING RINGS AND BUSH BEARINGS FABRICATED. SHAFT AND IMPELLOR REPAIRED BY MACHINING AND FITTED BACK. PUMP TESTING WORKING SATISFACTORILY. ","2022-01-21T23:59:35","","Completed","2022-01-03T23:59:35","No","No","No","Internal"]
[null,null,null,23558,null,"127_13-Jan-22 13:03:40","2022-02-20T23:59:35","Defect","Ship Staff","Ship Staff Insp.","FISH ROOM TEV DEFECTIVE. SILICA GEL NEEDS REPLACEMENT","Accommodation","MLC Related","Equipment Related","","","","","RO FANT210195 RAISED /PARTLY RECEIVED. RO FANT220021 RAISED FOR TEV","2022-06-27T23:59:35","","Completed","2022-05-28T23:59:35","No","No","No","Internal","Both RO were supplied on board & vessel rectified the problem.  Please check vessel record & close out the defect accordingly."]
[null,null,null,21254,null,"127_9/28/2021 3:10:49 PM","2022-02-22T23:59:35","Breakdown","Owner / Marine / Tech. Suptd.","Engineering Audit","MOTOR OF FIRE AND BILGE PUMP SHORTED","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Motor replaced","2022-06-27T23:59:35","","Completed","2022-05-28T23:59:35","No","No","No","Internal","Kindly  mention action taken correctly, \"NOT IN USE\" is no action. Vessel can mention RO no if spares are in order. This job already completed, kindly close out."]
[null,null,null,26954,null,"127_Thu Sep 22 2022 06:13:28 GMT+0000","2022-04-13T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","Portable foam fire extinguisher in engine room - found not ready for use. Cans liquid foam-missing","","","","","","Fire safety","","","2022-04-14T23:59:35","","Completed","2022-04-19T23:59:35","No","No","No","External"]
[null,null,null,26955,null,"127_Thu Sep 22 2022 06:16:26 GMT+0000","2022-04-13T23:59:35","Non Conformity","PSC Insp.","PSC Inspection","Some old spare parts keep in Engine Room and not lashing properly. (Code 99)","","Eng. / Strg. Comp.","","","","Other","","","2022-05-13T23:59:35","","Completed","2022-04-19T23:59:35","No","No","No","External"]
[null,null,null,25749,43614,"127_Fri Jun 17 2022 18:43:13 GMT+0800","2022-05-29T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME LO Sump local gauge non operational","Hull & Tanks","Eng. / Strg. Comp.","Equipment Related","","","","","Completed by replacing the broken wire","2022-07-12T23:59:35","","Completed","2022-06-28T23:59:35","No","No","No","Internal","This job need to completed on priority & report to office."]
[null,null,null,25750,46427,"127_Thu Jun 16 2022 21:43:47 GMT+0800","2022-05-29T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Port Anchor Gear assembly back lash has excessive vibration and noise","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Anchor lower down 1mtr into water and found satisfactory","2022-07-27T23:59:35","","Completed","2022-06-28T23:59:35","No","No","No","Internal","Port anchor to lower till water level & heave up couple of time at suitable & safe anchorage. Report to office once done."]
[null,null,null,25755,38169,"0_Fri Jun 17 2022 19:07:46 GMT+0800","2022-05-29T23:59:35","Breakdown,Defect","Ship Staff","Ship Staff Insp.","Toilet Flushing valve of most of the cabin is non operational","Accommodation","MLC Related","Equipment Related","","","","","All defective valves renewed with new spares. Presently all the cabins flush are working ","2022-07-29T23:59:35","FANT220188","Completed","2022-07-21T23:59:35","No","No","No","Internal","Flush valves to fit & report to office asap."]
[null,null,null,25758,29636,"0_Fri Jun 17 2022 18:47:48 GMT+0800","2022-05-29T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","#2 DG L.O. pressure transmitter, JCW HT display sensors, ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Rectified by with the new spares supplied","2022-07-12T23:59:35","FANT220189, FANT220173","Completed","2022-06-23T23:59:35","No","No","No","Internal","Spares approved by owner & will be connected"]
[null,null,null,25759,88423,"0_Fri Jun 17 2022 18:52:12 GMT+0800","2022-05-29T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","ME LO Purifier non operational due to breakdown and no spares onboard","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Tried out and found working normal after adjusting operational parameters","2022-07-12T23:59:35","FANT220162","Completed","2022-06-30T23:59:35","No","No","No","Internal","Owner's arranged spares will be connected in Suez."]
[null,null,null,25761,87028,"0_Fri Jun 17 2022 19:02:12 GMT+0800","2022-05-29T23:59:35","Defect","Ship Staff","Ship Staff Insp.","HATCH COVER CLOSING AND OPENING ELECTRIC MOTOR in Poor condition","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Required maintenance of Oil renewal carried out for all the Motors. Motor cleaning and painting needs to be done by the Deck staffs.","2022-07-29T23:59:35","FANT220141","Completed","2022-07-19T23:59:35","No","No","No","Internal","Being connected at Suez around 22nd June 2022."]
[null,null,null,25751,14804,"0_Thu Jun 16 2022 21:55:32 GMT+0800","2022-06-07T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Fwd. Spring Mooring winch controller is not working.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","New controller installed and working fine","2022-06-27T23:59:35","FANT220202","Completed","2022-07-05T23:59:35","No","No","No","Internal","New controller is in order, will be connected vessel asap."]
[null,null,null,25757,43709,"0_Fri Jun 17 2022 19:15:56 GMT+0800","2022-06-11T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Waste Oil tank Overflow line choked","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Line opened and cleared. ","2022-06-27T23:59:35","","Completed","2022-06-19T23:59:35","No","No","No","Internal","Please clean the line & complete this job asap & report to office & update DDRL."]
[null,null,null,26113,16959,"127_Fri Jul 08 2022 01:42:07 GMT+0800","2022-06-19T23:59:35","Defect","Ship Staff","Ship Staff Insp.","#3 DG Speed Switch is faulty.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Both RPM pick up sensor and speed switch renewed","2022-07-13T23:59:35","FANT220206","Completed","2022-07-09T23:59:35","No","No","No","Internal","Please close out with detail as issue has been sorted out."]
[null,null,null,26121,79910,"0_Fri Jul 08 2022 02:24:23 GMT+0800","2022-06-29T23:59:35","Defect","Ship Staff","Ship Staff Insp.","No. 1 DG Circulating Pump Oil seal leaking.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Motor and Pump overhauled. Replaced mechanical & oil seal. Found working well","2022-07-29T23:59:35","FANT220244","Completed","2022-07-21T23:59:35","No","No","No","Internal","This can be PSC deficiency, kindly check the spare & overhaul asap."]
[null,null,null,26124,34269,"127_Fri Jul 08 2022 01:07:06 GMT+0800","2022-06-29T23:59:35","Defect","Ship Staff","Ship Staff Insp.","#2 DG LO sump low level alarm non operational","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Replaced the faulty switch and fault rectified.","2022-07-28T23:59:35","FANT220189","Completed","2022-07-14T23:59:35","No","No","No","Internal","Please renew the alarm switch asap & update office accordingly."]
[null,null,null,26956,null,"127_Thu Sep 22 2022 06:19:25 GMT+0000","2022-06-30T23:59:35","Observation","PSC Insp.","PSC Inspection","INTERNATIONAL TONNAGE CERTIFICATE has mistake with date on which keel was laid.","Documentation","Cert. & Docu.","","","","Certificates & Documentation",6,"","2022-09-30T23:59:35","","Completed","2022-07-10T23:59:35","No","No","No","External"]
[null,null,null,26957,null,"127_Thu Sep 22 2022 06:22:36 GMT+0000","2022-06-30T23:59:35","Observation","PSC Insp.","PSC Inspection","Main cooling SW pump has slight leak from gland","","","","","","Propulsion and auxiliary machinery",6,"","2022-09-30T23:59:35","","Completed","2022-07-10T23:59:35","No","No","No","External"]
[null,null,null,null,28309,"0_Sun Jul 24 2022 19:44:05 GMT+0800","2022-07-20T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Ballast Line Holed in ER","E/R - Pumps","Cargo / Ballast Systems","Equipment Related","","","","","Steel Plate insert done using Hot work after office concern","2022-09-29T08:00:00","","Completed","2022-08-30T08:00:00","No","No","No","Internal","Crop & renew this pipe otherwise weld insert asap. This can be cause PSC deficiency / detention of vessel."]
[null,null,null,null,66991,"127_Fri Jul 22 2022 22:00:19 GMT+0800","2022-07-17T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","#2 Prov. Ref compressor crank pin bearing metal squeezed out. Conrod bearing metal seating area damaged.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","COMPLETE OVERHAUL DONE AND TRIED OUT. IT IS IN USE WORKING SATISFACTORY. ","2022-09-29T08:00:00","FANT220231","Completed","2022-09-27T08:00:00","No","No","No","Internal","Spares are being arranged by owner, will liaise with owner supply team to connect spares asap."]
[null,null,null,null,44319,"0_Sun Jul 24 2022 19:04:32 GMT+0800","2022-07-14T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Not Possible to take DG Performance","E/R - Aux. Engine","Eng. / Strg. Comp.","Inappropriate Procedure","","","","","Indicator cock fixed on all DG. Performance taken. #3 DG #1 cock to be renewed as the hole is out of centre/","2022-08-30T08:00:00","","Completed","2022-09-23T08:00:00","No","No","No","Internal","Already under process, will endeavor to get this job done asap."]
[null,null,null,null,93591,"0_Sun Jul 24 2022 18:46:01 GMT+0800","2022-07-14T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Leaky main Fire Line on deck repaired with cold works ( 2 locations)","Deck - Pipe / Fittings","Safety / LSA / FFA","Equipment Related","","","","","4 section renewed and pressure tested","2022-08-30T08:00:00","","Completed","2022-09-01T08:00:00","No","No","No","Internal","Job to completed asap before arrival next port. Temporary repair on fire line is not acceptable at any standard. Both side of pipe full sleeve to weld as per class requireement."]
[null,null,null,null,58210,"0_Sun Jul 24 2022 20:29:38 GMT+0800","2022-07-10T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Incinerator is not firing due to improper operation of devices provided in the sludge line.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","W.O. pump overhauled. Faulty Pr. adjusting valve overhauled and working well","2022-08-30T08:00:00","","Completed","2022-08-23T08:00:00","No","No","No","Internal","Kindly update status of incinerator sludge pump asap to take necessary action."]
[null,null,null,null,11283,"127_Wed Jul 20 2022 20:56:49 GMT+0800","2022-07-09T08:00:00","Critical Equipment","Ship Staff","Ship Staff Insp.","#2 DG Speed Switch is fault at the feed signal short circuited.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Renewed with new spare. Working well","2022-08-30T08:00:00","FANT225043","Completed","2022-08-29T08:00:00","No","No","No","Internal","DG speed switch will be connected at China, kindly update once issue rectified."]
[null,null,null,null,70628,"0_Sun Jul 24 2022 19:59:50 GMT+0800","2022-07-03T08:00:00","Defect","Ship Staff","Ship Staff Insp.","#2 Fo purifier heater temp. controller inoperational.","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","Controller renewed. Purifier operation tried out found satisfactory. ","2022-08-30T08:00:00","","Completed","2022-08-29T08:00:00","No","No","No","Internal","Please update status of controller."]
[null,null,null,null,38812,"0_Sun Jul 24 2022 20:16:58 GMT+0800","2022-06-30T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Often ER door not closing automatically due to deformation of door and frame","Miscellaneous","Structural Condn. / WT integrity ","Equipment Related","","","","","Packing renewed. Hyd. closure adjusted.  After Air-condition broken ducts repaired, All the doors are working fine. ","2022-09-29T08:00:00","","Completed","2022-09-26T08:00:00","No","No","No","Internal","Kindly send current update on door status."]
[null,null,null,null,59884,"127_Sat Jul 23 2022 22:55:41 GMT+0800","2022-06-30T08:00:00","Non Conformity","Ship Staff","Ship Staff Insp.","ME Overspeed happens at 85.7 RPM after power limitation , which is limited maximum RPM. (over speed RPM must be more than this)","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Confirmed setting as per office / service technician recommendation. Found all in order. Reason might be propellor coming out from the water","2022-08-30T08:00:00","","Completed","2022-08-15T08:00:00","No","No","No","Internal","Following up with maker."]
[null,null,null,null,58955,"0_Sun Jul 24 2022 18:56:06 GMT+0800","2022-06-30T08:00:00","Defect","Ship Staff","Ship Staff Insp.","#5 unit water leak from Jacket bolt","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Overhauled by shore technician when the Vsl. calls singapore in Sept'22. No more leaks.","2022-08-30T08:00:00","","Completed","2022-09-15T08:00:00","No","No","No","Internal","Kindly update on the renewal of cylinder head jacket o-ring renewal."]
[null,null,null,null,81689,"0_Sun Jul 24 2022 18:38:10 GMT+0800","2022-06-30T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Heavy boxes and items kept near Engine room workshop and near No 5 FOT (S) not secured","Miscellaneous","Eng. / Strg. Comp.","Human Error","","","","","Most of the items shifted to Spare room. Few more items to be lashed properly. Hot work done, made clamps after getting office concern. ","2022-08-30T08:00:00","","Completed","2022-08-01T08:00:00","No","No","No","Internal","Kindly update on spare parts shifting & securing in place."]
[null,null,null,null,54257,"0_Fri Jul 22 2022 22:17:42 GMT+0800","2022-06-30T08:00:00","Observation","Ship Staff","Ship Staff Insp.","FO jet filter & DG FO Secondary filter not in use and the condition unknown.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Filter cleaned, control system confirmed put in use.","2022-08-30T08:00:00","","Completed","2022-09-01T08:00:00","No","No","No","Internal","Kindly try out jet filter & advise status asap."]
[null,null,null,null,56837,"0_Fri Jul 08 2022 02:21:19 GMT+0800","2022-06-29T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","DG LO Purifier not working.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Complete overhauling done and spare renewed. Tried out . working satisfactory.","2022-08-30T08:00:00","FANT220219","Completed","2022-09-03T08:00:00","No","No","No","Internal","Please follow up in separate message once inspection & troubleshooting carried out."]
[null,null,null,null,75845,"127_Fri Jul 08 2022 01:26:30 GMT+0800","2022-06-27T08:00:00","Defect","Ship Staff","Ship Staff Insp.","NO 2 DG C.W. BYPASS VALVE BODY FLANGE BROKEN. AND VALVE LEAKING FROM TALE TALE HOLE.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Valve renewed","2022-08-30T08:00:00","FANT220211","Completed","2022-09-01T08:00:00","No","No","No","Internal","RO supplied on board at Taicang, China, kindly update & close out accordingly."]
[null,null,null,null,59666,"0_Fri Jul 08 2022 01:46:54 GMT+0800","2022-06-20T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Forward Horn Solenoid valve is faulty. Presently not usable.","Deck - Machinery","Navigation","Equipment Related","","","","","Solenoid valve renewed and made operational.","2022-08-30T08:00:00","FANT220207","Completed","2022-08-29T08:00:00","No","No","No","Internal","RO already connected to vessel at Taicang, kindly carry out the job & update DDRL accordingly."]
[null,null,null,null,46593,"0_Fri Jul 08 2022 02:29:37 GMT+0800","2022-06-13T08:00:00","Defect","Ship Staff","Ship Staff Insp.","All FOT Heating steam coil Valves to renew","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","All the valves renewed and FOT heating coil pressure tested. Found normal. ","2022-08-30T08:00:00","FANT220219","Completed","2022-09-04T08:00:00","No","No","No","Internal","RO already connected to vessel at Taicang, kindly complete the job & DDRL accordingly."]
[null,null,null,null,59567,"0_Fri Jul 08 2022 02:16:23 GMT+0800","2022-06-13T08:00:00","Defect","Ship Staff","Ship Staff Insp.","FWG JCW Inlet and Bypass valve Frozen.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","ME JCW system valves replaced with good spare. Working good. ","2022-08-30T08:00:00","","Completed","2022-08-25T08:00:00","No","No","No","Internal","Please get this job done & update DDRL accordingly."]
[null,null,null,null,15712,"0_Fri Jul 08 2022 02:05:32 GMT+0800","2022-05-30T08:00:00","Defect","Ship Staff","Ship Staff Insp.","DG FO temp controller not accurate","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Renewed with Spare controller. ","2022-08-30T08:00:00","FANT225033","Completed","2022-08-30T08:00:00","No","No","No","Internal","Please complete the job & update accordingly."]
[null,null,null,null,76839,"0_Fri Jul 08 2022 01:56:26 GMT+0800","2022-05-30T08:00:00","Critical Equipment","Ship Staff","Ship Staff Insp.","Emergency Fire Pump Mechanical seal is not in good condition.","Critical Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Pump overhauled  and all parts renewed. ","2022-08-30T08:00:00","FANT220183","Completed","2022-09-28T08:00:00","No","No","No","Internal","Vessel already complete the job, kindly update DDRL."]
[null,null,null,null,96727,"0_Fri Jun 17 2022 18:55:15 GMT+0800","2022-05-29T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Accommodation AC performance is not satisfactory","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","",""," Evaporator coil renewed and system tested by shore technician in Port Constanta","2022-08-30T08:00:00","FANT220185","Completed","2022-09-22T08:00:00","No","No","No","Internal","New evaporator coil is being supplied by owner. Most likely same will be connected at Suez next call."]
[null,null,null,null,23869,"0_Fri Jun 17 2022 18:59:23 GMT+0800","2022-05-29T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","Hatch cover Hyd. Jacks 2 nos are non operational.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","All Jacks renewed and the status has been sent","2022-08-30T08:00:00","FANT220142","Completed","2022-09-26T08:00:00","No","No","No","Internal","We are trying to connect 8 nos new electro-jacks at China or Singapore. Kindly complete the job & update DDRL accordingly"]
[null,null,null,null,12541,"0_Thu Jun 16 2022 23:11:17 GMT+0800","2022-05-29T08:00:00","Defect","Ship Staff","Ship Staff Insp.","FWG Distillate pump is incapable of discharging into the filling line.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Motor and Pump renewed.","2022-10-30T08:00:00","FANT220201","Completed","2022-08-26T08:00:00","No","No","No","Internal","RO already supplied on board vessel, kindly complete the job & close out the DDRL."]
[null,null,null,null,19608,"0_Sun Jul 24 2022 19:15:15 GMT+0800","2022-07-02T08:00:00","Observation","Ship Staff","Ship Staff Insp.","#6 unit Decarb due to ring gap over limit. Onboard Spare Piston crown ring gap measurement is also out of limit","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Completed complete overhaul of unit and engine performance noted satisfactory","2022-12-30T08:00:00","FANT220222 / FANT220223","Completed","2022-10-06T08:00:00","No","No","No","Internal","Spare crown already connected at Singapore. Vessel to carry out the job at the earliest convenient port."]
[null,null,null,null,55989,"0_Fri Jul 08 2022 01:36:41 GMT+0800","2022-06-29T08:00:00","Defect","Ship Staff","Ship Staff Insp.","#2 Feed Pump abnormal alarm due to malfunction of the relay. No Electrical spares and Timer.  Also Quick coupling and its o ring on the boiler burner is leaking.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Trouble shooting cared out. For repairs Main engine should be in stopped condition as the Main engine slowdown alarm is also incorporated in the same alarm circuit as of feed pump. Power shut down of AMS to renew burnt UDI01 card and cleaned all cards. One used  spare UD101 card handed over to Elect Supt Mr. Sajeesh Prabhakaran","2023-01-31T08:00:00","FANT220215  Received","Completed","2023-01-31T08:00:00","No","No","No","Internal","RO FANT 220215 is under process, will be connected at NPOC."]
[null,null,null,null,81649,"0_Fri Jul 08 2022 02:10:39 GMT+0800","2022-05-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","ECR alarm Printer fault","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Requisition made for complete unit. Spare not yet received. \nBEMAC technician attended at ASL shipyard ,Batam . Printer paper feeder adjusted and old printer is presently functioning properly.","2023-02-28T08:00:00","FANT220278","Completed","2023-02-22T08:00:00","No","No","No","Internal","Already supplied to vessel, kindly confirm & close out the DDRL."]
[null,null,null,null,52768,"0_Thu Jun 16 2022 22:02:35 GMT+0800","2022-05-29T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Oxygen and Acetylene Flash back arrestor renewal date not available. It Should be less than 5 years","E/R - Aux. Mach.","ISM Related","Equipment Related","","","","","No history found. Vessel has raised PO for supply of flash arrestors with certificate as present ones are leaking..\nall regulators and flash arrester renewed with new spares","2023-01-31T08:00:00","FANT230014","Completed","2023-01-31T08:00:00","No","No","No","Internal","Need to check supply history during vessel take over. Please check & confirm accordingly."]
[null,null,null,null,60393,"127_Mon Dec 19 2022 17:54:53 GMT+0800","2022-11-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Main sea water pump No.2 & No.1stern tube L.O  Pump Standby function non operational","Elect. Mach. & Equip.,E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Trouble shooting carried out. Standby switches defective. RO raised.\nTimer setting adjusted by BEMAC technician . pumps are functioning normal","2023-02-07T08:00:00","FANT220363","Completed","2023-02-22T08:00:00","No","No","No","Internal"]
[null,null,null,null,82810,"0_Fri Jun 17 2022 19:11:31 GMT+0800","2022-05-29T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Bridge Split AC non operational","Accommodation","MLC Related","Equipment Related","","","","","Spare received . Spare spilt indoor unit  received fitted by shore workshop. Presently functional.","2023-02-28T08:00:00","Office to arrange","Completed","2023-02-22T08:00:00","No","No","No","Internal","Technician attended vessel at at Paradip found Split AC compressor blown off.  110v Split AC not readily available. Will try to arrange supply once vessel will be back to Singapore or China."]
[null,null,null,null,93094,"0_Fri Jun 17 2022 19:05:00 GMT+0800","2022-05-29T08:00:00","Defect","Ship Staff","Ship Staff Insp.","5P FO Bunker filling line has pin hole.","Deck - Pipe / Fittings","MARPOL Related","Equipment Related","","","","","It is added to REFMAN with details of Job scope. Plan has been made and sent to the office reg. renewal of pipe lines. \nPipe renewed after making tank gas free by yard staff at ASL shipyard Batam","2023-04-01T08:00:00","","Completed","2023-01-15T08:00:00","No","No","No","Internal","Ship staff to check for feasibility of Permanent repair & report to office in separate message, otherwise please transfer this job to DD. DD spec to make in REFMAN with all detail job scope."]
[null,null,null,null,62955,"127_Mon Dec 19 2022 19:24:22 GMT+0800","2022-12-01T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Aux booiler burner FO  temperature control faulty","Elect. Mach. & Equip.,E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Presently FO temperature adjusted manually.\nSpares received  and renewed. FO heater temperature controller is functioning properly","2023-03-01T08:00:00","FANT220304","Completed","2023-02-02T08:00:00","No","No","No","Internal"]
[null,null,null,null,89153,"127_Sun Jan 15 2023 16:18:27 GMT+0800","2023-01-14T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Calorifier tank leaking badly from different points around the tank. Material failure. Currently no Hot water Supply in accommodation and may pose an MLC Deficiency.","Accommodation","Eng. / Strg. Comp.","Equipment Related","","","","","Vessel staff patched with steel putty, and coated with cement. Tank leaking  due to thermal stress  and material wastage. PO raised\nNew calorifier fitted and functioning properly","2023-02-28T08:00:00","FANT 230014","Completed","2023-03-01T08:00:00","No","No","No","Internal"]
[null,null,null,null,87296,"127_Sun Jan 15 2023 19:31:59 GMT+0800","2022-12-26T08:00:00","Defect","Ship Staff","Ship Staff Insp.","#2 hatch cover drive motor for opening and closing hatch covers, defective and requires replacement.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Motor replaced with new motors for No.1 and no.2 hatch covers. (Supplied motors are of 190V DC brakes. same modified after informing office) Motors are presently functional","2023-02-28T08:00:00","","Completed","2023-02-10T08:00:00","No","No","No","Internal"]
[null,null,null,null,86460,"127_Sun Jan 15 2023 20:03:30 GMT+0800","2023-01-15T08:00:00","Other","Ship Staff","Ship Staff Insp.","Save all trays' plating has thinned down.","Miscellaneous","","","","","","","Thinned down sections cropped and renewed.","2023-04-15T08:00:00","","Completed","2023-02-27T08:00:00","No","No","No","Internal"]
[null,null,null,null,55575,"127_Sun Jan 15 2023 20:02:04 GMT+0800","2023-01-15T08:00:00","Other","Ship Staff","Ship Staff Insp.","Accommodation block's drain pipe are corroded at various locations.","Deck - Pipe / Fittings","","","","","","","Wasted drain pipes cropped and renewed.","2023-04-15T08:00:00","","Completed","2023-02-26T08:00:00","No","No","No","Internal"]
[null,null,null,null,53674,"127_Sun Jan 15 2023 20:00:25 GMT+0800","2023-01-08T08:00:00","Defect","Ship Staff","Ship Staff Insp.","#3 hatch cover, starboard panel, aft inboard wheel, wobbling.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Bush bearing changed.","2023-03-08T08:00:00","","Completed","2023-01-20T08:00:00","No","No","No","Internal"]
[null,null,null,null,42932,"127_Sun Jan 15 2023 19:57:28 GMT+0800","2022-12-05T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Forward port side mooring winch, end shaft bush bearing pillar fitted 180 degrees the wrong way.\nThis causes the shift of the shaft during operation.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Complete overhaul of the port winch assembly.\nClaw coupling renewed.","2024-03-15T08:00:00","","Completed","2023-02-27T08:00:00","Yes","No","No","Internal"]
[null,null,null,null,97217,"127_Sun Jan 15 2023 19:52:42 GMT+0800","2023-01-12T08:00:00","Critical Equipment,Defect","Ship Staff","Ship Staff Insp.","Fire line leaking on the main deck.","Critical Equip.","Safety / LSA / FFA","","","","","","Thinned down areas identified, cropped and renewed.","2023-04-12T08:00:00","","Completed","2023-02-18T08:00:00","No","No","No","Internal"]
[null,null,null,null,90008,"127_Sun Jan 15 2023 19:49:00 GMT+0800","2023-01-10T08:00:00","Breakdown,Defect","Ship Staff","Ship Staff Insp.","The junction where the anchor wash pipelines meet the hawse pipe observed to be cracked and fractured.\nCausing water to leak into the forecastle store when the port side anchor wash is used.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","External Factors","","","","","Wasted section of the pipelines cropped and renewed.","2023-02-28T08:00:00","","Completed","2023-02-14T08:00:00","No","No","No","Internal"]
[null,null,null,null,65387,"127_Sun Jan 15 2023 19:45:50 GMT+0800","2023-01-15T08:00:00","Other","Ship Staff","Ship Staff Insp.","Bridge wing undersides, paint peeling off and fittings rusted.","Accommodation","","External Factors","","","","","De-rusting and paint application with a compatible paint carried out.","2023-04-15T08:00:00","","Completed","2023-02-25T08:00:00","No","No","No","Internal"]
[null,null,null,null,57104,"127_Sun Jan 15 2023 19:41:24 GMT+0800","2022-12-26T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Mooring station pedestals wasted and some sections sheared off during heavy weather.","Miscellaneous","Structural Condn. / WT integrity ","External Factors","","","","","Pedestals renewed and strengthened. ","2023-03-15T08:00:00","","Completed","2023-02-13T08:00:00","No","No","No","Internal"]
[null,null,null,null,24019,"127_Sun Jan 15 2023 19:28:27 GMT+0800","2022-12-26T08:00:00","Breakdown,Critical Equipment","Ship Staff","Ship Staff Insp.","Forward mooring winch motors and control stands as water logged and inoperational.\nCaused due to heavy weather.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Mooring winches restored to operational condition.\nProtective covers fabricated and fitted.","2023-01-31T08:00:00","","Completed","2023-02-27T08:00:00","No","No","No","Internal"]
[null,null,null,null,24728,"127_Sun Jan 15 2023 19:23:44 GMT+0800","2022-11-25T08:00:00","Critical Equipment,Defect","Ship Staff","Ship Staff Insp.","Port anchor chain thinned down.\nSlipping when hoisting.","Critical Equip.,Deck - Mooring Machinery","Mooring","Equipment Related","","","","","The thinned down length renewed.\nTotal length of the cable renewed - three shackles.","2025-01-01T08:00:00","","Completed","2023-02-18T08:00:00","No","No","No","Internal"]
[null,null,null,null,31025,"127_Mon Dec 19 2022 17:10:22 GMT+0800","2022-12-14T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp."," Numerous roller covers at Forecastle found corroded.","Deck - Mooring Machinery","Structural Condn. / WT integrity ","Equipment Related","","","","","Wasted roller covers cropped and renewed.","2023-03-14T08:00:00","","Completed","2023-02-19T08:00:00","No","No","No","Internal"]
[null,null,null,null,86168,"127_Sun Jan 15 2023 20:05:07 GMT+0800","2023-01-15T08:00:00","Other","Ship Staff","Ship Staff Insp.","Accommodation block front, flaking paint.","Accommodation","","","","","","","The flaking paint removed, de-rusting done as and where needed followed by application of compatible paint. ","2023-04-15T08:00:00","","Completed","2023-02-17T08:00:00","No","No","No","Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["127","FANTASEA (13-08-2022)","127_1664159962749.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]