{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":23,"n_cols":28,"rows_kept":23,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","06-Sep-2023",null,null,"Ship Name","NATTY (28-03-2023)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,82923,"128_Thu Jun 16 2022 05:11:37 GMT+0800","2023-04-25T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Three way change over valve actuator of fuel oil inlet and return line for all three generator engine and main engine are not connected","E/R - Main Engine,E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Made RO , three way change over valves actuator checked , and found to be sluggish , same has been taken out from DG , required spare parts for overhauling is not on board , required parts inventory and requisition will be updated soon ft RO ","2023-09-30T08:00:00","NATT230080-SOLENOID VALVES FOR A/E ( DG ) FUEL REMOTE CHANGE OVER VALVES","Waiting spare",null,"No","No","No","Internal","Investigation to be done on priority & follow up with office via separate message."]
[null,null,null,null,21181,"128_Tue Jan 17 2023 08:50:56 GMT+0800","2023-01-12T08:00:00","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both ballast pump vacuum unit non operational ","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","We received only one float switch and was installed in #2 ballast pump. Second float switch received in singapore was of different arrangement and needs fabrication to accommodate in existing arrangement.","2023-09-30T08:00:00","NATT230048 RAISED FOR SPARE PARTS , MOST OF THE PARTS RECIEVED EXCEPT THE FLOAT SWITCHES ","In progress",null,"No","No","No","Internal","Both main ballast pump vacuum unit to check and report to office further follow up & make operational "]
[null,null,null,null,45680,"128_Tue Jan 17 2023 08:56:20 GMT+0800","2023-01-12T08:00:00","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All 3 auxiliary engine fuel oil change over valves not operational in auto mode ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","RO NATT230080 raised ,  All fuel change over valves pneumatic motors overhauled and cleaned , fresh grease applied for smooth operation , directional vv function checked , 3- way vv found very tight too . ","2023-09-30T08:00:00","NATT230080","Waiting spare",null,"No","No","No","Internal","change over valve auto mode operation to check and investigate , report to office for further follow up "]
[null,null,null,null,28760,"0_Wed Jan 18 2023 12:08:42 GMT+0800","2023-01-12T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Most of the hatch cover cleats found seized, same to overhaul & new rubber washer ( lying in forward stores to be fitted. Presently all the rubber washers are painted. \" RUBBER WASHER NOT TO BE PAINTED)","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Behaviour Based,Knowledge Based","","","","","Vessel will continue work of freeing/painting of remaining cleats of No.6 Cargo hold after Discharging/Hold washing completion. ","2023-09-30T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,75823,"0_Wed Jan 18 2023 13:13:23 GMT+0800","2023-01-12T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ALL HYDRAULIC JACK CYLINDERS FOR HC IN RUSTED CONDITION.","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related","","","","","Vessel planed to start after discharge port/hatch cleaning de-rusting & painting work of Hydraulic jack cylinders. target to complete by 30 Sept 2023.","2023-09-30T08:00:00","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,23109,"128_Fri Aug 11 2023 13:35:43 GMT+0800","2023-08-11T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Bunkering Audit","Magnetic float type level gauge for Serv Tk #2 is not operational.","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Magnetic float gauge to be removed and cleaned","2023-09-30T08:00:00","","Not Started",null,"No","No","No","Internal"]

{"sheet":"Completed","index":1,"n_rows":125,"n_cols":28,"rows_kept":125,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","06-Sep-2023",null,null,"Ship Name","NATTY (28-03-2023)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,26946,null,"128_Thu Sep 22 2022 05:24:01 GMT+0000","2022-01-19T23:59:35","Observation","PSC Insp.","PSC Inspection","Gangway, accommodation- Iadder GANGWAY SAFETY NET-NOT PROPERLY INSTALLED","","","","","","Other","","","2022-03-28T23:59:35","","Completed","2022-02-22T23:59:35","No","No","No","External"]
[null,null,null,26947,null,"128_Thu Sep 22 2022 05:26:43 GMT+0000","2022-01-19T23:59:35","Observation","PSC Insp.","PSC Inspection","Fire fighting equipment and appliances1FIRE FIGHTING UHF MISSING IMO SYMBOL","","Safety / LSA / FFA","","","","Fire safety","","","2022-03-28T23:59:35","","Completed","2022-02-22T23:59:35","No","No","No","External"]
[null,null,null,26948,null,"128_Thu Sep 22 2022 05:29:07 GMT+0000","2022-01-19T23:59:35","Observation","PSC Insp.","PSC Inspection","Fire control plan FlRE CONTROL PLAN REQUIRED FOR\nCORRECTION.","","Safety / LSA / FFA","","","","Fire safety","","","2022-03-28T23:59:35","","Completed","2022-02-22T23:59:35","No","No","No","External"]
[null,null,null,26949,null,"128_Thu Sep 22 2022 05:33:48 GMT+0000","2022-01-19T23:59:35","Observation","PSC Insp.","PSC Inspection","Magnetic compass/DEVIATION TABLE FOR SHIP DS CHARME REQUIRED FOR RENEWAL.","","Navigation","","","","Safety of Navigation","","","2022-03-28T23:59:35","","Completed","2022-02-22T23:59:35","No","No","No","External"]
[null,null,null,26950,null,"128_Thu Sep 22 2022 05:35:27 GMT+0000","2022-01-19T23:59:35","Observation","PSC Insp.","PSC Inspection","Electronic charts (ECDIS) ABORT POINT, ANCHORAGE NOT MARKED IN APPROACH","Navigation - ECDIS","Navigation","","","","Safety of Navigation","","","2022-03-28T23:59:35","","Completed","2022-02-22T23:59:35","No","No","No","External"]
[null,null,null,26952,null,"128_Thu Sep 22 2022 05:41:51 GMT+0000","2022-01-19T23:59:35","Observation","PSC Insp.","PSC Inspection","Compass error Iog COMPASS OBSERVATION MADE NOT EVERY WATCH.","","","","","","Safety of Navigation","","","2022-01-30T23:59:35","","Completed","2022-01-22T23:59:35","No","No","No","External"]
[null,null,null,26953,null,"128_Thu Sep 22 2022 05:43:36 GMT+0000","2022-01-19T23:59:35","Observation","PSC Insp.","PSC Inspection","Lights, shapes, sound Signalsl BATTERY FOR ALDIS LAMP REQUIRED FOR CHARGING.","","","","","","Safety of Navigation","","","2022-03-28T23:59:35","","Completed","2022-02-22T23:59:35","No","No","No","External"]
[null,null,null,26951,null,"128_Thu Sep 22 2022 05:37:09 GMT+0000","2022-01-20T23:59:35","Observation","PSC Insp.","PSC Inspection","Compass error Iog COMPASS OBSERVATION MADE NOT EVERY WATCH.","Navigation - Others","Navigation","","","","Safety of Navigation","","","2022-03-29T23:59:35","","Completed","2022-02-23T23:59:35","No","No","No","External"]
[null,null,null,29369,83208,"128_Wed Mar 08 2023 19:35:46 GMT+0800","2022-01-21T23:59:35","Observation","PSC Insp.","PSC Inspection","NAUTICAL PUBLICATIONS/ ITU CD, PSC PROCEDURES, IMDG CODE, LOADLINE,  OLD EDITION","Navigation - Others","Navigation","Human Error","","","",6,"New Publication Ordered and received onboard","2022-03-30T23:59:35","","Completed","2022-02-24T23:59:35","No","No","No","External"]
[null,null,null,29364,62550,"128_Wed Mar 08 2023 06:21:28 GMT+0800","2022-01-30T23:59:35","Observation","Ship Staff","Nav Audit / Verification","FEW PUBLICATIONS ONBOARD ARE OLD EDITION","Navigation - Others","Navigation","Human Error","","","","","ON BOARD INVENTORY WITH EDITION DATE SENT TO NAVTOR. LATEST EDITION RECEIVED ONBOARD.","2022-03-30T23:59:35","","Completed","2022-02-27T23:59:35","No","No","No","Internal"]
[null,null,null,29365,42659,"128_Wed Mar 08 2023 06:26:03 GMT+0800","2022-01-30T23:59:35","Observation","Ship Staff","Nav Audit / Verification","APCF NOT ONBOARD AS PER COMPANY REQUIREMENTS","Navigation - Others","Navigation","","","","","","VESSEL TAKENOVER FROM ANOTHER MANAGEMENT,  REQUESTED FOR APCF . AWAITING SUPPLY","2022-03-30T23:59:35","","Completed","2022-02-27T23:59:35","No","No","No","Internal"]
[null,null,null,25906,96371,"128_Thu Jun 16 2022 06:09:25 GMT+0800","2022-04-11T23:59:35","Defect","Ship Staff","Ship Staff Insp.","MAIN ENGINE UNIT NO 6 EXHAUST TEMPERATURE SENSOR OUTPUT COMMUNICATION ERROR . EXHAUST DEVIATION SLOWDOWN CANCELLED.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","NO.6 UNIT EXHAUST TEMP INDICATION RECTIFIED BY REPLACING THE COMBINED SENSOR.","2022-08-15T23:59:35","","Completed","2022-05-21T23:59:35","No","No","No","Internal"]
[null,null,null,25892,26829,"128_Thu Jun 16 2022 06:00:15 GMT+0800","2022-05-01T23:59:35","Defect","Ship Staff","Ship Staff Insp.","A/E NO 1 NOT OPERATIONAL DUE TO DAMAGED FLYWHEEL RIM, AIR MOTOR & PINION . AIR START SOLENOOID VALVE ALSO NON-OPERATIONAL","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","SPARES RECEIVED AND AE NO 1 IN OPERATION.","2022-07-29T23:59:35","","Completed","2022-06-27T23:59:35","No","No","No","Internal"]
[null,null,null,25890,76798,"128_Thu Jun 16 2022 05:28:43 GMT+0800","2022-05-08T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Spare parts room and Engine room store area, require housekeeping.","Miscellaneous","Eng. / Strg. Comp.","Human Error","","","","","COMPLETED. BUT THE SPARE AND STORE AREA NEED TO BE MAINTAINED ON CONTINUOUS BASIS.","2022-08-05T23:59:35","","Completed","2022-07-31T23:59:35","No","No","No","Internal","Need photograph of stores / spare parts room on weekly basis."]
[null,null,null,25885,77249,"128_Thu Jun 16 2022 13:31:07 GMT+0800","2022-05-12T23:59:35","Other","Ship Staff","Ship Staff Insp.","HATCH COVER HYD RAM LEAKING 2 AFT","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","COMPLETED.","2022-08-12T23:59:35","","Completed","2022-08-07T23:59:35","No","No","No","Internal","Please renew the ram asap & report to office. This can be PSC detention deficiency."]
[null,null,null,25904,62087,"128_Thu Jun 16 2022 10:18:14 GMT+0800","2022-05-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","HATCH COVER HYD RAM LEAKING NO.2 FWD RAM,","Deck - Machinery","MARPOL Related","External Factors","","","","","NO.2 FWD RAM RENEWED.","2022-08-14T23:59:35","","Completed","2022-05-18T23:59:35","No","No","No","Internal"]
[null,null,null,25905,63360,"128_Tue Jun 21 2022 06:02:12 GMT+0800","2022-05-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","BOILER ALARM AND SIGNAL CONTROL PANEL  AND COMMUNICATION WITH ECR CONTROL PANEL FOUND FAULTY.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","boiler technician came and programmed the PLC after that all alarm working in ams and hmi panel.","2022-08-13T23:59:35","","Completed","2022-06-08T23:59:35","No","No","No","Internal"]
[null,null,null,25880,98548,"128_Thu Jun 16 2022 04:59:52 GMT+0800","2022-05-16T23:59:35","Critical Equipment","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Emergency fire pump discharge pressure was at 7.0 bar, but no water discharge from forecastle fire hose.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","TRIED OUT WITH ANCHOR WASH CLOSED. GOT DISCHARGE AT FORECASTLE DECK. TESTED IN PRESENCE OF FSI AS WELL. AWAITING SPARES TO CARRY OUT COMPLETE OVERHAUL TO FURTHER IMPROVE PERFOMANCE.","2022-08-14T23:59:35"," RO -NATT220033","Completed","2022-08-04T23:59:35","No","No","No","Internal","Please investigate the reason no water will discharge when pump building up 7 bar pressure. Spares arranged by owner & we are pushing them to connect at Algeciras."]
[null,null,null,25901,71447,"128_Tue Jun 21 2022 05:53:26 GMT+0800","2022-05-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","mac 1 aft unit piston and liner seized found damaged piston scracthed liner, piston and piston rings damaged.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Aft unit of Mac 1  replaced with new liner and rings. Found fwd unit blowpast as well. MAC not building pressure . Require another liner block to make the compressor operational. MAC 1 FWD UNIT LINER REPLACED WITH SPARES RECEIVED. PISTON PIN O RING ALSO RENEWED. NO BLOWPAST NOW. COMPRESSOR WORKING ON AUTO.","2022-09-26T23:59:35","RO NO NATT220160.","Completed","2022-09-05T23:59:35","No","No","No","Internal","Trying to connect but long delivery time for the spares from Japan. Spares connected & vessel has completed the job. Please update in DDRL & close out."]
[null,null,null,25902,17015,"128_Fri Jun 24 2022 15:57:31 GMT+0800","2022-06-04T23:59:35","Defect","Ship Staff","Ship Staff Insp.","MAIN EGINE EXHAUST TEMPERATURE INDICATION FOR UNIT 1 NOT WORKING. HENCE EXHAUST DEVIATION SLOWDOWN CANCELLED.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","COMBINED SENSOR AND AMPLIFIER RECEICVED. BOTH RECEIVED WRONG SUPPLY. INFORMED OFFICE AND OWENRS' SUPPLY DEPT. AWAITING OWNER SIDE SUPPLY DEPT REVERT ON THIS. FOR NOW ADJUSTED TEMPERATURE RANGE OF AMPLIFIER TO GET SOME APPROXIMATED EXH VALUES ON ECR AMS.. STILL WOULD REQUIRE GENUINE SENSORS AND AMPLIFIER FOR A RELIABLE INDICATION.","2022-10-03T23:59:35","RO NO NATT220135.","Completed",null,"No","No","No","Internal","Correct spec of amplifier will be connected at next port of call"]
[null,null,null,25898,36558,"0_Thu Jun 16 2022 21:47:27 GMT+0800","2022-06-09T23:59:35","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Booby hatches heavily rusted","Deck - Pipe / Fittings","Cargo / Ballast Systems","Human Error","","","","","UPGRADATION IN PROGRESS. MANY AREAS FINISHED. NEED TO CONTINUE THE JOB.","2022-08-09T23:59:35","","Completed","2022-08-06T23:59:35","No","No","No","Internal","Vessel is in long voyage to Brazil, all booby hatches should be completed."]
[null,null,null,25893,50224,"0_Thu Jun 16 2022 15:03:58 GMT+0800","2022-06-28T23:59:35","Other","Ship Staff","Ship Staff Insp.","NO.7 hatch cover fwd  Hydraulic ram leakihg","Deck - Machinery","MARPOL Related","Equipment Related","","","","","RAM REPLACED","2022-09-27T23:59:35","","Completed","2022-08-29T23:59:35","No","No","No","Internal","Please raise RO for ram seal repair kit immediately."]
[null,null,null,25894,86053,"128_Thu Jun 16 2022 19:32:44 GMT+0800","2022-06-28T23:59:35","Other","Ship Staff","Ship Staff Insp.","HATCH COVER DRIVE MOTOR OF NO .2  PORT /STBD IS  LEAKING","Deck - Machinery","MARPOL Related","Equipment Related","","","","","2 STARBOARD MOTOR RENEWED AS BODY DAMAGED. \nSPARE MOTOR RECEIVED WILL PLAN RENEWAL AFTER DISCHARGE PORT.","2022-09-27T23:59:35","","Completed","2022-08-29T23:59:35","No","No","No","Internal","As informed vessel to raise RO for HC motor's gear box to make one complete hyd motor. Also the old one to off land for repair at Singapore."]
[null,null,null,25895,23663,"0_Thu Jun 16 2022 19:37:22 GMT+0800","2022-06-28T23:59:35","Other","Ship Staff","Ship Staff Insp.","HATCH COVER DRIVING MOTOR NO.4 PORT/STBD LEAKING","Deck - Pipe / Fittings","MARPOL Related","Equipment Related","","","","","Renewed with new motor","2022-09-27T23:59:35","","Completed","2022-08-29T23:59:35","No","No","No","Internal","Is there any RO raised by vessel? If not kindly raise RO with detail reason of asking the spares."]
[null,null,null,25900,17063,"0_Thu Jun 16 2022 22:08:55 GMT+0800","2022-06-28T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Hacth cover control lever union leaking for hatch no.2","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","",""," Renewed the bloc","2022-09-27T23:59:35","","Completed","2022-09-02T23:59:35","No","No","No","Internal","No reason this job kept under pending, kindly rectify & complete the job."]
[null,null,null,25881,88147,"128_Thu Jun 16 2022 05:08:14 GMT+0800","2022-07-11T23:59:35","Observation","Ship Staff","Ship Staff Insp.","SCBA COMPRESSOR FONDATION TO BE MADE.","Critical Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","COMPLETED.","2022-10-08T23:59:35","","Completed","2022-09-28T23:59:35","No","No","No","Internal","Noted this job already planned, please attend same at the earliest."]
[null,null,null,25903,86908,"128_Fri Jun 24 2022 16:01:33 GMT+0800","2022-07-29T23:59:35","Defect","Ship Staff","Ship Staff Insp.","AE 1 STARTING AIR LINE SPECIAL FLEXIBLE HOSE (MAKER SUPPY) BADLY DAMAGED.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","SPARE HOSE CONNECTED AT PORT CARTIER. SAME USED TO RENEW THE HOSE. PROBLEM RECTIFIED.","2022-10-27T23:59:35","NATT220172","Completed","2022-09-27T23:59:35","No","No","No","Internal","Spares to connect at Suez around 16th Oct 2022."]
[null,null,null,25897,99989,"0_Thu Jun 16 2022 21:07:26 GMT+0800","2022-08-04T23:59:35","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Deck rusted","Miscellaneous","Structural Condn. / WT integrity ","Human Error","","","","","upgradation in progress. Lot of areas de-rusted and painted after making hydro-blaster operational but Need to continue to the job.","2023-02-13T23:59:35","","Completed",null,"No","No","No","Internal","Need to make the Falch hydro blaster operational asap. Please check the require spares on board & raise requisition accordingly."]
[null,null,null,29367,48263,"128_Wed Mar 08 2023 19:44:35 GMT+0800","2022-08-15T23:59:35","Observation","PSC Insp.","PSC Inspection","The monitor of the 2nd ECDIS is not approved type.","Navigation - ECDIS","Navigation","Equipment Related","","","",7,"Monitor replaced with newly received approved type.","2022-11-14T23:59:35","","Completed","2022-10-31T23:59:35","No","No","No","External"]
[null,null,null,25888,27681,"128_Thu Jun 16 2022 06:07:50 GMT+0800","2022-09-08T23:59:35","Defect","Ship Staff","Ship Staff Insp.","MAIN AIR COMPRESSOR NO . 2  LUB OIL PRESSURE DROPPING DURING OPERATION.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","MAJOR OVERHAUL COMPLETED , NEW LO PUMP ALSO FIXED , NOW OK , HOWEVER WILL KEEP MONITORING ","2022-12-07T23:59:35","RO NO NATT220133","Completed","2022-10-08T23:59:35","No","No","No","Internal","Job already completed, kindly update DDRL & close out accordingly."]
[null,null,null,25887,89931,"128_Thu Jun 16 2022 06:11:25 GMT+0800","2022-09-26T23:59:35","Defect","Ship Staff","Ship Staff Insp.","WORKSHOP ELECTRIC BUFFING MOTOR FOUNDATION  LOOSE AND BROKEN.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","",""," FOUNDATION STAND REPAIRED ","2022-12-26T23:59:35","","Completed","2022-11-10T23:59:35","No","No","No","Internal","Noted, kindly update office once done."]
[null,null,null,27584,24815,"128_Sun Oct 16 2022 02:53:36 GMT+0800","2022-10-02T23:59:35","Defect","Ship Staff","Ship Staff Insp.","CARGO HOLD 5 P HATCH HYD MOTOR NOT OPERATIONAL. MOTOR BODY GETTING DAMAGED WHEN TRYING TO OPERATE HATCH COVER.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","1 HYD MOTOR AS PER RO NATT220296 RECIEVED IN SINGAPORE \nFIXED AND TESTED, FOUND SATISFACTORY. ","2022-11-28T23:59:35","NATT220247","Completed","2022-11-10T23:59:35","No","No","No","Internal"]
[null,null,null,27586,50271,"128_Mon Nov 07 2022 19:16:06 GMT+0800","2022-10-17T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Steering flat machinal mushroom vent mess plate found broken. ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Fabricated the mesh plate for mushroom vent of Steering flat  and boxed back.","2022-11-28T23:59:35","","Completed","2022-10-22T23:59:35","No","No","No","Internal"]
[null,null,null,27587,85156,"128_Mon Nov 07 2022 19:27:50 GMT+0800","2022-10-25T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NRV of cargo hold no 6 bilge line port side found chocked and not operational.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","NRV of cargo hold no 6 bilge line port side dismantle ,overhauled and boxed back.","2022-11-28T23:59:35","","Completed","2022-10-31T23:59:35","No","No","No","Internal"]
[null,null,null,25896,83100,"0_Thu Jun 16 2022 19:48:34 GMT+0800","2022-10-28T23:59:35","Critical Equipment","Owner / Marine / Tech. Suptd.","Suptd. Insp.","As per master Stbd windless bushes of chain roller was dried due to less greasing","Deck - Machinery","Mooring","Equipment Related","","","","","Before and during using stbd anchor time with gear, applied full system of greasing work. And then Tested before operating.  Found in satisfactory. And then need to follow greasing schedule in future as per PMS.","2023-01-29T23:59:35","","Completed","2023-01-22T23:59:35","No","No","No","Internal",""]
[null,null,null,27664,75492,"128_Wed Nov 16 2022 15:06:13 GMT+0800","2022-11-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Found ME LO Temperature control valve has leaks from the seals","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Same attended , & rectified the leak , now ok ","2022-11-28T23:59:35","","Completed","2022-11-30T23:59:35","No","No","No","Internal","Need to attend this job at next call China. Once completed kindly update DDRL accordingly."]
[null,null,null,27666,87505,"128_Wed Nov 16 2022 16:39:22 GMT+0800","2022-11-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","DG Backwash filter actuator is faulty","","Eng. / Strg. Comp.","Equipment Related","","","","","\nDG Back wash filter overhauled and  guide bush and bearing changed and , system back in use , ","2023-02-09T23:59:35","","Completed",null,"No","No","No","Internal","Spares already connected to vessel, complete the job & update DDRL accordingly."]
[null,null,null,27667,28500,"128_Wed Nov 16 2022 16:46:16 GMT+0800","2022-11-14T23:59:35","Other","Ship Staff","Ship Staff Insp.","ER Bilge areas are rusty & need cosmetic upgradation","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","Cleaning , leak rectification & tank top painting completed ","2023-03-21T23:59:35","","Completed","2023-03-11T23:59:35","No","No","No","Internal","Please complete the job asap & update."]
[null,null,null,27668,13583,"128_Wed Nov 16 2022 16:54:42 GMT+0800","2022-11-14T23:59:35","Defect,Other","Ship Staff","Ship Staff Insp.","Hydrophore Sight glass need to clean & rectify so that correct level can be seen","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","New sight glasses fitted , now ok , also as a safety all told to keep the valves shut in UMS mode to avoid leaks ","2022-12-29T23:59:35","","Completed","2023-01-01T23:59:35","No","No","No","Internal","Need to complete in this port."]
[null,null,null,27669,50986,"128_Wed Nov 16 2022 17:15:09 GMT+0800","2022-11-14T23:59:35","Other","Ship Staff","Ship Staff Insp.","Found that the ER spare parts are not in proper steel boxes but in cardboard boxes , need to rectify this","E/R - Aux. Mach.","Eng. / Strg. Comp.","Inappropriate Procedure","","","","","All the spare boxes received and painted , all the spares are shifted in to new boxes and secured in engine room spare parts room ","2023-01-22T23:59:35","","Completed","2023-01-22T23:59:35","No","No","No","Internal","Spare boxes also connected to vessel, kindly keep all the spares in steel boxes & update."]
[null,null,null,27670,58094,"128_Wed Nov 16 2022 16:43:16 GMT+0800","2022-11-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","FOUND THAT THE CALORIFIER UNIT COILS ARE GIVING 440 V INSULAITON ISSUE","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","",""," REQUISITION RECIEVED  : NATT220248 , INSTALLED THE SAME & WORKING GOOD NOW WITHOUT ANY 440 V INSULATION ","2022-12-28T23:59:35","NATT220248","Completed","2022-12-01T23:59:35","No","No","No","Internal","Spares already connected to vessel, please rectify & update."]
[null,null,null,27671,59845,"128_Wed Nov 16 2022 16:52:40 GMT+0800","2022-11-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Bunker Line Manifold valves are very tight , one of the valve handle is also not in good condition","Deck - Pipe / Fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Valve made free e ,new valve has been received in china  and same replaced ","2023-01-06T23:59:35","","Completed","2023-01-04T23:59:35","No","No","No","Internal","Kindly advise RO number for our process. : RO NATT220253 received at Lanshan / coafidian  "]
[null,null,null,27672,80223,"128_Wed Nov 16 2022 15:04:05 GMT+0800","2022-11-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Found ME Jacket water pump has significant leakages & performance need to be improved also of the pump by overhaul","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","main engine jacket cooling water pump leak rectified and new mechanical sea installed \nmotor side DE and NDE bearing renewed with new one ","2022-11-28T23:59:35","","Completed","2022-11-21T23:59:35","No","No","No","Internal","Vessel has spare mech seal, need to renew asap & update."]
[null,null,null,29366,61742,"128_Wed Mar 08 2023 06:38:59 GMT+0800","2022-11-21T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Nav Audit / Verification","Port Cartier: Entry for Con with Master missing","Navigation - Others,Documentation","Navigation","Human Error","","","","","NAV AUDIT CONDUCTED, LOG BOOKS CHECKED, ENTRIES MADE AS REQUIRED. MASTER HIMSELF ADVISE OOW TO MAKE AN LOG BOOK ENTRY FOR TAKING OVER CON / HANDING OVER CON.","2023-02-21T23:59:35","","Completed","2023-02-21T23:59:35","No","No","No","Internal"]
[null,null,null,28257,82589,"128_Sat Dec 17 2022 07:03:48 GMT+0800","2022-12-07T23:59:35","Defect","Ship Staff","Ship Staff Insp.","The fresh water line busted outside accommodation at D deck due to sub zero temp. ","Deck - Pipe / Fittings","Ice Opns.","External Factors","","","","","The fresh water line isolated immediately and pipe renewal done ","2023-01-11T23:59:35","","Completed","2023-01-05T23:59:35","No","No","No","Internal"]
[null,null,null,28254,18095,"128_Fri Jan 06 2023 16:50:31 GMT+0800","2023-01-05T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Leak noticed from the Falch Hydro Blaster Main Pump (  High Pressure Pump ) Body  ,( at the aft portion opposite side of the working pistons )","Deck - Machinery","General Appearance","Equipment Related","","","",""," Falch Hydroblaster end cover  repair work carried out with cold work , hydro blaster tried out  , found all in order and no leak ","2023-01-22T23:59:35","","Completed","2023-01-15T23:59:35","No","No","No","Internal"]
[null,null,null,28255,88747,"128_Fri Jan 06 2023 16:54:36 GMT+0800","2023-01-05T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Standby Boiler Feed Pump Contactors are erratic , standby start not available along with its alarms ","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","after some modification is circuit pump is running satisfactory ","2023-03-21T23:59:35","","Completed","2023-03-21T23:59:35","No","No","No","Internal"]
[null,null,null,28256,35221,"128_Fri Jan 06 2023 17:01:35 GMT+0800","2023-01-05T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NO.3 DIESEL GENERATOR F.O LEAKAGE LEVEL SENSOR ERRATIC SOMETIMES ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","vessel installed Newley received  FUEL OIL LEAKAGE LEVEL SENSOR FOR DIESEL GENERATOR  , now fully functional ","2023-02-27T23:59:35","NATT220327-FUEL OIL LEAKAGE LEVEL SENSOR FOR DIESEL GENERATOR  received ","Completed","2023-03-04T23:59:35","No","No","No","Internal"]
[null,null,null,29317,57624,"128_Tue Jan 17 2023 08:40:46 GMT+0800","2023-01-12T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MAC #1 Lube oil low pressure trip , ","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Lube oil pump already assembled  AND LUBE OIL PRESSURE MAINTAINING 3.0 BAR  and MAC #1  running satisfactory \n","2023-03-24T23:59:35","","Completed","2023-03-15T23:59:35","No","No","No","Internal","MAC#1 lube oil trip to investigate and rectify asap , vessel has already received RO  "]
[null,null,null,29345,94687,"128_Tue Jan 17 2023 08:44:11 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main engine Booster Module viscosity controller showing error alarm ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","main engine viscosity controller sometime give erratic reading due to dirt , same was taken out and cleaned with diesel oil , now showing reading 13 cst at 106 degree , reading compared with fuel oil report , working satisfactory ","2023-01-29T23:59:35","","Completed","2023-01-16T23:59:35","No","No","No","Internal","same to investigate and rectify / report to office for further follow up "]
[null,null,null,29346,62716,"0_Tue Jan 17 2023 09:10:29 GMT+0800","2023-01-12T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","FWG production has reduced drastically in recent past ","E/R - Aux. Mach.","","","","","","","evaporator , condenser plates cleaned , gasket condition checked , demister position checked and cleaned , boxed back , same will be in use after departure ","2023-01-15T23:59:35","","Completed",null,"No","No","No","Internal","same to investigate and check , done before departure Singapore "]
[null,null,null,29347,57809,"128_Wed Jan 18 2023 13:56:43 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port & Stbd Hawse pipe Anti-piracy covers were not in place.","Deck - Pipe / Fittings","ISPS Related","Human Error","","","","","Restowed in place and cover in position . Brief to all crew and explain regarding ISPS matters.","2023-01-17T23:59:35","","Completed","2023-01-17T23:59:35","No","No","No","Internal"]
[null,null,null,29348,26982,"0_Wed Jan 18 2023 14:53:27 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","EGC messages are not legible","Navigation - GMDSS & Communication","Navigation","Human Error","","","","","EGC message not legible.","2023-01-19T23:59:35","","Completed","2023-01-12T23:59:35","No","No","No","Internal"]
[null,null,null,29349,28067,"0_Wed Jan 18 2023 11:46:36 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","No.4(S) hatch cover hyd motor oil leakage observed from hydraulic hose couplings, same to check & rectify.","Deck - Machinery","MARPOL Related","Equipment Related","","","","","To check and renew hydraulic flexible hose.","2023-01-19T23:59:35","","Completed","2023-01-19T23:59:35","No","No","No","Internal"]
[null,null,null,29350,15963,"0_Wed Jan 18 2023 11:51:34 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","There are 2 hatch cover hyd motors & 2 hydraulic jacks kept in fwd store, please check all are suitable for vessel use & separately send office photographic report including RO nos. under which those are supplied.","Deck - Machinery","General Appearance","Equipment Related","","","","","To check and take photographs of 2 hatch cover hyd motors & 2 hydraulic jacks at Fwd store and report to Office.","2023-01-19T23:59:35","","Completed","2023-01-17T23:59:35","No","No","No","Internal"]
[null,null,null,29351,61917,"0_Wed Jan 18 2023 15:01:19 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Numerical number of IMO symbol were not posted next to the IMO symbols for LSA in bridge.","LSA / FFA","Safety / LSA / FFA","Human Error","","","","","To post numerical number of IMO symbol next to the IMO symbols for LSA in bridge.","2023-01-19T23:59:35","","Completed","2023-01-19T23:59:35","No","No","No","Internal"]
[null,null,null,29352,69529,"128_Wed Jan 18 2023 13:47:36 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port side midship gangway platform marking noted faded away.","","","","","","",""," Remarking the port side midship gangway platform.","2023-01-24T23:59:35","","Completed","2023-01-19T23:59:35","No","No","No","Internal"]
[null,null,null,29353,56325,"0_Tue Jan 17 2023 09:07:21 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Main engine unit no fuel pump puncture valve observed leaking ","E/R - Main Engine","Eng. / Strg. Comp.","","","","","","Spare puncture valve  used  , fuel pump cleaned ,  removed puncture valve overhauled ","2023-01-19T23:59:35","","Completed","2023-01-27T23:59:35","No","No","No","Internal","puncture valve leaking to rectify "]
[null,null,null,29354,32288,"0_Wed Jan 18 2023 14:45:18 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Paint completely removed from  the Hyd. room door located fwd.","","Structural Condn. / WT integrity ","External Factors","","","","","Hyd. room door located  fwd de-rust and paint.","2023-01-27T23:59:35","","Completed","2023-01-27T23:59:35","No","No","No","Internal"]
[null,null,null,29355,18067,"0_Wed Jan 18 2023 14:58:42 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Accommodation electrical duct space not maintained clean & tidy.","Accommodation","General Appearance","Knowledge Based","","","","","Accommodation Electrical duct space cleaned, arranged some electrical spare in the store.","2023-01-19T23:59:35","","Completed","2023-01-17T23:59:35","No","No","No","Internal"]
[null,null,null,29356,65263,"0_Wed Jan 18 2023 14:50:35 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Time and position of change over steering from Auto Manual were not recorded in bell book on 13 Jan 2023.","Documentation","Navigation","Human Error","","","","","Checked in bell book and record properly","2023-01-19T23:59:35","","Completed","2023-01-12T23:59:35","No","No","No","Internal"]
[null,null,null,29357,36864,"0_Wed Jan 18 2023 14:26:17 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hose boxes on deck not identified with numbers","LSA / FFA","Safety / LSA / FFA","Human Error","","","","","To identify the hose boxes on deck with number","2023-01-27T23:59:35","","Completed","2023-01-27T23:59:35","No","No","No","Internal"]
[null,null,null,29358,95917,"0_Wed Jan 18 2023 11:38:22 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hatch covers open / close hyd motor top gears & sliding racks found dry for all hatches, all racks & operating gears to clean & lubricate.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","To clean, and grease Hatch covers open / close hyd motor top gears, sliding racks &operating gears","2023-01-27T23:59:35","","Completed","2023-01-27T23:59:35","No","No","No","Internal"]
[null,null,null,29359,86212,"0_Wed Jan 18 2023 13:17:37 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All hyd jacks for hatch cover to grease points to mark yellow & greasing must be done asap.","Deck - Machinery","Structural Condn. / WT integrity ","Behaviour Based,Knowledge Based","","","","","Mark yellow & greasing of all hyd jacks for hatch covers.","2023-02-12T23:59:35","","Completed","2023-02-12T23:59:35","No","No","No","Internal"]
[null,null,null,29360,91834,"0_Wed Jan 18 2023 13:25:15 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All ballast tank vent head inspection & maintenance must be carried out. A separate report to be send with photographs upon completion.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","To overhaul and maintenance of all ballast tank vent head .","2023-02-27T23:59:35","","Completed","2023-03-03T23:59:35","No","No","No","Internal"]
[null,null,null,29361,66656,"128_Wed Jan 18 2023 13:41:42 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All winch & windlasses greasing, lubrication observed in very poor, kindly get these done on priority & report to  office","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Cleaning and greasing of all winches and windlass.","2023-02-27T23:59:35","","Completed","2023-02-27T23:59:35","No","No","No","Internal"]
[null,null,null,29368,98454,"0_Wed Jan 18 2023 15:04:10 GMT+0800","2023-01-12T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Lights in alleyways are needed to replace, bulkhead & floors to clean in accommodation.","Accommodation","General Appearance","Human Error,Knowledge Based","","","","","To check condition of lighting systems and comprehensive cleaning on the accommodation. ","2023-02-27T23:59:35","","Completed","2023-02-27T23:59:35","No","No","No","Internal"]
[null,null,null,29362,76201,"128_Thu Feb 16 2023 19:02:54 GMT+0800","2023-02-13T23:59:35","Defect,Observation","Ship Staff","Ship Staff Insp.","BOTH AHU MOTOR AND BELTS ARE DESIGNED WITHOUT ANY PROTECTIVE GUARD PLATES AROUND ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","NEW GUARD PLATE FABRICATION HAS BEEN STARTED , WILL BE FIXED SOON ON BOTH AHU BELTS ","2023-02-27T23:59:35","","Completed","2023-02-19T23:59:35","No","No","No","Internal"]
[null,null,null,29363,73388,"128_Thu Feb 16 2023 13:04:32 GMT+0800","2023-02-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","GARBAGE DRUMS LIDS ARE NOT OF THE LOCKING TYPE , NEED TO CORRECT ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Inappropriate Procedure","","","","","FABRICATION OF NEW DRUMS WITH LOCKING LID HAS BEEN COMPLETED , DRUMS WILL BE SHIFTED TO GARBAGE LOCATION ","2023-03-27T23:59:35","","Completed","2023-02-23T23:59:35","No","No","No","Internal"]
[null,null,null,29683,94606,"128_Thu Mar 23 2023 22:06:15 GMT+0800","2023-03-21T23:59:35","Observation","Ship Staff","Ship Staff Insp.","EXHAUST GAS MANOMETER IS NOT FUNCTIONAL ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","BOARD PREPRAED AND NEW MANOMETER INSTALLED , AND WATER FILLED , NOW WORKING ","2023-03-30T23:59:35","","Completed","2023-03-22T23:59:35","No","No","No","Internal"]
[null,null,null,null,90126,"128_Wed Feb 15 2023 19:39:31 GMT+0800","2023-02-11T08:00:00","Observation","Ship Staff","Ship Staff Insp.","LT COOLER ON BOARD NOT PROVIDED WITH FW CHEMICAL CLEANING LINE ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","NOT REQUIRED AS BACKWASH LINE IS THERE","2023-04-12T08:00:00","","Completed",null,"No","No","No","Internal"]
[null,null,null,null,82707,"128_Mon Nov 07 2022 19:22:26 GMT+0800","2022-10-31T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Aft peak  ballast tank vent head  float ball damaged.","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","PO raised and waiting for spare","2023-05-31T08:00:00","NATT220286 - APK  BALLAST  TANK VENT FLOAT BALL.","Completed","2022-10-31T08:00:00","No","No","No","Internal","New float already supplied at Taranto, Italy & fitted in place. Kindly update accordingly."]
[null,null,null,null,92377,"128_Thu Jun 16 2022 05:21:37 GMT+0800","2022-10-09T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Need to replace flouresent lamp with led lights in engine room and accomodation","Accommodation,Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","completed ","2023-04-20T08:00:00","","Completed","2023-04-11T08:00:00","No","No","No","Internal","Kindly get all the the lamp renewed in due course."]
[null,null,null,null,39647,"128_Thu Jun 16 2022 05:33:47 GMT+0800","2022-09-29T08:00:00","Other","Ship Staff","Ship Staff Insp.","LED MIGRATION NOT COMPLETED .","Elect. Mach. & Equip.","Eng. / Strg. Comp.","External Factors","","","","","completed ","2023-04-20T08:00:00","","Completed","2023-04-02T08:00:00","No","No","No","Internal","Please change all on board to LED asap."]
[null,null,null,null,45386,"0_Thu Jun 16 2022 21:53:40 GMT+0800","2022-08-30T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Ballast control console on bridge non operational","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","This is not a compulsory requirement , spares are obsolete ","2023-05-31T08:00:00","","Completed","2023-04-02T08:00:00","No","No","No","Internal","Need to investigate & advise in separate mail."]
[null,null,null,null,30011,"128_Wed Mar 08 2023 06:46:46 GMT+0800","2023-02-12T08:00:00","Observation","Ship Staff","Nav Audit / Verification","OOW's Not aware of PFI, manual plotting not done as required.","","Navigation","Knowledge Based","","","","","MEETING WAS CALLED WITH ALL OFFICER, AND TRAINING CONDUCTED, BRIEFED OUT COMPANY POSTN PLOTTING INTERVAL, AND TO FOLLOW RIGHT PRACTICE OF PLTTING POSTN BY USING RADAR AND FREQUENCY OF PLOTTING TO BE FOLLOWED AS PER PASSAGE PLAN.","2023-05-11T08:00:00","","Completed","2023-04-10T08:00:00","No","No","No","Internal"]
[null,null,null,null,88836,"0_Wed Mar 08 2023 06:48:52 GMT+0800","2023-02-12T08:00:00","Observation","Ship Staff","Nav Audit / Verification","Training on filling the permits correctly required, due to officer's first time in company.","Documentation","Navigation","Knowledge Based","","","","","MEETING WAS CALLED WITH ALL OFFICER, AND TRAINING CONDUCTED, BRIEFED OUT COMPANY PROCEDURES FOR FILLING THE PERMIT IN A RIGHT MANNER USING CHIEF OFFICER HANDBOOK SAMPLE FOR REFERENCE. AND TO FOLLOW RIGHT PROCEDURE OF FILLING THE PERMIT. ","2023-05-11T08:00:00","","Completed","2023-03-24T08:00:00","No","No","No","Internal"]
[null,null,null,null,98662,"0_Wed Mar 08 2023 06:50:13 GMT+0800","2023-02-12T08:00:00","Observation","Ship Staff","Nav Audit / Verification","Bridge watch take over checklist not being followed diligently.","Documentation","Navigation","Knowledge Based","","","","","MEETING WAS CALLED WITH ALL OFFICER, AND TRAINING CONDUCTED, BRIEFED OUT COMPANY REQUIREMENT OF COMPLYING WITH BRIDGE PROCEDURES. CHECKLIST HAS TO BE FILLED POSITIVELY BY ALL OFFICER'S, WITHOUT FAIL.","2023-05-11T08:00:00","","Completed","2023-03-30T08:00:00","No","No","No","Internal"]
[null,null,null,null,90802,"0_Wed Mar 08 2023 06:51:28 GMT+0800","2023-02-12T08:00:00","Observation","Ship Staff","Nav Audit / Verification","Chronometer log not being updated by receiving time signal through MFHF.","Documentation","Navigation","Knowledge Based","","","","","MEETING WAS CALLED WITH ALL OFFICER, AND TRAINING CONDUCTED, BRIEFED OUT RIGHT PROCEDURES TO USE TIME SIGNAL USING MF/HF. COMPANY PROCEDURES TO BE FOLLOWED IN RIGHT MANNER AND TO FOLLOW RIGHT PROCEDURE FOR RECEIVING TIME SIGNAL AND UPDATING CHRONOMETER LOG. ","2023-05-11T08:00:00","","Completed","2023-03-28T08:00:00","No","No","No","Internal"]
[null,null,null,null,11783,"0_Wed Mar 08 2023 06:53:03 GMT+0800","2023-02-12T08:00:00","Observation","Ship Staff","Nav Audit / Verification","Radar settings found not in compliance with company, AIS target data being used, SOG being used.","Navigation - Others","Navigation","Knowledge Based","","","","","MEETING WAS CALLED WITH ALL OFFICER, AND TRAINING CONDUCTED, BRIEFED ABOUT RIGHT PROCEDURE TO SET UP MARINE RADAR, NOT TO ACTIVATE RAIN UN-NECESARILY. AIS NOT BE ACTIVATED ON RADAR, AIS DATA NOT TO BE USED FOR COLLISION AVOIDANCE PURPOSE. ","2023-05-11T08:00:00","","Completed","2023-02-28T08:00:00","No","No","No","Internal"]
[null,null,null,null,58581,"0_Wed Mar 08 2023 07:03:52 GMT+0800","2023-02-12T08:00:00","Observation","Ship Staff","Nav Audit / Verification","Gyro error intake found poor","Documentation,Navigation - Others","Navigation","Human Error","","","","","MEETING WAS CALLED WITH ALL OFFICER, AND TRAINING CONDUCTED, BRIEFED ABOUT TAKING COMPASS ERROR AND RECORDED AT EVERY WATCH. IF UNABLE TO TAKE COMPASS ERROR, RECORD REASON WITHOUT FAIL AT EVERY WATCH AS PER COMPANY STANDING ORDER AND MASTER STANDING ORDER.","2023-05-11T08:00:00","","Completed","2023-04-04T08:00:00","No","No","No","Internal"]
[null,null,null,null,98023,"0_Wed Mar 08 2023 07:00:31 GMT+0800","2023-02-12T08:00:00","Observation","Ship Staff","Nav Audit / Verification","National & Ensign Flags found in poor condition, No maintenance and washing done.","Navigation - Others","Navigation","Human Error","","","","","WASHED AND SEWED TO ALL FLAGS.  AND THEN STOWED PROPERLY IN FLAG LOCKER.","2023-05-11T08:00:00","","Completed","2023-04-04T08:00:00","No","No","No","Internal"]
[null,null,null,null,82717,"0_Wed Mar 08 2023 07:02:23 GMT+0800","2023-02-12T08:00:00","Observation","Ship Staff","Nav Audit / Verification","Bridge not provided with centre repeater","Navigation - Others","Navigation","Equipment Related","","","","","AS PER SOLAS  V/2.5.1 & 2.5.3 REQUIREMENT, IT WAS NOT COMPULSORY IF GYRO COMPASS'S HEADING INFORMATION IS BEING CLEARLY READABLE BY HEMLSMAN AT THE MAIN STEERING POSITION. ","2023-05-11T08:00:00","","Completed","2023-04-04T08:00:00","No","No","No","Internal"]
[null,null,null,null,60058,"0_Wed Jan 18 2023 14:41:35 GMT+0800","2023-01-12T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Main deck iwo CH#1 & 2 noted with heavy rust.","","Structural Condn. / WT integrity ","External Factors","","","","","De-rust and paint CH#1 & 2  on main deck.","2023-04-29T08:00:00","","Completed","2023-04-10T08:00:00","No","No","No","Internal"]
[null,null,null,null,22991,"128_Fri Mar 31 2023 23:24:06 GMT+0800","2023-03-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","LOCAL TOUCH PANELS FOR AUX ENGINE STARTING IS NOT IN GOOD SHAPE  AND SOME TIME MAL-FUNCTION AND PUSH BUTTON DOESNT WORK ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","VESSEL HAS FOUND OUT FEW OLD SPARES AND SCREEN PANELS , IN PROGRESS NOW ","2023-04-30T08:00:00","","Completed","2023-04-30T08:00:00","No","No","No","Internal"]
[null,null,null,null,62103,"128_Thu Feb 16 2023 11:51:28 GMT+0800","2023-02-14T08:00:00","Defect","Ship Staff","Ship Staff Insp.","NOTICED SETTLING SERVICE DRAIN LINES ARE OPEN TYPE DESIGN WHICH REQUIRES A BUCKET TO BE KEPT ALWAYS , POSES FIRE HAZARD ","E/R - Main Engine,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Inappropriate Procedure,Equipment Related","","","","","TEMPORARILY ALL TOLD TO DAILY DRAIN THE BUCKETS , MODIFICATION FABRICATION STARTED SO THAT THE DRAIN CAN GO DIRECT TO A CLOSED CHAMBER ","2023-04-30T08:00:00","","Completed","2023-04-30T08:00:00","No","No","No","Internal"]
[null,null,null,null,20053,"128_Sat Jan 28 2023 11:54:36 GMT+0800","2023-01-27T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Cascade tank  found dirty , and return mesh to inspection tank is not in good condition ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","",""," cleaning of cascade tank done","2023-04-29T08:00:00","","Completed","2023-04-30T08:00:00","No","No","No","Internal"]
[null,null,null,null,31297,"0_Tue Jan 17 2023 09:01:53 GMT+0800","2023-01-12T08:00:00","Defect","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","VRCS system issue to investigate thoroughly and follow up to be carried out with office ","Cargo Mach.","","Equipment Related","","","","","Recently found 1 major leak in Duct keel area , same rectified , valves were responding well with in time ","2023-04-30T08:00:00","RO RAISED FOR SEAL KIT NATT230012","Completed","2023-04-30T08:00:00","No","No","No","Internal","VRCS system issue to check and follow up to be carried out with office "]
[null,null,null,null,63526,"128_Fri Jan 06 2023 16:47:21 GMT+0800","2023-01-05T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Main air compressor No.1 Forward Unit Piston needs to be replaced , also the NRV for this compressor not holding ","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","New piston and rings assembled and placed , mac 1 running satisfactory ","2023-04-30T08:00:00","-NATT220287-MAIN AIR COMPRESSOR SPARES \n\n-NATT220326-MAIN AIR COMPRESSOR URGENT SPARES \nreceived las","Completed","2023-04-30T08:00:00","No","No","No","Internal"]
[null,null,null,null,51456,"128_Tue May 02 2023 09:06:02 GMT+0800","2023-04-19T08:00:00","Observation","Ship Staff","Ship Staff Insp.","SETTLING TANK AND SERVICE TANK LEVEL GAUGE NOT WORKING , AND SHOWING ERRATIC READING ","E/R - Pipes/ valves & fittings","","External Factors","","","","","MAGNETIC INDICATOR LEVEL GAUGE REMOVED FROM THE PLACE , LINE CLEARED WITH DO , FLOAT CLEANED AND CHECKED ITS PERFORMANCE , INSTALLED BACK AND NOW WORKING SATISFACTORY ","2023-04-30T08:00:00","","Completed","2023-04-29T08:00:00","No","No","No","Internal"]
[null,null,null,null,88283,"128_Fri Mar 31 2023 23:17:16 GMT+0800","2023-03-27T08:00:00","Defect","Ship Staff","Ship Staff Insp.","STBD FW TANK AND DISTILLED WATER TANK GAUGES ARE NOT IN GOOD CONDITION ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","VESSEL HAS PLANNED TO REMOVED GAUGE GLASS , MEASUREMENTS TAKEN AND FABRICATION OF TUBE HAS BEEN DISCUSSED WITH FITTER , SAME WILL BE COMPLETED SOON ","2023-05-17T08:00:00","","Completed","2023-05-02T08:00:00","No","No","No","Internal"]
[null,null,null,null,58124,"128_Thu Jun 16 2022 05:18:58 GMT+0800","2022-08-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","F.W. generator not creating enough vacuum  with ejector p/p in loaded condition.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","IN DD CAN PLAN TO INSTALL BIGGER PUMP , ","2023-05-30T08:00:00","NATT220254","Completed","2023-05-01T08:00:00","No","No","No","Internal","Kindly raise RO for the require spares & mention RO in DDRL for our follow up to supply spares."]
[null,null,null,null,27424,"128_Wed Nov 16 2022 16:04:49 GMT+0800","2022-11-14T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Performance of Ballast Pump No.2 to be improved ","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Ballast pump No.2 again overhauled in April 2023 , improvement is there , however pump assembled with old mouth rings though clearance within limits , separate report sent to office by email ","2023-05-17T08:00:00","Requisition NATT230087-BALLAST PUMP SPARES -URGENT is also awaited ","Completed","2023-05-01T08:00:00","No","No","No","Internal","Vessel has spare mech seal & line bush, please renew & update job in DDRL."]
[null,null,null,null,25661,"128_Thu Jun 16 2022 08:58:34 GMT+0800","2022-08-24T08:00:00","Breakdown","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mono rail crane was not operational fully, travelling gear and pinion not meshing , issue is with the traversing plate","Miscellaneous","General Appearance","Equipment Related","","","","","DETAILED REPORT & JOB SCOPE ALREADY SENT TO OFFICE .  PLATES HAD BEEN ORDERED FOR REPAIR . PLANNING TO GET IT DONE IN DD OR SHIP YARD  RO RAISED NATT230063 , also NATT235017 was raised for Pre Inspection of crane by technician at Fangcheng China  , same completed , report sent to office ","2023-05-31T08:00:00"," RO RAISED NATT230063 , also NATT235017 was raised for Pre Inspection of crane by technician at Fangcheng China  , same completed , report sent to office ","Completed","2023-05-01T08:00:00","No","No","No","Internal","Need to arrange W/S attendance during next call China, discharge port."]
[null,null,null,null,59058,"128_Thu Jun 16 2022 05:15:00 GMT+0800","2022-08-10T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Engine room Service Air Compressor not operational","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","New compressor can be installed in DD  , As per discussion with office , plan has been sent for installation of screw type service air compressor in due course so as to reduce the running hours of Main compressors ","2023-06-30T08:00:00","Plan to install new compressor at DD ","Completed","2023-05-01T08:00:00","No","No","No","Internal","Need to dismantle the complete compressor & revert which all parts require to renew to make the compressor operational."]
[null,null,null,null,54750,"128_Sat Apr 29 2023 03:19:31 GMT+0800","2023-04-24T08:00:00","Other,Observation","Ship Staff","Ship Staff Insp.","Upon departure from Singapore on 11 Feb 2023, Visitor log book and visitor card inspected. Found visitor card number 4/7/8/15 found missing.","Miscellaneous","ISPS Related","Human Error","","","","","New visitor card received along with on - signer's at Zhoushan shipyard","2023-05-31T08:00:00","","Completed","2023-05-25T08:00:00","No","No","No","Internal"]
[null,null,null,null,56016,"128_Fri Mar 31 2023 23:20:04 GMT+0800","2023-03-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","COMPOSITE BOILER GAUGE GLASS STBD SIDE IS FULLY DIRTY AND LEAKING FROM THE GASKET ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","BOILER GAUGE GLASS RENEWED AND LINE CLEAERED , NOW WORKING SATIFACTORY ","2023-05-30T08:00:00","NATT230079","Completed","2023-05-23T08:00:00","No","No","No","Internal"]
[null,null,null,null,33748,"128_Thu Mar 23 2023 21:55:29 GMT+0800","2023-03-21T08:00:00","Observation","Ship Staff","Ship Staff Insp.","EXHAUST GAS BOILER CHEMICAL SOOT BLOW CHAMBER & PIPE LINES FOUND CHOKED","E/R - Boiler","Eng. / Strg. Comp.","","","","","","EXHAUST GAS CHEMICAL CLEANING LINE INSTALLED AND WORKING SATISFACTORY NOW ","2023-05-25T08:00:00","","Completed","2023-05-23T08:00:00","No","No","No","Internal"]
[null,null,null,null,69973,"128_Tue Mar 07 2023 20:02:47 GMT+0800","2023-03-03T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Forward on foremast, Bridge wing port side and stbd side P.A speaker not working. Checked the insulation and found not up to the mark.","Elect. Mach. & Equip.","Safety / LSA / FFA","External Factors","","","","","ALL THE SPEAKERS RECIEVED AND INSTALLED IN PLACE , WORKIING SATIFACTORY ","2023-05-30T08:00:00","NATT230091","Completed","2023-05-22T08:00:00","No","No","No","Internal"]
[null,null,null,null,87959,"128_Tue Mar 07 2023 22:00:30 GMT+0800","2023-02-21T08:00:00","Defect","Ship Staff","Ship Staff Insp.","LUBE OIL PURIFIER COMMUNICATION ERROR ALRAM IS VERY FREQUENT , DUE TO WHICH SOMETIME LUBE OIL PURIFIER IS NON-OPERATIONAL ","E/R - Purifier","","Equipment Related","","","","","LUBE OIL PURIFIER  50 RECIEVIED AND CHANGED WITH OLD ONE , NOW LO PURIFIER WORKING FINE ","2023-05-31T08:00:00","NATT230068-EPC 50 OP BOARD FOR LO PURIFIER RAISED AND RECEIVED ","Completed","2023-05-19T08:00:00","No","No","No","Internal"]
[null,null,null,null,66785,"128_Fri Dec 09 2022 15:05:37 GMT+0800","2022-12-06T08:00:00","Defect","Ship Staff","Ship Staff Insp.","JACKET WATER CONTROLLER FOR MAIN ENGINE NOT WORKING PROPERLY AND GIVING ERRATIC FEEDBACK DUE WICCH JACKET WATER FOR MAIN ENGINE NOT STABLE ","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","JCFW CONTROLLER STILL EARRTIC IN NATURE , ALTHOUGH CONTROLLER FOR MAIN ENGINE LUBE OIL CONTROLLER AND LT COOLER CONTROLLER CHANGED WITH WORKING IN ORDER ","2023-05-30T08:00:00","NATT230027 Received ","Completed","2023-05-18T08:00:00","No","No","No","Internal"]
[null,null,null,null,41521,"0_Wed Jan 18 2023 15:06:38 GMT+0800","2023-01-12T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hydraulic pipe for hatch cover noted corroded","Deck - Pipe / Fittings","MARPOL Related","Equipment Related","","","","","All leaky hydraulic pipe leaks have been arrested, about 20% hydraulic pipes have been renewed. No present leaks on main deck. Further will keep identifying and renew as required.","2023-06-15T08:00:00","","Completed","2023-05-25T08:00:00","No","No","No","Internal"]
[null,null,null,null,73035,"0_Wed Jan 18 2023 11:57:11 GMT+0800","2023-01-12T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Corroded hydraulic pipe for hatch covers to renew. RO for hatch cover hydraulic pipes already received by vessel.","Deck - Pipe / Fittings","MARPOL Related","Equipment Related","","","","","All leaky hydraulic pipe leaks have been arrested, about 20% hydraulic pipes have been renewed. No present leaks on main deck. Further will keep identifying and renew as required.","2023-05-31T08:00:00","","Completed","2023-05-25T08:00:00","No","No","No","Internal"]
[null,null,null,null,29282,"128_Tue Mar 07 2023 20:15:08 GMT+0800","2023-02-27T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Quick closing valve for respective aux engine for shutting off the fuel is not in good condition , Pneumatic cylinder found working but erratic , but need overhauling ","E/R - Aux. Engine","","Equipment Related","","","","","Defective QCV replaced with new one","2023-06-15T08:00:00","NATT230106","Completed","2023-07-01T08:00:00","No","No","No","Internal"]
[null,null,null,null,45414,"0_Wed Jan 18 2023 12:01:16 GMT+0800","2023-01-12T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Mooring winch & windlass hydraulic lines observed corroded, same to renew with available hydraulic pipes asap. Please identify the priority ones to renew first.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","All mooring winches lines are in satisfactory condition & renewed with spare lines. ","2023-08-30T08:00:00","","Completed","2023-08-19T08:00:00","No","No","No","Internal"]
[null,null,null,null,72351,"0_Fri Aug 11 2023 13:39:43 GMT+0800","2023-08-11T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Bunkering Audit","U-clamp supporting the section at bunker manifold flange missing. All load is on the filter box.","E/R - Pipes/ valves & fittings","General Appearance","Equipment Related","","","","","New U clamp fitted on both port and stbd bunker manifold along with teflon sheet underneath upon receipt of spares. Photographs sent to office after completion of work.","2023-09-30T08:00:00","","Completed","2023-08-31T08:00:00","No","No","No","Internal"]
[null,null,null,null,85104,"0_Fri Aug 11 2023 13:38:04 GMT+0800","2023-08-11T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Bunkering Audit","Manifold flange connections - bolts of uneven size. Few bolts, threads were not visible after securing the nut.","E/R - Pipes/ valves & fittings","General Appearance","Equipment Related","","","","","All bolts of manifold flange were renewed on both side upon receipt of spares.","2023-09-30T08:00:00","","Completed","2023-08-31T08:00:00","No","No","No","Internal"]
[null,null,null,null,91724,"0_Wed Jan 18 2023 14:56:17 GMT+0800","2023-01-12T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Whole accommodation area noted spot rusts, pain faded","Accommodation","Structural Condn. / WT integrity ","External Factors","","","","","Complete accommodation has been power tooled / hydro blasted. E/D/C Deck has been completed with painting job as well. Remaining B & A deck painting will be completed after cargo hold cleaning is completed.","2023-08-31T08:00:00","","Completed","2023-08-31T08:00:00","No","No","No","Internal"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["128","NATTY (28-03-2023)","128_1681127181234.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]