{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":23,"n_cols":28,"rows_kept":23,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","16-Sep-2023",null,null,"Ship Name","SCARLETT (10-09-2023)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,29897,10809,"112_Mon May 01 2023 20:26:26 GMT+0800","2023-07-19T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME and AE viscosity controller unit not showing correct viscosity value.","E/R - Main Engine,E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Spares received. Vessel will renew the unit controller at the earliest opportunity.","2023-10-19T23:59:35","","Not Started",null,"No","No","No","Internal","Update when the job is completed."]
[null,null,null,29602,62733,"112_Sat Apr 01 2023 22:41:18 GMT+0800","2023-07-26T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Deck lights & fittings, Flood lights damaged and defective due to corrosion. Causing low insulation alarm. Request raised awaiting for spares.","Accommodation","ISM Related","Equipment Related","","","","","RO raised to renew  lightings on deck around accommodation.\nRO: SCAR230189 for Emergency light fixtures is awaiting supply at Jingtang.\nOnce received all defective ones will be renewed.","2023-08-26T23:59:35","SCAR230064","Waiting spare",null,"No","No","No","Internal","Lights were supplied at Jingtang. Please update the job in next export file."]
[null,null,null,29898,57599,"112_Sun Apr 16 2023 12:28:53 GMT+0800","2023-08-03T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Galley air conditioning compressor not in position and evaporator found damaged. Other electrical and AC components are wasted.","Accommodation","MLC Related","Equipment Related","","","","","Awaiting advise from office on the below for carrying out the repairs:\nTo be replace Compressor , evaporator, Thermostatic valve, Solenoid valve, LP and HP pressure switch, pressure gauges, sensing valve, Filter, Laggings, other electrical components and wasted evaporator base plate.","2023-11-29T23:59:35","","Not Started",null,"No","No","No","Internal","Disconnect power supply and do not use it. Create RO for new unit cooler. We will supply it upon owners approval."]
[null,null,null,29899,46614,"112_Sun Apr 16 2023 14:46:20 GMT+0800","2023-08-19T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Bridge air conditioning system outdoor unit wasted and compressor fan broken.","Accommodation","Navigation","Equipment Related","","","","","New  2 Split ACs of 1.5 tones to be installed  at Port & Stbd side of Bridge,\nOffice to advise regarding raising the RO for the same.","2023-11-29T23:59:35","","Not Started",null,"No","No","No","Internal","Create RO for spares as required or order for complete unit."]
[null,null,null,31522,54284,"112_Sat Sep 09 2023 20:15:25 GMT+0800","2023-08-23T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Main Engine Emergency Stop is not operational from Bridge or ECR.\nNeeds renewal of DPU20 - RDI32 & LTU ESS cable as per the advise of attending service technician.","E/R - Main Engine","Emgcy. Systems","Equipment Related","","","","","Replacement of f DPU20 - RDI32 & LTU ESS cable once received.","2023-09-29T23:59:35","Raised from the office end.","Waiting spare",null,"No","No","No","Internal","PO issued via email for Cable and pre-programmed RDI."]
[null,null,null,31520,21708,"112_Sat Sep 09 2023 20:23:25 GMT+0800","2023-08-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ER Alarm Signal Column faulty are various locations as below:\n1. ER UPPER DECK : Near Incinerator Yellow light fixture rotating motor is faulty.\n2. ER 2nd DECK STBD : Inside Purifier room Yellow Light fixture rotating motor is faulty.\n3. ER 3rd DECK STBD : Audio speaker not working and PCB is faulty.\n4. ER BOTTOM FLAT FORM STBD : Audio Speaker and PCB is faulty, Blue color cover is missing.\n5. ER BOTTOM FLAT FORM PORT: Yellow light fixture rotating motor faulty.\n6. ER BOTTOM FLAT FORM AFT : Yellow Light fixture rotating motor is faulty and Audio speaker is faulty.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Awaiting spares for rectification of faults.","2023-09-29T23:59:35","SCAR230166","Waiting spare",null,"No","No","No","Internal","Order placed and dispatched from supplier. Will be supplied at next suitable port."]

{"sheet":"Completed","index":1,"n_rows":182,"n_cols":28,"rows_kept":182,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","16-Sep-2023",null,null,"Ship Name","SCARLETT (10-09-2023)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,20608,null,"112_31/7/2021 6:16:24 PM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The accommodation ladder and combination ladder wire rope need renewal not exceed 30 months as company's policy, order wire rope & carry out renewal once received","Accommodation,Deck - Machinery","General Appearance","External Factors","","","","","the accommodation ladder and pilot combination ladders wire repes all renewed.","2021-06-09T23:59:35","","Completed","2021-07-04T23:59:35","No","No","No","Internal"]
[null,null,null,18361,null,"112_19/3/2021 1:29:57 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The protecting plate of provision crane hook damaged, fabricate new plate onboard","Deck - Machinery","General Appearance","Equipment Related","","","","","Fabricate new plate onboard and renewl.","2021-03-19T23:59:35","","Completed","2021-03-09T23:59:35","No","No","No","Internal"]
[null,null,null,18362,null,"112_19/3/2021 1:37:41 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Some oil trap corroded, order  as required","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","derust the oil trap","2021-03-30T23:59:35","","Completed","2021-03-16T23:59:35","No","No","No","Internal"]
[null,null,null,18363,null,"112_19/3/2021 1:40:28 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Accommodation rust partly, Plan derusting of area which can be accessible","Accommodation","General Appearance","External Factors","","","","","Derusted and painted","2021-04-09T23:59:35","","Completed","2021-04-08T23:59:35","No","No","No","Internal"]
[null,null,null,18365,null,"112_20/3/2021 3:32:36 PM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fresh water production is low ,need to adjust the feed rate to increase the capacity.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Adjusted the heating water feed rate to increase the capacity. At the end of adjusting, the product is about 16ton /day maxmum","2021-03-14T23:59:35","","Completed","2021-03-14T23:59:35","No","No","No","Internal"]
[null,null,null,18367,null,"112_19/3/2021 1:21:23 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fill mooring winch gear oil tank up to half level ,some gauge glass not able to see, order new glass & plan for renewal once received","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Fill mooring winch gear oil tank up to half level ,renewal new glass .","2021-06-09T23:59:35","","Completed","2021-03-07T23:59:35","No","No","No","Internal"]
[null,null,null,18369,null,"112_19/3/2021 2:02:42 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The accommodation ladder and combination ladder wire rope need renewal not exceed 30 months as company's policy, order wire rope & carry out renewal once received","Accommodation,Deck - Machinery","General Appearance","External Factors","","","","","new wires received on board, renewal conducted on July 15,2021 all wire ropes in good condition ","2021-06-09T23:59:35","SCAR210015","Completed","2021-07-04T23:59:35","No","No","No","Internal","will supply in convenient port"]
[null,null,null,18370,null,"112_19/3/2021 2:09:44 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","hatch cover for emergency operation pump, try out the pump & make sure crew is aware of procedures for using in emergency, wire of pump should be put in each hatch plug to make sure the pump can be started & cover all the hatches (if required)","Deck - Machinery","General Appearance","Knowledge Based","","","","","Tye out the emergency operation pump ,training crews how to used the emergency pump.","2021-06-09T23:59:35","","Completed","2021-04-30T23:59:35","No","No","No","Internal","please provide RO number for tracing and supply"]
[null,null,null,18372,null,"112_2021/3/17 19:04:18","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The accommodation floors are dirty, same to be cleaned with hard chemical & stripper","Accommodation","MLC Related","External Factors","","","","","clean The accommodation floors ","2021-02-15T23:59:35","","Completed","2021-02-15T23:59:35","No","No","No","Internal"]
[null,null,null,18373,null,"112_2021/3/17 19:08:42","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Bridge wing portside, the lower position switch of bottom control box cover does not rotate. Same to be freed","Navigation - Others","Navigation","External Factors","","","","","repair and grease the switch of bottom control box cover","2021-03-09T23:59:35","","Completed","2021-03-07T23:59:35","No","No","No","Internal"]
[null,null,null,18374,null,"112_19/3/2021 5:18:28 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Portside rudder angle indicator cover not clean, not able to read carefully ,cover to remove and clean.","Cargo Mach.,Navigation - Others","Navigation","External Factors","","","","","CLEAN Portside rudder angle indicator cover ","2021-02-15T23:59:35","","Completed","2021-02-15T23:59:35","No","No","No","Internal"]
[null,null,null,18375,null,"112_19/3/2021 1:04:18 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The door closer of watertight door at E deck starboard side door is broken ,order & replace with new. Always keep min 3 closure doors as spare all the times","Accommodation","Structural Condn. / WT integrity ","External Factors","","","","","Replace with new","2021-02-28T23:59:35","","Completed","2021-02-28T23:59:35","No","No","No","Internal"]
[null,null,null,18376,null,"112_19/3/2021 1:00:04 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Whistle pipe drain valve on compass deck not rotate ,to make it free ","Navigation - Others","Navigation","External Factors","","","","","Make it free","2021-02-15T23:59:35","","Completed","2021-02-15T23:59:35","No","No","No","Internal"]
[null,null,null,18378,null,"112_20/3/2021 5:32:01 PM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Various places pressure gauges are blurred & damaged ,same to identify, ordered & renewed","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Renew damaged pressure gauges","2021-03-19T23:59:35","","Completed","2021-03-19T23:59:35","No","No","No","Internal"]
[null,null,null,18380,null,"112_19/3/2021 1:09:24 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All lubricating nipple need to marked with yellow color","Deck - Machinery,Deck - Mooring Machinery","General Appearance","Equipment Related","","","","","Marked All lubricating with yellow color","2021-02-25T23:59:35","","Completed","2021-02-25T23:59:35","No","No","No","Internal"]
[null,null,null,18381,null,"112_19/3/2021 1:13:35 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Remove all the tool in Suez crew room to bosun store, get  the mattress back in position","Accommodation","Structural Condn. / WT integrity ","External Factors","","","","","Remove all the tool in Suez crew room to bosun store, get  the mattress back in position?clean","2021-02-15T23:59:35","","Completed","2021-02-15T23:59:35","No","No","No","Internal"]
[null,null,null,18382,null,"112_19/3/2021 1:18:32 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","To perform maintenance of  the greasing nipple of mooring winches ,Colour code yellow to avoid missing it out","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Perform maintenance of  the greasing nipple of mooring winches ?Remarked the nipple with yellow.","2021-02-27T23:59:35","","Completed","2021-02-27T23:59:35","No","No","No","Internal"]
[null,null,null,18384,null,"112_19/3/2021 1:25:58 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Watertight door of acetylene store room corroded, plan to derust & Paint","Miscellaneous","Structural Condn. / WT integrity ","External Factors","","","","","Derust & paint.","2021-03-07T23:59:35","","Completed","2021-03-07T23:59:35","No","No","No","Internal"]
[null,null,null,18385,null,"112_19/3/2021 1:34:43 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Some oil trap plugs are not in proper size and not fixed ,order correct size as required","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","Change proper size plugs and fixed","2021-03-10T23:59:35","","Completed","2021-03-10T23:59:35","No","No","No","Internal"]
[null,null,null,18386,null,"112_19/3/2021 1:43:33 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","To check hose crane limit switch if working normal or not","Deck - Machinery","General Appearance","Equipment Related","","","","","Check hose crane limit ,in good order.","2021-03-07T23:59:35","","Completed","2021-03-07T23:59:35","No","No","No","Internal"]
[null,null,null,18387,null,"112_19/3/2021 1:55:30 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Rescue boat accumulators to try out at angle specified in manual without motor starting, also need to make sure accumulator is filled to required pressure at all times.","Critical Equip.","Safety / LSA / FFA","Equipment Related","","","","","Repaired the accumulator and filled pressure.","2021-03-06T23:59:35","","Completed","2021-03-06T23:59:35","No","No","No","Internal"]
[null,null,null,18388,null,"112_19/3/2021 2:15:29 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The list of helicopter operation is not consistent to actual existing devices check ","LSA / FFA","General Appearance","External Factors","","","","","Supplement the short devices of the list of helicopter operation","2021-02-15T23:59:35","","Completed","2021-02-15T23:59:35","No","No","No","Internal"]
[null,null,null,18389,null,"112_19/3/2021 2:54:57 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The co2 release box for forecastle paint room corroded, to derust & paint","LSA / FFA","Safety / LSA / FFA","External Factors","","","","","derust & paint the co2 release box for forecastle paint room ","2021-03-07T23:59:35","","Completed","2021-03-07T23:59:35","No","No","No","Internal"]
[null,null,null,18390,null,"112_19/3/2021 2:59:19 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The p ‘side windlass gear box cover is heavily corroded","Deck - Machinery","General Appearance","External Factors","","","","","derusted and repaired the p ‘side windlass gear box cover ","2021-03-01T23:59:35","","Completed","2021-02-27T23:59:35","No","No","No","Internal"]
[null,null,null,18391,null,"112_19/3/2021 3:04:42 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","There is't O-ring for oil fill hole on top of windlass which can lead to water ingress, check the actual arrangement from drawing & fabricate accordingly to avoid ingress of water","Deck - Machinery","General Appearance","Equipment Related,External Factors","","","","","repaired the oil fill hole cover","2021-02-27T23:59:35","","Completed","2021-02-27T23:59:35","No","No","No","Internal"]
[null,null,null,18392,null,"112_19/3/2021 3:07:55 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The scupper in upper deck WC room is obstructed, same to cleared.","Accommodation","Structural Condn. / WT integrity ","External Factors","","","","","Clear the scupper","2021-03-04T23:59:35","","Completed","2021-03-03T23:59:35","No","No","No","Internal"]
[null,null,null,18393,null,"112_19/3/2021 3:19:17 AM","2021-02-10T23:59:35","Breakdown","Owner / Marine / Tech. Suptd.","Suptd. Insp."," old broken chairs to be scrapped off & replace with new supply.","Accommodation","General Appearance","External Factors","","","","","replace with new supply.","2021-02-12T23:59:35","","Completed","2021-02-12T23:59:35","No","No","No","Internal"]
[null,null,null,18394,null,"112_19/3/2021 3:22:06 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","repaired upholstery(sofas) needs to be fitted back in place ","Accommodation","General Appearance","External Factors","","","","","Fitted the sofas back in place","2021-02-12T23:59:35","","Completed","2021-02-12T23:59:35","No","No","No","Internal"]
[null,null,null,18395,null,"112_19/3/2021 3:27:17 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Cargo hold ventilation Louvers to check ,if any rusted to take out & carry out  maintenance","Deck - Machinery","General Appearance","External Factors","","","","","Check and rusted the Cargo hold ventilation Louvers ","2021-03-07T23:59:35","","Completed","2021-03-07T23:59:35","No","No","No","Internal"]
[null,null,null,18396,null,"112_20/3/2021 3:46:33 PM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sludge & Bilge pp greasing oil pot empty, oil need to be refilled.","E/R - Pumps","Eng. / Strg. Comp.","Human Error","","","","","refill oil to grease pots","2021-03-19T23:59:35","","Completed","2021-02-19T23:59:35","No","No","No","Internal"]
[null,null,null,18397,null,"112_20/3/2021 4:09:16 PM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All 3 DGs LO Lube oil renewal to carry out as part of 2000 hours routines","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Renewed no.1 &2 DG sump tank L.O. on 08/03/2021  09/03/2021, the L.O. in NO.3 DG running hour no yet reach 2000hours","2021-02-27T23:59:35","","Completed","2021-02-26T23:59:35","No","No","No","Internal"]
[null,null,null,18398,null,"112_20/3/2021 5:28:41 PM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","line inside Acetylene room leaking ,source to find & rectify","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Retified the leaking part","2021-02-17T23:59:35","","Completed","2021-02-14T23:59:35","No","No","No","Internal"]
[null,null,null,18399,null,"112_19/3/2021 3:16:36 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All posters such as company's policy must be posted on the green board in alley way & Engine control room.","Accommodation","General Appearance","External Factors","","","","","posted All posters such as company's policy  on the green board in alley way & Engine control room.","2021-02-15T23:59:35","","Completed","2021-02-15T23:59:35","No","No","No","Internal"]
[null,null,null,18400,null,"112_19/3/2021 1:59:32 AM","2021-02-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The oil level of s'side combination ladder can not read,check & replenish oil","Deck - Machinery","General Appearance","External Factors","","","","","Replenished oil to s'side combination ladder ","2021-03-30T23:59:35","","Completed","2021-03-12T23:59:35","No","No","No","Internal"]
[null,null,null,18478,null,"112_31/3/2021 8:43:44 PM","2021-03-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","NO.10 D.B.WBTK (wash water tank) air vent head fly net cover seriously corroded, need to fabricated new cover to change it","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","Fabricated new cover and changed ","2021-03-23T23:59:35","","Completed","2021-03-26T23:59:35","No","No","No","Internal"]
[null,null,null,18477,null,"112_31/3/2021 9:05:53 PM","2021-03-20T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Boiler cascade enter some oil, investigated found the A/E booster unit no.1 F.O. heater leaking.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Removed the oil and cleaned inspection tank of boiler cascade tank,  dismantled A/E no.1 F.O. Heater and pressure tested found leaking tube 1pc  and plugged,after install tested good","2021-03-23T23:59:35","","Completed","2021-03-22T23:59:35","No","No","No","Internal","Kindly let us know when you are going to open AE #1 FO heater to locate leaking tube."]
[null,null,null,18930,null,"112_28/4/2021 9:39:32 AM","2021-03-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","L.T water expension tank level drop down, suspected the boiler atmoshpere condenser tube leaking","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Open up both side cover of atmoshpere condenser, cleaned and carried pressure tested, found 3 tubes leaking, plugged them by newly made brass plugs. total 16pcs tubes hae been plugged","2021-04-11T23:59:35","","Completed","2021-04-11T23:59:35","No","No","No","Internal"]
[null,null,null,18931,null,"112_28/4/2021 9:47:35 AM","2021-04-04T23:59:35","Observation","Ship Staff","Ship Staff Insp."," F.W.G. heating water inlet valve and by pass valve leaking water from  vavle spindle seal.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Renewed both valves with new spare valves. checked the old valves found the rubber damaged","2021-04-12T23:59:35","","Completed","2021-04-12T23:59:35","No","No","No","Internal"]
[null,null,null,18932,null,"112_28/4/2021 9:52:01 AM","2021-04-04T23:59:35","Observation","Ship Staff","Ship Staff Insp.","NO.2 central cooler backflush sea water inlet valve stuck, could not open","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Renewed the valve, check the old butterfly valve inside rubber is deformed and damaged.","2021-04-14T23:59:35","","Completed","2021-04-14T23:59:35","No","No","No","Internal"]
[null,null,null,18933,null,"112_28/4/2021 10:07:30 AM","2021-04-16T23:59:35","Observation","Ship Staff","Ship Staff Insp.","No.1 generator control panel voltage is not stable.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Renewed the AVR for No.1 generator, tested found good.","2021-04-16T23:59:35","","Completed","2021-04-16T23:59:35","No","No","No","Internal"]
[null,null,null,19533,null,"112_6/5/2021 8:50:53 AM","2021-04-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","All steam traps in E/R and deck did not overhaul","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Checked and Overhauled E/R and deck steam traps.","2021-04-29T23:59:35","","Completed","2021-05-01T23:59:35","No","No","No","Internal"]
[null,null,null,23132,null,"112_15/11/2021 7:04:58 PM","2021-10-24T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Oil leakages observed from the hatch cover hydraulic pipelines for cargo holds #1 and #3.","Cargo Mach.,Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Full length of the leaking pipelines renewed.","2022-01-21T23:59:35","","Completed","2022-01-09T23:59:35","No","No","No","Internal"]
[null,null,null,23133,null,"112_15/11/2021 7:09:14 PM","2021-10-24T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Tank level gauges for the following tanks show erroneous readings.\n\na.\tWBT #1C\n\nb.\tWBT #4P\n\nc.\tWBT #6P\n\nd.\tWBT #7S","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","All tank level gauges inspection and calibration were carried out during Drydock by General Marine.","2022-01-21T23:59:35","","Completed","2022-10-10T23:59:35","Yes","No","No","Internal","please check and confirm. Raise RO as required"]
[null,null,null,23134,null,"112_15/11/2021 7:13:04 PM","2021-10-24T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Valve indication for the following shows erroneous positions\n\na.\tWBV 01\n\nb.\tWBV 21\n\nc.\t2WV 50\n\nd.\t2WV 51\n\ne.\t2WV 52\n\nf.\t2 WV 53\n\ng.\t2 WV 56\n\nh.\t1 WV 17                                               a.\tBGV 02                    \n\nb.\tBGV 12","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","VRCS calibration carried out, solenoid setpoints calibration carried out during drydock and rectified.","2022-01-21T23:59:35","","Completed","2022-10-09T23:59:35","Yes","No","No","Internal","vessel electrician to check and investigation. update final condition. Raise Ro as required"]
[null,null,null,23135,null,"112_15/11/2021 7:27:59 PM","2021-10-24T23:59:35","Critical Equipment,Non Conformity","Ship Staff","Ship Staff Insp.","The pilots ladders presently on board are defective/damaged and unsafe of use in the current condition.","Critical Equip.,Miscellaneous","Safety / LSA / FFA","Behaviour Based,External Factors,Human Error,Inappropriate Procedure","","","","","Ladders replaced with new supply.","2022-01-22T23:59:35","","Completed","2022-12-10T23:59:35","No","No","No","Internal"]
[null,null,null,19532,null,"112_6/5/2021 8:39:29 AM","2021-10-27T23:59:35","Observation","Ship Staff","Ship Staff Insp.","G/E F.O. flowmeter is not working","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Vessel received new flow meter during dry dock . Old meter was replaced with new meter.","2022-01-25T23:59:35","SCAR215078","Completed","2022-10-07T23:59:35","No","No","No","Internal","spare will supply in convenient port"]
[null,null,null,23136,null,"112_4/12/2021 6:58:51 PM","2021-10-28T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME fuel valve testing machine out of order","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","New Fuel testing machine installed","2022-01-21T23:59:35","SCAR210086","Completed","2022-01-17T23:59:35","No","No","No","Internal"]
[null,null,null,23131,null,"112_4/12/2021 7:16:31 PM","2021-11-05T23:59:35","Defect","Ship Staff","Ship Staff Insp.","OWS BILGE PUMP NOT OPERATIONAL","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","COMPLETE PUMP RECEIVED AND INSTALLED ","2022-02-04T23:59:35","SCAR215173","Completed","2022-01-19T23:59:35","No","No","No","Internal","complete pump will supply in present port once vessel berthing"]
[null,null,null,23139,null,"112_4/12/2021 7:43:37 PM","2021-11-06T23:59:35","Defect","Ship Staff","Ship Staff Insp.","AHU#1 MOTOR CONTACTOR BURNT OUT","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","NEW CONTACTOR RENEWED & WORKING SATISFACTORY","2022-02-04T23:59:35","SCAR210121","Completed","2022-03-05T23:59:35","No","No","No","Internal",""]
[null,null,null,23137,null,"112_4/12/2021 7:56:22 PM","2021-11-07T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME OMD SENSORS SHOWING FAULT ALARM ON 3 UNITS","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","OMD sensors tested, tried out and found to be in good operational condition.","2022-02-03T23:59:35","SCAR215170","Completed","2022-04-15T23:59:35","No","No","No","Internal","spare will supply in present port once vessel berthing"]
[null,null,null,23138,null,"112_4/12/2021 8:08:13 PM","2021-11-07T23:59:35","Defect","Ship Staff","Ship Staff Insp.","DEFECTIVE SUCTION AND DISCHARGE PRESSURE GAUGES ON REEFER COMPRESSOR #1,2","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Replaced with new pressure gauge","2022-02-04T23:59:35","SCAR210120","Completed","2022-07-10T23:59:35","No","No","No","Internal","spare will supply in present port once vessel berthing"]
[null,null,null,18377,null,"112_20/3/2021 3:35:09 PM","2021-11-07T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME T/C gauge lube oil outlet gauge glass broken, need to order & renew.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Glass renewed.","2022-01-30T23:59:35","","Completed","2022-02-22T23:59:35","No","No","No","Internal","please raise RO for the spare. Vsl to confirm no oil leak from gauge glass."]
[null,null,null,18364,null,"112_20/3/2021 4:14:10 PM","2021-11-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All generators performance not satisfactory With no.2 DG Lo consumption on higher side around 60 Ltr per day, Need to carry out overhauling of DGs & supply spare parts accordingly.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","All generators overhauled. performance taken. All 3 generators performance is satisfactory.","2022-02-04T23:59:35","SCAR215105","Completed","2022-10-18T23:59:35","No","No","No","Internal","spare will supply in convenient port"]
[null,null,null,18383,null,"112_20/3/2021 3:59:13 PM","2021-11-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","GE & ME Viscotherm sensor to be procured & replaced","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Control valve renewed during recently concluded dry dock. Now both re operational","2022-02-04T23:59:35","SCAR215076    215077","Completed","2022-10-05T23:59:35","No","No","No","Internal","spare will supply in convenient port"]
[null,null,null,18371,null,"112_20/3/2021 3:43:06 PM","2021-11-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both Aircon units AHU evaporator coil needs to be replaced for running the system in full load ,at present No.2 Compressor not able to run as liquid gas returning into the suction side of compressor due to lack of heat transfer.No.1 system not able to load above 75% due to  lack of heat transfer  from Evaporator","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Evaporator renewed","2022-02-04T23:59:35","SCAR215036","Completed","2022-02-22T23:59:35","No","No","No","Internal","Starboard side evaporator has been replaced during vessel singapore call, vessel to update defect accordingly."]
[null,null,null,23140,null,"112_5/12/2021 4:36:29 AM","2021-11-11T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Corroded FL light fittings at various locations near accomodation area","Elect. Mach. & Equip.","Safety / LSA / FFA","Equipment Related","","","","","All corroded FL lights replaced with new ones","2022-02-09T23:59:35","SCAR210134","Completed","2022-10-11T23:59:35","No","No","No","Internal","spare will supply in next port"]
[null,null,null,18366,null,"112_19/3/2021 1:49:48 AM","2021-11-11T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Some oil pressure gauge of hatch cover open control system lost and damaged, order the gauges","Deck - Machinery","General Appearance","External Factors","","","","","The gauges have been receipt, but the connect were corroded serously, had raised requisition for connect again. Gauges renewed.","2022-02-09T23:59:35","SCAR215115,SCAR21083","Completed","2022-01-27T23:59:35","No","No","No","Internal"]
[null,null,null,23141,null,"112_7/12/2021 12:26:07 PM","2021-11-12T23:59:35","Defect","Ship Staff","Nav Audit / Verification","Forward navigation light shows back scatter even in good weather and clear visibilty.","Navigation - Others","Navigation","Equipment Related","","","","","NEW LIGHT INSTALLED","2022-02-09T23:59:35","","Completed","2022-04-02T23:59:35","No","No","No","Internal",""]
[null,null,null,23142,null,"112_15/12/2021 7:33:39 AM","2021-11-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","AE#1,2,3 LT system inlet and outlet valves not holding","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Valves replaced with new one.","2022-03-20T23:59:35","SCAR210139","Completed","2022-09-21T23:59:35","No","No","No","Internal","spare will supply in convenient port."]
[null,null,null,23143,null,"112_15/12/2021 7:45:31 AM","2021-11-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","UV steriliser germicidal lamp fused","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","LAMP RENEWED.","2022-02-09T23:59:35","SCAR215167","Completed","2022-05-30T23:59:35","No","No","No","Internal",""]
[null,null,null,23144,null,"112_15/12/2021 8:01:11 AM","2021-11-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Boiler smoke sensor for hypermist system inoperational","LSA / FFA","Eng. / Strg. Comp.","Equipment Related","","","","","Replaced with new spare","2022-02-09T23:59:35","SCAR215165","Completed","2022-07-22T23:59:35","No","No","No","Internal","spare sensor will supply in present port once vessel berthing"]
[null,null,null,18379,null,"112_20/3/2021 3:50:59 PM","2021-11-14T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LT,HT & Lo temp control vv actuator to be procured & supplied to vessel ,presently the controller & working in manual mode","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Actuators replaced with new one.","2022-02-09T23:59:35","","Completed","2022-09-27T23:59:35","No","No","No","Internal","please update status"]
[null,null,null,23145,null,"112_15/12/2021 8:09:59 AM","2021-11-15T23:59:35","Defect","Ship Staff","Ship Staff Insp.","AE#3 fuel leak off tank float chamberhigh level  alarm inoperational","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","ALARM TRIED OUT WORKING SATISFACTORY","2022-01-20T23:59:35","SCAR210130","Completed","2022-03-30T23:59:35","No","No","No","Internal",""]
[null,null,null,23146,null,"112_15/12/2021 8:32:55 PM","2021-11-21T23:59:35","Non Conformity","Ship Staff","Ship Staff Insp.","Rubber packings of the accommodation vent/fire flaps observed to be in poor condition.","Accommodation","Structural Condn. / WT integrity ","Equipment Related","","","","","Rubber packingS renewed.","2021-12-17T23:59:35","","Completed","2021-12-10T23:59:35","No","No","No","Internal"]
[null,null,null,23147,null,"112_15/12/2021 5:49:17 PM","2021-12-01T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Remote display of the aft draught in the cargo control room giving a false reading.","Miscellaneous","Cargo / Ballast Systems","Equipment Related","","","","","Aft draft gauge calibration carried out in DD and rectified.","2022-02-01T23:59:35","","Completed","2022-10-08T23:59:35","No","No","No","Internal","please check and confirm the draft gauge working condition and update"]
[null,null,null,26224,48210,"112_Fri Apr 29 2022 17:02:50 GMT+0800","2022-02-18T23:59:35","Defect,Non Conformity","Ship Staff","Ship Staff Insp.","44 nos. of ballast tank air vent covers observed to be defective/holed.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","The defective/holed section of the ballast tank air vent covers cropped and inserts of appropriate thickness put in.  ","2022-05-30T23:59:35","","Completed","2022-05-13T23:59:35","No","No","No","Internal"]
[null,null,null,26208,22990,"112_Wed May 25 2022 21:01:20 GMT+0800","2022-05-14T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","MLC OBS: Color coded chopping board and knives were not available on board.","Miscellaneous","MLC Related","Equipment Related","","","","","New chopping boards procured and colour coded.","2022-08-14T23:59:35","","Completed","2022-07-23T23:59:35","No","No","No","Internal","Will supply as required. to provide RO"]
[null,null,null,26209,15136,"112_Wed May 25 2022 21:13:57 GMT+0800","2022-05-14T23:59:35","Observation","Ship Staff","Ship Staff Insp.","The forward anchor light located atop the forward mast is located in an area of a very high potential near miss.\nAlthough fitted with a fixed working platform, said platform does not have hand railings on the outboard side i.e. any slip or loss of balance will inevitably result in a fall from height for the personnel working atop the mast.","Miscellaneous","Navigation","Equipment Related","","","","","Work aloft procedures to be complied with. Verified during DD that the renewal of light can be carried out safely with procedures in place and closed.","2022-08-20T23:59:35","","Completed","2022-09-25T23:59:35","No","No","No","Internal","Will check and install during DD"]
[null,null,null,26210,40115,"112_Wed May 25 2022 21:20:13 GMT+0800","2022-05-14T23:59:35","Non Conformity","Owner / Marine / Tech. Suptd.","ISPS Audit","ISPS NC: Stbd anchor hawse pipe cover securing arrangement found damaged. Same to be repaired.","Deck - Pipe / Fittings","ISPS Related","Equipment Related","","","","","Hawse pipe cover securing arrangement renewed","2022-08-14T23:59:35","","Completed","2022-09-30T23:59:35","No","No","No","Internal","This item has been included additional DD spec?"]
[null,null,null,26211,75800,"112_Wed May 25 2022 21:40:04 GMT+0800","2022-05-14T23:59:35","Observation","Owner / Marine / Tech. Suptd.","ISM Audit","ISM OBS: Gear oil gauge found opaque on multiple mooring winches.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Replaced with new ones","2022-08-14T23:59:35","","Completed","2022-09-30T23:59:35","No","No","No","Internal","To provide RO number"]
[null,null,null,26212,82843,"112_Wed May 25 2022 22:12:08 GMT+0800","2022-05-14T23:59:35","Non Conformity","Owner / Marine / Tech. Suptd.","ISM Audit","ISM NC: Vessel found not in compliance with TECHNICAL CIRCULAR/T-001R-2021 / E/R WORKSHOP MACHINERIES - OPERATION PHILOSOPHY.","Miscellaneous","ISM Related","Equipment Related","","","","","SPARES RECEIVED, FOOT SWITCH INSTALLED FOR ALL THE WORKSHOP MACHINES, WORKING SATISFACTORILY","2022-08-14T23:59:35","","Completed","2022-07-19T23:59:35","No","No","No","Internal"]
[null,null,null,26225,74172,"112_Wed May 25 2022 21:54:16 GMT+0800","2022-05-14T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ISM OBS: Safety Campaign 001 of 2022 has not been complied with in the E/R.","Miscellaneous","ISM Related","Human Error","","","","","Stenciling carried out in compliance with the Safety Campaign 001 of 2022.","2022-08-14T23:59:35","","Completed","2022-05-27T23:59:35","No","No","No","Internal"]
[null,null,null,26214,25422,"112_Fri Jul 01 2022 14:21:31 GMT+0800","2022-06-06T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Hatch cover opening gear seal leaking for no.6 cargo hold.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","Hatch cover motor overhauling carried out leak rectified","2022-08-21T23:59:35","","Completed","2022-10-02T23:59:35","No","No","No","Internal","To carry out overhaul during DD. make sure to keep spare kit on board"]
[null,null,null,26226,16088,"112_Fri Jul 01 2022 14:23:57 GMT+0800","2022-06-06T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Cargo hold booby hatch access  closure mechanism seized for No.1 & No.2 Cargo holds","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Inappropriate Procedure","","","","","Closure mechanism eased up and greased.","2022-07-06T23:59:35","","Completed","2022-06-12T23:59:35","No","No","No","Internal"]
[null,null,null,26215,75199,"112_Fri Jul 01 2022 14:27:54 GMT+0800","2022-06-09T23:59:35","Defect","Ship Staff","Ship Staff Insp.","One side bursting strap for forward life raft has come loose. ","LSA / FFA","Safety / LSA / FFA","External Factors","","","","","The bursting strap temporarily taped.","2022-08-20T23:59:35","","Completed","2022-07-11T23:59:35","No","No","No","Internal"]
[null,null,null,26216,85764,"0_Fri Jul 01 2022 14:34:35 GMT+0800","2022-06-09T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Most of the main deck & poop deck mushroom vent operating wheel found broken.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Inappropriate Procedure","","","","","Poop deck mushroom vent wheels lubricated and eased up. All mushroom vents on main deck replaced with new ones.","2022-08-09T23:59:35","","Completed","2022-09-22T23:59:35","No","No","No","Internal","lack of maintenance. to update till completion"]
[null,null,null,26223,14613,"0_Fri Jul 01 2022 14:30:28 GMT+0800","2022-06-09T23:59:35","Defect","Ship Staff","Ship Staff Insp.","No.1 hatch forward booby hatch access heavily rusted/ corroded.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Inappropriate Procedure","","","","","De-rusting of booby hatch area completed and area painted","2022-08-09T23:59:35","","Completed","2022-07-24T23:59:35","No","No","No","Internal","To carry out maintenance and update"]
[null,null,null,26227,40714,"0_Fri Jul 01 2022 14:33:14 GMT+0800","2022-06-09T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Most of the mushroom vents on main deck & poop deck found frozen to operate.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Inappropriate Procedure","","","","","All vents wheels freed up and greased.","2022-08-09T23:59:35","","Completed","2022-06-16T23:59:35","No","No","No","Internal"]
[null,null,null,26219,26594,"112_Mon Jul 04 2022 22:15:14 GMT+0800","2022-06-10T23:59:35","Defect","Ship Staff","Ship Staff Insp.","No.2 & No.8 cargo holds water ingress system pre-alarm and the main alarm is active in the panel.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","Both the cargo hold water ingress alarms were tested and found operational. After completion of test confirm that there are no any active alarms in the panel.","2022-07-30T23:59:35","","Completed","2022-09-30T23:59:35","No","No","No","Internal","to check and raise necessary RO if spare required"]
[null,null,null,26217,38550,"112_Fri Jul 01 2022 14:39:54 GMT+0800","2022-06-11T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Most of the scupper drain mesh outside accommodation are wasted.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","External Factors","","","","","Drain meshes renewed","2022-08-20T23:59:35","","Completed","2022-10-10T23:59:35","No","No","No","Internal","To fabricate drain mesh with vessel sample during DD"]
[null,null,null,26213,75031,"112_Fri Jul 01 2022 13:48:53 GMT+0800","2022-06-16T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Most of the manholes on main deck observed with studs missing/broken","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","External Factors","","","","","Missing studs were renewed during Drydock","2022-08-19T23:59:35","","Completed","2022-10-08T23:59:35","No","No","No","Internal","To be carry out during vessel in DD"]
[null,null,null,26218,12287,"112_Sat Jul 02 2022 20:16:27 GMT+0800","2022-06-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Control Air Drier is out of service since long time.  Both the control air drier PCBs found to be faulty.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","One Control Air Drier replaced with new one and put in use.","2022-08-19T23:59:35","SCAR220207","Completed","2022-10-05T23:59:35","No","No","No","Internal","spare will supply for 1 set of complete air dryer. will check PCB spare for another set."]
[null,null,null,26228,38289,"112_Sat Jul 02 2022 20:21:35 GMT+0800","2022-06-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","No.1 Refer system is not in operation since early June 2022 due to bend in the motor shaft.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Vessel received new motor and same fitted. & equipment is operational.","2022-08-19T23:59:35","","Completed","2022-07-04T23:59:35","No","No","No","Internal"]
[null,null,null,26220,95152,"112_Fri Jul 15 2022 18:07:47 GMT+0800","2022-06-22T23:59:35","Defect","Ship Staff","Ship Staff Insp.","MAIN ENGINE EMG MANUVERING CONSOLE TACHOMETER IS INOPERATIONAL","E/R - Main Engine","Emgcy. Systems","Equipment Related","","","","","NEW TACHOMETER RECEIVED AND FIXED ON ME LOCAL CONSOLE ","2022-09-04T23:59:35","SCAR210110","Completed","2022-08-24T23:59:35","No","No","No","Internal","Spare under processing. to collect during vessel DD"]
[null,null,null,26222,47605,"112_Fri Jul 15 2022 22:11:57 GMT+0800","2022-06-24T23:59:35","Defect","Ship Staff","Ship Staff Insp.","LT cooler inlet and outlet pipes have leakage.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","External Factors","","","","","PIPE RENEWED IN DRY DOCK","2022-09-19T23:59:35","","Completed","2022-08-18T23:59:35","No","No","No","Internal","Will renew during DD"]
[null,null,null,26221,77772,"112_Fri Jul 15 2022 22:09:31 GMT+0800","2022-06-25T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Most of the accommodation outside FRP weathertight doors are not sealing properly and few door are defective","Accommodation","Structural Condn. / WT integrity ","External Factors","","","","","Defective FRP weathertight doors have been renewed during DD.","2022-09-19T23:59:35","","Completed","2022-10-04T23:59:35","No","No","No","Internal","Will attend during DD"]
[null,null,null,29220,49091,"112_Wed Mar 08 2023 03:26:53 GMT+0800","2022-06-28T23:59:35","Observation","Ship Staff","Nav Audit / Verification","No distraction policy not posted. on bridge","","Navigation","Inappropriate Procedure","","","","","policy posted/closed out","2022-09-28T23:59:35","","Completed","2022-06-29T23:59:35","No","No","No","Internal"]
[null,null,null,29221,16231,"0_Wed Mar 08 2023 03:28:23 GMT+0800","2022-06-28T23:59:35","Non Conformity","Ship Staff","Nav Audit / Verification","nav warnings received not signed by all OOW's","","Navigation","Inappropriate Procedure","","","","","immediately all OOW's briefed/ closed out","2022-09-28T23:59:35","","Completed","2022-06-28T23:59:35","No","No","No","Internal"]
[null,null,null,29222,86318,"0_Wed Mar 08 2023 03:29:44 GMT+0800","2022-06-28T23:59:35","Observation","Ship Staff","Nav Audit / Verification","cyber security policy not posted","","Navigation","Inappropriate Procedure","","","","","policy posted/ closed out","2022-09-28T23:59:35","","Completed","2022-06-28T23:59:35","No","No","No","Internal"]
[null,null,null,26404,90521,"112_Wed Aug 03 2022 12:25:03 GMT+0800","2022-07-04T23:59:35","Observation","Ship Staff","Ship Staff Insp.","The VDR software is available onboard but same is not configured","Navigation - VDR / BNWAS","Navigation","Inappropriate Procedure","","","","","VDR software configuration completed and installed on both NAV laptops","2022-11-03T23:59:35","","Completed","2022-10-07T23:59:35","No","No","No","Internal","to liaise with IT department and get update"]
[null,null,null,26403,17056,"112_Sun Jul 31 2022 10:51:58 GMT+0800","2022-07-17T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","FORWARD BOSUN STORE MOTOR ISINOPERATION. MOTOR ROTOR FOUND WORN OUT AND IMBALANCE DUE TO WATER INGRESS.","Deck - Machinery","Safety / LSA / FFA","Equipment Related","","","","","Replaced with new motor","2022-09-17T23:59:35","SCAR 220211","Completed","2022-10-12T23:59:35","No","No","No","Internal","Spare motor will supply during DD"]
[null,null,null,27335,62231,"0_Wed Nov 02 2022 09:19:20 GMT+0800","2022-09-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All mooring winches to maintenance","Deck - Mooring Machinery","Mooring","External Factors,Inappropriate Procedure","","","","","Fwd spring winch de rusted and painted - all mooring winch in good conditions\n","2023-08-24T23:59:35","","Completed","2023-05-17T23:59:35","No","No","No","Internal","To complete and update within due date"]
[null,null,null,27317,27758,"0_Tue Nov 01 2022 18:09:42 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ER Entrance step of china passage to repair","Miscellaneous","Eng. / Strg. Comp.","","","","","","Entrance step of china passage repaired by fabricated new step in place.","2022-11-15T23:59:35","","Completed","2023-01-12T23:59:35","No","No","No","Internal","To carry out as per schedule"]
[null,null,null,27318,22485,"112_Tue Nov 01 2022 18:07:03 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ER bulkhead to soap wash and paint","Miscellaneous","Eng. / Strg. Comp.","","","","","","Bulkhead cleaned and paintned.","2022-11-20T23:59:35","","Completed","2023-03-26T23:59:35","No","No","No","Internal","To update once complete"]
[null,null,null,27319,82707,"112_Tue Nov 01 2022 18:08:06 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Tank top to clean and paint","Miscellaneous","Eng. / Strg. Comp.","","","","","","Remaining 20% of the tank top area cleaned and painted.","2022-11-22T23:59:35","","Completed","2023-02-25T23:59:35","No","No","No","Internal","To carry out as per plan"]
[null,null,null,27320,64722,"0_Tue Nov 01 2022 18:12:02 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Spare and store room to arrange properly.","Miscellaneous","Eng. / Strg. Comp.","","","","","","Store room cleaned and arranged.","2022-11-17T23:59:35","","Completed","2023-02-22T23:59:35","No","No","No","Internal","To update once job completion"]
[null,null,null,27321,46599,"0_Tue Nov 01 2022 18:13:29 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Purifier room oil to clean up","E/R - Pumps,E/R - Purifier","Eng. / Strg. Comp.","Behaviour Based","","","","","Purifier room leaks rectified, cleaned and painted.","2022-11-20T23:59:35","","Completed","2022-12-23T23:59:35","No","No","No","Internal","To update once job done"]
[null,null,null,27322,30928,"0_Tue Nov 01 2022 18:22:51 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NEW SEA WATER PIPE AND BWTS PIPE TO PAINT","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","","","","","","BWTS pipeline installed newly cleaning and painting completed.","2022-11-22T23:59:35","","Completed","2023-01-25T23:59:35","No","No","No","Internal","To expedite the job"]
[null,null,null,27323,26501,"0_Tue Nov 01 2022 18:21:03 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","BOTTOM FLOOR FUSED LAMP AND DAMAGED COVER TO RENEW","Miscellaneous","Eng. / Strg. Comp.","","","","","","All fused lamps and damaged covers have been renewed.","2022-10-17T23:59:35","","Completed","2022-10-25T23:59:35","No","No","No","Internal"]
[null,null,null,27324,23419,"0_Tue Nov 01 2022 18:25:21 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","ALL BURNING MARK DUE TO BWTS INSTALLATION TO TOUCH UP","Miscellaneous","Eng. / Strg. Comp.","","","","","","All burning marks due to BWTS installation painted.","2022-11-15T23:59:35","","Completed","2023-01-07T23:59:35","No","No","No","Internal","To carry out as per plan and update"]
[null,null,null,27325,37068,"0_Tue Nov 01 2022 18:19:11 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ALL FLOOR TO CLEAN AND PAINT","Miscellaneous","Eng. / Strg. Comp.","","","","","","Cleaning , de-rusting and painting carried out.","2022-11-30T23:59:35","","Completed","2022-12-13T23:59:35","No","No","No","Internal","To carry out within the due date"]
[null,null,null,27326,73712,"0_Tue Nov 01 2022 18:17:11 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME LINER PLATFORM TO REMOVE SOOT AND CLEAN","Miscellaneous","Eng. / Strg. Comp.","","","","","","ME liner platform all soot removed and cleaned.","2022-11-17T23:59:35","","Completed","2023-01-05T23:59:35","No","No","No","Internal","To complete within due date"]
[null,null,null,27327,82311,"0_Wed Nov 02 2022 08:59:44 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fwd new platform to paint","Miscellaneous","General Appearance","Inappropriate Procedure","","","","","Platform to be painted after power tooling paint damage areas","2022-11-15T23:59:35","","Completed","2022-12-02T23:59:35","No","No","No","Internal","To complete job ASAP"]
[null,null,null,27328,96391,"0_Wed Nov 02 2022 08:55:02 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fwd store fan to recover","Elect. Mach. & Equip.","General Appearance","Equipment Related","","","","","Fan motor has been fitted and tried out","2022-10-13T23:59:35","","Completed","2022-10-18T23:59:35","No","No","No","Internal"]
[null,null,null,27329,90279,"0_Wed Nov 02 2022 09:01:40 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","New installed Panama chock and bollard welding area to paint","Deck - Pipe / Fittings","Mooring","External Factors","","","","","Welding areas of panama chock & bollard areas to de-rust & paint","2022-11-15T23:59:35","","Completed","2022-12-01T23:59:35","No","No","No","Internal","To carry out and update"]
[null,null,null,27330,74204,"0_Tue Nov 01 2022 18:31:03 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AC ROOM TO ARRANGE AND CLEAN UP","Miscellaneous","Eng. / Strg. Comp.","","","","","","Air Con Room arranged , cleaned and painted","2022-11-07T23:59:35","","Completed","2022-11-06T23:59:35","No","No","No","Internal"]
[null,null,null,27331,84966,"112_Wed Nov 02 2022 08:48:37 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fwd store to arrange and clean up bulkhead and paint","Miscellaneous","General Appearance","External Factors","","","","","Fwd store arranged & cleaned","2022-11-04T23:59:35","","Completed","2022-11-07T23:59:35","No","No","No","Internal"]
[null,null,null,27332,74986,"0_Wed Nov 02 2022 09:16:43 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All new hydraulic pipes to paint","Deck - Pipe / Fittings","General Appearance","Inappropriate Procedure","","","","","Hydraulic pipelines to be painted after cleaning","2022-11-30T23:59:35","","Completed","2022-12-05T23:59:35","No","No","No","Internal","To carry out and update"]
[null,null,null,27333,65446,"0_Wed Nov 02 2022 09:04:47 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Remaining hatch cover back side to chip and paint","Miscellaneous","General Appearance","Inappropriate Procedure,External Factors","","","","","Almost all HC underneath maintenance job has been completed, No 6 will be carried out at next anchorage","2023-07-29T23:59:35","","Completed","2023-05-06T23:59:35","No","No","No","Internal","To complete as per vessel schedule"]
[null,null,null,27334,51262,"0_Wed Nov 02 2022 09:43:19 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both bunker hose crane to maintenance and paint, stbd wire end to fix bolt for clamp","Miscellaneous","General Appearance","Inappropriate Procedure","","","","","Bunker davits to be de-rusted and painted","2022-12-24T23:59:35","","Completed","2023-02-08T23:59:35","No","No","No","Internal","To carry out as per vessel plan"]
[null,null,null,27336,17022,"0_Wed Nov 02 2022 09:45:41 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Railings which repaired to paint","Miscellaneous","General Appearance","Inappropriate Procedure","","","","","Repaired railings to be painted","2022-11-15T23:59:35","","Completed","2022-12-08T23:59:35","No","No","No","Internal","To complete and update within due date"]
[null,null,null,27337,16658,"0_Wed Nov 02 2022 09:50:12 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Renewed fire line and air line to paint","Deck - Pipe / Fittings","General Appearance","Inappropriate Procedure","","","","","All fire line & air line painting in progress","2022-11-15T23:59:35","","Completed","2022-11-27T23:59:35","No","No","No","Internal","To complete and update within due date"]
[null,null,null,27338,66656,"0_Wed Nov 02 2022 09:53:45 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Port and stbd navigation light casing to maintenance","Navigation - Others","General Appearance","External Factors","","","","","derusted and painted","2022-12-24T23:59:35","","Completed","2023-03-10T23:59:35","No","No","No","Internal","To complete and update within due date"]
[null,null,null,27339,97873,"0_Wed Nov 02 2022 09:54:47 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Accommodation remaining area to paint final coat","Accommodation","General Appearance","External Factors","","","","","Major part of accommodation is been covered, rest is ongoing process.\n","2023-08-24T23:59:35","","Completed","2023-05-24T23:59:35","No","No","No","Internal","To complete and update within due date"]
[null,null,null,27340,32784,"0_Tue Nov 01 2022 18:15:16 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","3 SETS OF AUX ENGINE BODY AND UNDERNEATH AREA TO CLEAN AND PAINT","E/R - Aux. Engine","Eng. / Strg. Comp.","Behaviour Based","","","","","Cleaning and painting carried out","2022-11-20T23:59:35","","Completed","2022-12-08T23:59:35","No","No","No","Internal","To rectify leakage if any then carry out clean and paint"]
[null,null,null,27341,76973,"0_Wed Nov 02 2022 09:34:40 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Painting to carry out for hatch cover operation control boxes","Miscellaneous","General Appearance","External Factors","","","","","lower edges of control boxes cropped and renewed and painted ","2023-08-26T23:59:35","","Completed","2023-05-26T23:59:35","No","No","No","Internal","To complete and update within due date"]
[null,null,null,27342,25544,"112_Tue Nov 01 2022 18:04:12 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Funnel Chamber fused lights to rectify","E/R - Main Engine,Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","All fused lights in funnel chamber replaced.","2022-10-13T23:59:35","","Completed","2022-10-13T23:59:35","No","No","No","Internal"]
[null,null,null,27343,68151,"0_Wed Nov 02 2022 09:14:44 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","All hatch pinion gear, roll up gear to grease","Miscellaneous","General Appearance","Inappropriate Procedure,External Factors","","","","","All hatch cover cog wheels greasing carried out","2022-10-17T23:59:35","","Completed","2022-10-18T23:59:35","No","No","No","Internal"]
[null,null,null,27344,13902,"0_Wed Nov 02 2022 08:57:51 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both  windlass to grease and maintenance","Deck - Mooring Machinery","Mooring","Inappropriate Procedure","","","","","Both windlasses greasing carried out.","2022-10-15T23:59:35","","Completed","2022-10-18T23:59:35","No","No","No","Internal"]
[null,null,null,27345,41293,"0_Tue Nov 01 2022 18:26:59 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","USED SPARES TO ARRANGE AND SECURE","Miscellaneous","Eng. / Strg. Comp.","","","","","","ALL SPARES ARRANGED AND SECURED.","2022-10-17T23:59:35","","Completed","2022-10-15T23:59:35","No","No","No","Internal"]
[null,null,null,27346,22285,"112_Wed Nov 02 2022 09:32:07 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Hatch cover hydraulic pump room to arrange and clean up","Miscellaneous","General Appearance","Inappropriate Procedure","","","","","Hatch cover hydraulic pump room cleaning carried out & arranged","2022-10-14T23:59:35","","Completed","2022-10-14T23:59:35","No","No","No","Internal"]
[null,null,null,27347,72390,"0_Tue Nov 01 2022 18:32:29 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","EMG GENERATOR ROOM TO CLEAN UP","Miscellaneous","Eng. / Strg. Comp.","","","","","","EMG GEN ROOM CLEANED.","2022-10-15T23:59:35","","Completed","2022-10-14T23:59:35","No","No","No","Internal"]
[null,null,null,27348,14815,"0_Tue Nov 01 2022 18:29:15 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME EXHAUST MANIFOLD END COVER TO PAINT","E/R - Main Engine","Eng. / Strg. Comp.","","","","","","ME EXHAUST MANIFOLD END COVER PAINTED ","2022-11-12T23:59:35","","Completed","2022-10-15T23:59:35","No","No","No","Internal"]
[null,null,null,27349,85314,"0_Wed Nov 02 2022 09:51:36 GMT+0800","2022-10-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fwd liferaft casing to remove stain colour","LSA / FFA","General Appearance","External Factors","","","","","Life raft casing cleaning carried out","2022-10-15T23:59:35","","Completed","2022-10-15T23:59:35","No","No","No","Internal"]
[null,null,null,28069,60339,"112_Thu Dec 22 2022 08:41:19 GMT+0800","2022-10-25T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Steering room bilge alarm starboard side float switch defective.","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Bilge level float received and fitted in place. Alarm tested working satisfactory.","2023-01-24T23:59:35","SCAR 220252","Completed","2022-12-19T23:59:35","No","No","No","Internal","spare will supply next convenient port"]
[null,null,null,27590,97016,"112_Tue Nov 15 2022 20:02:15 GMT+0800","2022-10-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Lifeboat hook was found to be painted","LSA / FFA","Safety / LSA / FFA","Inappropriate Procedure","","","","","Paint  removed and hook  greased","2022-12-10T23:59:35","","Completed","2022-12-10T23:59:35","No","No","No","Internal","To complete ASAP"]
[null,null,null,27591,39560,"0_Tue Nov 15 2022 20:04:01 GMT+0800","2022-10-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Greasing of hatch cover cleats to be carried out","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Inappropriate Procedure","","","","","All hatch cover auto cleats greasing completed","2022-12-24T23:59:35","","Completed","2023-01-04T23:59:35","No","No","No","Internal","To complete prior target date and update"]
[null,null,null,27592,37726,"112_Tue Nov 15 2022 20:45:00 GMT+0800","2022-10-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Few of the crew members were using walkie takies without holsters.","Miscellaneous","Crew Management","Equipment Related","","","","","completed","2022-12-16T23:59:35","","Completed","2022-12-18T23:59:35","No","No","No","Internal","Spare case will supply in next convenient port"]
[null,null,null,27593,31552,"112_Tue Nov 15 2022 20:48:49 GMT+0800","2022-10-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Scupper plug openings on the main deck to be clear of rust and all scupper plugs to be tight.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Inappropriate Procedure","","","","","Scupper plug openings on the main deck cleared of rust and all scupper plugs  tight.","2022-11-20T23:59:35","","Completed","2022-12-10T23:59:35","No","No","No","Internal","to complete ASAP"]
[null,null,null,27594,63723,"112_Tue Nov 15 2022 20:54:29 GMT+0800","2022-10-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Monorail hook swivel to be eased up and free.","Deck - Machinery","ISM Related","Inappropriate Procedure","","","","","Monorail hook swivel to be eased up and free.","2022-11-15T23:59:35","","Completed","2022-11-17T23:59:35","No","No","No","Internal","To carry out ASAP"]
[null,null,null,27595,20755,"112_Tue Nov 15 2022 20:56:47 GMT+0800","2022-10-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Monorail hook safety latch is to be renewed.","Deck - Machinery","ISM Related","Inappropriate Procedure","","","","","Monorail hook safety latch wasted .same to be renewed","2022-11-15T23:59:35","","Completed","2022-11-16T23:59:35","No","No","No","Internal","To fabricate and install as plan"]
[null,null,null,27596,87225,"0_Tue Nov 15 2022 20:58:25 GMT+0800","2022-10-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Save all tray drain plugs to be attached with chain or wire","Miscellaneous","MARPOL Related","Inappropriate Procedure","","","","","Completed","2022-12-24T23:59:35","","Completed","2023-03-04T23:59:35","No","No","No","Internal","To fabricate and install as plan"]
[null,null,null,27597,24613,"0_Tue Nov 15 2022 21:00:13 GMT+0800","2022-10-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Mooring winch sight glasses to be clear and not painted over.","Deck - Mooring Machinery","Mooring","Inappropriate Procedure","","","","","Mooring winch sight glasses  cleared ","2022-11-23T23:59:35","","Completed","2022-12-10T23:59:35","No","No","No","Internal","To carry out and update ASAP"]
[null,null,null,27598,57125,"112_Tue Nov 15 2022 21:01:57 GMT+0800","2022-10-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","All mooring winch & windlass greasing points to be identified, highlighted and numbered as per manual.","Deck - Machinery","Mooring","Inappropriate Procedure","","","","","All mooring winch & windlass greasing points  identified, highlighted and numbered as per manual.","2022-12-24T23:59:35","","Completed","2023-01-24T23:59:35","No","No","No","Internal","TO make it as per vessel planning."]
[null,null,null,27599,25631,"112_Tue Nov 15 2022 17:55:48 GMT+0800","2022-10-31T23:59:35","Non Conformity","FSC Inspector","Flag State Insp.","Oil Leakage from Auxiliary Engine Noticed","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Oil Leakages Rectified. Auxiliary Engine trays cleaned and painted","2022-11-14T23:59:35","","Completed","2022-11-04T23:59:35","No","No","No","External"]
[null,null,null,27600,40030,"112_Tue Nov 15 2022 18:10:57 GMT+0800","2022-10-31T23:59:35","Non Conformity","FSC Inspector","Flag State Insp.","Fire Damper Of Emergency Generator Air Intake is out of service","Miscellaneous","Safety / LSA / FFA","Equipment Related","","","","","Emergency Generator Radiator damper has been made operational.","2022-11-14T23:59:35","","Completed","2022-11-04T23:59:35","No","No","No","External"]
[null,null,null,27601,27961,"112_Tue Nov 15 2022 18:02:11 GMT+0800","2022-10-31T23:59:35","Non Conformity","FSC Inspector","Flag State Insp.","Emergency Switchboard 220V Panel - Low Insulation","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","","","","","Emergency Switchboard press button for insulation checking was malfunctioning. Same has been replaced with new one.","2022-11-14T23:59:35","","Completed","2022-11-06T23:59:35","No","No","No","External"]
[null,null,null,28066,62668,"112_Thu Dec 22 2022 08:26:56 GMT+0800","2022-11-24T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Deck lights & fittings, Flood lights damaged and defective due to corrosion. Causing low insulation alarm. Request raised awaiting for spares.","Elect. Mach. & Equip.","ISPS Related","Equipment Related","","","","","Received as per RO SCAR 220262, deck and flood light fittings renewed deck lightings.","2023-01-26T23:59:35","SCAR 220262","Completed","2023-03-11T23:59:35","No","No","No","Internal","spare will supply next convenient port"]
[null,null,null,28067,57893,"112_Thu Dec 22 2022 08:31:07 GMT+0800","2022-11-24T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Engine room lighting diffusers cracked and discolored need replacement.","Elect. Mach. & Equip.","Safety / LSA / FFA","Equipment Related","","","","","New requisition has been raised as SCAR 230094.\nNeed to renew the lamp shade covers.","2023-05-26T23:59:35","SCAR230094","Completed","2023-05-26T23:59:35","No","No","No","Internal","spare will supply next convenient port"]
[null,null,null,28068,61232,"112_Thu Dec 22 2022 08:34:08 GMT+0800","2022-11-30T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Signaling light switches defective, need replacement.","Navigation - Others","Navigation","Equipment Related","","","","","RO received and defective panel switch replaced.","2023-01-24T23:59:35","SCAR 220162","Completed","2023-03-25T23:59:35","No","No","No","Internal","spare will supply next convenient port"]
[null,null,null,28244,83715,"112_Fri Jan 06 2023 17:34:26 GMT+0800","2022-12-10T23:59:35","Defect","Ship Staff","Ship Staff Insp.","AE flowmeter not working, not showing fuel consumption.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Informed office and maker, as per their instructions flowmeter opened and cleaned and put back in use. Now its working and showing fuel consumption.","2023-01-25T23:59:35","","Completed","2022-12-30T23:59:35","No","No","No","Internal"]
[null,null,null,28242,70497,"112_Fri Jan 06 2023 17:45:10 GMT+0800","2022-12-14T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Hypermist detection system showing faulty alarm due to fire detection sensor base in purifier room.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","RO received, faulty sensor replaced. System tested working satisfactory without any faulty alarm.","2023-02-22T23:59:35","SCAR220265","Completed","2023-02-10T23:59:35","No","No","No","Internal"]
[null,null,null,29218,78447,"112_Wed Mar 08 2023 03:17:46 GMT+0800","2022-12-16T23:59:35","Observation","Ship Staff","Nav Audit / Verification","COURSE RECORDER PLOTTER PEN INOPERATIONAL","Navigation - Others","Navigation","Equipment Related","","","","","received required spares/ Closed out","2023-03-15T23:59:35","","Completed","2023-01-21T23:59:35","No","No","No","Internal"]
[null,null,null,29219,71285,"112_Wed Mar 08 2023 03:23:57 GMT+0800","2022-12-16T23:59:35","Observation","Ship Staff","Nav Audit / Verification","FIRE ALARM PANEL HAVE A BATTERY FAULT ALARM","Accommodation","Safety / LSA / FFA","Equipment Related","","","","","Battery received and replaced/ closed out","2023-03-15T23:59:35","","Completed","2022-12-18T23:59:35","No","No","No","Internal"]
[null,null,null,29223,38133,"112_Wed Mar 08 2023 03:21:23 GMT+0800","2022-12-16T23:59:35","Observation","Ship Staff","Nav Audit / Verification","BRIDGE WINDOW WIPERS HAVE NO SPARES ONBOARD","Navigation - Others","Navigation","Equipment Related","","","","","spares received/closed out","2023-03-15T23:59:35","","Completed","2022-12-18T23:59:35","No","No","No","Internal"]
[null,null,null,28243,21183,"112_Fri Jan 06 2023 17:41:10 GMT+0800","2022-12-18T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","In engine room workshop, fire retardant curtain not in place for welding area.","Miscellaneous","Safety / LSA / FFA","Equipment Related","","","","","Fire retardant curtain received and installed in place.","2023-02-22T23:59:35","SCAR230004","Completed","2023-01-10T23:59:35","No","No","No","Internal"]
[null,null,null,30210,35589,"112_Tue May 30 2023 21:34:15 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FWD MAST LIGHT FACING AFT AND DECK LIGHT ON THE MONKEY ISLAND FACING FWD NOTED OUT OF ORDER.","Miscellaneous","General Appearance","Equipment Related","","","","","LIGHTS REPAIRED AND IN WORKING CONDITION","2023-01-31T23:59:35","","Completed","2023-01-31T23:59:35","No","No","No","Internal"]
[null,null,null,30211,12967,"112_Tue May 30 2023 21:38:35 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","GANGWAY SAFETY CHAINS NEXT TO THE PORT AND STBD GANGWAYS NOTED SLACK","Miscellaneous","General Appearance","Human Error","","","","","SAFETY CHAINS TIGHTENED.","2023-02-02T23:59:35","","Completed","2023-02-01T23:59:35","No","No","No","Internal"]
[null,null,null,30212,75814,"112_Tue May 30 2023 21:41:03 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NUMBERS OF IMO SYMBOLS ON DECK NOTED FADED AWAY","LSA / FFA","Safety / LSA / FFA","Human Error","","","","","ALL IMO SYMBOLS WERE CHECKED AND THE FADED SYMBOLS WERE REPLACED WITH NEW ONES.","2023-02-02T23:59:35","","Completed","2023-02-01T23:59:35","No","No","No","Internal"]
[null,null,null,30213,51793,"112_Tue May 30 2023 21:43:37 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","OXYGEN AND ACETYLENE STORES IN POOP DECK NOT ARRANGED, POOR HOUSEKEEPING NOTED","Miscellaneous","General Appearance","Human Error","","","","","STORE ARRANGED AND ALL THE CYLINDERS MARKED AND SECURED.","2023-02-02T23:59:35","","Completed","2023-01-31T23:59:35","No","No","No","Internal"]
[null,null,null,30214,22022,"112_Tue May 30 2023 21:45:32 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","THREE LIGHTS IN CO2 ROOM FOUND OUT OF ORDER","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","BUSTED LIGHTS REPLACED.","2023-02-01T23:59:35","","Completed","2023-02-01T23:59:35","No","No","No","Internal"]
[null,null,null,30215,72270,"112_Tue May 30 2023 21:47:43 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","FEW FRESH WATER VALVE ON DECK WITHOUT CAP","Deck - Pipe / Fittings","General Appearance","Equipment Related","","","","","NEW CAPS FABRICATED AND INSTALLED.","2023-02-04T23:59:35","","Completed","2023-02-03T23:59:35","No","No","No","Internal"]
[null,null,null,30216,28493,"112_Tue May 30 2023 21:50:39 GMT+0800","2023-01-30T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AC COMPRESSOR GAUGE TO CHECK CONDITION","Elect. Mach. & Equip.","MLC Related","Equipment Related","","","","","REPLACED THE DEFECTIVE GAUGES WITH NEW SPARE, AND CARRIED-OUT LEAK TEST OF THE GAUGES FITTINGS.","2023-02-01T23:59:35","","Completed","2023-01-31T23:59:35","No","No","No","Internal",""]
[null,null,null,30217,29033,"112_Tue May 30 2023 23:48:40 GMT+0800","2023-01-30T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LEAKING OBSERVED FROM THE FO PURIFIER","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","RECTIFIED LEAKING FROM THE PURIFIER BY RENEWAL OF O-RING FROM THE DUPLEX FILTER WITH NEW SPARE.","2023-02-06T23:59:35","","Completed","2023-02-04T23:59:35","No","No","No","Internal"]
[null,null,null,30218,98106,"112_Tue May 30 2023 21:19:51 GMT+0800","2023-01-30T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NUMBER OF FAIRLEADS(FWD & AFT SPRINGS) ON DECK NOTED CEASED AND NOT MOVING AT ALL.","Deck - Pipe / Fittings","Mooring","Human Error","","","","","ALL THE FAIRLEADS CHECKED, GREASED AND MOVED. ALL THE FAIRLEADS IN MOVING CONDITION.","2023-02-19T23:59:35","","Completed","2023-02-15T23:59:35","No","No","No","Internal"]
[null,null,null,30219,35451,"112_Tue May 30 2023 23:55:27 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","ME TC FLOOR TO CLEAN AND PAINT","E/R - Main Engine","Eng. / Strg. Comp.","External Factors","","","","","CARRIED-OUT PARTIAL DE-RUSTING BY CHIPPING AND OF THE ME FLOORINGS AND APPLIED 2 COATS OF PRIMER PAINTS AND 1 COAT OF TOP COAT PAINT","2023-02-14T23:59:35","","Completed","2023-02-11T23:59:35","No","No","No","Internal"]
[null,null,null,30220,31448,"112_Tue May 30 2023 23:54:11 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","WELDING MACHINE MCB TO FABRICATE BOX AND INSTALL","Elect. Mach. & Equip.","Emgcy. Systems","Equipment Related","","","","","FABRICATED NEW STEEL BOX FOR WELDING MACHINE MCB AND INSTALLED IN POSITION.","2023-02-06T23:59:35","","Completed","2023-02-06T23:59:35","No","No","No","Internal"]
[null,null,null,30221,98243,"112_Tue May 30 2023 23:52:51 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","TANK TOP REST 20% TO COMPLETE CHIPPING AND PAINT ","Miscellaneous","General Appearance","External Factors","","","","","CARRIED-OUT TOP TANK CLEANING, DE-RUSTING AND REPAINTING WITH PRIMER AND TOP COAT.","2023-02-07T23:59:35","","Completed","2023-02-09T23:59:35","No","No","No","Internal"]
[null,null,null,30222,35650,"112_Tue May 30 2023 23:51:26 GMT+0800","2023-01-30T23:59:35","Critical Equipment","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NO.2 BALLAST PUMP LEAKING FROM MECHANICAL SEAL","E/R - Pumps","Cargo / Ballast Systems","Equipment Related","","","","","CARRIED-OUT OVERHAULING OF THE BALLAST PUMP NO. 2, RENEWED THE MECHANICAL SEAL, WEAR RING, SLEEVE, LINE BEARING. AFTER OVERHAULING AND BOXED-UP THE PUMP WERE TESTED AND FOUND SATISFACTORY.","2023-02-09T23:59:35","","Completed","2023-02-08T23:59:35","No","No","No","Internal"]
[null,null,null,30223,59246,"112_Tue May 30 2023 23:50:10 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","COSMETIC APPEARANCE IN THE ENGINE ROOM NEEDS TO BE IMPROVED AND SPARES & STORES TO ARRANGE","Miscellaneous","Eng. / Strg. Comp.","Human Error","","","","","CARRIED-OUT COSMETICS ON VARIOUS LOCATION IN ENGINE ROOM BY CLEANING AND REPAINTING. SPARES AND STORE ROOM WERE CLEANED AND ARRANGE THE SPARE PARTS AND TOOLS.  ","2023-02-09T23:59:35","","Completed","2023-02-05T23:59:35","No","No","No","Internal"]
[null,null,null,30224,75767,"112_Tue May 30 2023 23:56:35 GMT+0800","2023-01-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","WASTER OIL TANK UNDERNEATH TO CLEAN AND PAINT","Miscellaneous","Eng. / Strg. Comp.","External Factors","","","","","CARRIED-OUT SCRAPING, CLEANING AND REPAINTING OF THE WASTE OIL TANK BENEATH PLATFORM.","2023-02-04T23:59:35","","Completed","2023-02-04T23:59:35","No","No","No","Internal"]
[null,null,null,29216,97834,"112_Sun Mar 05 2023 22:43:32 GMT+0800","2023-02-11T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Fire and GS pump leaking from mechanical seal, whether running or not running.","E/R - Pumps","Emgcy. Systems","Equipment Related","","","","","Fire and GS pump overhauled, and renewed mechanical seal.","2023-02-22T23:59:35","","Completed","2023-02-12T23:59:35","No","No","No","Internal"]
[null,null,null,29901,62166,"112_Sun Apr 16 2023 12:31:44 GMT+0800","2023-04-03T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Ballast pump #1 shaft mechanical seal leaking.","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Vessel replaced Mechanical seal, line bearing and assembled pump and motor in place and tested, now working without any leakage.","2023-07-11T23:59:35","","Completed","2023-04-14T23:59:35","No","No","No","Internal"]
[null,null,null,29900,27911,"112_Sun Apr 30 2023 12:17:05 GMT+0800","2023-04-24T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Stbd side mid ship accommodation ladder electric winch gear box leaking ","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","leakage of accommodation ladder electric winch gear box to be rectify, It was found that oil level were overfilled during last changed-oil. Partially drained the oil to the upper level, then checked the unit and found no more oil leakages.","2023-06-25T23:59:35","","Completed","2023-06-26T23:59:35","No","No","No","Internal"]
[null,null,null,null,71392,"112_Sat Sep 09 2023 10:03:03 GMT+0800","2023-08-20T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Main Engine Oil Mist Detector LCD display is showing Replace EPROM.\nAs per the Makers Instruction it needs Renewal.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Spares received under PO: SCAR235052.\nSame renewed & programmed as per maker's instructions.\nSystem normal, alarm tried out working satisfactory.","2023-09-29T08:00:00","SCAR235052","Completed","2023-09-14T08:00:00","No","No","No","Internal","Item is dispatched to Dampier."]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME"]
["112","SCARLETT (10-09-2023)","112_1694345879055.xlsm"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]