{"text_format":"1","workbook":"xlsx","n_sheets":24,"sheets":["Mainsheet","Completed","Calc","Areaofobs","Vessel_type","Deficiency_type","VIQrefno","Equipment_list","PSC_MOU","Inspection_type","Deficiency_Cause","Observer_code","Status_code","PSC_ref_no","Risk_value_of_obs","Year","Month","Date_","Sheet1","Ship_information","External_Deficiency_type","External_Inspection_type","External_Observer_code","Sheet Version"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mainsheet","index":0,"n_rows":30,"n_cols":28,"rows_kept":30,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","31-Mar-2024",null,null,"Ship Name","CAPE BOSS (21-12-2023)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,null,25204,"111_Sat Apr 15 2023 09:55:24 GMT+0800","2023-04-15T08:00:00","Defect","Ship Staff","Ship Staff Insp.","ALARM INDICATION LAMPS ON BRIDGE FOR STEERING GEAR IS NON FUNCTIONAL","Navigation - Others","Navigation","Equipment Related","","","","","RO RAISED AS ALARM INDICATION LAMPS ON BRIDGE FOR STEERING GEAR PLC FOR STEERING GEAR ALARM PANEL ON BRIDGE  MAKER NAIS MODEL FPO- C14RM CONTROL VOLTAGE 24VOLTS, REQ NO-CBOS230003\nService Engineer attended at Singapore on 19/Nov/23 and advise to change PLC. New requisition raised in 2024 CBOS240014.","2024-05-15T08:00:00","CBOS240014","Waiting spare",null,"No","No","No","Internal","21/12 - Service attendace made and repairs attempted. due to out dated  - same spares/ alternative being sourced - target date renewed."]
[null,null,null,32545,12608,"111_Sun Oct 22 2023 21:20:01 GMT+0800","2023-10-16T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Diesel oil storage tank sounding pipe on deck holed ","Deck - Pipe / Fittings,Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related","","","","","","2025-04-16T23:59:35","","Deferred to D D",null,"No","Yes","No","Internal"]
[null,null,null,null,29627,"111_Thu Nov 16 2023 13:50:12 GMT+0800","2023-10-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Heavy Vibration in No.1 (S) E/R Blower during running.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Major maintenance was carried out at China Drydock in July 2023.\nWorkshop assistance will be provided for the above job as per office instructions. Shore workshop attended again on 19/nov/2023, but the spare motor could not be fixed as the support leg location and hole sizes does not match. Same has been landed and will be fabricated and fitted next voyage to Singapore.","2024-04-15T08:00:00","","In progress",null,"No","No","No","Internal","21/12 - despite various attempts from shore workshops. this remains open. spare blowert assembly is beiong overhauled and balanced- issued remains open. extyension granted until mid feb 2023 provided all runing paramters are maintained."]
[null,null,null,null,21893,"111_Fri Dec 29 2023 04:23:11 GMT+0800","2024-02-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","All Cargo Hold Bilge suction valves not operational as the actuators are stuck.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Overhauling of actuators and exercising of the valves to be done.","2024-04-30T08:00:00","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,34388,"111_Fri Dec 29 2023 04:29:26 GMT+0800","2024-03-02T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Pipe supports on deck wasted.","Deck - Pipe / Fittings","General Appearance","External Factors","","","","","Cropping / Renewal of wasted pipe supports to be done.","2024-05-30T08:00:00","","In progress",null,"No","No","No","Internal"]
[null,null,null,null,22757,"111_Fri Dec 29 2023 04:34:47 GMT+0800","2024-02-02T08:00:00","Defect","Ship Staff","Ship Staff Insp.","1P DBT stripping valve actuator missing.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Awaiting Spare actuator.","2024-04-30T08:00:00","CBOS230235","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,65526,"111_Sat Dec 30 2023 13:52:28 GMT+0800","2023-12-20T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Port side bunker davit wire drum lips are totally wasted.","Deck - Machinery","General Appearance","Equipment Related","","","","","Repairs & renewal of wasted area to be done.","2024-04-20T08:00:00","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,50247,"111_Mon Jan 01 2024 08:31:01 GMT+0800","2023-12-27T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","Main Air Compressor No. 1  Cylinder head cracked near base of cylinder head bolt.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Spare received, will be renewed.","2024-04-15T08:00:00","CBOS240010","Waiting spare",null,"No","No","No","Internal"]
[null,null,null,null,44452,"111_Tue Jan 09 2024 16:28:01 GMT+0800","2024-01-07T08:00:00","Defect","Ship Staff","Ship Staff Insp.","During De-Ballasting operations at Vostochny, numerous valves in the Ballast piping system found not holding. Valve no. EM05, ES13, ES14 ","E/R - Pipes/ valves & fittings","Cargo / Ballast Systems","Equipment Related","","","","","Valves to be overhauled and seatring to be checked. If damaged to be replaced.","2024-04-09T08:00:00","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,18165,"111_Thu Feb 15 2024 17:47:09 GMT+0800","2023-11-15T08:00:00","Other","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Safety Notice issued for CO2 system cylinders manufactured by NK Co. LTD bursting disc material is changed from Copper to Nickle. ","LSA / FFA","Safety / LSA / FFA","Industry Issue","","","","","bursting disc material to change from Copper to Nickle. ","2024-05-15T08:00:00","","Deferred to D D",null,"No","No","No","Internal"]
[null,null,null,null,70344,"111_Thu Mar 07 2024 13:20:16 GMT+0800","2024-02-23T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","(S) tank fresh water (sunken type) sounding pipe plug type with threads is currently replaced with just a plug with no threads","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Inappropriate Procedure","","","","","","2024-04-15T08:00:00","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,96273,"111_Thu Mar 07 2024 13:27:44 GMT+0800","2024-02-24T08:00:00","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","One air line on deck has got leaks in 2 locations","Deck - Pipe / Fittings","","Equipment Related","","","","","","2024-04-15T08:00:00","","Not Started",null,"No","No","No","Internal"]
[null,null,null,null,11357,"111_Tue Mar 19 2024 21:06:05 GMT+0800","2024-03-08T08:00:00","Critical Equipment","Ship Staff","Ship Staff Insp.","SI lights battery drained","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Requisition raised. Awaiting spares","2024-04-10T08:00:00","CBOS240049","Waiting spare",null,"No","No","No","Internal"]

{"sheet":"Completed","index":1,"n_rows":192,"n_cols":28,"rows_kept":192,"cut":false,"hidden":false,"merged":[[10,8,10,9],[10,12,10,13],[12,6,12,27],[8,6,8,27]]}
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,"Defect - Damage Monitoring Sheet"]
[]
[null,null,null,null,null,null,null,"Date of Report","31-Mar-2024",null,null,"Ship Name","CAPE BOSS (21-12-2023)"]
[]
[null,null,null,null,null,null,"VERSION : 2.0"]
[]
[]
[]
[null,null,null,"ID","SHIPSIDE UNIQUEID","UNIQUE ID","Date Recorded","Type of Deficiency","Observer code","Type of Inspection","Description of Deficiency","Equipment Categories","Area of Observation","Deficiency Cause","VIQ Ref Number","Risk Value of Obs","PSC Ref Number","PSC MOU ID","Action Taken or Required","Target Date","PO Ref No.","Status Code","Date Completed","Drydock","Info Sharing","Critical Item","Audit Type","Superintendent Remarks"]
[null,null,null,18246,null,"111_16/3/2021 1:39:51 AM","2021-03-14T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Forecastle port& starboard windlass handling area slightly leaking","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Completed fix by engineer","2021-06-30T23:59:35","","Completed","2021-03-22T23:59:35","No","No","No","Internal"]
[null,null,null,18247,null,"111_16/3/2021 1:43:08 AM","2021-03-14T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Forepeak tank hydraulic valve both leaking","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Already fixed","2021-06-30T23:59:35","","Completed","2021-03-21T23:59:35","No","No","No","Internal"]
[null,null,null,18250,null,"111_16/3/2021 1:55:42 AM","2021-03-14T23:59:35","Observation","Ship Staff","Ship Staff Insp.","NO.1 TO 9 hatch cover handling block slightly leaking,part of hydraulic soft pipe leaking uncertainly","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","Leaking problem already fixed by engineer","2021-06-30T23:59:35","","Completed","2021-06-05T23:59:35","No","No","No","Internal","please raise RO for hyd hose to rectify leakage. rest will carry out in DD"]
[null,null,null,18251,null,"111_16/3/2021 2:00:17 AM","2021-03-14T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Part of hatch cover wheels abrasion seriously lead difficulty to close it","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","Rectify that piece of  track  was badly corroded lead to difficulty to close it. After derusted  can normal open & close hatch cover.","2021-06-30T23:59:35","","Completed","2021-03-22T23:59:35","No","No","No","Internal"]
[null,null,null,18258,null,"111_16/3/2021 2:22:46 AM","2021-03-14T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Dashboard of rudder angle,proeller shat tachometer,telegaph repeater on port& starboard side no light","Navigation - Others","Navigation","Equipment Related","","","","","Already fixed","2021-06-30T23:59:35","","Completed","2021-03-21T23:59:35","No","No","No","Internal"]
[null,null,null,18259,null,"111_16/3/2021 2:25:25 AM","2021-03-14T23:59:35","Observation","Ship Staff","Ship Staff Insp.","NO.5 TST 5S over board valve leaking","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Already put gasket inside anti leaking","2021-04-04T23:59:35","","Completed","2021-03-27T23:59:35","No","No","No","Internal"]
[null,null,null,18244,null,"111_15/3/2021 10:32:03 PM","2021-03-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Elevator annual inspection going to due 21 MAR 2021","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","completed.","2021-04-19T23:59:35","","Completed","2021-04-14T23:59:35","No","No","No","Internal"]
[null,null,null,18241,null,"111_15/3/2021 10:24:02 PM","2021-05-13T23:59:35","Observation","Ship Staff","Ship Staff Insp.","ER overhead crane wire found twist .","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","ER overhead crane wire renewed","2021-05-29T23:59:35","","Completed","2021-05-13T23:59:35","No","No","No","Internal"]
[null,null,null,19017,null,"111_30/4/2021 10:36:44 PM","2021-05-13T23:59:35","Observation","Ship Staff","Ship Staff Insp.","PORT side bilge well high level switch not working sometime.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Troubleshooting carried out and all saisfactory.","2021-05-31T23:59:35","","Completed","2021-05-13T23:59:35","No","No","No","Internal"]
[null,null,null,18240,null,"111_15/3/2021 10:20:29 PM","2021-05-28T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Main air compressor NO.2  major overhaul to be carried out.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Main air compressor#2 major overhaul completed and tested ,all satisfactory.","2021-05-31T23:59:35","CBOS210048,CBOS210045","Completed","2021-05-28T23:59:35","No","No","No","Internal","spare  under processing"]
[null,null,null,18243,null,"111_15/3/2021 10:29:41 PM","2021-06-04T23:59:35","Observation","Ship Staff","Ship Staff Insp.","The gland packing type Boiler water circulating pumps found worn out easily, casuing steam enters into bearing housing and damage the bearings. ","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Boiler water circulting pump#1&2 major overhaul completed and tested,all satisfactory.","2021-06-04T23:59:35","CBOS210061,CBOS210043","Completed","2021-06-04T23:59:35","No","No","No","Internal","please provide RO number for tracing"]
[null,null,null,18233,null,"111_15/3/2021 9:55:27 PM","2021-06-29T23:59:35","Observation","Ship Staff","Ship Staff Insp.","steering gear rams leaking through seal","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Tightened gland for rams few times, leakage stop/minimize.Please refer to DD spec 9- steering gear rams packing renewal &servicing","2021-07-31T23:59:35","CBOS210086","Completed","2021-06-29T23:59:35","Yes","No","No","Internal","will repair in DD, can try to tighten gland for ram. please update status"]
[null,null,null,18237,null,"111_15/3/2021 10:06:24 PM","2021-06-29T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Both life boat batteries found exhausted , one set of battery only can start the life boat engine one time.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Life boat batteries renewed with spare, tested and all satisfactory.","2021-06-29T23:59:35","CBOS 210084","Completed","2021-06-29T23:59:35","No","No","No","Internal","spare battery will supply in Singapore, please update status"]
[null,null,null,19020,null,"111_30/4/2021 10:47:33 PM","2021-06-29T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","AE # 1 LOP LO feed pump gear worn out and PT 4 presure sensor not working","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","PT 4 pressure sensor renewed, faulty LO feed pump renewed with spare.","2021-06-30T23:59:35","CBOS210040","Completed","2021-06-29T23:59:35","No","No","No","Internal","will supply spare at convenient port, please carry out renewal once receive spare."]
[null,null,null,18229,null,"111_15/3/2021 10:13:11 PM","2021-07-14T23:59:35","Observation","Ship Staff","Ship Staff Insp."," Found LT cooler SW outlet line low pressure even after NO.2 LT cooler plates cleaning.","E/R - Pipes/ valves & fittings,E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","LT cooler chemical cleaning and back washing carried out.","2021-07-31T23:59:35"," RO CBOS210094 was raised for main cooling SW pumps overhaul.","Completed","2021-07-14T23:59:35","No","No","No","Internal","will supply in next convenient port"]
[null,null,null,19019,null,"111_30/4/2021 10:45:06 PM","2021-07-14T23:59:35","Observation","Ship Staff","Ship Staff Insp.","NO #1 LT cooler SW discharge vavle not holding, SW suction strainer become very weak and unable to be taken out.LT cooler plates to be cleaned.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","NO.1 LT cooler discharge valve renewed with spare, SW suction strainer renewed with spare. LT cooler chemical cleaning and back washing carried out.","2021-07-31T23:59:35","","Completed","2021-07-14T23:59:35","No","No","No","Internal","will carry out in DD"]
[null,null,null,18262,null,"111_16/3/2021 2:08:38 AM","2021-07-30T23:59:35","Observation","Ship Staff","Ship Staff Insp.","NO.4-8 hatch coaming& hatch cover badly corroded,","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","completed derusted hatch cover 4-9","2021-07-30T23:59:35","","Completed","2021-07-30T23:59:35","No","No","No","Internal","to expedite the job and bring up vessel performance"]
[null,null,null,19528,null,"111_14/5/2021 5:34:59 PM","2021-08-30T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","LSA,FFE&GMDSS radio equipment annual service expired on MAY-2021","Critical Equip.","Cert. & Docu.","Equipment Related","","","","","Completed GMDSS annual service   at newcastle","2021-08-31T23:59:35","","Completed","2021-08-30T23:59:35","No","No","No","Internal","please update status"]
[null,null,null,19018,null,"111_30/4/2021 10:41:00 PM","2021-08-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","AE#2&3 MGO return line valves found not holding","E/R - Aux. Engine,E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","AE#2&3 MGO return line valves renewed with spare.","2021-08-31T23:59:35","RO CBOS 210083 reveived","Completed","2021-08-30T23:59:35","No","No","No","Internal","please update status."]
[null,null,null,22402,null,"111_30/10/2021 10:02:03 PM","2021-10-27T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","No: 2 Lube oil purifer bowl speed low","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","Purifer Complete overhaul carried out. Vertical shaft and horizontal clutch assembly overhauled.Working satisfactory ","2021-11-01T23:59:35","","Completed","2021-10-28T23:59:35","No","No","No","Internal"]
[null,null,null,23175,null,"111_18/12/2021 9:53:19 AM","2021-10-27T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NO:1 Lube oil purifier compressing tool damaged while assembly","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","RO CBOS210250 received and purifier assembled back.","2021-12-30T23:59:35","","Completed","2021-12-10T23:59:35","No","No","No","Internal"]
[null,null,null,23176,null,"111_18/12/2021 10:36:44 AM","2021-10-30T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NO:1 HFO Puriifer abnormal noise from the motor side ","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","Complete overhaul of motor, Horizontal centrifugal clutch and vertical shaft assembly carried out.","2021-11-09T23:59:35","","Completed","2021-11-02T23:59:35","No","No","No","Internal"]
[null,null,null,23177,null,"111_18/12/2021 10:41:14 AM","2021-11-01T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Fresh water generator ejector pump overhaul ","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Complete overhaul of pump and motor carried out. Mouth rings and mechanical seal renewed.","2021-11-09T23:59:35","","Completed","2021-11-05T23:59:35","No","No","No","Internal"]
[null,null,null,23178,null,"111_18/12/2021 11:42:02 AM","2021-11-05T23:59:35","Defect","Ship Staff","Ship Staff Insp.","STBD side combination ladder not working","Deck - Machinery","Eng. / Strg. Comp.","Equipment Related","","","","","Motor overhauled and fitted back. Rasied RO CBOS210274 for spare motor","2021-11-09T23:59:35","","Completed","2021-11-07T23:59:35","No","No","No","Internal"]
[null,null,null,23179,null,"111_18/12/2021 10:00:46 AM","2021-11-10T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","NO:1 Boiler water Circulating Pump shaft found damaged","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Ro CBOS210233 received and pump overhauled.Working satisfactory.","2022-01-10T23:59:35","","Completed","2021-12-12T23:59:35","No","No","No","Internal"]
[null,null,null,23180,null,"111_18/12/2021 11:54:15 AM","2021-11-14T23:59:35","Critical Equipment,Defect","Ship Staff","Ship Staff Insp.","Emergency generator thermostatic expansion valve not working.","Critical Equip.","Emgcy. Systems","Equipment Related","","","","","Spare received from RO CBOS210283 and thermostat renewed. System working satisfactory.","2022-01-14T23:59:35","","Completed","2021-12-09T23:59:35","No","No","No","Internal"]
[null,null,null,19025,null,"111_1/5/2021 12:46:14 AM","2021-11-16T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Air pipe line& fresh water line on main deck need to be renewal including valves due to badly rusted","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","Already renewed fresh water line valve&air line valve which  spares on board,work in progress","2022-02-14T23:59:35","CBOS210106","Completed","2022-02-13T23:59:35","No","No","No","Internal","please update status and advice when will be completed"]
[null,null,null,23181,null,"111_18/12/2021 12:07:45 PM","2021-11-16T23:59:35","Defect","Ship Staff","Ship Staff Insp.","A/E # 1 tripped on high voltage.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","AVR renewed and generator working satisfactory. RO raised for spare AVR CBOS210291","2021-11-19T23:59:35","","Completed","2021-11-17T23:59:35","No","No","No","Internal"]
[null,null,null,18238,null,"111_15/3/2021 10:10:29 PM","2021-11-17T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Main cooling sea water pipe coated rubber found aged and broken, the thickness of the pipes to be checked","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Main cooling sea water pipe renewed after pump discharge in DD","2022-02-14T23:59:35","","Completed","2022-01-31T23:59:35","Yes","No","No","Internal","condition to be monitoring and update"]
[null,null,null,18248,null,"111_16/3/2021 1:50:06 AM","2021-11-17T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Cargo hold bilge weel hydraulic valve no working","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","To be overhauled during docking","2022-02-14T23:59:35","","Completed","2022-02-13T23:59:35","Yes","No","No","Internal","will carry out in DD"]
[null,null,null,23182,null,"111_18/12/2021 11:59:30 AM","2021-11-17T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NO:1 HFO Purifier feed pump not rotating freely. ","E/R - Pumps,E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","Motor and pump overhauled. Bearings renewed.ROB of mechanical seal zero, RO rasied for same CBOS210288 ","2022-02-17T23:59:35","","Completed","2021-11-19T23:59:35","No","No","No","Internal"]
[null,null,null,19635,null,"111_1/6/2021 4:46:04 PM","2021-11-17T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Weakness point of anti piracy,easy to embarkation.","Accommodation","ISPS Related","Equipment Related","","","","","Installed & added steel bar fence for accommodation LB deck clear window ","2022-02-14T23:59:35","","Completed","2022-02-03T23:59:35","Yes","No","No","Internal","will carry out in dry dock"]
[null,null,null,23183,null,"111_18/12/2021 3:33:33 PM","2021-11-18T23:59:35","Defect","Ship Staff","Ship Staff Insp.","A/C drain line to scupper chocked.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","All pipe section total 8in number removed and line cleared. ","2021-11-30T23:59:35","","Completed","2021-11-23T23:59:35","No","No","No","Internal"]
[null,null,null,18232,null,"111_15/3/2021 9:52:18 PM","2021-11-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","AE NO.2&3 running hours due for major overhaul  and observed high LO consumption.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","AE 1, 2 and 3 turbocharger were overhauled in DD , AE 1 and 2 decarb completed.","2022-02-14T23:59:35","CBOS210124,210103","Completed","2022-01-27T23:59:35","Yes","No","No","Internal","Raise RO for GE and TC overhaul spare, pick sensor to be renewed once receive"]
[null,null,null,19016,null,"111_30/4/2021 10:33:15 PM","2021-11-19T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Ballast/bilge strip eductor bust due be badly corrosion","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Eductor renewed after receiving spare.","2022-02-14T23:59:35","CBOS210050","Completed","2022-01-25T23:59:35","Yes","No","No","Internal","spare will supply in convenient port, once receiving please renewed"]
[null,null,null,19021,null,"111_1/5/2021 12:18:22 AM","2021-11-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Windlass brake line need to be renewal","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","To be carried out in DD","2022-02-14T23:59:35","CBOS210105,CBOS210076","Completed","2022-02-13T23:59:35","Yes","No","No","Internal","will supply in convenient port to carry out renew"]
[null,null,null,19022,null,"111_1/5/2021 12:24:26 AM","2021-11-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Mooring winch brake line need to be renewal& test","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Waiting spare& renew brakelining in progress","2022-02-14T23:59:35","CBOS210031","Completed","2020-02-13T23:59:35","No","No","No","Internal","will supply in convenient port to carry out renew or carry out in DD"]
[null,null,null,18255,null,"111_16/3/2021 1:46:46 AM","2021-11-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Port&starboard anchor chain easy to twist","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","completed in DD","2022-02-14T23:59:35","","Completed","2022-02-11T23:59:35","Yes","No","No","Internal","to be check and repair in DD. please including in DD spec"]
[null,null,null,19023,null,"111_1/5/2021 12:28:06 AM","2021-11-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","TST Manhole need to be renewal from NO.1 to NO.5 port& starboard side","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","To be attended during dry docking","2022-02-14T23:59:35","","Completed","2022-02-13T23:59:35","Yes","No","No","Internal","please include in DD spec"]
[null,null,null,18256,null,"111_16/3/2021 2:17:08 AM","2021-11-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Ladders in all cargo hold found badly corroded","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","To be overhauled in dry docking","2022-02-14T23:59:35","","Completed","2022-02-13T23:59:35","Yes","No","No","Internal","will repair in DD, please including in DD spec"]
[null,null,null,19024,null,"111_1/5/2021 12:43:11 AM","2021-11-19T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Fire line behind NO.2 cargo hold about 20 meters& paltform after each cargo hold to be renewal","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","To be carried out in phased manner","2022-02-14T23:59:35","CBOS210107","Completed","2022-02-09T23:59:35","No","No","No","Internal","to be renewed lines which are more susceptible to leak first."]
[null,null,null,23184,null,"111_18/12/2021 12:24:13 PM","2021-11-19T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Eductor driving line from fire, bilge and ballast pump leaking. ","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Pipe renewed with newly fabricated pipe. ","2021-12-19T23:59:35","","Completed","2021-11-30T23:59:35","No","No","No","Internal"]
[null,null,null,18235,null,"111_15/3/2021 10:01:37 PM","2021-11-24T23:59:35","Observation","Ship Staff","Ship Staff Insp.","sewage treatment plant division plates badly corroded","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Division plate renewed in DD","2022-02-19T23:59:35","","Completed","2022-02-09T23:59:35","Yes","No","No","Internal","will carry out repair in DD"]
[null,null,null,18236,null,"111_15/3/2021 10:04:06 PM","2021-11-24T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","FWD ICCP found no DCA output current","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Please refer to DD spec -FWD ICCP TROUBLESHOOTING.","2022-02-19T23:59:35","CBOS210113","Completed","2022-02-14T23:59:35","Yes","No","No","Internal","will carry out in DD"]
[null,null,null,18245,null,"111_16/3/2021 1:35:16 AM","2021-11-24T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Provision crane badly corroded,power cable to be renewed","Deck - Machinery","Eng. / Strg. Comp.","Equipment Related","","","","","monorail hoist, derusted and power cable renewed.","2022-02-19T23:59:35","RO CBOS210097 was raised for cable.","Completed","2022-01-26T23:59:35","Yes","No","No","Internal","will carry out in dock.  spare cable will supply as per dd spare."]
[null,null,null,18254,null,"111_16/3/2021 2:15:25 AM","2021-11-24T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Ballast tank inside found badly corroded","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","Attended in DD","2022-02-19T23:59:35","","Completed","2022-02-13T23:59:35","Yes","No","No","Internal","to be carry out maintenance. damage part will repair in DD"]
[null,null,null,19026,null,"111_1/5/2021 12:49:44 AM","2021-11-24T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Replace & load testing of life boat wire due to will be expired","Critical Equip.","Safety / LSA / FFA","Equipment Related","","","","","To be attended during docking","2022-02-19T23:59:35","CBOS210053","Completed","2022-02-14T23:59:35","Yes","No","No","Internal","to be carry out during dock. ensure including in the DD spec"]
[null,null,null,22401,null,"111_30/10/2021 9:39:43 PM","2021-11-26T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Fwg ejector pump suction flter casing found leaking","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Casing was renewed after receiving spare.","2022-02-18T23:59:35","","Completed","2022-01-25T23:59:35","No","No","No","Internal","please update spare received or not"]
[null,null,null,23185,null,"111_18/12/2021 12:16:55 PM","2021-11-28T23:59:35","Critical Equipment,Defect","Ship Staff","Ship Staff Insp.","Emergency fire pump attached vacuum pump not disengaging after building discharge pressure. ","Critical Equip.","Emgcy. Systems","Equipment Related","","","","","Vacuum pump overhauled. Working satisfactory. RO CBOS210321 has been raised as ROB is zero","2021-12-01T23:59:35","","Completed","2021-11-28T23:59:35","No","No","No","Internal"]
[null,null,null,18231,null,"111_15/3/2021 9:47:31 PM","2021-11-29T23:59:35","Observation","Ship Staff","Ship Staff Insp.","ME intermediate shaft beaing found leaking.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Intermediate shaft bearing cover opened and seal renewed. leak was rectified.","2022-02-24T23:59:35","CBOS210096","Completed","2022-01-23T23:59:35","Yes","No","No","Internal","will carry out during vessel DD"]
[null,null,null,18239,null,"111_15/3/2021 10:18:41 PM","2021-11-29T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Found main cooling sea water line, ballast line and fire &GS  line a lot of valves not holding. Ballast suction line doublers were applied","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","LT cooler NO.1 discharge valve renewed with spare valves.","2022-02-24T23:59:35","","Completed","2022-02-19T23:59:35","Yes","No","No","Internal","valve to be checked and opened up to identify exact condition. pipe to be renew if vessel staff able to do. please  update status."]
[null,null,null,18242,null,"111_15/3/2021 10:26:03 PM","2021-11-29T23:59:35","Observation","Ship Staff","Suptd. Insp.","AE NO.1 VLSFO and MGO outlet leaking valves to be renewed.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","","","","","","The valves to be renewed when have the chance to stop FO booster unit.","2022-02-24T23:59:35","RO CBOS210083 received.","Completed","2022-01-18T23:59:35","No","No","No","Internal","understand spare received, please update status"]
[null,null,null,18253,null,"111_16/3/2021 2:12:39 AM","2021-11-29T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Galley drain line & boat deck port side pipes choked","Accommodation","Structural Condn. / WT integrity ","Equipment Related","","","","","All lines cleared. All sinks and drainage lines in accomodation in working order.","2022-02-24T23:59:35","","Completed","2022-07-21T23:59:35","No","No","No","Internal","please expedite the job to complete asap"]
[null,null,null,18257,null,"111_16/3/2021 2:20:08 AM","2021-11-29T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Airpurge systerm & ballast,draft indication panel display malfunctioning","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","System fault rectified","2022-02-24T23:59:35","","Completed","2022-02-02T23:59:35","Yes","No","No","Internal","will repair in DD, please including in DD spec"]
[null,null,null,23186,null,"111_18/12/2021 12:28:04 PM","2021-12-10T23:59:35","Defect","Ship Staff","Ship Staff Insp.","A/E # 3 turbocharger surging at high load.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Turbocharher overhauled. All clearances taken. Working satisfactory. ","2021-12-14T23:59:35","","Completed","2021-12-12T23:59:35","No","No","No","Internal"]
[null,null,null,23187,null,"111_18/12/2021 12:32:15 PM","2021-12-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","NO:1 Fresh water hydrophore pump leaking.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","Pump overhauled. Mechanical seal and sleeve renewed.","2021-12-19T23:59:35","","Completed","2021-12-15T23:59:35","No","No","No","Internal"]
[null,null,null,29253,34524,"111_Sat Mar 11 2023 18:26:50 GMT+0800","2022-04-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Discharge of sewage overboard A4 size poster - still with previous ships name ","E/R - Pipes/ valves & fittings","Cert. & Docu.","Human Error","","","","","Poster with incorrect vessel name was removed and new poster attached.","2022-06-28T23:59:35","","Completed","2022-04-23T23:59:35","No","No","No","Internal"]
[null,null,null,29254,68393,"111_Sat Mar 11 2023 18:32:45 GMT+0800","2022-04-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Both Anchor wire lashings - wire snotters  to be replaced (SWL of snottter = weight of anchor + chain links + 10%)( ","Miscellaneous","Safety / LSA / FFA","Knowledge Based","","","","","Both Anchor wire lashings - wire snotters  replaced with marking.","2022-06-28T23:59:35","","Completed","2022-05-20T23:59:35","No","No","No","Internal"]
[null,null,null,29255,85008,"111_Sat Mar 11 2023 18:35:31 GMT+0800","2022-04-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","SLOAS training manual - to have index & separators for each equipment. Replace generic photos of each LSA & FFA  equipment with current ones. Add a page in front - when last reviewed and counter signed by Ch.off during each contract","LSA / FFA","Cert. & Docu.","Knowledge Based","","","","","Index and separator inserted in SOLAS training manual for each equipment. Photos replaced for each LSA/FFA equipment's with latest. Page added for review.","2022-06-28T23:59:35","","Completed","2022-04-25T23:59:35","No","No","No","Internal"]
[null,null,null,29256,52866,"111_Sat Mar 11 2023 18:38:04 GMT+0800","2022-04-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Anchor hawse pipe - did not sight any perforate plate to prevent a pirate from boarding & climbing up the Anchor chain?  ","Deck - Pipe / Fittings","ISPS Related","Industry Issue","","","","","New hawse pipe covers received in Dubai DD, same is in use when vessel is at sea.","2022-06-28T23:59:35","","Completed","2022-05-06T23:59:35","No","No","No","Internal"]
[null,null,null,29259,79209,"111_Sat Mar 11 2023 18:40:18 GMT+0800","2022-04-10T23:59:35","Non Conformity","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Chemical MSDS sheets: must be available for each type and must be published <5 years old. ","Documentation","Cert. & Docu.","Knowledge Based","","","","","MSDS was requested and received from office and was put in chemical MSDS file near chemicals.","2022-06-28T23:59:35","","Completed","2022-04-23T23:59:35","No","No","No","Internal"]
[null,null,null,29260,36008,"111_Sat Mar 11 2023 18:45:46 GMT+0800","2022-04-10T23:59:35","Non Conformity","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Enclosed space entry checklist: Permit validity - TIME starts only after Master has signed in section 3 ","Documentation","Cert. & Docu.","Knowledge Based","","","","","MEETING CARRIED OUT AND DISCUSSED CORRECT PROCEDURE OF FILLING UP ENCLOSED SPACE ENTRY C/L","2022-06-28T23:59:35","","Completed","2022-05-23T23:59:35","No","No","No","Internal"]
[null,null,null,29261,53761,"111_Sat Mar 11 2023 18:48:05 GMT+0800","2022-04-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Pl ensure all ISPS drill are carried out as per Code 1. Piracy attacks while at Sea, anchor & in port\nCode 2. Finding Foreign/Unidentified Object, Bomb/Explosive\nCode 3. Stowaway, intruder or Unauthorised access\nCode 4. Hijacking – Terrorists / Pirates Boarding the Vessel or Seizure of the Vessel or Persons on Board\nCode 5. Evacuation of the Ship as per recommended frequency in drill matrix\n","Documentation","Cert. & Docu.","Knowledge Based","","","","","ISPS drills carried out as per drill schedule.","2022-06-28T23:59:35","","Completed","2022-04-25T23:59:35","No","No","No","Internal"]
[null,null,null,29262,17941,"111_Sat Mar 11 2023 18:50:38 GMT+0800","2022-04-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","GMDSS log book - entries  to be made by each and every OOW ","Navigation - GMDSS & Communication","Cert. & Docu.","Knowledge Based","","","","","Bridge team meeting carried out. All bridge team members briefed about company policy & procedures and log keeping.","2022-06-28T23:59:35","","Completed","2022-04-25T23:59:35","No","No","No","Internal"]
[null,null,null,29267,65015,"111_Sat Mar 11 2023 18:29:52 GMT+0800","2022-04-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Dry provision stores: Basmati rice is better stored in reefer handling area to keep the weevils from forming ","Miscellaneous","Crew Management","Human Error","","","","","Basmati rice transferred and stored in reefer handling area to prevent forming of weevils.","2022-06-28T23:59:35","","Completed","2022-04-24T23:59:35","No","No","No","Internal"]
[null,null,null,29270,27668,"111_Sat Mar 11 2023 18:43:42 GMT+0800","2022-04-10T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fridge in pantry - did not sight and fixed lashing during heavy weather ","","Safety / LSA / FFA","Knowledge Based","","","","","Lashing taken of fridge in pantry.","2022-06-28T23:59:35","","Completed","2022-05-21T23:59:35","No","No","No","Internal"]
[null,null,null,26963,null,"111_Thu Sep 22 2022 07:50:46 GMT+0000","2022-05-05T23:59:35","Observation","PSC Insp.","PSC Inspection","P&I Cert. of financial security  in respect of seafarers repatriation cost and liability as required under MLC- NOT AS REQUIRED","Documentation","Cert. & Docu.","","","","Certificates & Documentation","","","2022-05-19T23:59:35","","Completed","2022-05-09T23:59:35","No","No","No","External"]
[null,null,null,26964,null,"111_Thu Sep 22 2022 07:51:54 GMT+0000","2022-05-05T23:59:35","Observation","PSC Insp.","PSC Inspection","P&I Cert. of finalcial security relating to the ship owners liability not as required","Documentation","Cert. & Docu.","","","","Certificates & Documentation","","","2022-05-19T23:59:35","","Completed","2022-05-09T23:59:35","No","No","No","External"]
[null,null,null,29242,75856,"111_Sat Mar 11 2023 13:45:23 GMT+0800","2022-05-06T23:59:35","Observation","PSC Insp.","PSC Inspection","P&I Cert. of financial security relating to the ship owners liability not as required","Documentation","Cert. & Docu.","Inappropriate Procedure","","","",1,"New corrected certificate issued","2022-05-20T23:59:35","","Completed","2022-05-10T23:59:35","No","No","No","External"]
[null,null,null,29251,30381,"111_Sat Mar 11 2023 13:42:08 GMT+0800","2022-05-06T23:59:35","Observation","PSC Insp.","PSC Inspection","P&I Cert. of financial security  in respect of seafarers repatriation cost and liability as required under MLC- NOT AS REQUIRED","Documentation","Cert. & Docu.","Inappropriate Procedure","","","",1,"New corrected certificate issued by administration","2022-05-20T23:59:35","","Completed","2022-05-10T23:59:35","No","No","No","External"]
[null,null,null,25659,97196,"0_Wed Jun 15 2022 13:00:03 GMT+0800","2022-05-31T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Main Engine fuel pump inspection window covers deformed/discolored.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","All the Fuel Pumps Window glass renewed.","2023-03-31T23:59:35","CBOS220204","Completed","2023-03-13T23:59:35","No","No","No","Internal","Spare will supply next convenient port"]
[null,null,null,25656,86031,"111_Wed Jun 15 2022 12:53:33 GMT+0800","2022-06-01T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","STP discharge pump level cut in and cut off switch and float malfunctioning.","Critical Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","To install the defective component on receiving spares","2022-07-14T23:59:35","CBOS220164","Completed","2022-08-12T23:59:35","No","No","No","Internal","Spare will supply next convenient port"]
[null,null,null,25649,37755,"111_Tue Jun 14 2022 16:23:21 GMT+0800","2022-06-04T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Cargo Holds Hatch Covers natural ventilation found hardly corroded.","Deck - Machinery,Cargo Mach.","Cargo / Ballast Systems","Inappropriate Procedure","","","","","Cargo Holds Hatch Covers natural ventilation repaired as required","2022-07-31T23:59:35","","Completed","2022-06-21T23:59:35","No","No","No","Internal"]
[null,null,null,25661,53471,"111_Wed Jun 15 2022 13:25:45 GMT+0800","2022-06-05T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Life boat battery charger transformer burnt.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Battery charger received at Singapore on 17 dec 2022","2022-12-10T23:59:35","CBOS220138","Completed","2022-12-17T23:59:35","No","No","No","Internal",""]
[null,null,null,25662,20674,"0_Wed Jun 15 2022 13:28:41 GMT+0800","2022-06-05T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Port life boat engine starter assembly poor performance.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Starter assembly renewed. lifeboat engine tried out. working satisfactory","2022-09-14T23:59:35","CBOS220136","Completed","2022-08-17T23:59:35","No","No","No","Internal",""]
[null,null,null,25650,49495,"111_Tue Jun 14 2022 16:26:39 GMT+0800","2022-06-08T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Cargo Holds entrance booby hatches observed difficulties with open/close. Need to chip, wire brush, exercise and grease.","Deck - Pipe / Fittings,Cargo Mach.","Cargo / Ballast Systems","External Factors","","","","","All Cargo Holds entrance booby hatches  chipped, wire brush, exercise and grease.","2022-08-31T23:59:35","","Completed","2022-06-27T23:59:35","No","No","No","Internal"]
[null,null,null,25652,19979,"111_Tue Jun 14 2022 23:09:56 GMT+0800","2022-06-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Level gauge for ballast tanks are not operational. same to be repaired and calibrated.","Hull & Tanks","Cargo / Ballast Systems","Equipment Related","","","","","Ballast Level Gauge System Decomissioned by Class","2022-09-29T23:59:35","","Completed","2022-07-06T23:59:35","No","No","No","Internal"]
[null,null,null,25653,69715,"111_Tue Jun 14 2022 23:12:49 GMT+0800","2022-06-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Draft Gauge not operational.","Deck - Machinery","Cargo / Ballast Systems","Equipment Related","","","","","Remote Draft Gauge System Decommissioned by Class","2022-09-29T23:59:35","","Completed","2022-07-06T23:59:35","No","No","No","Internal"]
[null,null,null,25657,38630,"111_Wed Jun 15 2022 01:17:24 GMT+0800","2022-06-14T23:59:35","Other","Ship Staff","Ship Staff Insp.","Alcohol meter calibration certificate is expired.","","Cert. & Docu.","Equipment Related","","","","","New Alcometer with certificate recieved.","2022-07-30T23:59:35","","Completed","2022-06-21T23:59:35","No","No","No","Internal"]
[null,null,null,25658,96652,"111_Wed Jun 15 2022 12:22:22 GMT+0800","2022-06-14T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Steering gear Aft Ram (Stbd) leak from gland due to deep scoring marks on the Ram surface. Leak is persisting since vessel take over.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Steering gear forward ram port side cylinder and aft ram starboard side cylinder oil leakage rectified. Packing taken out of cylinder and replaced with new packing.","2022-09-14T23:59:35","","Completed","2022-09-05T23:59:35","No","No","No","Internal",""]
[null,null,null,25948,46045,"111_Fri Jul 01 2022 18:16:48 GMT+0800","2022-06-17T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Starboard life boat engine starter assembly exterior appears rusted and no record of prior maintenance / overhaul found.","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Starter assembly was dismantled, cleaned, windings Varnished, dried and assembled. Tried out after overhaul and observed working satisfactorily.","2022-06-29T23:59:35","NA","Completed","2022-06-29T23:59:35","No","No","No","Internal"]
[null,null,null,26965,null,"111_Thu Sep 22 2022 07:56:10 GMT+0000","2022-06-21T23:59:35","Observation","PSC Insp.","PSC Inspection","Some Lights in Engine Room Inoperative","Elect. Mach. & Equip.","","","","","","","","2022-06-25T23:59:35","","Completed","2022-06-21T23:59:35","No","No","No","External"]
[null,null,null,26966,null,"111_Thu Sep 22 2022 07:58:10 GMT+0000","2022-06-21T23:59:35","Observation","PSC Insp.","PSC Inspection","ITU 4th Edition 2021 missing","","","","","","","","","2022-06-25T23:59:35","","Completed","2022-06-21T23:59:35","No","No","No","External"]
[null,null,null,29240,11668,"111_Sat Mar 11 2023 13:29:25 GMT+0800","2022-06-22T23:59:35","Observation","PSC Insp.","PSC Inspection","Some Lights in Engine Room Inoperative","Accommodation","Safety / LSA / FFA","Human Error","","","",6,"All inoperative lights are replaced immediately. ","2022-06-26T23:59:35","","Completed","2022-06-22T23:59:35","No","No","No","External"]
[null,null,null,29241,21819,"111_Sat Mar 11 2023 13:33:33 GMT+0800","2022-06-22T23:59:35","Observation","PSC Insp.","PSC Inspection","ITU 4th Edition 2021 missing","Documentation","Cert. & Docu.","Knowledge Based","","","",6,"New edition received on board","2022-06-26T23:59:35","","Completed","2022-06-22T23:59:35","No","No","No","External"]
[null,null,null,25947,15267,"111_Fri Jul 01 2022 18:04:39 GMT+0800","2022-06-23T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Aux Boiler pilot burner plug caps insulation damaged. Temporarily repaired by insulation tape. Needs replacement.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Aux Boiler pilot burner plug caps insulation renewed with new spare ones. Boiler tried out, working satisfactory","2022-09-29T23:59:35","CBOS220178","Completed","2022-08-12T23:59:35","No","No","No","Internal",""]
[null,null,null,26231,35159,"111_Mon Jul 18 2022 17:55:04 GMT+0800","2022-06-26T23:59:35","Other","Ship Staff","Ship Staff Insp.","CH Bilges No. 1 / 2 / 3 / 4 / 5 / 6 / 8 / 9 found not taking suction during routine inspection prior cleaning","Miscellaneous","Cargo / Ballast Systems","Inappropriate Procedure","","","","","All bilges inspected and valves checked. All valves found working satisfactorily from CCR. Bilges found full with previous cargoes. Bilges 1-2-3-4-5 cleaned and all cargo removed. About 1-2 cbm cargo recovered from each hold. Suctions of No 6-8-9 cleared. Complete Cargo removal not carried out due to time constraints. Same will be done on priority basis during next hold cleaning. All Bilges now having good suction and working satisfactory.","2022-08-30T23:59:35","","Completed","2022-07-10T23:59:35","No","No","No","Internal"]
[null,null,null,26230,41102,"111_Mon Jul 18 2022 17:47:29 GMT+0800","2022-06-27T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Mushroom Vents on Deck found non operational with corroded body and holed at few places","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Equipment Related","","","","","9 Nos Mushroom Vents for Duct Keel / Steering Gear Room / E/R Spaces / Accomodation Spaces dismantled. Found spindle broken/frozen and sealing disk corroded. Same renewed and made free. Corroded Vent heads taken to E/R workshop for buildup. Stencilling of Vent Heads in progress.","2022-08-30T23:59:35","","Completed","2022-07-08T23:59:35","No","No","No","Internal"]
[null,null,null,26232,10640,"111_Mon Jul 18 2022 17:58:45 GMT+0800","2022-06-30T23:59:35","Other","Ship Staff","Ship Staff Insp.","NRV Drains of Cargo Holds found chocked.","Deck - Pipe / Fittings","Structural Condn. / WT integrity ","Inappropriate Procedure","","","","","All NRV Drains cleaned. Crew instructed that during cargo ops same to blocked with burlap and burlap to be removed after completion of cargo ops.","2022-08-30T23:59:35","","Completed","2022-07-08T23:59:35","No","No","No","Internal"]
[null,null,null,26233,73385,"111_Tue Jul 19 2022 01:32:12 GMT+0800","2022-07-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME Fuel oil circulating pump observed to be leaking. ","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","ME fuel oil circulating pump dismantled and mechanical seal renewed. ","2022-07-20T23:59:35","","Completed","2022-07-13T23:59:35","No","No","No","Internal"]
[null,null,null,26332,94815,"111_Sun Jul 31 2022 03:44:28 GMT+0800","2022-07-15T23:59:35","Critical Equipment","Ship Staff","Ship Staff Insp.","Emergency generator battery damaged during starting.","Critical Equip.","Emgcy. Systems","Equipment Related","","","","","New battery receive at loading port has been fitted and connected to Emergency generator.","2022-07-30T23:59:35","","Completed","2022-07-28T23:59:35","No","No","No","Internal"]
[null,null,null,26331,14155,"111_Sun Jul 31 2022 03:48:22 GMT+0800","2022-07-20T23:59:35","Defect","Ship Staff","Ship Staff Insp.","AE2 Jacket water pump found leaking. ","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","AE2 Jacket water pump dismounted and dismantled. Mechanical seal renewed.","2022-07-30T23:59:35","","Completed","2022-07-21T23:59:35","No","No","No","Internal"]
[null,null,null,26329,76000,"0_Sun Jul 31 2022 16:28:37 GMT+0800","2022-07-23T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","1 Nos Riken Keiki Portable Gas Multigas meter not working.","Miscellaneous","Safety / LSA / FFA","Equipment Related","","","","","All Gas meters sent for shore calibration and recvd back. All gas meters working satisfactory","2023-01-31T23:59:35","CBOS220239","Completed","2022-12-17T23:59:35","No","No","No","Internal","will supply spare sensor once receive RO. vessel have enough gas meter will not affect safe operation."]
[null,null,null,26327,20977,"0_Sun Jul 31 2022 16:21:22 GMT+0800","2022-07-24T23:59:35","Defect","Ship Staff","Ship Staff Insp.","No. 4 Stbd TST overboard valve observed to be leaking","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Valve Gasket Renewed during vessels stay at Isdemir. Valve found holding.","2022-09-29T23:59:35","","Completed","2022-08-20T23:59:35","No","No","No","Internal","to carry out repair job and update office. to raise RO for necessary spare seat ring of valve."]
[null,null,null,26328,90753,"0_Sun Jul 31 2022 16:25:07 GMT+0800","2022-07-25T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Stbd side midship combination ladder not operational due to damaged bearings.","Deck - Machinery","Safety / LSA / FFA","Equipment Related","","","","","Damaged Bearing received in Isdemir. Same renewed. Motor presently in working condition. Awaiting other bearings for complete O/H","2022-08-19T23:59:35","","Completed","2022-08-22T23:59:35","No","No","No","Internal","RO received and will process. to carry out temporary repair if available. update office"]
[null,null,null,26330,89945,"0_Sun Jul 31 2022 16:31:29 GMT+0800","2022-07-26T23:59:35","Defect","Ship Staff","Ship Staff Insp.","During Mooring ops at PDM observed that mooring winches not holding on brakes due to worn out brake liner.","Deck - Machinery","Mooring","Equipment Related","","","","","Damaged brake liner have been renewed","2022-10-31T23:59:35","","Completed","2022-08-15T23:59:35","No","No","No","Internal","to carry out brake lining and update office. please raise RO for spare to keep on board."]
[null,null,null,26326,95553,"111_Sun Jul 31 2022 16:19:33 GMT+0800","2022-07-27T23:59:35","Defect","Ship Staff","Ship Staff Insp.","No.5 Stbd TST Inlet valve found o be leaking.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Valves reconditioned and fitted back. Tested. No leakages found.","2022-09-29T23:59:35","","Completed","2022-07-31T23:59:35","No","No","No","Internal","to carry out and update status"]
[null,null,null,26650,78921,"111_Mon Aug 15 2022 21:26:53 GMT+0800","2022-08-06T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Stbd Bilge well high level alarm float not operating.,","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Float replaced with new spare float received  on 02 Nov 2022. Alarm tried out, working satisfactory. Job reported in PAL PMS- Job Order No- V-CBOS009110/22","2022-11-30T23:59:35","CBOS220254","Completed","2022-11-03T23:59:35","No","No","No","Internal",""]
[null,null,null,25654,56397,"0_Wed Jun 15 2022 01:10:10 GMT+0800","2022-08-14T23:59:35","Defect","Ship Staff","Ship Staff Insp.","RPM repeater on bridge showing erratic reading","Navigation - RADAR","Navigation","Equipment Related","","","","","Ship Staff did fine adjustment and performance is satisfactory at different rpm levels","2023-01-31T23:59:35","","Completed","2023-01-12T23:59:35","No","No","No","Internal",""]
[null,null,null,29263,39721,"111_Sat Mar 11 2023 18:59:41 GMT+0800","2022-11-07T23:59:35","Non Conformity","Owner / Marine / Tech. Suptd.","Ship Staff Insp.","Eye washes not available at various locations in engine room.","Miscellaneous","Safety / LSA / FFA","Equipment Related","","","",""," Vessel ordered New eye washes immediately. Vessel received eye washes on 17th November 2022. Same placed at all required locations in ER.","2023-02-07T23:59:35","","Completed","2022-11-17T23:59:35","No","No","No","Internal"]
[null,null,null,29244,39173,"111_Sat Mar 11 2023 17:57:16 GMT+0800","2022-12-17T23:59:35","Non Conformity","Owner / Marine / Tech. Suptd.","ISM Audit","ISM Audit – MSDS for Choguku and PPG Paints not kept in Paint store.","Documentation","ISM Related","Knowledge Based","","","","","V/L  PUT MSDS IN PAINT LOCKER. ","2023-03-16T23:59:35","","Completed","2023-01-04T23:59:35","No","No","No","Internal"]
[null,null,null,29245,96842,"111_Sat Mar 11 2023 18:01:11 GMT+0800","2022-12-17T23:59:35","Non Conformity","Owner / Marine / Tech. Suptd.","ISM Audit","ISM Audit – Garbage bins inside Accommodation are not color coded as per Garbage Mgmt Plan.","Accommodation","ISM Related","Knowledge Based","","","","","ALL GARBAGE BINS COLOUR CODED AS PER MARPOL ANNEX V","2023-03-16T23:59:35","","Completed","2022-12-27T23:59:35","No","No","No","Internal"]
[null,null,null,29246,39802,"111_Sat Mar 11 2023 18:04:13 GMT+0800","2022-12-17T23:59:35","Observation","Owner / Marine / Tech. Suptd.","ISM Audit","ISM Audit - All portable ladders on Deck and Engine room are not tagged and inventory not maintained.","Miscellaneous","ISM Related","Knowledge Based","","","","","ALL PORTABLE LADDERS IN DECK AND ENGINE ROOM INVENTORY TAKEN AND TAGGED EACH ITEM AS APPLICABLE ","2023-03-16T23:59:35","","Completed","2023-01-10T23:59:35","No","No","No","Internal"]
[null,null,null,29247,16606,"111_Sat Mar 11 2023 18:07:14 GMT+0800","2022-12-17T23:59:35","Observation","Owner / Marine / Tech. Suptd.","ISM Audit","ISM Audit - All portable lifting equipment’s on Deck and Engine room are not tagged and inventory not maintained.","Documentation","ISM Related","Knowledge Based","","","","","ALL PORTABLE LIFTING APPLIANCE ON DECK AND ENGINE ROOM TAGGED AND INVENTORY UPDATED ","2023-03-16T23:59:35","","Completed","2023-01-11T23:59:35","No","No","No","Internal"]
[null,null,null,29248,71296,"111_Sat Mar 11 2023 18:12:26 GMT+0800","2022-12-17T23:59:35","Observation","Owner / Marine / Tech. Suptd.","ISM Audit","ISM Audit – Portable Fire extinguisher kept in Paint store is obstructed.","LSA / FFA","ISM Related","Human Error","","","","","FIRE EXTINGUSHER IN PAINT STORE CLEARED OF OBSTRUCTIONS AND MARKINGS DONE ","2023-03-16T23:59:35","","Completed","2022-12-23T23:59:35","No","No","No","Internal"]
[null,null,null,29249,26739,"111_Sat Mar 11 2023 18:17:06 GMT+0800","2022-12-17T23:59:35","Observation","Owner / Marine / Tech. Suptd.","ISPS Audit","ISPS Audit – ‘Restricted Area. Authorized personnel only’ poster missing on many exterior doors of Accommodation.","Accommodation","ISPS Related","Knowledge Based","","","","","Posters replaced","2023-03-16T23:59:35","","Completed","2022-12-22T23:59:35","No","No","No","Internal"]
[null,null,null,29250,93906,"111_Sat Mar 11 2023 18:19:02 GMT+0800","2022-12-17T23:59:35","Observation","Owner / Marine / Tech. Suptd.","MLC Audit","MLC Audit - Weekly menus for Indian and Filipinos cuisines not posted in the Messrooms.","Accommodation","MLC Related","Knowledge Based","","","","","WEEKLY MENU PUT IN OFFICERS AND CREW MESS ROOMS ","2023-03-16T23:59:35","","Completed","2022-12-24T23:59:35","No","No","No","Internal"]
[null,null,null,29252,81380,"111_Sat Mar 11 2023 18:21:18 GMT+0800","2022-12-17T23:59:35","Observation","Owner / Marine / Tech. Suptd.","MLC Audit","MLC Audit – No cleaning schedule posted for Galley Exhaust mesh.","Accommodation","MLC Related","Knowledge Based","","","","","GALLEY EXHAUST MESH TO BE CLEANED AND CLEANING SCHEDULE PASTED IN GALLY ","2023-03-16T23:59:35","","Completed","2022-12-29T23:59:35","No","No","No","Internal"]
[null,null,null,29257,86106,"111_Sat Mar 11 2023 18:14:56 GMT+0800","2022-12-17T23:59:35","Observation","Owner / Marine / Tech. Suptd.","ISM Audit","ISM Audit - Both Accommodation Gangways and Both Pilot Combination ladder gangways Angle indicators are frozen and stencil of Max/Min angle is missing.","Deck - Pipe / Fittings","ISM Related","External Factors","","","","","BOTH ACCOMMODATION LADDERS AND BOTH PILOT COMBINATION LADDERS ANGLE INDICATORS FREED AND GREASED ","2023-03-16T23:59:35","","Completed","2023-01-05T23:59:35","No","No","No","Internal"]
[null,null,null,29258,48734,"111_Sat Mar 11 2023 18:09:53 GMT+0800","2022-12-17T23:59:35","Observation","Owner / Marine / Tech. Suptd.","ISM Audit","ISM Audit – Some mooring winches BRC marking are faded and illegible.","Deck - Mooring Machinery","ISM Related","External Factors","","","","","BRC MARKINGS OF MOORING WINCHES CHECKED AND FADED MARKINGS REMARKED ","2023-03-16T23:59:35","","Completed","2023-01-09T23:59:35","No","No","No","Internal"]
[null,null,null,29264,96797,"111_Sat Mar 11 2023 19:04:16 GMT+0800","2022-12-17T23:59:35","Non Conformity","Others (Eg. Insurance etc.)","Nav Audit / Verification","UKC Calculation for the laden passage from Taman to Suez and Suez to Singapore was not calculated using Form 12.01.14.021.00.","Navigation - Others","","","","","","","UKC Form completed as per company procedures.","2023-03-16T23:59:35","","Completed","2023-01-07T23:59:35","No","No","No","External"]
[null,null,null,29265,55797,"111_Sat Mar 11 2023 19:07:38 GMT+0800","2022-12-17T23:59:35","Observation","Others (Eg. Insurance etc.)","Nav Audit / Verification","Safety contour settings for Open Seas was incorrectly mentioned in Passage plan from Taman to Suez and Suez to Singapore.","Navigation - ECDIS","Navigation","Knowledge Based","","","","","Safety Contour settings was properly inserted in passage plan","2023-03-16T23:59:35","","Completed","2022-12-19T23:59:35","No","No","No","External"]
[null,null,null,29266,38680,"111_Sat Mar 11 2023 19:09:56 GMT+0800","2022-12-17T23:59:35","Observation","Others (Eg. Insurance etc.)","Nav Audit / Verification","Change of Conn and Changeover of Steering from Auto to Hand and vice versa was not mentioned in Deck log book or Bridge note book for last call at Taman, Suez and Singapore.","Documentation","Cert. & Docu.","Knowledge Based","","","","","Change of Conn and steering entered in Logbook","2023-03-16T23:59:35","","Completed","2022-12-31T23:59:35","No","No","No","External"]
[null,null,null,29268,60240,"111_Sat Mar 11 2023 19:13:46 GMT+0800","2022-12-17T23:59:35","Observation","Others (Eg. Insurance etc.)","Nav Audit / Verification","Last Navigation Audit by the Master was carried out on 28th Oct 2022 however copy of the same was not sent to Office nor uploaded in PAL.","Navigation - Others","Cert. & Docu.","Human Error","","","","","UPDATED","2023-03-16T23:59:35","","Completed","2023-01-09T23:59:35","No","No","No","External"]
[null,null,null,29269,40053,"111_Sat Mar 11 2023 19:11:45 GMT+0800","2022-12-17T23:59:35","Observation","Others (Eg. Insurance etc.)","Nav Audit / Verification","Systematic NAVAREA Warnings and Navtex Warning file was not maintained.","Navigation - Others","Cert. & Docu.","Knowledge Based","","","","","Nav warnings filed","2023-03-16T23:59:35","","Completed","2023-01-01T23:59:35","No","No","No","External"]
[null,null,null,29243,55323,"111_Sat Mar 11 2023 17:44:40 GMT+0800","2022-12-20T23:59:35","Observation","Ship Staff","Ship Staff Insp.","CREW LAUNDRY ROOM DOOR WAS KEPT IN OPEN CONDITION BY MEANS OF A ROPE. ETO NOTICED IT DURING HIS DAILY ROUTINE ACCOMODATION ROUNDS. THE DOOR WAS SHUT IMMEDIATELY. IT WAS IMMEDIATELY REPORTED TO CH OFF AND MASTER. ALL SHIP STAFF WERE ASSEMBLED AND BRIEFED REGARDING THE INCIDENT. ALL SHIP STAFF WERE BRIEFED ABOUT THE IMPORTANCE OF LAUNDRY ROOM DOOR TO BE KEPT SHUT AT ALL TIMES.","Accommodation","Safety / LSA / FFA","Knowledge Based","","","","","LAUNDRY ROOM DOOR WAS SHUT IMMEDIATELY","2023-03-20T23:59:35","","Completed","2022-12-20T23:59:35","No","No","No","Internal"]
[null,null,null,29271,19716,"111_Sat Feb 18 2023 17:13:47 GMT+0800","2023-02-15T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Main Air Compressor#2 Abnormal alarm activated when Compressor was in use. Upon further investigation, it was found that motor insulation was ZERO. Motor was opened up for further inspection. Black spots were observed on stator windings.","E/R - Air Comp.","Eng. / Strg. Comp.","Equipment Related","","","","","Motor Renewed, Compressor tried out, working satisfactory, Amps checked, found within the required limit.","2023-05-15T23:59:35","CBOS 230038","Completed","2023-03-07T23:59:35","No","No","No","Internal"]
[null,null,null,29237,23198,"111_Mon Mar 13 2023 19:09:58 GMT+0800","2023-03-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","Inboard sea chest valve port side sea chest not holding","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","valve renewed in Dry dock ","2023-07-31T23:59:35","","Completed",null,"Yes","No","No","Internal"]
[null,null,null,29238,48257,"111_Mon Mar 13 2023 19:05:26 GMT+0800","2023-03-13T23:59:35","Defect","Ship Staff","Ship Staff Insp.","SW Inlet and outlet valves of both LT coolers not holding.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","valves renewed  in dry dock ","2023-07-31T23:59:35","CBOS230052","Completed",null,"Yes","No","No","Internal"]
[null,null,null,29239,86260,"111_Mon Mar 13 2023 19:02:23 GMT+0800","2023-03-13T23:59:35","Breakdown","Ship Staff","Ship Staff Insp.","Lub oil purifier no.1 not operational. ","E/R - Purifier","Eng. / Strg. Comp.","Equipment Related","","","","","1. PT1 was giving alarm, no pressure was observed (LO Supp Pump)--- Pressure switch changed. Rectified.\n2. Water block SVI 10 (Displacement water), SV15, 16(Closing/opening water) water flow rate checked as per manual, found satisfactory. Orifice cleaning done.\n3. Purifier started, during running found same was not going beyond the sequence 66 (Leaktest). on investigation found the Pneumatic back pressure valve was malfuncitoing, same opened up, position adjusted, boxed back, purifier started again, found all the sequence been followed, & running satisfactory. De-Slugding done, found working satisfactory. ALl the parameters (PT1, PT4, PT5) found in required range. Purifier run for one hour, no leakage detected","2023-04-15T23:59:35","","Completed","2023-04-04T23:59:35","No","No","No","Internal"]
[null,null,null,31866,45785,"111_Thu Aug 17 2023 17:19:15 GMT+0800","2023-06-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LBs chargers to fit new (received in Hadong)","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Both Life Boat  Battery Charger Renewed ","2023-07-05T23:59:35","CBOS22138","Completed","2023-06-11T23:59:35","Yes","No","No","Internal"]
[null,null,null,31873,63055,"111_Thu Aug 17 2023 17:57:35 GMT+0800","2023-06-05T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Boiler feed water pumps (both) seals leaking","","Eng. / Strg. Comp.","Equipment Related","","","","","Both Pump's overhauled & Seals Renewed, ","2023-07-05T23:59:35","","Completed","2023-07-03T23:59:35","Yes","No","No","Internal"]
[null,null,null,31874,33087,"111_Thu Aug 17 2023 18:05:12 GMT+0800","2023-06-05T23:59:35","Observation","Ship Staff","Suptd. Insp.","Ultra sonic filter cleaner not working","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","Ultrasonic   Filter  Put in use after Minor repairs ","2023-08-20T23:59:35","","Completed","2023-08-03T23:59:35","Yes","No","No","Internal"]
[null,null,null,31868,78257,"111_Thu Aug 17 2023 17:28:20 GMT+0800","2023-06-06T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NO.1 DG AutoStart not functioning/ erratic. Trouble shoot and repair","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Reason was  Loose Connection of Relay in   Control  Circuit Box, Same tightened  &  Gen Auto Start Confirmed .  ","2023-07-07T23:59:35","","Completed","2023-07-12T23:59:35","Yes","No","No","Internal"]
[null,null,null,31872,21582,"111_Thu Aug 17 2023 17:53:34 GMT+0800","2023-06-07T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","\tSTP blower damaged","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Blower renewed with new Spare ","2023-07-07T23:59:35","","Completed","2023-07-02T23:59:35","Yes","No","No","Internal"]
[null,null,null,31857,38498,"111_Tue Aug 15 2023 18:49:57 GMT+0800","2023-06-09T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","NO. 1 CH bilge suction valves (P) actuator leaking","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Leakage rectified","2023-09-09T23:59:35","","Completed","2023-06-19T23:59:35","No","No","No","Internal"]
[null,null,null,31858,53396,"111_Tue Aug 15 2023 19:05:25 GMT+0800","2023-06-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Canvas cover for gangway motors and gyro repeaters to renews","Miscellaneous","General Appearance","Knowledge Based","","","","","Canvas covers for gangway motors and Gyro repeaters fabricated and covered.","2023-09-09T23:59:35","","Completed","2023-06-10T23:59:35","No","No","No","Internal"]
[null,null,null,31859,48664,"111_Tue Aug 15 2023 19:09:21 GMT+0800","2023-06-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Safety railing chains around accommodation rusted and seized.","LSA / FFA","Safety / LSA / FFA","Industry Issue","","","","","All safety railing chains around accommodation de-rusted, painted and mounted back.","2023-09-09T23:59:35","","Completed","2023-06-15T23:59:35","No","No","No","Internal"]
[null,null,null,31860,37594,"111_Tue Aug 15 2023 19:42:45 GMT+0800","2023-06-09T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Duck keel Exh vent between CH 8 and 9 – completed rusted.","Deck - Pipe / Fittings","Safety / LSA / FFA","Equipment Related","","","","","Crop and renew of wasted body of exhaust vent carried out.","2023-09-09T23:59:35","","Completed","2023-06-17T23:59:35","No","No","No","Internal"]
[null,null,null,31861,85361,"111_Thu Aug 17 2023 16:12:06 GMT+0800","2023-06-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fire Hydrants – (03) – aft stations and forward fcle deck , NO.7 CH port leaking","LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","Leakage from fire hydrants rectified","2023-09-09T23:59:35","","Completed","2023-06-12T23:59:35","No","No","No","Internal"]
[null,null,null,31862,20654,"111_Thu Aug 17 2023 16:14:17 GMT+0800","2023-06-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CCR / Ship’s office flooring to change from Dark green to lighter colour.","Miscellaneous","General Appearance","Behaviour Based","","","","","Flooring colour changed to light green","2023-09-09T23:59:35","","Completed","2023-06-14T23:59:35","No","No","No","Internal"]
[null,null,null,31863,36800,"111_Thu Aug 17 2023 16:51:11 GMT+0800","2023-06-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Forepeak tank manual hydraulic actuators on deck to trouble shoot and repair ","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Manual hydraulic actuator repaired and made operational.","2023-09-09T23:59:35","","Completed","2023-07-24T23:59:35","No","No","No","Internal"]
[null,null,null,31864,68803,"111_Thu Aug 17 2023 16:58:14 GMT+0800","2023-06-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","AC fresh air intake damper stuck / frozen","Accommodation","MLC Related","Equipment Related","","","","","Damper was Renewed in  Zhoushan  Repair Yard  ","2023-08-09T23:59:35","","Completed","2023-07-12T23:59:35","No","No","No","Internal"]
[null,null,null,31865,47053,"111_Thu Aug 17 2023 16:55:41 GMT+0800","2023-06-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","A60 insulation at entrance from ER to HVAC room damaged","E/R - Pipes/ valves & fittings","Safety / LSA / FFA","Industry Issue","","","","","Section Damaged Insulation Renewed. ","2023-07-09T23:59:35","","Completed","2023-07-01T23:59:35","No","No","No","Internal"]
[null,null,null,31867,45720,"111_Thu Aug 17 2023 17:21:07 GMT+0800","2023-06-09T23:59:35","Breakdown","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Starboard pilot ladder motor not working – troubleshooting to carry out and repairs","Elect. Mach. & Equip.","ISPS Related","Equipment Related","","","","","Stbd pilot ladder worn-out bearing changed and ladder made operational.","2023-09-09T23:59:35","","Completed","2023-07-12T23:59:35","No","No","No","Internal"]
[null,null,null,31869,62404,"111_Thu Aug 17 2023 17:36:43 GMT+0800","2023-06-09T23:59:35","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","04 cargo hold bilge level alarms not working","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Bilge alarm float replaced by new and defect rectified.","2023-09-09T23:59:35","","Completed","2023-06-26T23:59:35","No","No","No","Internal"]
[null,null,null,31870,78678,"111_Thu Aug 17 2023 17:44:38 GMT+0800","2023-06-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Water mist detector alarm for forepeak in alarm condition","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Water mist detector alarm reset and rectified.","2023-09-09T23:59:35","","Completed","2023-06-24T23:59:35","No","No","No","Internal"]
[null,null,null,31871,28514,"111_Thu Aug 17 2023 17:47:19 GMT+0800","2023-06-09T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","CH Bilge valve actuators (2P, 4P,4S, 8P) - leaking ","Cargo Mach.","Cargo / Ballast Systems","Equipment Related","","","","","Leaking actuators repaired and leakage rectified.","2023-09-09T23:59:35","","Completed","2023-06-28T23:59:35","No","No","No","Internal"]
[null,null,null,31856,62972,"111_Wed Jul 19 2023 06:11:58 GMT+0800","2023-07-04T23:59:35","Defect","Ship Staff","Ship Staff Insp.","BOILER FUEL OIL PUMP SEAL LEAKAGE","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","seal renewed and pump overhauled ","2023-07-20T23:59:35","","Completed","2023-07-19T23:59:35","No","No","No","Internal"]
[null,null,null,32550,96481,"111_Wed Sep 20 2023 19:49:27 GMT+0800","2023-07-29T23:59:35","Observation","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","Findings The containment boxes for Fuel oil tank sounding pipes (5 pieces) on accommodation deck were not provided.","Deck - Pipe / Fittings","MARPOL Related","Equipment Related","","","","","Fuel oil tank sounding pipes containment boxes to be provided. Containment boxes fabricated and installed.","2023-11-10T23:59:35","","Completed","2023-10-25T23:59:35","No","No","No","External"]
[null,null,null,32551,37008,"111_Wed Sep 20 2023 19:34:02 GMT+0800","2023-07-29T23:59:35","Observation","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","The storage wire end connected with securing points provied on theaccommodation ladder's hoisting mechanism was changed by crew using two clamps which was not following the maker's designed securing arrangement by using the wire eyes with thimble and sleeve.","Deck - Machinery","ISM Related","Inappropriate Procedure","","","","","Wires replaced by new.","2023-09-30T23:59:35","","Completed","2023-09-15T23:59:35","No","No","No","External"]
[null,null,null,31875,83834,"111_Thu Aug 17 2023 18:15:56 GMT+0800","2023-07-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The top flashlight on the stbd lifeboat was noted with water accumulations.","","Safety / LSA / FFA","Equipment Related","","","","","Flash Light sealing screw was   loose & same retightened . Confirm no ingress of water / moisture ","2023-08-30T23:59:35","","Completed","2023-08-03T23:59:35","No","No","No","Internal"]
[null,null,null,31876,50690,"111_Fri Aug 18 2023 06:47:46 GMT+0800","2023-07-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The top flashlight on the stbd lifeboat was noted with water accumulations.","","Safety / LSA / FFA","Equipment Related","","","","","sealing screw of the light was loose same was tightened ","2023-09-03T23:59:35","","Completed","2023-08-02T23:59:35","Yes","No","No","Internal"]
[null,null,null,31877,81984,"111_Fri Aug 18 2023 06:51:40 GMT+0800","2023-07-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","The exhaust fan for engine room located on port side of funnel deck, the fan damper was installed in the position of open hatch of the observation window that the damper could not properly block the exhaust duct. This is original design and needs modification","","Structural Condn. / WT integrity ","Equipment Related","","","","","Sealing arrangement was fabricated so that fan duct will be sealed when flap in close condition ","2023-09-30T23:59:35","","Completed","2023-08-11T23:59:35","Yes","No","No","Internal"]
[null,null,null,31878,81050,"111_Fri Aug 18 2023 06:57:13 GMT+0800","2023-07-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Damaged A60 insulation to repair (store deck elevator casing)","","Eng. / Strg. Comp.","Equipment Related","","","","","Damaged Insulation renewed ","2023-08-30T23:59:35","","Completed","2023-08-03T23:59:35","No","No","No","Internal"]
[null,null,null,31879,82667,"111_Fri Aug 18 2023 07:07:46 GMT+0800","2023-07-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Newly installed BWTS system PMS jobs to upload in PAL","","Cargo / Ballast Systems","External Factors","","","","","BWTS system PMS jobs  uploaded in PAL  and same Triggered on 11 Aug 2023 ","2023-08-30T23:59:35","","Completed","2023-08-11T23:59:35","No","No","No","Internal"]
[null,null,null,31880,92946,"111_Fri Aug 18 2023 07:00:03 GMT+0800","2023-07-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","\t\tEmergency Gen Fuel tank remote quick closing device box, cover missing\t\t","Elect. Mach. & Equip.","Eng. / Strg. Comp.","Equipment Related","","","","","cover   fabricated. ","2023-09-15T23:59:35","","Completed","2023-08-18T23:59:35","Yes","No","No","Internal"]
[null,null,null,31881,93939,"111_Fri Aug 18 2023 07:03:46 GMT+0800","2023-07-30T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","\tEmergency exit platforms in the ER to clean and paint\t\t","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","Emergency exit platforms in the ER to cleaned and painted\t\t","2023-08-30T23:59:35","","Completed","2023-08-23T23:59:35","Yes","No","No","Internal"]
[null,null,null,31855,60512,"111_Wed Aug 23 2023 20:19:37 GMT+0800","2023-08-03T23:59:35","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","\t\tStern tube header tank oil leak to arrest\t60\t\t","","Eng. / Strg. Comp.","Equipment Related","","","","","Leaking pipe retightened ","2023-09-15T23:59:35","","Completed","2023-10-01T23:59:35","Yes","No","No","Internal"]
[null,null,null,32549,26940,"111_Thu Nov 16 2023 14:01:40 GMT+0800","2023-10-28T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Oxygen-Acetylene system: Various pipe joint connections and its hoses are of different sizes and fitted with jubilee clips.","Miscellaneous","Eng. / Strg. Comp.","Equipment Related","","","","","All used pipe connections in Oxy Ace Gas bottles room removed and installed with new supplied pipe connections, new Back fire valve and new regulator. All Hose connections properly made by crimpling tools. ","2023-12-15T23:59:35","","Completed","2023-12-04T23:59:35","No","No","No","Internal"]
[null,null,null,32542,98882,"111_Thu Nov 16 2023 14:24:17 GMT+0800","2023-11-08T23:59:35","Observation","Ship Staff","Ship Staff Insp.","Steering gear No. 1 pump and Servo motor No. 1 pump leaking from its seal. ","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Office informed about leakage. Shore workshop will attend the leak as per office advise at coming call Singapore. Service attendance was arranged and rectified on 19/nov/2023 at singapore.","2023-11-20T23:59:35","","Completed","2023-11-19T23:59:35","No","No","No","Internal"]
[null,null,null,33232,31519,"111_Fri Dec 01 2023 09:37:56 GMT+0800","2023-11-21T23:59:35","Defect","Ship Staff","Ship Staff Insp.","ME control air reducing valve malfunctioned.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","ME control air reducer renewed with new spare.","2023-11-21T23:59:35","","Completed","2023-11-21T23:59:35","No","No","No","Internal"]
[null,null,null,null,63720,"0_Thu Nov 16 2023 14:42:56 GMT+0800","2023-11-10T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Aux Boiler Safety Valve is leaking.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Requisition raised CBOS230240, Spare received and safety valve replaced . ","2024-02-05T08:00:00","CBOS230240","Completed","2023-12-18T08:00:00","No","No","No","Internal","21/12 - CBOS230240 has been supplied onboard as per records. please update repairs plan"]
[null,null,null,null,82447,"111_Wed May 31 2023 12:46:03 GMT+0800","2023-05-20T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Found AE#3, in stop condition, Jacket temperature was dropping, heater checked, was working satisfactory, on investigation, observed the COOLING LT AUTO SHUTOFF VALVE (Operated by LO Pressure) was leaking,  resulting drop in LT water temperature of DG#3, Valve is requested.","E/R - Aux. Engine","Eng. / Strg. Comp.","Equipment Related","","","","","Spare received RO: CBOS230093. Presently Cooling LT Auto Shutoff valve working satisfactory. Spare kept for future use.","2024-01-15T08:00:00","Requisition No: CBOS230093","Completed","2023-12-18T08:00:00","No","No","No","Internal","21/12 - subject spare has been delivered oboard on 14th Dec; please update once it has been isntalled. target date differed accrindly."]
[null,null,null,null,97567,"111_Sun Dec 24 2023 09:14:53 GMT+0800","2023-12-21T08:00:00","Breakdown","Ship Staff","Ship Staff Insp.","Ballast Pump No.1 leaking from its seal.","E/R - Pumps","Cargo / Ballast Systems","Equipment Related","","","","","Ballast pump No. 1 mechanical seal renewed.","2024-01-02T08:00:00","","Completed","2023-12-21T08:00:00","No","No","No","Internal"]
[null,null,null,null,87427,"111_Mon Jan 01 2024 08:33:57 GMT+0800","2023-12-28T08:00:00","Defect","Ship Staff","Ship Staff Insp.","ME Jacket water pump No. 1 leaking from its seal.","E/R - Pumps","Eng. / Strg. Comp.","Equipment Related","","","","","ME jacket pump complete overhauled. Mechanical seal renewed.","2024-01-10T08:00:00","","Completed","2023-12-28T08:00:00","No","No","No","Internal"]
[null,null,null,null,68539,"111_Thu Nov 23 2023 20:52:10 GMT+0800","2023-11-12T08:00:00","Observation","Ship Staff","Ship Staff Insp.","FWG Ejector Pump Suction Filter conditions deteriorated.","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Requisition raised, RO CBOS230250. Spare received.\nVessel replaced the complete filter on 02-Jan-2024. ","2024-02-10T08:00:00","","Completed","2024-01-02T08:00:00","No","No","No","Internal","21/12 - complete filer has been fabricated and has been deliveeed onboard on 14 dec 2023. kindly followup and have it installed in place at soonest without compromising safety."]
[null,null,null,null,97181,"111_Thu Nov 23 2023 15:28:12 GMT+0800","2023-11-21T08:00:00","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","LOCTITE 5910 REQUIRE TO USE FOR ME TIE ROD NUTS MATING SURFACE AREA SEALING ON A FRAME AS ADVISED FROM THE OFFICE.","E/R - Main Engine","Eng. / Strg. Comp.","Equipment Related","","","","","REQUISITION RAISED FOR LOCTITE 5910 REQUIRE TO USE FOR ME TIE ROD NUTS MATING SURFACE AREA SEALING ON A FRAME AS ADVISED FROM THE OFFICE. RO NO.-CBOS230254. Spare received. Work in progress. Job completed on 09/Jan/2024.","2024-01-15T08:00:00","","Completed","2024-01-09T08:00:00","No","No","No","Internal","21/12 - supplies have been arranged and shall be delivered onboard."]
[null,null,null,null,72290,"111_Sun Jan 21 2024 20:56:16 GMT+0800","2024-01-21T08:00:00","Observation","SIRE / CDI Insp.","OM Insp. (Eg. SIRE / CDI etc.)","Forward hydraulic Deck machinery sea water cooling system leaking.","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Cooling water pipe fabricated and replaced.\n.","2024-02-10T08:00:00","","Completed","2024-01-24T08:00:00","No","No","No","External"]
[null,null,null,null,55778,"111_Thu Feb 01 2024 15:26:08 GMT+0800","2024-01-27T08:00:00","Observation","Ship Staff","Ship Staff Insp.","No.3 CH Hydraulic Motor Stbd Side leaking.","Deck - Machinery","Cargo / Ballast Systems","","","","","","No.3 CH Hydraulic Motor Stbd oil seal renewed. Leakage Rectified.","2024-02-10T08:00:00","","Completed","2024-01-31T08:00:00","No","No","No","Internal"]
[null,null,null,null,42314,"0_Thu Nov 16 2023 14:48:36 GMT+0800","2023-11-11T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Aux Boiler Salinometer is malfunctioned.","E/R - Boiler","Eng. / Strg. Comp.","Equipment Related","","","","","Aux Boiler Salinometer requisition raised CBOS230249. Salinometer sensor and display renewed. ","2024-02-10T08:00:00","CBOS230249","Completed","2024-02-09T08:00:00","No","No","No","Internal","21/12 - as per records CBOS230249 has been dekivered onboard. please update installtoin and closure of this obs"]
[null,null,null,null,14888,"111_Thu Feb 15 2024 17:59:25 GMT+0800","2023-11-19T08:00:00","Defect,Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Sewage Treatment plant top cover found with soft patches.","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Vessel crop the wasted area of STP tank top and new plate inserted. Office concurrence taken for the hot work job.","2024-02-15T08:00:00","","Completed","2024-02-15T08:00:00","No","No","No","Internal"]
[null,null,null,null,98653,"111_Thu Feb 15 2024 18:03:58 GMT+0800","2024-02-05T08:00:00","Defect","Ship Staff","Ship Staff Insp.","ME Jacket pre heater tube leaking","E/R - Aux. Mach.","Eng. / Strg. Comp.","Equipment Related","","","","","Vessel dismantled the Jacket pre heater.  Leaky tube plugged and pressure test carried out.","2024-02-15T08:00:00","","Completed","2024-02-05T08:00:00","No","No","No","Internal"]
[null,null,null,null,15208,"0_Tue Jan 09 2024 16:29:49 GMT+0800","2024-01-04T08:00:00","Observation","Ship Staff","Ship Staff Insp.","Control lever block for Breast mooring winch is leaking.","Deck - Machinery","Mooring","Equipment Related","","","","","O-ring/seal  replaced. leak rectified.","2024-04-09T08:00:00","CBOS240039","Completed","2024-03-01T08:00:00","No","No","No","Internal"]
[null,null,null,null,25915,"0_Fri Dec 29 2023 04:25:46 GMT+0800","2023-12-26T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Port Anchor windlass brake spindle broken apart. ","Deck - Mooring Machinery","Mooring","Equipment Related","","","","","Temporary repairs done by welding the spindle. It must be replaced by a new spindle.","2024-01-31T08:00:00","","Completed","2024-01-25T08:00:00","No","No","No","Internal"]
[null,null,null,null,89049,"0_Fri Dec 01 2023 16:25:15 GMT+0800","2023-11-01T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Port anchor Bitter end plate is bent","Deck - Mooring Machinery","Emgcy. Systems","Equipment Related","","","","","Hot work to carried out. Pin to be heated and hammered straight.","2024-01-30T08:00:00","","Completed","2024-01-02T08:00:00","No","No","No","Internal"]
[null,null,null,null,18557,"111_Wed Sep 20 2023 19:38:03 GMT+0800","2023-07-29T08:00:00","Observation","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","Seven cleats on No.6 hatch cover could not be secured in correct position, the wedges and saddles were misaligned.","Deck - Machinery","Structural Condn. / WT integrity ","Equipment Related","","","","","All cleats to be aligned.","2024-01-15T08:00:00","","Completed","2024-01-18T08:00:00","No","No","No","External","21/12 - Job requries hot work - vessel has been on long loaded coal voyage. please carry out the repairs at earliest opportunity. target date differed accordingly"]
[null,null,null,null,66237,"0_Fri Dec 01 2023 16:17:33 GMT+0800","2023-11-01T08:00:00","Other","Ship Staff","Ship Staff Insp.","Spindle for Mushroom Vent in Cross deck between No.01 and No.02 cargo hold is bent","Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related","","","","","Hotwork require to fabricate cover and straighten the Spindle.","2024-01-25T08:00:00","","Completed","2024-01-13T08:00:00","No","No","No","Internal","21/12 - job to be taken up at first opportunity for hot wrk"]
[null,null,null,null,87115,"0_Fri Dec 01 2023 16:19:36 GMT+0800","2023-10-31T08:00:00","Defect","Ship Staff","Ship Staff Insp.","Auto-cleat on few hatch covers needs to be adjusted.","Deck - Pipe / Fittings","Cargo / Ballast Systems","Equipment Related","","","","","Spares received at Singapore. Will need hot work. To be completed after discharge port.","2024-01-31T08:00:00","","Completed","2024-03-02T08:00:00","No","No","No","Internal"]
[null,null,null,null,57872,"111_Fri Dec 01 2023 16:13:57 GMT+0800","2023-10-30T08:00:00","Critical Equipment","Ship Staff","Ship Staff Insp.","Cargo Hatch Rest Pads having gap","Hull & Tanks","Structural Condn. / WT integrity ","Equipment Related","","","","","To be build up. Office trying to arrange specialist to inspect and advise. Hot work will be required and can be done after discharge port","2024-03-15T08:00:00","","Completed","2024-01-01T08:00:00","No","No","No","Internal"]
[null,null,null,null,21091,"111_Wed Sep 20 2023 19:41:03 GMT+0800","2023-07-29T08:00:00","Observation","Others (Eg. Insurance etc.)","Others (Eg. Insurance etc.)","The bearing pads on all hatch cover were worn-out, the hatch cover was rested on the rubber packing.","Cargo Mach.","Structural Condn. / WT integrity ","Equipment Related","","","","","Buildup of rest pads to be carried out.","2024-03-15T08:00:00","","Completed","2024-01-01T08:00:00","No","No","No","External","21/12 - job requires hot work and vessel has been on a long coal laden voyage. please carry out soonest hot work opportunity. target date differed accordingly."]
[null,null,null,null,87682,"111_Thu Mar 07 2024 13:16:53 GMT+0800","2024-02-23T08:00:00","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","Fire line aft of Nr.6 hold has a pin hole leak","Deck - Pipe / Fittings,LSA / FFA","Safety / LSA / FFA","Equipment Related","","","","","","2024-03-05T08:00:00","","Completed","2024-03-02T08:00:00","No","No","No","Internal"]
[null,null,null,null,43987,"111_Thu Mar 07 2024 13:24:12 GMT+0800","2024-02-24T08:00:00","Observation","Owner / Marine / Tech. Suptd.","Suptd. Insp.","At least 12 hatch cover cleat fittings are waiting to be installed - of which one at # 4 (S) side was fitted wrongly - this can cause  a hydrauic pipe burst if hatch cleat is being closed under pressure  ","Cargo Mach.","Cargo / Ballast Systems","Inappropriate Procedure","","","","","","2024-03-05T08:00:00","","Completed","2024-03-02T08:00:00","No","No","No","Internal"]
[null,null,null,null,11621,"111_Thu Mar 07 2024 13:40:17 GMT+0800","2024-02-25T08:00:00","Defect","Owner / Marine / Tech. Suptd.","Suptd. Insp.","One electrical switch box ford of # 5 hold (P) side frame is corrosed and wasted - to fit back ","Elect. Mach. & Equip.","Cargo / Ballast Systems","Inappropriate Procedure","","","","","","2024-03-10T08:00:00","","Completed","2024-03-05T08:00:00","No","No","No","Internal"]
[null,null,null,null,45885,"111_Thu Nov 23 2023 20:56:30 GMT+0800","2023-11-16T08:00:00","Defect","Ship Staff","Ship Staff Insp.","FWG Condensor Sea Water Outlet pipe leaking","E/R - Pipes/ valves & fittings","Eng. / Strg. Comp.","Equipment Related","","","","","Pipe renewed.","2024-03-15T08:00:00","","Completed","2024-03-10T08:00:00","No","No","No","Internal","21/12 - supplied spare os of wrong specificaiton / type- mistake by suppliers. in view of above reasons, new spare will be arranged on exchange"]

{"sheet":"Calc","index":2,"n_rows":28,"n_cols":12,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Def_type","Def_cause","Equipments","VIQrefno","Observer_code"]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,"Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"   dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"   startRow=1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        If ListBox1.Selected(itemSele) = True Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele)"]
[null,null,null,null,null,null,null,null,null,null,null,"        startRow = startRow + 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"Dim LastRowA As String"]
[null,null,null,null,null,null,null,null,null,null,null,"        Dim itemSele As Long"]
[null,null,null,null,null,null,null,null,null,null,null,"       Dim startRow as integer"]
[null,null,null,null,null,null,null,null,null,null,null,"        LastRowA = ActiveSheet.Cells(Rows.count, \"A\").End(xlUp).row"]
[null,null,null,null,null,null,null,null,null,null,null,"        startQue = 0"]
[null,null,null,null,null,null,null,null,null,null,null,"        For itemSele = 0 To ListBox1.ListCount - 1"]
[null,null,null,null,null,null,null,null,null,null,null,"        For startRow = 1 To LastRowA"]
[null,null,null,null,null,null,null,null,null,null,null,"        If Worksheets(\"WorksheetName\").Range(\"A\" & startRow).Value = ListBox1.List(itemSele) Then"]
[null,null,null,null,null,null,null,null,null,null,null,"        ListBox1.Selected(itemSele) = True"]
[null,null,null,null,null,null,null,null,null,null,null,"        Exit For"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next j"]
[null,null,null,null,null,null,null,null,null,null,null,"        Next"]
[null,null,null,null,null,null,null,null,null,null,null,"        End If"]

{"sheet":"Areaofobs","index":3,"n_rows":17,"n_cols":2,"rows_kept":17,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo / Ballast Systems",11]
["Cert. & Docu.",2]
["Communication",6]
["Crew Management",3]
["Emgcy. Systems",13]
["Eng. / Strg. Comp.",14]
["General Appearance",15]
["Ice Opns.",17]
["ISM Related",7]
["ISPS Related",10]
["MARPOL Related",9]
["MLC Related",4]
["Mooring",12]
["Navigation",5]
["Safety / LSA / FFA",8]
["Structural Condn. / WT integrity ",16]

{"sheet":"Vessel_type","index":4,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Vessel_type","ID"]

{"sheet":"Deficiency_type","index":5,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Breakdown",null,6]
["Critical Equipment",null,4]
["Defect",null,1]
["Guarantee Claim",null,8]
["Non Conformity",null,2]
["Observation",null,3]
["Other",null,7]

{"sheet":"VIQrefno","index":6,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["VIQ_ref_no","Risk Value of observation","ID"]

{"sheet":"Equipment_list","index":7,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["TITLE","Equipment_list_description","ID"]
["Accommodation",null,12]
["Cargo Mach.",null,13]
["Critical Equip.",null,16]
["Deck - Machinery",null,18]
["Deck - Mooring Machinery",null,15]
["Deck - Pipe / Fittings",null,20]
["Documentation",null,21]
["E/R - Air Comp.",null,8]
["E/R - Aux. Engine",null,4]
["E/R - Aux. Mach.",null,7]
["E/R - Boiler",null,5]
["E/R - Main Engine",null,3]
["E/R - Pipes/ valves & fittings",null,9]
["E/R - Pumps",null,32]
["E/R - Purifier",null,6]
["Elect. Mach. & Equip.",null,10]
["Hull & Tanks",null,19]
["Inert Gas",null,14]
["LSA / FFA",null,17]
["Miscellaneous",null,22]
["Navigation - DGPS / EPFS / AIS",null,28]
["Navigation - ECDIS",null,25]
["Navigation - Echo Sounder / Speed Log",null,26]
["Navigation - GMDSS & Communication",null,23]
["Navigation - Others",null,11]
["Navigation - RADAR",null,24]
["Navigation - VDR / BNWAS",null,30]

{"sheet":"PSC_MOU","index":8,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","PSC_MOU_description","ID"]
["Asia and the Pacific",null,2]
["Caribbean",null,4]
["Europe and the North Atlantic",null,1]
["Latin America",null,3]
["The Black Sea region",null,6]
["The Indian Ocean",null,8]
["The Mediterranean",null,7]
["The Riyadh MoU",null,9]
["USCG",null,10]
["West and Central Africa",null,5]

{"sheet":"Inspection_type","index":9,"n_rows":13,"n_cols":2,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Bunkering Audit",14]
["Cargo Audit",17]
["Engineering Audit",16]
["ISM Audit",2]
["ISPS Audit",3]
["IT Audit",10]
["MLC Audit",1]
["Mooring Audit",9]
["Nav Audit / Verification",8]
["Onboard Training",18]
["Ship Staff Insp.",15]
["Suptd. Insp.",13]

{"sheet":"Deficiency_Cause","index":10,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["TITLE","Deficiency_Cause_description","ID"]
["Behaviour Based",null,1]
["Equipment Related",null,4]
["External Factors",null,5]
["Human Error",null,7]
["Inappropriate Procedure",null,8]
["Industry Issue",null,6]
["Knowledge Based",null,3]

{"sheet":"Observer_code","index":11,"n_rows":3,"n_cols":3,"rows_kept":3,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Owner / Marine / Tech. Suptd.",null,3]
["Ship Staff",null,2]

{"sheet":"Status_code","index":12,"n_rows":6,"n_cols":3,"rows_kept":6,"cut":false,"hidden":true,"merged":[]}
["TITLE","Status_code_description","ID"]
["Completed",null,6]
["Deferred to D D",null,5]
["In progress",null,3]
["Not Started",null,2]
["Waiting spare",null,4]

{"sheet":"PSC_ref_no","index":13,"n_rows":19,"n_cols":2,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Alarms",9]
["Cargo operations including equipment",7]
["Certificates & Documentation",2]
["Dangerous Goods",13]
["Emergency Systems",5]
["Fire safety",8]
["ISM",16]
["ISPS",17]
["Life saving appliances",12]
["MLC, 2006",18]
["Other",19]
["Pollution Prevention",15]
["Propulsion and auxiliary machinery",14]
["Radio communication",6]
["Safety of Navigation",11]
["Structural condition",3]
["Water/Weathertight condition",4]
["Working and Living Conditions",10]

{"sheet":"Risk_value_of_obs","index":14,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Risk Value of observation","ID"]

{"sheet":"Year","index":15,"n_rows":18,"n_cols":1,"rows_kept":18,"cut":false,"hidden":true,"merged":[]}
["Year"]
[2014]
[2015]
[2016]
[2017]
[2018]
[2019]
[2020]
[2021]
[2022]
[2023]
[2024]
[2025]
[2026]
[2027]
[2028]
[2029]
[2030]

{"sheet":"Month","index":16,"n_rows":13,"n_cols":1,"rows_kept":13,"cut":false,"hidden":true,"merged":[]}
["Month"]
["Jan"]
["Feb"]
["Mar"]
["Apr"]
["May"]
["Jun"]
["Jul"]
["Aug"]
["Sep"]
["Oct"]
["Nov"]
["Dec"]

{"sheet":"Date_","index":17,"n_rows":32,"n_cols":1,"rows_kept":32,"cut":false,"hidden":true,"merged":[]}
["Date"]
["01"]
["02"]
["03"]
["04"]
["05"]
["06"]
["07"]
["08"]
["09"]
[10]
[11]
[12]
[13]
[14]
[15]
[16]
[17]
[18]
[19]
[20]
[21]
[22]
[23]
[24]
[25]
[26]
[27]
[28]
[29]
[30]
[31]

{"sheet":"Sheet1","index":18,"n_rows":24,"n_cols":6,"rows_kept":24,"cut":false,"hidden":true,"merged":[]}
[]
[null,"ID","E",null,"Date Recorded",1]
[null,"UNIQUE ID","F",null,"Type of Deficiency",2]
[1,"Date Recorded","G",null,"Observer code",3]
["ignore","Vessel Type","H",null,"Type of Inspection",4]
[null,"Internal / External","I",null,"Description of Deficiency",5]
[null,"Drydock","J",null,"Equipment Categories",6]
[null,"Information Sharing","K",null,"Area of Observation",7]
[null,"Critical_item","L",null,"Deficiency Cause",8]
[null,"Deficiency Type","M",null,"VIQ Ref Number",9]
[null,"Deficiency Cause","N",null,"Risk Value of Obs",10]
[null,"Inspection Type","O",null,"PSC Ref Number",11]
[null,"Equipments","P",null,"PSC MOU ID",12]
[null,"VIQ Reference Number","Q",null,"Action Taken or Required",13]
[null,"Risk Value of the observation","R",null,"Target Date",14]
[null,"PSC Reference Number","S",null,"PO Ref No.",15]
[null,"PSC MOU","T",null,"Status Code",16]
[null,"Observer Code","U",null,"Date Completed",17]
[null,"Target Date","V",null,"Drydock",18]
[null,"Status Code","W",null,"Info Sharing",19]
[null,"Description of Deficiency","X",null,"Critical Item Flag",20]
[null,"Action taken / required","Y",null,"Audit Type",21]
[null,"PO ref no","Z"]
[null,"Date completed","AA"]

{"sheet":"Ship_information","index":19,"n_rows":2,"n_cols":4,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Ship_ID","Ship_Name","FILE_NAME","Export_Date"]
["111","CAPE BOSS (21-12-2023)","111_1703153057334.xlsm","2024-03-31 17:03:69"]

{"sheet":"External_Deficiency_type","index":20,"n_rows":5,"n_cols":3,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["TITLE","Type of deficiency_description","ID"]
["Condn of Class / Memo",null,5]
["Defect",null,1]
["Non Conformity",null,2]
["Observation",null,3]

{"sheet":"External_Inspection_type","index":21,"n_rows":11,"n_cols":2,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["TITLE","ID"]
["Cargo Audit",17]
["Flag State Insp.",5]
["ISM Audit",2]
["ISPS Audit",3]
["MLC Audit",1]
["Nav Audit / Verification",8]
["OM Insp. (Eg. SIRE / CDI etc.)",6]
["Others (Eg. Insurance etc.)",12]
["PSC Inspection",4]
["Terminal Insp.",11]

{"sheet":"External_Observer_code","index":22,"n_rows":7,"n_cols":3,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["TITLE","Observer_code_description","ID"]
["Class Surveyor",null,4]
["FSC Inspector",null,5]
["Others (Eg. Insurance etc.)",null,9]
["PSC Insp.",null,6]
["SIRE / CDI Insp.",null,8]
["Terminal Insp.",null,7]

{"sheet":"Sheet Version","index":23,"n_rows":2,"n_cols":2,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Version","Title"]
["2.0","Version 2.0"]